## Scenario A
Row_ID | Deliverable_Code | Task_Code | Service_Department | Deliverable | Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes | Rate_USD | Price_USD
[5 empty] | Casa-Dragones-Digital-MKT-RFP | 1 |  | Casa-Dragones-Digital-MKT-RFP | Project |  |  |  | 0 | 0 |  |  |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1 | 1 | Campaign Strategy |  |  |  |  | 109 | 0 | 15 |  |  | Advanced/T2_MediumVolume | 195 | 21255
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1 | 1.1 | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) |  |  |  | 17 | 0 | 11 | 1.1 |  |  | 195 | 3315
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1 | 1.1.1 | Channel Roles & Cadence | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Channel Roles & Cadence |  |  | 0 | 0 | 6 | 1.1.1 |  |  | 0 | 0
714 | DEL-0011 | TSK-00705 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.1 | 1.1.1.1 | Channel Roles & Cadence | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Channel Roles & Cadence | Creative Director | Lead/Director | 2 |  |  | 1.1.1.1 |  |  | 0 | 0
715 | DEL-0011 | TSK-00706 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.2 | 1.1.1.1 | Channel Roles & Cadence | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Channel Roles & Cadence | Designer | Mid | 9 |  |  | 1.1.1.1.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2 | 1.1.1 | Internal Review & Critique | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.1.1.2 |  |  | 0 | 0
720 | DEL-0011 | TSK-00711 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.1 | 1.1.1.2 | Internal Review & Critique | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.1.2 |  |  | 0 | 0
721 | DEL-0011 | TSK-00712 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.2 | 1.1.1.2 | Internal Review & Critique | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.1.2.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3 | 1.1.1 | Client Review & Revisions | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.1.2.2 |  |  | 0 | 0
716 | DEL-0011 | TSK-00707 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.1 | 1.1.1.3 | Client Review & Revisions | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.1.3 |  |  | 0 | 0
717 | DEL-0011 | TSK-00708 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.2 | 1.1.1.3 | Client Review & Revisions | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.1.3.1 |  |  | 0 | 0
718 | DEL-0011 | TSK-00709 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.3 | 1.1.1.3 | Client Review & Revisions | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.1.3.2 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2 | 1.1 | 10k Ft View | 10k Ft View |  |  |  | 15 | 6 | 9 | 1.1.1 |  |  | 195 | 2925
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.1 | 1.1.2 | Visual Summary | 10k Ft View | Visual Summary |  |  | 0 | 6 | 4 | 1.1.2 |  |  | 0 | 0
705 | DEL-0011 | TSK-00696 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.1.1 | 1.1.2.1 | Visual Summary | 10k Ft View | Visual Summary | Designer | Mid | 2 |  |  | 1.1.2.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.2 | 1.1.2 | Internal Review & Critique | 10k Ft View | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.2.1.1 |  |  | 0 | 0
701 | DEL-0011 | TSK-00692 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.2.1 | 1.1.2.2 | Internal Review & Critique | 10k Ft View | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.2.2 |  |  | 0 | 0
702 | DEL-0011 | TSK-00693 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.2.2 | 1.1.2.2 | Internal Review & Critique | 10k Ft View | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.2.2.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.3 | 1.1.2 | Client Review & Revisions | 10k Ft View | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.2.2.2 |  |  | 0 | 0
696 | DEL-0011 | TSK-00687 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.3.1 | 1.1.2.3 | Client Review & Revisions | 10k Ft View | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.2.3 |  |  | 0 | 0
697 | DEL-0011 | TSK-00688 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.3.2 | 1.1.2.3 | Client Review & Revisions | 10k Ft View | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.1.2.3.1 |  |  | 0 | 0
698 | DEL-0011 | TSK-00689 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.3.3 | 1.1.2.3 | Client Review & Revisions | 10k Ft View | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.2.3.2 |  |  | 0 | 0
699 | DEL-0011 | TSK-00690 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.3.4 | 1.1.2.3 | Client Review & Revisions | 10k Ft View | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.2.3.3 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.4 | 1.1.2 | Narrative Overview | 10k Ft View | Narrative Overview |  |  | 0 | 15 | 0 | 1.1.2.3.4 |  |  | 0 | 0
703 | DEL-0011 | TSK-00694 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.4.1 | 1.1.2.4 | Narrative Overview | 10k Ft View | Narrative Overview | Copywriter | Mid | 2 |  |  | 1.1.2.4 |  |  | 0 | 0
704 | DEL-0011 | TSK-00695 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.4.2 | 1.1.2.4 | Narrative Overview | 10k Ft View | Narrative Overview | Creative Director | Lead/Director | 2 |  |  | 1.1.2.4.1 |  |  | 0 | 0
700 | DEL-0011 | TSK-00691 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.4.3 | 1.1.2.4 | Narrative Overview | 10k Ft View | Narrative Overview | Designer | Mid | 2 |  |  | 1.1.2.4.2 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3 | 1.1 | Image Usage Guidelines | Image Usage Guidelines |  |  |  | 27 | 10 | 5 | 1.1.2 |  |  | 195 | 5265
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.1 | 1.1.3 | Internal Review & Critique | Image Usage Guidelines | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.3 |  |  | 0 | 0
712 | DEL-0011 | TSK-00703 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.1.1 | 1.1.3.1 | Internal Review & Critique | Image Usage Guidelines | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.3.1 |  |  | 0 | 0
713 | DEL-0011 | TSK-00704 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.1.2 | 1.1.3.1 | Internal Review & Critique | Image Usage Guidelines | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.3.1.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.2 | 1.1.3 | Client Review & Revisions | Image Usage Guidelines | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.3.1.2 |  |  | 0 | 0
706 | DEL-0011 | TSK-00697 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.2.1 | 1.1.3.2 | Client Review & Revisions | Image Usage Guidelines | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.3.2 |  |  | 0 | 0
707 | DEL-0011 | TSK-00698 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.2.2 | 1.1.3.2 | Client Review & Revisions | Image Usage Guidelines | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.3.2.1 |  |  | 0 | 0
708 | DEL-0011 | TSK-00699 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.2.3 | 1.1.3.2 | Client Review & Revisions | Image Usage Guidelines | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.3.2.2 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.3 | 1.1.3 | Examples | Image Usage Guidelines | Examples |  |  | 0 | 15 | 0 | 1.1.3.2.3 |  |  | 0 | 0
711 | DEL-0011 | TSK-00702 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.3.1 | 1.1.3.3 | Examples | Image Usage Guidelines | Examples | Art Director | Lead/Director | 1 |  |  | 1.1.3.3 |  |  | 0 | 0
709 | DEL-0011 | TSK-00700 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.3.2 | 1.1.3.3 | Examples | Image Usage Guidelines | Examples | Designer | Mid | 20 |  |  | 1.1.3.3.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4 | 1.1 | Media Assets | Media Assets |  |  |  | 12 | 10 | 5 | 1.1.3 |  |  | 195 | 2340
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.1 | 1.1.4 | Internal Review & Critique | Media Assets | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.4 |  |  | 0 | 0
729 | DEL-0011 | TSK-00720 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.1.1 | 1.1.4.1 | Internal Review & Critique | Media Assets | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.4.1 |  |  | 0 | 0
730 | DEL-0011 | TSK-00721 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.1.2 | 1.1.4.1 | Internal Review & Critique | Media Assets | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.4.1.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.2 | 1.1.4 | Client Review & Revisions | Media Assets | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.4.1.2 |  |  | 0 | 0
725 | DEL-0011 | TSK-00716 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.2.1 | 1.1.4.2 | Client Review & Revisions | Media Assets | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.4.2 |  |  | 0 | 0
726 | DEL-0011 | TSK-00717 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.2.2 | 1.1.4.2 | Client Review & Revisions | Media Assets | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.4.2.1 |  |  | 0 | 0
727 | DEL-0011 | TSK-00718 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.2.3 | 1.1.4.2 | Client Review & Revisions | Media Assets | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.4.2.2 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.3 | 1.1.4 | Asset Matrix | Media Assets | Asset Matrix |  |  | 0 | 15 | 0 | 1.1.4.2.3 |  |  | 0 | 0
723 | DEL-0011 | TSK-00714 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.3.1 | 1.1.4.3 | Asset Matrix | Media Assets | Asset Matrix | Designer | Mid | 5 |  |  | 1.1.4.3 |  |  | 0 | 0
724 | DEL-0011 | TSK-00715 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.3.2 | 1.1.4.3 | Asset Matrix | Media Assets | Asset Matrix | Project Manager | Mid | 1 |  |  | 1.1.4.3.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5 | 1.1 | Photo / Video Direction | Photo / Video Direction |  |  |  | 14 | 10 | 5 | 1.1.4 |  |  | 195 | 2730
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.1 | 1.1.5 | Internal Review & Critique | Photo / Video Direction | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.5 |  |  | 0 | 0
737 | DEL-0011 | TSK-00728 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.1.1 | 1.1.5.1 | Internal Review & Critique | Photo / Video Direction | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.5.1 |  |  | 0 | 0
738 | DEL-0011 | TSK-00729 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.1.2 | 1.1.5.1 | Internal Review & Critique | Photo / Video Direction | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.5.1.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.2 | 1.1.5 | Client Review & Revisions | Photo / Video Direction | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.5.1.2 |  |  | 0 | 0
731 | DEL-0011 | TSK-00722 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.2.1 | 1.1.5.2 | Client Review & Revisions | Photo / Video Direction | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.5.2 |  |  | 0 | 0
732 | DEL-0011 | TSK-00723 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.2.2 | 1.1.5.2 | Client Review & Revisions | Photo / Video Direction | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.5.2.1 |  |  | 0 | 0
733 | DEL-0011 | TSK-00724 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.2.3 | 1.1.5.2 | Client Review & Revisions | Photo / Video Direction | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.5.2.2 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.3 | 1.1.5 | Direction Notes | Photo / Video Direction | Direction Notes |  |  | 0 | 15 | 0 | 1.1.5.2.3 |  |  | 0 | 0
734 | DEL-0011 | TSK-00725 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.3.1 | 1.1.5.3 | Direction Notes | Photo / Video Direction | Direction Notes | Art Director | Lead/Director | 1 |  |  | 1.1.5.3 |  |  | 0 | 0
735 | DEL-0011 | TSK-00726 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.3.2 | 1.1.5.3 | Direction Notes | Photo / Video Direction | Direction Notes | Creative Director | Lead/Director | 2 |  |  | 1.1.5.3.1 |  |  | 0 | 0
736 | DEL-0011 | TSK-00727 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.3.3 | 1.1.5.3 | Direction Notes | Photo / Video Direction | Direction Notes | Designer | Mid | 5 |  |  | 1.1.5.3.2 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6 | 1.1 | Rollout | Rollout |  |  |  | 14 | 10 | 5 | 1.1.5 |  |  | 195 | 2730
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.1 | 1.1.6 | Internal Review & Critique | Rollout | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.6 |  |  | 0 | 0
744 | DEL-0011 | TSK-00735 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.1.1 | 1.1.6.1 | Internal Review & Critique | Rollout | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.6.1 |  |  | 0 | 0
745 | DEL-0011 | TSK-00736 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.1.2 | 1.1.6.1 | Internal Review & Critique | Rollout | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.6.1.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.2 | 1.1.6 | Client Review & Revisions | Rollout | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.6.1.2 |  |  | 0 | 0
740 | DEL-0011 | TSK-00731 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.2.1 | 1.1.6.2 | Client Review & Revisions | Rollout | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.6.2 |  |  | 0 | 0
741 | DEL-0011 | TSK-00732 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.2.2 | 1.1.6.2 | Client Review & Revisions | Rollout | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.6.2.1 |  |  | 0 | 0
742 | DEL-0011 | TSK-00733 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.2.3 | 1.1.6.2 | Client Review & Revisions | Rollout | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.6.2.2 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.3 | 1.1.6 | Phasing & Milestones | Rollout | Phasing & Milestones |  |  | 0 | 15 | 0 | 1.1.6.2.3 |  |  | 0 | 0
746 | DEL-0011 | TSK-00737 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.3.1 | 1.1.6.3 | Phasing & Milestones | Rollout | Phasing & Milestones | Creative Director | Lead/Director | 2 |  |  | 1.1.6.3 |  |  | 0 | 0
743 | DEL-0011 | TSK-00734 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.3.2 | 1.1.6.3 | Phasing & Milestones | Rollout | Phasing & Milestones | Designer | Mid | 5 |  |  | 1.1.6.3.1 |  |  | 0 | 0
747 | DEL-0011 | TSK-00738 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.3.3 | 1.1.6.3 | Phasing & Milestones | Rollout | Phasing & Milestones | Project Manager | Mid | 1 |  |  | 1.1.6.3.2 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7 | 1.1 | Use Cases | Use Cases |  |  |  | 10 | 10 | 5 | 1.1.6 |  |  | 195 | 1950
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.1 | 1.1.7 | Internal Review & Critique | Use Cases | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.7 |  |  | 0 | 0
753 | DEL-0011 | TSK-00744 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.1.1 | 1.1.7.1 | Internal Review & Critique | Use Cases | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.7.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.2 | 1.1.7 | Client Review & Revisions | Use Cases | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.7.1.1 |  |  | 0 | 0
749 | DEL-0011 | TSK-00740 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.2.1 | 1.1.7.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.7.2 |  |  | 0 | 0
750 | DEL-0011 | TSK-00741 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.2.2 | 1.1.7.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.7.2.1 |  |  | 0 | 0
751 | DEL-0011 | TSK-00742 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.2.3 | 1.1.7.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.7.2.2 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.3 | 1.1.7 | Final Packaging | Use Cases | Final Packaging |  |  | 0 | 15 | 0 | 1.1.7.2.3 |  |  | 0 | 0
752 | DEL-0011 | TSK-00743 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.3.1 | 1.1.7.3 | Final Packaging | Use Cases | Final Packaging | Designer | Mid | 5 |  |  | 1.1.7.3 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2 | 1 | Creative Strategy / Campaign Plan Deck |  |  |  |  | 582 | 15 | 28 | 1.1 |  | Advanced/T2_MediumVolume | 195 | 113490
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1 | 1.2 | Activation Ideas | Activation Ideas |  |  |  | 40 | 15 | 11 | 1.2 |  |  | 195 | 7800
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1 | 1.2.1 | Idea Write-Ups | Activation Ideas | Idea Write-Ups |  |  | 0 | 15 | 6 | 1.2.1 |  |  | 0 | 0
1475 | DEL-0036 | TSK-01466 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.1 | 1.2.1.1 | Idea Write-Ups | Activation Ideas | Idea Write-Ups | Copywriter | Mid | 4 |  |  | 1.2.1.1 |  |  | 0 | 0
1477 | DEL-0036 | TSK-01468 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.2 | 1.2.1.1 | Idea Write-Ups | Activation Ideas | Idea Write-Ups | Creative Director | Lead/Director | 3 |  |  | 1.2.1.1.1 |  |  | 0 | 0
1474 | DEL-0036 | TSK-01465 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.3 | 1.2.1.1 | Idea Write-Ups | Activation Ideas | Idea Write-Ups | Designer | Mid | 16 |  |  | 1.2.1.1.2 |  |  | 0 | 0
1476 | DEL-0036 | TSK-01467 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.4 | 1.2.1.1 | Idea Write-Ups | Activation Ideas | Idea Write-Ups | Strategist | Mid | 12 |  |  | 1.2.1.1.3 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.2 | 1.2.1 | Internal Review & Critique | Activation Ideas | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.1.1.4 |  |  | 0 | 0
1479 | DEL-0036 | TSK-01470 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.2.1 | 1.2.1.2 | Internal Review & Critique | Activation Ideas | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.1.2 |  |  | 0 | 0
1480 | DEL-0036 | TSK-01471 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.2.2 | 1.2.1.2 | Internal Review & Critique | Activation Ideas | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.1.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3 | 1.2.1 | Client Review & Revisions | Activation Ideas | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.1.2.2 |  |  | 0 | 0
1471 | DEL-0036 | TSK-01462 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3.1 | 1.2.1.3 | Client Review & Revisions | Activation Ideas | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.1.3 |  |  | 0 | 0
1472 | DEL-0036 | TSK-01463 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3.2 | 1.2.1.3 | Client Review & Revisions | Activation Ideas | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.1.3.1 |  |  | 0 | 0
1473 | DEL-0036 | TSK-01464 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3.3 | 1.2.1.3 | Client Review & Revisions | Activation Ideas | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.1.3.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2 | 1.2 | Art Direction | Art Direction |  |  |  | 29 | 15 | 11 | 1.2.1 |  |  | 195 | 5655
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2.1 | 1.2.2 | Moodboards & References | Art Direction | Moodboards & References |  |  | 0 | 15 | 6 | 1.2.2 |  |  | 0 | 0
1487 | DEL-0036 | TSK-01478 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2.1.1 | 1.2.2.1 | Moodboards & References | Art Direction | Moodboards & References | Creative Director | Lead/Director | 3 |  |  | 1.2.2.1 |  |  | 0 | 0
1484 | DEL-0036 | TSK-01475 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2.1.2 | 1.2.2.1 | Moodboards & References | Art Direction | Moodboards & References | Designer | Mid | 16 |  |  | 1.2.2.1.1 |  |  | 0 | 0
1489 | DEL-0036 | TSK-01480 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2.1.3 | 1.2.2.1 | Moodboards & References | Art Direction | Moodboards & References | Strategist | Mid | 6 |  |  | 1.2.2.1.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2.2 | 1.2.2 | Internal Review & Critique | Art Direction | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.2.1.3 |  |  | 0 | 0
1485 | DEL-0036 | TSK-01476 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2.2.1 | 1.2.2.2 | Internal Review & Critique | Art Direction | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.2.2 |  |  | 0 | 0
1486 | DEL-0036 | TSK-01477 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2.2.2 | 1.2.2.2 | Internal Review & Critique | Art Direction | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.2.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2.3 | 1.2.2 | Client Review & Revisions | Art Direction | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.2.2.2 |  |  | 0 | 0
1482 | DEL-0036 | TSK-01473 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2.3.1 | 1.2.2.3 | Client Review & Revisions | Art Direction | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.2.3 |  |  | 0 | 0
1483 | DEL-0036 | TSK-01474 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2.3.2 | 1.2.2.3 | Client Review & Revisions | Art Direction | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.2.3.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.3 | 1.2 | Brand Approach for Campaign Period | Brand Approach for Campaign Period |  |  |  | 32 | 15 | 11 | 1.2.2 |  |  | 195 | 6240
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.3.1 | 1.2.3 | Approach Outline | Brand Approach for Campaign Period | Approach Outline |  |  | 0 | 15 | 6 | 1.2.3 |  |  | 0 | 0
1494 | DEL-0036 | TSK-01485 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.3.1.1 | 1.2.3.1 | Approach Outline | Brand Approach for Campaign Period | Approach Outline | Designer | Mid | 16 |  |  | 1.2.3.1 |  |  | 0 | 0
1490 | DEL-0036 | TSK-01481 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.3.1.2 | 1.2.3.1 | Approach Outline | Brand Approach for Campaign Period | Approach Outline | Strategist | Mid | 12 |  |  | 1.2.3.1.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.3.2 | 1.2.3 | Internal Review & Critique | Brand Approach for Campaign Period | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.3.1.2 |  |  | 0 | 0
1495 | DEL-0036 | TSK-01486 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.3.2.1 | 1.2.3.2 | Internal Review & Critique | Brand Approach for Campaign Period | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.3.2 |  |  | 0 | 0
1496 | DEL-0036 | TSK-01487 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.3.2.2 | 1.2.3.2 | Internal Review & Critique | Brand Approach for Campaign Period | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.3.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.3.3 | 1.2.3 | Client Review & Revisions | Brand Approach for Campaign Period | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.3.2.2 |  |  | 0 | 0
1491 | DEL-0036 | TSK-01482 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.3.3.1 | 1.2.3.3 | Client Review & Revisions | Brand Approach for Campaign Period | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.3.3 |  |  | 0 | 0
1492 | DEL-0036 | TSK-01483 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.3.3.2 | 1.2.3.3 | Client Review & Revisions | Brand Approach for Campaign Period | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.3.3.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4 | 1.2 | Campaign Roll-Out/Launch Road Map | Campaign Roll-Out/Launch Road Map |  |  |  | 30 | 15 | 11 | 1.2.3 |  |  | 195 | 5850
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4.1 | 1.2.4 | Phasing & Milestones | Campaign Roll-Out/Launch Road Map | Phasing & Milestones |  |  | 0 | 15 | 6 | 1.2.4 |  |  | 0 | 0
1501 | DEL-0036 | TSK-01492 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4.1.1 | 1.2.4.1 | Phasing & Milestones | Campaign Roll-Out/Launch Road Map | Phasing & Milestones | Designer | Mid | 16 |  |  | 1.2.4.1 |  |  | 0 | 0
1500 | DEL-0036 | TSK-01491 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4.1.2 | 1.2.4.1 | Phasing & Milestones | Campaign Roll-Out/Launch Road Map | Phasing & Milestones | Project Manager | Mid | 4 |  |  | 1.2.4.1.1 |  |  | 0 | 0
1505 | DEL-0036 | TSK-01496 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4.1.3 | 1.2.4.1 | Phasing & Milestones | Campaign Roll-Out/Launch Road Map | Phasing & Milestones | Strategist | Mid | 6 |  |  | 1.2.4.1.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4.2 | 1.2.4 | Internal Review & Critique | Campaign Roll-Out/Launch Road Map | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.4.1.3 |  |  | 0 | 0
1502 | DEL-0036 | TSK-01493 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4.2.1 | 1.2.4.2 | Internal Review & Critique | Campaign Roll-Out/Launch Road Map | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.4.2 |  |  | 0 | 0
1503 | DEL-0036 | TSK-01494 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4.2.2 | 1.2.4.2 | Internal Review & Critique | Campaign Roll-Out/Launch Road Map | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.4.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4.3 | 1.2.4 | Client Review & Revisions | Campaign Roll-Out/Launch Road Map | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.4.2.2 |  |  | 0 | 0
1498 | DEL-0036 | TSK-01489 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4.3.1 | 1.2.4.3 | Client Review & Revisions | Campaign Roll-Out/Launch Road Map | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.4.3 |  |  | 0 | 0
1499 | DEL-0036 | TSK-01490 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4.3.2 | 1.2.4.3 | Client Review & Revisions | Campaign Roll-Out/Launch Road Map | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.4.3.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5 | 1.2 | Content Plan | Content Plan |  |  |  | 37 | 15 | 11 | 1.2.4 |  |  | 195 | 7215
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.1 | 1.2.5 | Calendar Draft | Content Plan | Calendar Draft |  |  | 0 | 15 | 6 | 1.2.5 |  |  | 0 | 0
1507 | DEL-0036 | TSK-01498 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.1.1 | 1.2.5.1 | Calendar Draft | Content Plan | Calendar Draft | Copywriter | Mid | 8 |  |  | 1.2.5.1 |  |  | 0 | 0
1513 | DEL-0036 | TSK-01504 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.1.2 | 1.2.5.1 | Calendar Draft | Content Plan | Calendar Draft | Designer | Mid | 16 |  |  | 1.2.5.1.1 |  |  | 0 | 0
1508 | DEL-0036 | TSK-01499 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.1.3 | 1.2.5.1 | Calendar Draft | Content Plan | Calendar Draft | Project Manager | Mid | 2 |  |  | 1.2.5.1.2 |  |  | 0 | 0
1517 | DEL-0036 | TSK-01508 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.1.4 | 1.2.5.1 | Calendar Draft | Content Plan | Calendar Draft | Strategist | Mid | 6 |  |  | 1.2.5.1.3 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.2 | 1.2.5 | Internal Review & Critique | Content Plan | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.5.1.4 |  |  | 0 | 0
1515 | DEL-0036 | TSK-01506 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.2.1 | 1.2.5.2 | Internal Review & Critique | Content Plan | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.5.2 |  |  | 0 | 0
1516 | DEL-0036 | TSK-01507 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.2.2 | 1.2.5.2 | Internal Review & Critique | Content Plan | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.5.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.3 | 1.2.5 | Client Review & Revisions | Content Plan | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.5.2.2 |  |  | 0 | 0
1509 | DEL-0036 | TSK-01500 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.3.1 | 1.2.5.3 | Client Review & Revisions | Content Plan | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.5.3 |  |  | 0 | 0
1510 | DEL-0036 | TSK-01501 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.3.2 | 1.2.5.3 | Client Review & Revisions | Content Plan | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.5.3.1 |  |  | 0 | 0
1511 | DEL-0036 | TSK-01502 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.3.3 | 1.2.5.3 | Client Review & Revisions | Content Plan | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.5.3.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6 | 1.2 | Content Production Shoot Approach | Content Production Shoot Approach |  |  |  | 26 | 15 | 19 | 1.2.5 |  |  | 195 | 5070
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.1 | 1.2.6 | Final Packaging | Content Production Shoot Approach | Final Packaging |  |  | 0 | 15 | 6 | 1.2.6 |  |  | 0 | 0
1520 | DEL-0036 | TSK-01511 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.1.1 | 1.2.6.1 | Final Packaging | Content Production Shoot Approach | Final Packaging | Designer | Mid | 16 |  |  | 1.2.6.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.2 | 1.2.6 | Shoot Approach & Logistics | Content Production Shoot Approach | Shoot Approach & Logistics |  |  | 0 | 26 | 8 | 1.2.6.1.1 |  |  | 0 | 0
1523 | DEL-0036 | TSK-01514 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.2.1 | 1.2.6.2 | Shoot Approach & Logistics | Content Production Shoot Approach | Shoot Approach & Logistics | Creative Director | Lead/Director | 1 |  |  | 1.2.6.2 |  |  | 0 | 0
1524 | DEL-0036 | TSK-01515 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.2.2 | 1.2.6.2 | Shoot Approach & Logistics | Content Production Shoot Approach | Shoot Approach & Logistics | Project Manager | Mid | 4 |  |  | 1.2.6.2.1 |  |  | 0 | 0
1525 | DEL-0036 | TSK-01516 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.2.3 | 1.2.6.2 | Shoot Approach & Logistics | Content Production Shoot Approach | Shoot Approach & Logistics | Strategist | Mid | 1 |  |  | 1.2.6.2.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.3 | 1.2.6 | Internal Review & Critique | Content Production Shoot Approach | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.6.2.3 |  |  | 0 | 0
1521 | DEL-0036 | TSK-01512 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.3.1 | 1.2.6.3 | Internal Review & Critique | Content Production Shoot Approach | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.6.3 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.4 | 1.2.6 | Client Review & Revisions | Content Production Shoot Approach | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.6.3.1 |  |  | 0 | 0
1518 | DEL-0036 | TSK-01509 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.4.1 | 1.2.6.4 | Client Review & Revisions | Content Production Shoot Approach | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.2.6.4 |  |  | 0 | 0
1519 | DEL-0036 | TSK-01510 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.4.2 | 1.2.6.4 | Client Review & Revisions | Content Production Shoot Approach | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.6.4.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7 | 1.2 | Content Types across Full Funnel | Content Types across Full Funnel |  |  |  | 37 | 15 | 11 | 1.2.6 |  |  | 195 | 7215
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.1 | 1.2.7 | Content Type Matrix | Content Types across Full Funnel | Content Type Matrix |  |  | 0 | 15 | 6 | 1.2.7 |  |  | 0 | 0
1537 | DEL-0036 | TSK-01528 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.1.1 | 1.2.7.1 | Content Type Matrix | Content Types across Full Funnel | Content Type Matrix | Copywriter | Mid | 4 |  |  | 1.2.7.1 |  |  | 0 | 0
1538 | DEL-0036 | TSK-01529 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.1.2 | 1.2.7.1 | Content Type Matrix | Content Types across Full Funnel | Content Type Matrix | Designer | Mid | 16 |  |  | 1.2.7.1.1 |  |  | 0 | 0
1539 | DEL-0036 | TSK-01530 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.1.3 | 1.2.7.1 | Content Type Matrix | Content Types across Full Funnel | Content Type Matrix | Strategist | Mid | 12 |  |  | 1.2.7.1.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.2 | 1.2.7 | Internal Review & Critique | Content Types across Full Funnel | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.7.1.3 |  |  | 0 | 0
1542 | DEL-0036 | TSK-01533 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.2.1 | 1.2.7.2 | Internal Review & Critique | Content Types across Full Funnel | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.7.2 |  |  | 0 | 0
1543 | DEL-0036 | TSK-01534 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.2.2 | 1.2.7.2 | Internal Review & Critique | Content Types across Full Funnel | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.7.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.3 | 1.2.7 | Client Review & Revisions | Content Types across Full Funnel | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.7.2.2 |  |  | 0 | 0
1534 | DEL-0036 | TSK-01525 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.3.1 | 1.2.7.3 | Client Review & Revisions | Content Types across Full Funnel | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.7.3 |  |  | 0 | 0
1535 | DEL-0036 | TSK-01526 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.3.2 | 1.2.7.3 | Client Review & Revisions | Content Types across Full Funnel | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.7.3.1 |  |  | 0 | 0
1536 | DEL-0036 | TSK-01527 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.3.3 | 1.2.7.3 | Client Review & Revisions | Content Types across Full Funnel | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.7.3.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8 | 1.2 | Copy Bank | Copy Bank |  |  |  | 17 | 15 | 11 | 1.2.7 |  |  | 195 | 3315
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8.1 | 1.2.8 | Copy Examples (Headlines/Captions/CTAs) | Copy Bank | Copy Examples (Headlines/Captions/CTAs) |  |  | 0 | 15 | 6 | 1.2.8 |  |  | 0 | 0
1547 | DEL-0036 | TSK-01538 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8.1.1 | 1.2.8.1 | Copy Examples (Headlines/Captions/CTAs) | Copy Bank | Copy Examples (Headlines/Captions/CTAs) | Copywriter | Mid | 4 |  |  | 1.2.8.1 |  |  | 0 | 0
1548 | DEL-0036 | TSK-01539 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8.1.2 | 1.2.8.1 | Copy Examples (Headlines/Captions/CTAs) | Copy Bank | Copy Examples (Headlines/Captions/CTAs) | Designer | Mid | 8 |  |  | 1.2.8.1.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8.2 | 1.2.8 | Internal Review & Critique | Copy Bank | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.8.1.2 |  |  | 0 | 0
1549 | DEL-0036 | TSK-01540 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8.2.1 | 1.2.8.2 | Internal Review & Critique | Copy Bank | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.8.2 |  |  | 0 | 0
1550 | DEL-0036 | TSK-01541 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8.2.2 | 1.2.8.2 | Internal Review & Critique | Copy Bank | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.8.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8.3 | 1.2.8 | Client Review & Revisions | Copy Bank | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.8.2.2 |  |  | 0 | 0
1544 | DEL-0036 | TSK-01535 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8.3.1 | 1.2.8.3 | Client Review & Revisions | Copy Bank | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.8.3 |  |  | 0 | 0
1545 | DEL-0036 | TSK-01536 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8.3.2 | 1.2.8.3 | Client Review & Revisions | Copy Bank | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.8.3.1 |  |  | 0 | 0
1546 | DEL-0036 | TSK-01537 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8.3.3 | 1.2.8.3 | Client Review & Revisions | Copy Bank | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.8.3.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.9 | 1.2 | Customer Journey | Customer Journey |  |  |  | 26 | 15 | 11 | 1.2.8 |  |  | 195 | 5070
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.9.1 | 1.2.9 | Journey Mapping | Customer Journey | Journey Mapping |  |  | 0 | 15 | 6 | 1.2.9 |  |  | 0 | 0
1553 | DEL-0036 | TSK-01544 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.9.1.1 | 1.2.9.1 | Journey Mapping | Customer Journey | Journey Mapping | Designer | Mid | 16 |  |  | 1.2.9.1 |  |  | 0 | 0
1557 | DEL-0036 | TSK-01548 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.9.1.2 | 1.2.9.1 | Journey Mapping | Customer Journey | Journey Mapping | Strategist | Mid | 6 |  |  | 1.2.9.1.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.9.2 | 1.2.9 | Internal Review & Critique | Customer Journey | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.9.1.2 |  |  | 0 | 0
1554 | DEL-0036 | TSK-01545 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.9.2.1 | 1.2.9.2 | Internal Review & Critique | Customer Journey | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.9.2 |  |  | 0 | 0
1555 | DEL-0036 | TSK-01546 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.9.2.2 | 1.2.9.2 | Internal Review & Critique | Customer Journey | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.9.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.9.3 | 1.2.9 | Client Review & Revisions | Customer Journey | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.9.2.2 |  |  | 0 | 0
1551 | DEL-0036 | TSK-01542 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.9.3.1 | 1.2.9.3 | Client Review & Revisions | Customer Journey | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.9.3 |  |  | 0 | 0
1552 | DEL-0036 | TSK-01543 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.9.3.2 | 1.2.9.3 | Client Review & Revisions | Customer Journey | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.9.3.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10 | 1.2 | High-Fidelity Organic Social Mock-Ups | High-Fidelity Organic Social Mock-Ups |  |  |  | 28 | 15 | 11 | 1.2.9 |  |  | 195 | 5460
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.1 | 1.2.10 | Concept & Layouts (3-4 ex.) | High-Fidelity Organic Social Mock-Ups | Concept & Layouts (3-4 ex.) |  |  | 0 | 15 | 6 | 1.2.10 |  |  | 0 | 0
1561 | DEL-0036 | TSK-01552 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.1.1 | 1.2.10.1 | Concept & Layouts (3-4 ex.) | High-Fidelity Organic Social Mock-Ups | Concept & Layouts (3-4 ex.) | Copywriter | Mid | 4 |  |  | 1.2.10.1 |  |  | 0 | 0
1562 | DEL-0036 | TSK-01553 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.1.2 | 1.2.10.1 | Concept & Layouts (3-4 ex.) | High-Fidelity Organic Social Mock-Ups | Concept & Layouts (3-4 ex.) | Creative Director | Lead/Director | 3 |  |  | 1.2.10.1.1 |  |  | 0 | 0
1563 | DEL-0036 | TSK-01554 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.1.3 | 1.2.10.1 | Concept & Layouts (3-4 ex.) | High-Fidelity Organic Social Mock-Ups | Concept & Layouts (3-4 ex.) | Designer | Mid | 16 |  |  | 1.2.10.1.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.2 | 1.2.10 | Internal Review & Critique | High-Fidelity Organic Social Mock-Ups | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.10.1.3 |  |  | 0 | 0
1565 | DEL-0036 | TSK-01556 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.2.1 | 1.2.10.2 | Internal Review & Critique | High-Fidelity Organic Social Mock-Ups | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.10.2 |  |  | 0 | 0
1566 | DEL-0036 | TSK-01557 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.2.2 | 1.2.10.2 | Internal Review & Critique | High-Fidelity Organic Social Mock-Ups | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.10.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.3 | 1.2.10 | Client Review & Revisions | High-Fidelity Organic Social Mock-Ups | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.10.2.2 |  |  | 0 | 0
1558 | DEL-0036 | TSK-01549 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.3.1 | 1.2.10.3 | Client Review & Revisions | High-Fidelity Organic Social Mock-Ups | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.10.3 |  |  | 0 | 0
1559 | DEL-0036 | TSK-01550 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.3.2 | 1.2.10.3 | Client Review & Revisions | High-Fidelity Organic Social Mock-Ups | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.10.3.1 |  |  | 0 | 0
1560 | DEL-0036 | TSK-01551 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.3.3 | 1.2.10.3 | Client Review & Revisions | High-Fidelity Organic Social Mock-Ups | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.10.3.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11 | 1.2 | High-Fidelity Paid Media Mock-Ups | High-Fidelity Paid Media Mock-Ups |  |  |  | 28 | 15 | 11 | 1.2.10 |  |  | 195 | 5460
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.1 | 1.2.11 | Concept & Layouts (3-4 ex.) | High-Fidelity Paid Media Mock-Ups | Concept & Layouts (3-4 ex.) |  |  | 0 | 15 | 6 | 1.2.11 |  |  | 0 | 0
1570 | DEL-0036 | TSK-01561 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.1.1 | 1.2.11.1 | Concept & Layouts (3-4 ex.) | High-Fidelity Paid Media Mock-Ups | Concept & Layouts (3-4 ex.) | Copywriter | Mid | 4 |  |  | 1.2.11.1 |  |  | 0 | 0
1571 | DEL-0036 | TSK-01562 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.1.2 | 1.2.11.1 | Concept & Layouts (3-4 ex.) | High-Fidelity Paid Media Mock-Ups | Concept & Layouts (3-4 ex.) | Creative Director | Lead/Director | 3 |  |  | 1.2.11.1.1 |  |  | 0 | 0
1572 | DEL-0036 | TSK-01563 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.1.3 | 1.2.11.1 | Concept & Layouts (3-4 ex.) | High-Fidelity Paid Media Mock-Ups | Concept & Layouts (3-4 ex.) | Designer | Mid | 16 |  |  | 1.2.11.1.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.2 | 1.2.11 | Internal Review & Critique | High-Fidelity Paid Media Mock-Ups | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.11.1.3 |  |  | 0 | 0
1574 | DEL-0036 | TSK-01565 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.2.1 | 1.2.11.2 | Internal Review & Critique | High-Fidelity Paid Media Mock-Ups | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.11.2 |  |  | 0 | 0
1575 | DEL-0036 | TSK-01566 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.2.2 | 1.2.11.2 | Internal Review & Critique | High-Fidelity Paid Media Mock-Ups | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.11.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.3 | 1.2.11 | Client Review & Revisions | High-Fidelity Paid Media Mock-Ups | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.11.2.2 |  |  | 0 | 0
1567 | DEL-0036 | TSK-01558 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.3.1 | 1.2.11.3 | Client Review & Revisions | High-Fidelity Paid Media Mock-Ups | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.11.3 |  |  | 0 | 0
1568 | DEL-0036 | TSK-01559 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.3.2 | 1.2.11.3 | Client Review & Revisions | High-Fidelity Paid Media Mock-Ups | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.11.3.1 |  |  | 0 | 0
1569 | DEL-0036 | TSK-01560 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.3.3 | 1.2.11.3 | Client Review & Revisions | High-Fidelity Paid Media Mock-Ups | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.11.3.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12 | 1.2 | Influencer Partnership Approach | Influencer Partnership Approach |  |  |  | 31 | 15 | 11 | 1.2.11 |  |  | 195 | 6045
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.1 | 1.2.12 | Outreach & Compensation Framework | Influencer Partnership Approach | Outreach & Compensation Framework |  |  | 0 | 15 | 6 | 1.2.12 |  |  | 0 | 0
1583 | DEL-0036 | TSK-01574 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.1.1 | 1.2.12.1 | Outreach & Compensation Framework | Influencer Partnership Approach | Outreach & Compensation Framework | Account Manager | Mid | 2 |  |  | 1.2.12.1 |  |  | 0 | 0
1579 | DEL-0036 | TSK-01570 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.1.2 | 1.2.12.1 | Outreach & Compensation Framework | Influencer Partnership Approach | Outreach & Compensation Framework | Copywriter | Mid | 4 |  |  | 1.2.12.1.1 |  |  | 0 | 0
1580 | DEL-0036 | TSK-01571 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.1.3 | 1.2.12.1 | Outreach & Compensation Framework | Influencer Partnership Approach | Outreach & Compensation Framework | Designer | Mid | 8 |  |  | 1.2.12.1.2 |  |  | 0 | 0
1584 | DEL-0036 | TSK-01575 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.1.4 | 1.2.12.1 | Outreach & Compensation Framework | Influencer Partnership Approach | Outreach & Compensation Framework | Strategist | Mid | 12 |  |  | 1.2.12.1.3 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.2 | 1.2.12 | Internal Review & Critique | Influencer Partnership Approach | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.12.1.4 |  |  | 0 | 0
1581 | DEL-0036 | TSK-01572 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.2.1 | 1.2.12.2 | Internal Review & Critique | Influencer Partnership Approach | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.12.2 |  |  | 0 | 0
1582 | DEL-0036 | TSK-01573 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.2.2 | 1.2.12.2 | Internal Review & Critique | Influencer Partnership Approach | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.12.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.3 | 1.2.12 | Client Review & Revisions | Influencer Partnership Approach | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.12.2.2 |  |  | 0 | 0
1576 | DEL-0036 | TSK-01567 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.3.1 | 1.2.12.3 | Client Review & Revisions | Influencer Partnership Approach | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.12.3 |  |  | 0 | 0
1577 | DEL-0036 | TSK-01568 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.3.2 | 1.2.12.3 | Client Review & Revisions | Influencer Partnership Approach | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.12.3.1 |  |  | 0 | 0
1578 | DEL-0036 | TSK-01569 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.3.3 | 1.2.12.3 | Client Review & Revisions | Influencer Partnership Approach | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.12.3.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13 | 1.2 | Kick-Off Session | Kick-Off Session |  |  |  | 55 | 15 | 11 | 1.2.12 |  |  | 195 | 10725
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.1 | 1.2.13 | Agenda & Materials Prep | Kick-Off Session | Agenda & Materials Prep |  |  | 0 | 15 | 6 | 1.2.13 |  |  | 0 | 0
1586 | DEL-0036 | TSK-01577 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.1.1 | 1.2.13.1 | Agenda & Materials Prep | Kick-Off Session | Agenda & Materials Prep | Account Manager | Mid | 6 |  |  | 1.2.13.1 |  |  | 0 | 0
1593 | DEL-0036 | TSK-01584 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.1.2 | 1.2.13.1 | Agenda & Materials Prep | Kick-Off Session | Agenda & Materials Prep | Creative Director | Lead/Director | 3 |  |  | 1.2.13.1.1 |  |  | 0 | 0
1587 | DEL-0036 | TSK-01578 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.1.3 | 1.2.13.1 | Agenda & Materials Prep | Kick-Off Session | Agenda & Materials Prep | Designer | Mid | 16 |  |  | 1.2.13.1.2 |  |  | 0 | 0
1588 | DEL-0036 | TSK-01579 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.1.4 | 1.2.13.1 | Agenda & Materials Prep | Kick-Off Session | Agenda & Materials Prep | Project Manager | Mid | 2 |  |  | 1.2.13.1.3 |  |  | 0 | 0
1589 | DEL-0036 | TSK-01580 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.1.5 | 1.2.13.1 | Agenda & Materials Prep | Kick-Off Session | Agenda & Materials Prep | Strategist | Mid | 24 |  |  | 1.2.13.1.4 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.2 | 1.2.13 | Internal Review & Critique | Kick-Off Session | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.13.1.5 |  |  | 0 | 0
1596 | DEL-0036 | TSK-01587 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.2.1 | 1.2.13.2 | Internal Review & Critique | Kick-Off Session | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.13.2 |  |  | 0 | 0
1597 | DEL-0036 | TSK-01588 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.2.2 | 1.2.13.2 | Internal Review & Critique | Kick-Off Session | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.13.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.3 | 1.2.13 | Client Review & Revisions | Kick-Off Session | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.13.2.2 |  |  | 0 | 0
1590 | DEL-0036 | TSK-01581 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.3.1 | 1.2.13.3 | Client Review & Revisions | Kick-Off Session | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.13.3 |  |  | 0 | 0
1591 | DEL-0036 | TSK-01582 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.3.2 | 1.2.13.3 | Client Review & Revisions | Kick-Off Session | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.13.3.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14 | 1.2 | Messaging Framework (by Audience) | Messaging Framework (by Audience) |  |  |  | 37 | 15 | 11 | 1.2.13 |  |  | 195 | 7215
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.1 | 1.2.14 | Draft Messaging | Messaging Framework (by Audience) | Draft Messaging |  |  | 0 | 15 | 6 | 1.2.14 |  |  | 0 | 0
1605 | DEL-0036 | TSK-01596 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.1.1 | 1.2.14.1 | Draft Messaging | Messaging Framework (by Audience) | Draft Messaging | Copywriter | Mid | 4 |  |  | 1.2.14.1 |  |  | 0 | 0
1604 | DEL-0036 | TSK-01595 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.1.2 | 1.2.14.1 | Draft Messaging | Messaging Framework (by Audience) | Draft Messaging | Designer | Mid | 16 |  |  | 1.2.14.1.1 |  |  | 0 | 0
1606 | DEL-0036 | TSK-01597 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.1.3 | 1.2.14.1 | Draft Messaging | Messaging Framework (by Audience) | Draft Messaging | Strategist | Mid | 12 |  |  | 1.2.14.1.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.2 | 1.2.14 | Internal Review & Critique | Messaging Framework (by Audience) | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.14.1.3 |  |  | 0 | 0
1608 | DEL-0036 | TSK-01599 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.2.1 | 1.2.14.2 | Internal Review & Critique | Messaging Framework (by Audience) | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.14.2 |  |  | 0 | 0
1609 | DEL-0036 | TSK-01600 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.2.2 | 1.2.14.2 | Internal Review & Critique | Messaging Framework (by Audience) | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.14.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.3 | 1.2.14 | Client Review & Revisions | Messaging Framework (by Audience) | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.14.2.2 |  |  | 0 | 0
1601 | DEL-0036 | TSK-01592 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.3.1 | 1.2.14.3 | Client Review & Revisions | Messaging Framework (by Audience) | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.14.3 |  |  | 0 | 0
1602 | DEL-0036 | TSK-01593 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.3.2 | 1.2.14.3 | Client Review & Revisions | Messaging Framework (by Audience) | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.14.3.1 |  |  | 0 | 0
1603 | DEL-0036 | TSK-01594 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.3.3 | 1.2.14.3 | Client Review & Revisions | Messaging Framework (by Audience) | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.14.3.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15 | 1.2 | Platform/Channel Approach | Platform/Channel Approach |  |  |  | 29 | 15 | 15 | 1.2.14 |  |  | 195 | 5655
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.1 | 1.2.15 | Baseline KPIs | Platform/Channel Approach | Baseline KPIs |  |  | 0 | 15 | 6 | 1.2.15 |  |  | 0 | 0
1611 | DEL-0036 | TSK-01602 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.1.1 | 1.2.15.1 | Baseline KPIs | Platform/Channel Approach | Baseline KPIs | Analyst | Mid | 3 |  |  | 1.2.15.1 |  |  | 0 | 0
1616 | DEL-0036 | TSK-01607 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.1.2 | 1.2.15.1 | Baseline KPIs | Platform/Channel Approach | Baseline KPIs | Designer | Mid | 8 |  |  | 1.2.15.1.1 |  |  | 0 | 0
1612 | DEL-0036 | TSK-01603 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.1.3 | 1.2.15.1 | Baseline KPIs | Platform/Channel Approach | Baseline KPIs | Strategist | Mid | 12 |  |  | 1.2.15.1.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.2 | 1.2.15 | Summary Slides | Platform/Channel Approach | Summary Slides |  |  | 0 | 34 | 4 | 1.2.15.1.3 |  |  | 0 | 0
1619 | DEL-0036 | TSK-01610 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.2.1 | 1.2.15.2 | Summary Slides | Platform/Channel Approach | Summary Slides | Designer | Mid | 2 |  |  | 1.2.15.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.3 | 1.2.15 | Internal Review & Critique | Platform/Channel Approach | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.15.2.1 |  |  | 0 | 0
1617 | DEL-0036 | TSK-01608 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.3.1 | 1.2.15.3 | Internal Review & Critique | Platform/Channel Approach | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.15.3 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.4 | 1.2.15 | Client Review & Revisions | Platform/Channel Approach | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.15.3.1 |  |  | 0 | 0
1614 | DEL-0036 | TSK-01605 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.4.1 | 1.2.15.4 | Client Review & Revisions | Platform/Channel Approach | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.2.15.4 |  |  | 0 | 0
1615 | DEL-0036 | TSK-01606 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.4.2 | 1.2.15.4 | Client Review & Revisions | Platform/Channel Approach | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.15.4.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.16 | 1.2 | Social Templates | Social Templates |  |  |  | 31 | 15 | 11 | 1.2.15 |  |  | 195 | 6045
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.16.1 | 1.2.16 | Template Exploration | Social Templates | Template Exploration |  |  | 0 | 15 | 6 | 1.2.16 |  |  | 0 | 0
1626 | DEL-0036 | TSK-01617 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.16.1.1 | 1.2.16.1 | Template Exploration | Social Templates | Template Exploration | Creative Director | Lead/Director | 3 |  |  | 1.2.16.1 |  |  | 0 | 0
1622 | DEL-0036 | TSK-01613 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.16.1.2 | 1.2.16.1 | Template Exploration | Social Templates | Template Exploration | Designer | Mid | 24 |  |  | 1.2.16.1.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.16.2 | 1.2.16 | Internal Review & Critique | Social Templates | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.16.1.2 |  |  | 0 | 0
1623 | DEL-0036 | TSK-01614 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.16.2.1 | 1.2.16.2 | Internal Review & Critique | Social Templates | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.16.2 |  |  | 0 | 0
1624 | DEL-0036 | TSK-01615 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.16.2.2 | 1.2.16.2 | Internal Review & Critique | Social Templates | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.16.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.16.3 | 1.2.16 | Client Review & Revisions | Social Templates | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.16.2.2 |  |  | 0 | 0
1620 | DEL-0036 | TSK-01611 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.16.3.1 | 1.2.16.3 | Client Review & Revisions | Social Templates | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.16.3 |  |  | 0 | 0
1621 | DEL-0036 | TSK-01612 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.16.3.2 | 1.2.16.3 | Client Review & Revisions | Social Templates | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.16.3.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17 | 1.2 | Visual Approach | Visual Approach |  |  |  | 29 | 15 | 11 | 1.2.16 |  |  | 195 | 5655
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17.1 | 1.2.17 | Moodboards & References | Visual Approach | Moodboards & References |  |  | 0 | 15 | 6 | 1.2.17 |  |  | 0 | 0
1633 | DEL-0036 | TSK-01624 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17.1.1 | 1.2.17.1 | Moodboards & References | Visual Approach | Moodboards & References | Creative Director | Lead/Director | 3 |  |  | 1.2.17.1 |  |  | 0 | 0
1630 | DEL-0036 | TSK-01621 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17.1.2 | 1.2.17.1 | Moodboards & References | Visual Approach | Moodboards & References | Designer | Mid | 16 |  |  | 1.2.17.1.1 |  |  | 0 | 0
1635 | DEL-0036 | TSK-01626 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17.1.3 | 1.2.17.1 | Moodboards & References | Visual Approach | Moodboards & References | Strategist | Mid | 6 |  |  | 1.2.17.1.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17.2 | 1.2.17 | Internal Review & Critique | Visual Approach | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.17.1.3 |  |  | 0 | 0
1631 | DEL-0036 | TSK-01622 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17.2.1 | 1.2.17.2 | Internal Review & Critique | Visual Approach | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.17.2 |  |  | 0 | 0
1632 | DEL-0036 | TSK-01623 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17.2.2 | 1.2.17.2 | Internal Review & Critique | Visual Approach | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.17.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17.3 | 1.2.17 | Client Review & Revisions | Visual Approach | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.17.2.2 |  |  | 0 | 0
1628 | DEL-0036 | TSK-01619 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17.3.1 | 1.2.17.3 | Client Review & Revisions | Visual Approach | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.17.3 |  |  | 0 | 0
1629 | DEL-0036 | TSK-01620 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17.3.2 | 1.2.17.3 | Client Review & Revisions | Visual Approach | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.17.3.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18 | 1.2 | Voice & Tone | Voice & Tone |  |  |  | 27 | 15 | 11 | 1.2.17 |  |  | 195 | 5265
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.1 | 1.2.18 | Principles Outline | Voice & Tone | Principles Outline |  |  | 0 | 15 | 6 | 1.2.18 |  |  | 0 | 0
1639 | DEL-0036 | TSK-01630 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.1.1 | 1.2.18.1 | Principles Outline | Voice & Tone | Principles Outline | Copywriter | Mid | 8 |  |  | 1.2.18.1 |  |  | 0 | 0
1640 | DEL-0036 | TSK-01631 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.1.2 | 1.2.18.1 | Principles Outline | Voice & Tone | Principles Outline | Designer | Mid | 8 |  |  | 1.2.18.1.1 |  |  | 0 | 0
1644 | DEL-0036 | TSK-01635 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.1.3 | 1.2.18.1 | Principles Outline | Voice & Tone | Principles Outline | Strategist | Mid | 6 |  |  | 1.2.18.1.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.2 | 1.2.18 | Internal Review & Critique | Voice & Tone | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.18.1.3 |  |  | 0 | 0
1641 | DEL-0036 | TSK-01632 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.2.1 | 1.2.18.2 | Internal Review & Critique | Voice & Tone | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.18.2 |  |  | 0 | 0
1642 | DEL-0036 | TSK-01633 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.2.2 | 1.2.18.2 | Internal Review & Critique | Voice & Tone | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.18.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.3 | 1.2.18 | Client Review & Revisions | Voice & Tone | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.18.2.2 |  |  | 0 | 0
1636 | DEL-0036 | TSK-01627 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.3.1 | 1.2.18.3 | Client Review & Revisions | Voice & Tone | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.18.3 |  |  | 0 | 0
1637 | DEL-0036 | TSK-01628 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.3.2 | 1.2.18.3 | Client Review & Revisions | Voice & Tone | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.18.3.1 |  |  | 0 | 0
1638 | DEL-0036 | TSK-01629 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.3.3 | 1.2.18.3 | Client Review & Revisions | Voice & Tone | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.18.3.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.19 | 1.2 | Content Production Shot List Review & Guidance | Content Production Shot List Review & Guidance |  |  |  | 13 | 21 | 5 | 1.2.18 |  |  | 195 | 2535
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.19.1 | 1.2.19 | Client Review & Revisions | Content Production Shot List Review & Guidance | Client Review & Revisions |  |  | 0 | 21 | 5 | 1.2.19 |  |  | 0 | 0
1527 | DEL-0036 | TSK-01518 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.19.1.1 | 1.2.19.1 | Client Review & Revisions | Content Production Shot List Review & Guidance | Client Review & Revisions | Account Manager | Mid | 3 |  |  | 1.2.19.1 |  |  | 0 | 0
1530 | DEL-0036 | TSK-01521 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.19.1.2 | 1.2.19.1 | Client Review & Revisions | Content Production Shot List Review & Guidance | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.19.1.1 |  |  | 0 | 0
1529 | DEL-0036 | TSK-01520 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.19.1.3 | 1.2.19.1 | Client Review & Revisions | Content Production Shot List Review & Guidance | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.2.19.1.2 |  |  | 0 | 0
1528 | DEL-0036 | TSK-01519 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.19.1.4 | 1.2.19.1 | Client Review & Revisions | Content Production Shot List Review & Guidance | Client Review & Revisions | Strategist | Mid | 6 |  |  | 1.2.19.1.3 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3 | 1 | Paid Media Strategy |  |  |  |  | 162 | 43 | 46 | 1.2 |  | Advanced/T2_MediumVolume | 195 | 31590
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.1 | 1.3 | Audience Research | Audience Research |  |  |  | 13 | 43 | 9 | 1.3 |  |  | 195 | 2535
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.1.1 | 1.3.1 | Audience Build & Rationale | Audience Research | Audience Build & Rationale |  |  | 0 | 43 | 4 | 1.3.1 |  |  | 0 | 0
1266 | DEL-0030 | TSK-01257 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.1.1.1 | 1.3.1.1 | Audience Build & Rationale | Audience Research | Audience Build & Rationale | Analyst | Mid | 5 |  |  | 1.3.1.1 |  |  | 0 | 0
1261 | DEL-0030 | TSK-01252 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.1.1.2 | 1.3.1.1 | Audience Build & Rationale | Audience Research | Audience Build & Rationale | Media Strategist | Mid | 4 |  |  | 1.3.1.1.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.1.2 | 1.3.1 | Internal Review & Critique | Audience Research | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.1.1.2 |  |  | 0 | 0
1264 | DEL-0030 | TSK-01255 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.1.2.1 | 1.3.1.2 | Internal Review & Critique | Audience Research | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.1.2 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.1.3 | 1.3.1 | Client Review & Revisions | Audience Research | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.1.2.1 |  |  | 0 | 0
1262 | DEL-0030 | TSK-01253 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.1.3.1 | 1.3.1.3 | Client Review & Revisions | Audience Research | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.3.1.3 |  |  | 0 | 0
1263 | DEL-0030 | TSK-01254 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.1.3.2 | 1.3.1.3 | Client Review & Revisions | Audience Research | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.1.3.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2 | 1.3 | Keyword List Development | Keyword List Development |  |  |  | 16 | 43 | 20 | 1.3.1 |  |  | 195 | 3120
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2.1 | 1.3.2 | Keyword Discovery | Keyword List Development | Keyword Discovery |  |  | 0 | 43 | 4 | 1.3.2 |  |  | 0 | 0
1290 | DEL-0030 | TSK-01281 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2.1.1 | 1.3.2.1 | Keyword Discovery | Keyword List Development | Keyword Discovery | Analyst | Mid | 5 |  |  | 1.3.2.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2.2 | 1.3.2 | List Development & Grouping | Keyword List Development | List Development & Grouping |  |  | 0 | 71 | 11 | 1.3.2.1.1 |  |  | 0 | 0
1291 | DEL-0030 | TSK-01282 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2.2.1 | 1.3.2.2 | List Development & Grouping | Keyword List Development | List Development & Grouping | Media Strategist | Mid | 7 |  |  | 1.3.2.2 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2.3 | 1.3.2 | Internal Review & Critique | Keyword List Development | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.2.2.1 |  |  | 0 | 0
1288 | DEL-0030 | TSK-01279 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2.3.1 | 1.3.2.3 | Internal Review & Critique | Keyword List Development | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.2.3 |  |  | 0 | 0
1289 | DEL-0030 | TSK-01280 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2.3.2 | 1.3.2.3 | Internal Review & Critique | Keyword List Development | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.2.3.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2.4 | 1.3.2 | Client Review & Revisions | Keyword List Development | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.2.3.2 |  |  | 0 | 0
1286 | DEL-0030 | TSK-01277 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2.4.1 | 1.3.2.4 | Client Review & Revisions | Keyword List Development | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.2.4 |  |  | 0 | 0
1287 | DEL-0030 | TSK-01278 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2.4.2 | 1.3.2.4 | Client Review & Revisions | Keyword List Development | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.2.4.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3 | 1.3 | Paid Media & Paid Creative Audit | Paid Media & Paid Creative Audit |  |  |  | 23 | 43 | 15 | 1.3.2 |  |  | 195 | 4485
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.1 | 1.3.3 | Platform/Creative Audit | Paid Media & Paid Creative Audit | Platform/Creative Audit |  |  | 0 | 43 | 4 | 1.3.3 |  |  | 0 | 0
1308 | DEL-0030 | TSK-01299 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.1.1 | 1.3.3.1 | Platform/Creative Audit | Paid Media & Paid Creative Audit | Platform/Creative Audit | Analyst | Mid | 5 |  |  | 1.3.3.1 |  |  | 0 | 0
1304 | DEL-0030 | TSK-01295 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.1.2 | 1.3.3.1 | Platform/Creative Audit | Paid Media & Paid Creative Audit | Platform/Creative Audit | Designer | Mid | 3 |  |  | 1.3.3.1.1 |  |  | 0 | 0
1309 | DEL-0030 | TSK-01300 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.1.3 | 1.3.3.1 | Platform/Creative Audit | Paid Media & Paid Creative Audit | Platform/Creative Audit | Media Strategist | Mid | 3 |  |  | 1.3.3.1.2 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.2 | 1.3.3 | Findings Deck | Paid Media & Paid Creative Audit | Findings Deck |  |  | 0 | 47 | 6 | 1.3.3.1.3 |  |  | 0 | 0
1305 | DEL-0030 | TSK-01296 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.2.1 | 1.3.3.2 | Findings Deck | Paid Media & Paid Creative Audit | Findings Deck | Designer | Mid | 8 |  |  | 1.3.3.2 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.3 | 1.3.3 | Internal Review & Critique | Paid Media & Paid Creative Audit | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.3.2.1 |  |  | 0 | 0
1306 | DEL-0030 | TSK-01297 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.3.1 | 1.3.3.3 | Internal Review & Critique | Paid Media & Paid Creative Audit | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.3.3 |  |  | 0 | 0
1307 | DEL-0030 | TSK-01298 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.3.2 | 1.3.3.3 | Internal Review & Critique | Paid Media & Paid Creative Audit | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.3.3.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.4 | 1.3.3 | Client Review & Revisions | Paid Media & Paid Creative Audit | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.3.3.2 |  |  | 0 | 0
1302 | DEL-0030 | TSK-01293 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.4.1 | 1.3.3.4 | Client Review & Revisions | Paid Media & Paid Creative Audit | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.3.4 |  |  | 0 | 0
1303 | DEL-0030 | TSK-01294 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.4.2 | 1.3.3.4 | Client Review & Revisions | Paid Media & Paid Creative Audit | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.3.4.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4 | 1.3 | Mock Ad Examples | Mock Ad Examples |  |  |  | 16 | 53 | 17 | 1.3.3 |  |  | 195 | 3120
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.1 | 1.3.4 | Concept & Copy | Mock Ad Examples | Concept & Copy |  |  | 0 | 53 | 4 | 1.3.4 |  |  | 0 | 0
1296 | DEL-0030 | TSK-01287 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.1.1 | 1.3.4.1 | Concept & Copy | Mock Ad Examples | Concept & Copy | Copywriter | Mid | 3 |  |  | 1.3.4.1 |  |  | 0 | 0
1297 | DEL-0030 | TSK-01288 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.1.2 | 1.3.4.1 | Concept & Copy | Mock Ad Examples | Concept & Copy | Creative Director | Lead/Director | 2 |  |  | 1.3.4.1.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.2 | 1.3.4 | Design (3-4 mocks) | Mock Ad Examples | Design (3-4 mocks) |  |  | 0 | 57 | 8 | 1.3.4.1.2 |  |  | 0 | 0
1298 | DEL-0030 | TSK-01289 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.2.1 | 1.3.4.2 | Design (3-4 mocks) | Mock Ad Examples | Design (3-4 mocks) | Designer | Mid | 4 |  |  | 1.3.4.2 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.3 | 1.3.4 | Internal Review & Critique | Mock Ad Examples | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.4.2.1 |  |  | 0 | 0
1300 | DEL-0030 | TSK-01291 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.3.1 | 1.3.4.3 | Internal Review & Critique | Mock Ad Examples | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.4.3 |  |  | 0 | 0
1301 | DEL-0030 | TSK-01292 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.3.2 | 1.3.4.3 | Internal Review & Critique | Mock Ad Examples | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.4.3.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.4 | 1.3.4 | Client Review & Revisions | Mock Ad Examples | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.4.3.2 |  |  | 0 | 0
1293 | DEL-0030 | TSK-01284 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.4.1 | 1.3.4.4 | Client Review & Revisions | Mock Ad Examples | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.4.4 |  |  | 0 | 0
1294 | DEL-0030 | TSK-01285 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.4.2 | 1.3.4.4 | Client Review & Revisions | Mock Ad Examples | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.3.4.4.1 |  |  | 0 | 0
1295 | DEL-0030 | TSK-01286 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.4.3 | 1.3.4.4 | Client Review & Revisions | Mock Ad Examples | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.4.4.2 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.5 | 1.3.4 | Final Packaging | Mock Ad Examples | Final Packaging |  |  | 0 | 89 | 0 | 1.3.4.4.3 |  |  | 0 | 0
1299 | DEL-0030 | TSK-01290 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.5.1 | 1.3.4.5 | Final Packaging | Mock Ad Examples | Final Packaging | Designer | Mid | 2 |  |  | 1.3.4.5 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.5 | 1.3 | Campaigns | Campaigns |  |  |  | 24 | 65 | 11 | 1.3.4 |  |  | 195 | 4680
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.5.1 | 1.3.5 | Campaign Architecture | Campaigns | Campaign Architecture |  |  | 0 | 65 | 6 | 1.3.5 |  |  | 0 | 0
1273 | DEL-0030 | TSK-01264 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.5.1.1 | 1.3.5.1 | Campaign Architecture | Campaigns | Campaign Architecture | Media Planner | Mid | 10 |  |  | 1.3.5.1 |  |  | 0 | 0
1274 | DEL-0030 | TSK-01265 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.5.1.2 | 1.3.5.1 | Campaign Architecture | Campaigns | Campaign Architecture | Media Strategist | Mid | 10 |  |  | 1.3.5.1.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.5.2 | 1.3.5 | Internal Review & Critique | Campaigns | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.5.1.2 |  |  | 0 | 0
1277 | DEL-0030 | TSK-01268 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.5.2.1 | 1.3.5.2 | Internal Review & Critique | Campaigns | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.5.2 |  |  | 0 | 0
1278 | DEL-0030 | TSK-01269 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.5.2.2 | 1.3.5.2 | Internal Review & Critique | Campaigns | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.5.2.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.5.3 | 1.3.5 | Client Review & Revisions | Campaigns | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.5.2.2 |  |  | 0 | 0
1275 | DEL-0030 | TSK-01266 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.5.3.1 | 1.3.5.3 | Client Review & Revisions | Campaigns | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.5.3 |  |  | 0 | 0
1276 | DEL-0030 | TSK-01267 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.5.3.2 | 1.3.5.3 | Client Review & Revisions | Campaigns | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.5.3.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.6 | 1.3 | Ad Funnel | Ad Funnel |  |  |  | 16 | 82 | 5 | 1.3.5 |  |  | 195 | 3120
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.6.1 | 1.3.6 | Internal Review & Critique | Ad Funnel | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.6 |  |  | 0 | 0
1257 | DEL-0030 | TSK-01248 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.6.1.1 | 1.3.6.1 | Internal Review & Critique | Ad Funnel | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.6.1 |  |  | 0 | 0
1258 | DEL-0030 | TSK-01249 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.6.1.2 | 1.3.6.1 | Internal Review & Critique | Ad Funnel | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.6.1.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.6.2 | 1.3.6 | Client Review & Revisions | Ad Funnel | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.6.1.2 |  |  | 0 | 0
1253 | DEL-0030 | TSK-01244 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.6.2.1 | 1.3.6.2 | Client Review & Revisions | Ad Funnel | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.6.2 |  |  | 0 | 0
1254 | DEL-0030 | TSK-01245 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.6.2.2 | 1.3.6.2 | Client Review & Revisions | Ad Funnel | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.6.2.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.6.3 | 1.3.6 | Messaging/Asset Mapping | Ad Funnel | Messaging/Asset Mapping |  |  | 0 | 89 | 0 | 1.3.6.2.2 |  |  | 0 | 0
1256 | DEL-0030 | TSK-01247 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.6.3.1 | 1.3.6.3 | Messaging/Asset Mapping | Ad Funnel | Messaging/Asset Mapping | Designer | Mid | 5 |  |  | 1.3.6.3 |  |  | 0 | 0
1255 | DEL-0030 | TSK-01246 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.6.3.2 | 1.3.6.3 | Messaging/Asset Mapping | Ad Funnel | Messaging/Asset Mapping | Media Strategist | Mid | 7 |  |  | 1.3.6.3.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.7 | 1.3 | Budget Distribution | Budget Distribution |  |  |  | 6 | 82 | 7 | 1.3.6 |  |  | 195 | 1170
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.7.1 | 1.3.7 | Internal Review & Critique | Budget Distribution | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.7 |  |  | 0 | 0
1271 | DEL-0030 | TSK-01262 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.7.1.1 | 1.3.7.1 | Internal Review & Critique | Budget Distribution | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.7.1 |  |  | 0 | 0
1272 | DEL-0030 | TSK-01263 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.7.1.2 | 1.3.7.1 | Internal Review & Critique | Budget Distribution | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.7.1.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.7.2 | 1.3.7 | Client Review & Revisions | Budget Distribution | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.7.1.2 |  |  | 0 | 0
1269 | DEL-0030 | TSK-01260 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.7.2.1 | 1.3.7.2 | Client Review & Revisions | Budget Distribution | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.7.2 |  |  | 0 | 0
1270 | DEL-0030 | TSK-01261 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.7.2.2 | 1.3.7.2 | Client Review & Revisions | Budget Distribution | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.7.2.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.7.3 | 1.3.7 | Allocation Modeling | Budget Distribution | Allocation Modeling |  |  | 0 | 87 | 2 | 1.3.7.2.2 |  |  | 0 | 0
1267 | DEL-0030 | TSK-01258 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.7.3.1 | 1.3.7.3 | Allocation Modeling | Budget Distribution | Allocation Modeling | Media Planner | Mid | 1 |  |  | 1.3.7.3 |  |  | 0 | 0
1268 | DEL-0030 | TSK-01259 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.7.3.2 | 1.3.7.3 | Allocation Modeling | Budget Distribution | Allocation Modeling | Media Strategist | Mid | 1 |  |  | 1.3.7.3.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.8 | 1.3 | Identification of Media Needs | Identification of Media Needs |  |  |  | 12 | 82 | 5 | 1.3.7 |  |  | 195 | 2340
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.8.1 | 1.3.8 | Internal Review & Critique | Identification of Media Needs | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.8 |  |  | 0 | 0
1282 | DEL-0030 | TSK-01273 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.8.1.1 | 1.3.8.1 | Internal Review & Critique | Identification of Media Needs | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.8.1 |  |  | 0 | 0
1283 | DEL-0030 | TSK-01274 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.8.1.2 | 1.3.8.1 | Internal Review & Critique | Identification of Media Needs | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.8.1.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.8.2 | 1.3.8 | Client Review & Revisions | Identification of Media Needs | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.8.1.2 |  |  | 0 | 0
1279 | DEL-0030 | TSK-01270 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.8.2.1 | 1.3.8.2 | Client Review & Revisions | Identification of Media Needs | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.8.2 |  |  | 0 | 0
1280 | DEL-0030 | TSK-01271 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.8.2.2 | 1.3.8.2 | Client Review & Revisions | Identification of Media Needs | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.8.2.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.8.3 | 1.3.8 | Needs Matrix (Assets/Specs/Formats) | Identification of Media Needs | Needs Matrix (Assets/Specs/Formats) |  |  | 0 | 89 | 0 | 1.3.8.2.2 |  |  | 0 | 0
1281 | DEL-0030 | TSK-01272 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.8.3.1 | 1.3.8.3 | Needs Matrix (Assets/Specs/Formats) | Identification of Media Needs | Needs Matrix (Assets/Specs/Formats) | Designer | Mid | 5 |  |  | 1.3.8.3 |  |  | 0 | 0
1285 | DEL-0030 | TSK-01276 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.8.3.2 | 1.3.8.3 | Needs Matrix (Assets/Specs/Formats) | Identification of Media Needs | Needs Matrix (Assets/Specs/Formats) | Media Strategist | Mid | 3 |  |  | 1.3.8.3.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9 | 1.3 | Paid Media Recommendations | Paid Media Recommendations |  |  |  | 15 | 82 | 5 | 1.3.8 |  |  | 195 | 2925
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.1 | 1.3.9 | Internal Review & Critique | Paid Media Recommendations | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.9 |  |  | 0 | 0
1313 | DEL-0030 | TSK-01304 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.1.1 | 1.3.9.1 | Internal Review & Critique | Paid Media Recommendations | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.9.1 |  |  | 0 | 0
1314 | DEL-0030 | TSK-01305 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.1.2 | 1.3.9.1 | Internal Review & Critique | Paid Media Recommendations | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.9.1.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.2 | 1.3.9 | Client Review & Revisions | Paid Media Recommendations | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.9.1.2 |  |  | 0 | 0
1310 | DEL-0030 | TSK-01301 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.2.1 | 1.3.9.2 | Client Review & Revisions | Paid Media Recommendations | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.9.2 |  |  | 0 | 0
1311 | DEL-0030 | TSK-01302 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.2.2 | 1.3.9.2 | Client Review & Revisions | Paid Media Recommendations | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.9.2.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.3 | 1.3.9 | Prioritized Recs | Paid Media Recommendations | Prioritized Recs |  |  | 0 | 89 | 0 | 1.3.9.2.2 |  |  | 0 | 0
1312 | DEL-0030 | TSK-01303 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.3.1 | 1.3.9.3 | Prioritized Recs | Paid Media Recommendations | Prioritized Recs | Designer | Mid | 3 |  |  | 1.3.9.3 |  |  | 0 | 0
1315 | DEL-0030 | TSK-01306 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.3.2 | 1.3.9.3 | Prioritized Recs | Paid Media Recommendations | Prioritized Recs | Media Planner | Mid | 4 |  |  | 1.3.9.3.1 |  |  | 0 | 0
1316 | DEL-0030 | TSK-01307 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.3.3 | 1.3.9.3 | Prioritized Recs | Paid Media Recommendations | Prioritized Recs | Media Strategist | Mid | 3 |  |  | 1.3.9.3.2 |  |  | 0 | 0
1317 | DEL-0030 | TSK-01308 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.3.4 | 1.3.9.3 | Prioritized Recs | Paid Media Recommendations | Prioritized Recs | Project Manager | Mid | 1 |  |  | 1.3.9.3.3 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.10 | 1.3 | Platform Identification | Platform Identification |  |  |  | 11 | 82 | 5 | 1.3.9 |  |  | 195 | 2145
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.10.1 | 1.3.10 | Internal Review & Critique | Platform Identification | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.10 |  |  | 0 | 0
1320 | DEL-0030 | TSK-01311 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.10.1.1 | 1.3.10.1 | Internal Review & Critique | Platform Identification | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.10.1 |  |  | 0 | 0
1321 | DEL-0030 | TSK-01312 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.10.1.2 | 1.3.10.1 | Internal Review & Critique | Platform Identification | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.10.1.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.10.2 | 1.3.10 | Client Review & Revisions | Platform Identification | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.10.1.2 |  |  | 0 | 0
1318 | DEL-0030 | TSK-01309 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.10.2.1 | 1.3.10.2 | Client Review & Revisions | Platform Identification | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.10.2 |  |  | 0 | 0
1319 | DEL-0030 | TSK-01310 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.10.2.2 | 1.3.10.2 | Client Review & Revisions | Platform Identification | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.10.2.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.10.3 | 1.3.10 | Platform Fit Assessment | Platform Identification | Platform Fit Assessment |  |  | 0 | 89 | 0 | 1.3.10.2.2 |  |  | 0 | 0
1322 | DEL-0030 | TSK-01313 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.10.3.1 | 1.3.10.3 | Platform Fit Assessment | Platform Identification | Platform Fit Assessment | Media Planner | Mid | 4 |  |  | 1.3.10.3 |  |  | 0 | 0
1323 | DEL-0030 | TSK-01314 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.10.3.2 | 1.3.10.3 | Platform Fit Assessment | Platform Identification | Platform Fit Assessment | Media Strategist | Mid | 3 |  |  | 1.3.10.3.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.11 | 1.3 | Target Audience & Demographics | Target Audience & Demographics |  |  |  | 10 | 82 | 5 | 1.3.10 |  |  | 195 | 1950
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.11.1 | 1.3.11 | Internal Review & Critique | Target Audience & Demographics | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.11 |  |  | 0 | 0
1328 | DEL-0030 | TSK-01319 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.11.1.1 | 1.3.11.1 | Internal Review & Critique | Target Audience & Demographics | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.11.1 |  |  | 0 | 0
1329 | DEL-0030 | TSK-01320 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.11.1.2 | 1.3.11.1 | Internal Review & Critique | Target Audience & Demographics | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.11.1.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.11.2 | 1.3.11 | Client Review & Revisions | Target Audience & Demographics | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.11.1.2 |  |  | 0 | 0
1326 | DEL-0030 | TSK-01317 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.11.2.1 | 1.3.11.2 | Client Review & Revisions | Target Audience & Demographics | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.11.2 |  |  | 0 | 0
1327 | DEL-0030 | TSK-01318 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.11.2.2 | 1.3.11.2 | Client Review & Revisions | Target Audience & Demographics | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.11.2.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.11.3 | 1.3.11 | Audience Definition | Target Audience & Demographics | Audience Definition |  |  | 0 | 89 | 0 | 1.3.11.2.2 |  |  | 0 | 0
1324 | DEL-0030 | TSK-01315 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.11.3.1 | 1.3.11.3 | Audience Definition | Target Audience & Demographics | Audience Definition | Analyst | Mid | 3 |  |  | 1.3.11.3 |  |  | 0 | 0
1325 | DEL-0030 | TSK-01316 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.11.3.2 | 1.3.11.3 | Audience Definition | Target Audience & Demographics | Audience Definition | Media Strategist | Mid | 3 |  |  | 1.3.11.3.1 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4 | 1 | Paid Media Planning |  |  |  |  | 82 | 89 | 33 | 1.3 |  | Advanced/T2_MediumVolume | 195 | 15990
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1 | 1.4 | Media Planning Deck | Media Planning Deck |  |  |  | 19 | 89 | 16 | 1.4 |  |  | 195 | 3705
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.1 | 1.4.1 | Deck Narrative | Media Planning Deck | Deck Narrative |  |  | 0 | 89 | 6 | 1.4.1 |  |  | 0 | 0
1241 | DEL-0029 | TSK-01232 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.1.1 | 1.4.1.1 | Deck Narrative | Media Planning Deck | Deck Narrative | Designer | Mid | 8 |  |  | 1.4.1.1 |  |  | 0 | 0
1240 | DEL-0029 | TSK-01231 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.1.2 | 1.4.1.1 | Deck Narrative | Media Planning Deck | Deck Narrative | Media Strategist | Mid | 4 |  |  | 1.4.1.1.1 |  |  | 0 | 0
1244 | DEL-0029 | TSK-01235 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.1.3 | 1.4.1.1 | Deck Narrative | Media Planning Deck | Deck Narrative | Project Manager | Mid | 2 |  |  | 1.4.1.1.2 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.2 | 1.4.1 | Deck Build | Media Planning Deck | Deck Build |  |  | 0 | 101 | 5 | 1.4.1.1.3 |  |  | 0 | 0
1239 | DEL-0029 | TSK-01230 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.2.1 | 1.4.1.2 | Deck Build | Media Planning Deck | Deck Build | Designer | Mid | 2 |  |  | 1.4.1.2 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.3 | 1.4.1 | Internal Review & Critique | Media Planning Deck | Internal Review & Critique |  |  | 0 | 117 | 2 | 1.4.1.2.1 |  |  | 0 | 0
1242 | DEL-0029 | TSK-01233 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.3.1 | 1.4.1.3 | Internal Review & Critique | Media Planning Deck | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.1.3 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.4 | 1.4.1 | Client Review & Revisions | Media Planning Deck | Client Review & Revisions |  |  | 0 | 119 | 3 | 1.4.1.3.1 |  |  | 0 | 0
1237 | DEL-0029 | TSK-01228 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.4.1 | 1.4.1.4 | Client Review & Revisions | Media Planning Deck | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.4.1.4 |  |  | 0 | 0
1238 | DEL-0029 | TSK-01229 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.4.2 | 1.4.1.4 | Client Review & Revisions | Media Planning Deck | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.4.1.4.1 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2 | 1.4 | Paid Media Plan | Paid Media Plan |  |  |  | 29 | 95 | 11 | 1.4.1 |  |  | 195 | 5655
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.1 | 1.4.2 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes |  |  | 0 | 95 | 6 | 1.4.2 |  |  | 0 | 0
1248 | DEL-0029 | TSK-01239 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.1.1 | 1.4.2.1 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes | Designer | Mid | 3 |  |  | 1.4.2.1 |  |  | 0 | 0
1252 | DEL-0029 | TSK-01243 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.1.2 | 1.4.2.1 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes | Media Planner | Mid | 10 |  |  | 1.4.2.1.1 |  |  | 0 | 0
1245 | DEL-0029 | TSK-01236 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.1.3 | 1.4.2.1 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes | Media Strategist | Mid | 10 |  |  | 1.4.2.1.2 |  |  | 0 | 0
1251 | DEL-0029 | TSK-01242 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.1.4 | 1.4.2.1 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes | Project Manager | Mid | 2 |  |  | 1.4.2.1.3 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.2 | 1.4.2 | Internal Review & Critique | Paid Media Plan | Internal Review & Critique |  |  | 0 | 117 | 2 | 1.4.2.1.4 |  |  | 0 | 0
1249 | DEL-0029 | TSK-01240 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.2.1 | 1.4.2.2 | Internal Review & Critique | Paid Media Plan | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.2.2 |  |  | 0 | 0
1250 | DEL-0029 | TSK-01241 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.2.2 | 1.4.2.2 | Internal Review & Critique | Paid Media Plan | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.4.2.2.1 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.3 | 1.4.2 | Client Review & Revisions | Paid Media Plan | Client Review & Revisions |  |  | 0 | 119 | 3 | 1.4.2.2.2 |  |  | 0 | 0
1246 | DEL-0029 | TSK-01237 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.3.1 | 1.4.2.3 | Client Review & Revisions | Paid Media Plan | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.4.2.3 |  |  | 0 | 0
1247 | DEL-0029 | TSK-01238 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.3.2 | 1.4.2.3 | Client Review & Revisions | Paid Media Plan | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.4.2.3.1 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3 | 1.4 | Ad Unit & Format POV | Ad Unit & Format POV |  |  |  | 16 | 106 | 16 | 1.4.2 |  |  | 195 | 3120
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.1 | 1.4.3 | Spec Page Build | Ad Unit & Format POV | Spec Page Build |  |  | 0 | 106 | 11 | 1.4.3 |  |  | 0 | 0
1227 | DEL-0029 | TSK-01218 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.1.1 | 1.4.3.1 | Spec Page Build | Ad Unit & Format POV | Spec Page Build | Designer | Mid | 3 |  |  | 1.4.3.1 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.2 | 1.4.3 | Internal Review & Critique | Ad Unit & Format POV | Internal Review & Critique |  |  | 0 | 117 | 2 | 1.4.3.1.1 |  |  | 0 | 0
1223 | DEL-0029 | TSK-01214 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.2.1 | 1.4.3.2 | Internal Review & Critique | Ad Unit & Format POV | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.3.2 |  |  | 0 | 0
1224 | DEL-0029 | TSK-01215 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.2.2 | 1.4.3.2 | Internal Review & Critique | Ad Unit & Format POV | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.4.3.2.1 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.3 | 1.4.3 | Client Review & Revisions | Ad Unit & Format POV | Client Review & Revisions |  |  | 0 | 119 | 3 | 1.4.3.2.2 |  |  | 0 | 0
1220 | DEL-0029 | TSK-01211 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.3.1 | 1.4.3.3 | Client Review & Revisions | Ad Unit & Format POV | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.4.3.3 |  |  | 0 | 0
1221 | DEL-0029 | TSK-01212 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.3.2 | 1.4.3.3 | Client Review & Revisions | Ad Unit & Format POV | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.4.3.3.1 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.4 | 1.4.3 | Spec Matrix & POV | Ad Unit & Format POV | Spec Matrix & POV |  |  | 0 | 122 | 0 | 1.4.3.3.2 |  |  | 0 | 0
1222 | DEL-0029 | TSK-01213 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.4.1 | 1.4.3.4 | Spec Matrix & POV | Ad Unit & Format POV | Spec Matrix & POV | Designer | Mid | 3 |  |  | 1.4.3.4 |  |  | 0 | 0
1225 | DEL-0029 | TSK-01216 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.4.2 | 1.4.3.4 | Spec Matrix & POV | Ad Unit & Format POV | Spec Matrix & POV | Media Planner | Mid | 3 |  |  | 1.4.3.4.1 |  |  | 0 | 0
1226 | DEL-0029 | TSK-01217 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.4.3 | 1.4.3.4 | Spec Matrix & POV | Ad Unit & Format POV | Spec Matrix & POV | Media Strategist | Mid | 3 |  |  | 1.4.3.4.2 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4 | 1.4 | Channel & Vendor Evaluation | Channel & Vendor Evaluation |  |  |  | 18 | 117 | 5 | 1.4.3 |  |  | 195 | 3510
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.1 | 1.4.4 | Internal Review & Critique | Channel & Vendor Evaluation | Internal Review & Critique |  |  | 0 | 117 | 2 | 1.4.4 |  |  | 0 | 0
1231 | DEL-0029 | TSK-01222 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.1.1 | 1.4.4.1 | Internal Review & Critique | Channel & Vendor Evaluation | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.4.1 |  |  | 0 | 0
1232 | DEL-0029 | TSK-01223 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.1.2 | 1.4.4.1 | Internal Review & Critique | Channel & Vendor Evaluation | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.4.4.1.1 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.2 | 1.4.4 | Client Review & Revisions | Channel & Vendor Evaluation | Client Review & Revisions |  |  | 0 | 119 | 3 | 1.4.4.1.2 |  |  | 0 | 0
1228 | DEL-0029 | TSK-01219 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.2.1 | 1.4.4.2 | Client Review & Revisions | Channel & Vendor Evaluation | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.4.4.2 |  |  | 0 | 0
1229 | DEL-0029 | TSK-01220 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.2.2 | 1.4.4.2 | Client Review & Revisions | Channel & Vendor Evaluation | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.4.4.2.1 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.3 | 1.4.4 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review |  |  | 0 | 122 | 0 | 1.4.4.2.2 |  |  | 0 | 0
1236 | DEL-0029 | TSK-01227 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.3.1 | 1.4.4.3 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review | Account Manager | Mid | 2 |  |  | 1.4.4.3 |  |  | 0 | 0
1230 | DEL-0029 | TSK-01221 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.3.2 | 1.4.4.3 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review | Designer | Mid | 2 |  |  | 1.4.4.3.1 |  |  | 0 | 0
1233 | DEL-0029 | TSK-01224 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.3.3 | 1.4.4.3 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review | Media Planner | Mid | 7 |  |  | 1.4.4.3.2 |  |  | 0 | 0
1234 | DEL-0029 | TSK-01225 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.3.4 | 1.4.4.3 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review | Media Strategist | Mid | 3 |  |  | 1.4.4.3.3 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5 | 1 | Paid Media Assets |  |  |  |  | 148 | 122 | 23 | 1.4 |  | Advanced/T2_MediumVolume | 195 | 28860
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1 | 1.5 | Awareness Assets (Paid) | Awareness Assets (Paid) |  |  |  | 23 | 122 | 20 | 1.5 |  |  | 195 | 4485
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.1 | 1.5.1 | Concept & Copy | Awareness Assets (Paid) | Concept & Copy |  |  | 0 | 122 | 4 | 1.5.1 |  |  | 0 | 0
897 | DEL-0016 | TSK-00888 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.1.1 | 1.5.1.1 | Concept & Copy | Awareness Assets (Paid) | Concept & Copy | Copywriter | Mid | 3 |  |  | 1.5.1.1 |  |  | 0 | 0
898 | DEL-0016 | TSK-00889 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.1.2 | 1.5.1.1 | Concept & Copy | Awareness Assets (Paid) | Concept & Copy | Creative Director | Lead/Director | 2 |  |  | 1.5.1.1.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.2 | 1.5.1 | Design Explorations (3-4) | Awareness Assets (Paid) | Design Explorations (3-4) |  |  | 0 | 126 | 8 | 1.5.1.1.2 |  |  | 0 | 0
899 | DEL-0016 | TSK-00890 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.2.1 | 1.5.1.2 | Design Explorations (3-4) | Awareness Assets (Paid) | Design Explorations (3-4) | Designer | Mid | 4 |  |  | 1.5.1.2 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.3 | 1.5.1 | Quality Check (Specs/Accessibility) | Awareness Assets (Paid) | Quality Check (Specs/Accessibility) |  |  | 0 | 137 | 3 | 1.5.1.2.1 |  |  | 0 | 0
903 | DEL-0016 | TSK-00894 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.3.1 | 1.5.1.3 | Quality Check (Specs/Accessibility) | Awareness Assets (Paid) | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.5.1.3 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.4 | 1.5.1 | Internal Review & Critique | Awareness Assets (Paid) | Internal Review & Critique |  |  | 0 | 140 | 2 | 1.5.1.3.1 |  |  | 0 | 0
901 | DEL-0016 | TSK-00892 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.4.1 | 1.5.1.4 | Internal Review & Critique | Awareness Assets (Paid) | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.5.1.4 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.5 | 1.5.1 | Client Review & Revisions | Awareness Assets (Paid) | Client Review & Revisions |  |  | 0 | 142 | 3 | 1.5.1.4.1 |  |  | 0 | 0
893 | DEL-0016 | TSK-00884 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.5.1 | 1.5.1.5 | Client Review & Revisions | Awareness Assets (Paid) | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.1.5 |  |  | 0 | 0
894 | DEL-0016 | TSK-00885 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.5.2 | 1.5.1.5 | Client Review & Revisions | Awareness Assets (Paid) | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.5.1.5.1 |  |  | 0 | 0
895 | DEL-0016 | TSK-00886 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.5.3 | 1.5.1.5 | Client Review & Revisions | Awareness Assets (Paid) | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.5.1.5.2 |  |  | 0 | 0
896 | DEL-0016 | TSK-00887 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.5.4 | 1.5.1.5 | Client Review & Revisions | Awareness Assets (Paid) | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.5.1.5.3 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.6 | 1.5.1 | Final Packaging | Awareness Assets (Paid) | Final Packaging |  |  | 0 | 145 | 0 | 1.5.1.5.4 |  |  | 0 | 0
900 | DEL-0016 | TSK-00891 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.6.1 | 1.5.1.6 | Final Packaging | Awareness Assets (Paid) | Final Packaging | Designer | Mid | 5 |  |  | 1.5.1.6 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2 | 1.5 | Unique Assets | Unique Assets |  |  |  | 18 | 122 | 12 | 1.5.1 |  |  | 195 | 3510
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.1 | 1.5.2 | Build & Polish | Unique Assets | Build & Polish |  |  | 0 | 122 | 4 | 1.5.2 |  |  | 0 | 0
963 | DEL-0016 | TSK-00954 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.1.1 | 1.5.2.1 | Build & Polish | Unique Assets | Build & Polish | Designer | Mid | 3 |  |  | 1.5.2.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.2 | 1.5.2 | Quality Check (Specs/Accessibility) | Unique Assets | Quality Check (Specs/Accessibility) |  |  | 0 | 137 | 3 | 1.5.2.1.1 |  |  | 0 | 0
972 | DEL-0016 | TSK-00963 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.2.1 | 1.5.2.2 | Quality Check (Specs/Accessibility) | Unique Assets | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.5.2.2 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.3 | 1.5.2 | Internal Review & Critique | Unique Assets | Internal Review & Critique |  |  | 0 | 140 | 2 | 1.5.2.2.1 |  |  | 0 | 0
970 | DEL-0016 | TSK-00961 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.3.1 | 1.5.2.3 | Internal Review & Critique | Unique Assets | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.5.2.3 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.4 | 1.5.2 | Client Review & Revisions | Unique Assets | Client Review & Revisions |  |  | 0 | 142 | 3 | 1.5.2.3.1 |  |  | 0 | 0
964 | DEL-0016 | TSK-00955 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.4.1 | 1.5.2.4 | Client Review & Revisions | Unique Assets | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.2.4 |  |  | 0 | 0
965 | DEL-0016 | TSK-00956 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.4.2 | 1.5.2.4 | Client Review & Revisions | Unique Assets | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.5.2.4.1 |  |  | 0 | 0
966 | DEL-0016 | TSK-00957 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.4.3 | 1.5.2.4 | Client Review & Revisions | Unique Assets | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.5.2.4.2 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.5 | 1.5.2 | Custom Concept | Unique Assets | Custom Concept |  |  | 0 | 145 | 0 | 1.5.2.4.3 |  |  | 0 | 0
967 | DEL-0016 | TSK-00958 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.5.1 | 1.5.2.5 | Custom Concept | Unique Assets | Custom Concept | Copywriter | Mid | 2 |  |  | 1.5.2.5 |  |  | 0 | 0
968 | DEL-0016 | TSK-00959 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.5.2 | 1.5.2.5 | Custom Concept | Unique Assets | Custom Concept | Designer | Mid | 5 |  |  | 1.5.2.5.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3 | 1.5 | Conversion Assets (Paid) | Conversion Assets (Paid) |  |  |  | 20 | 126 | 16 | 1.5.2 |  |  | 195 | 3900
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.1 | 1.5.3 | Design Variants (3-4) | Conversion Assets (Paid) | Design Variants (3-4) |  |  | 0 | 126 | 8 | 1.5.3 |  |  | 0 | 0
909 | DEL-0016 | TSK-00900 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.1.1 | 1.5.3.1 | Design Variants (3-4) | Conversion Assets (Paid) | Design Variants (3-4) | Designer | Mid | 4 |  |  | 1.5.3.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.2 | 1.5.3 | Quality Check (Specs/Accessibility) | Conversion Assets (Paid) | Quality Check (Specs/Accessibility) |  |  | 0 | 137 | 3 | 1.5.3.1.1 |  |  | 0 | 0
914 | DEL-0016 | TSK-00905 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.2.1 | 1.5.3.2 | Quality Check (Specs/Accessibility) | Conversion Assets (Paid) | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.5.3.2 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.3 | 1.5.3 | Internal Review & Critique | Conversion Assets (Paid) | Internal Review & Critique |  |  | 0 | 140 | 2 | 1.5.3.2.1 |  |  | 0 | 0
911 | DEL-0016 | TSK-00902 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.3.1 | 1.5.3.3 | Internal Review & Critique | Conversion Assets (Paid) | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.5.3.3 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.4 | 1.5.3 | Client Review & Revisions | Conversion Assets (Paid) | Client Review & Revisions |  |  | 0 | 142 | 3 | 1.5.3.3.1 |  |  | 0 | 0
905 | DEL-0016 | TSK-00896 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.4.1 | 1.5.3.4 | Client Review & Revisions | Conversion Assets (Paid) | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.3.4 |  |  | 0 | 0
906 | DEL-0016 | TSK-00897 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.4.2 | 1.5.3.4 | Client Review & Revisions | Conversion Assets (Paid) | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.5.3.4.1 |  |  | 0 | 0
907 | DEL-0016 | TSK-00898 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.4.3 | 1.5.3.4 | Client Review & Revisions | Conversion Assets (Paid) | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.5.3.4.2 |  |  | 0 | 0
908 | DEL-0016 | TSK-00899 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.4.4 | 1.5.3.4 | Client Review & Revisions | Conversion Assets (Paid) | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.5.3.4.3 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.5 | 1.5.3 | Final Packaging | Conversion Assets (Paid) | Final Packaging |  |  | 0 | 145 | 0 | 1.5.3.4.4 |  |  | 0 | 0
913 | DEL-0016 | TSK-00904 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.5.1 | 1.5.3.5 | Final Packaging | Conversion Assets (Paid) | Final Packaging | Copywriter | Mid | 2 |  |  | 1.5.3.5 |  |  | 0 | 0
910 | DEL-0016 | TSK-00901 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.5.2 | 1.5.3.5 | Final Packaging | Conversion Assets (Paid) | Final Packaging | Designer | Mid | 5 |  |  | 1.5.3.5.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.4 | 1.5 | National Spotify Audio (Paid) | National Spotify Audio (Paid) |  |  |  | 19 | 134 | 3 | 1.5.3 |  |  | 195 | 3705
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.4.1 | 1.5.4 | Client Review & Revisions | National Spotify Audio (Paid) | Client Review & Revisions |  |  | 0 | 134 | 3 | 1.5.4 |  |  | 0 | 0
926 | DEL-0016 | TSK-00917 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.4.1.1 | 1.5.4.1 | Client Review & Revisions | National Spotify Audio (Paid) | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.5.4.1 |  |  | 0 | 0
931 | DEL-0016 | TSK-00922 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.4.1.2 | 1.5.4.1 | Client Review & Revisions | National Spotify Audio (Paid) | Client Review & Revisions | Art Director | Lead/Director | 2 |  |  | 1.5.4.1.1 |  |  | 0 | 0
927 | DEL-0016 | TSK-00918 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.4.1.3 | 1.5.4.1 | Client Review & Revisions | National Spotify Audio (Paid) | Client Review & Revisions | Copywriter | Mid | 4 |  |  | 1.5.4.1.2 |  |  | 0 | 0
928 | DEL-0016 | TSK-00919 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.4.1.4 | 1.5.4.1 | Client Review & Revisions | National Spotify Audio (Paid) | Client Review & Revisions | Creative Director | Lead/Director | 4 |  |  | 1.5.4.1.3 |  |  | 0 | 0
930 | DEL-0016 | TSK-00921 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.4.1.5 | 1.5.4.1 | Client Review & Revisions | National Spotify Audio (Paid) | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.5.4.1.4 |  |  | 0 | 0
929 | DEL-0016 | TSK-00920 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.4.1.6 | 1.5.4.1 | Client Review & Revisions | National Spotify Audio (Paid) | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.5.4.1.5 |  |  | 0 | 0
925 | DEL-0016 | TSK-00916 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.4.1.7 | 1.5.4.1 | Client Review & Revisions | National Spotify Audio (Paid) | Client Review & Revisions | Sound Designer | Mid | 5 |  |  | 1.5.4.1.6 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.5 | 1.5 | Regional Spotify Audio (Paid) | Regional Spotify Audio (Paid) |  |  |  | 19 | 134 | 3 | 1.5.4 |  |  | 195 | 3705
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.5.1 | 1.5.5 | Client Review & Revisions | Regional Spotify Audio (Paid) | Client Review & Revisions |  |  | 0 | 134 | 3 | 1.5.5 |  |  | 0 | 0
945 | DEL-0016 | TSK-00936 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.5.1.1 | 1.5.5.1 | Client Review & Revisions | Regional Spotify Audio (Paid) | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.5.5.1 |  |  | 0 | 0
950 | DEL-0016 | TSK-00941 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.5.1.2 | 1.5.5.1 | Client Review & Revisions | Regional Spotify Audio (Paid) | Client Review & Revisions | Art Director | Lead/Director | 2 |  |  | 1.5.5.1.1 |  |  | 0 | 0
946 | DEL-0016 | TSK-00937 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.5.1.3 | 1.5.5.1 | Client Review & Revisions | Regional Spotify Audio (Paid) | Client Review & Revisions | Copywriter | Mid | 4 |  |  | 1.5.5.1.2 |  |  | 0 | 0
947 | DEL-0016 | TSK-00938 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.5.1.4 | 1.5.5.1 | Client Review & Revisions | Regional Spotify Audio (Paid) | Client Review & Revisions | Creative Director | Lead/Director | 4 |  |  | 1.5.5.1.3 |  |  | 0 | 0
949 | DEL-0016 | TSK-00940 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.5.1.5 | 1.5.5.1 | Client Review & Revisions | Regional Spotify Audio (Paid) | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.5.5.1.4 |  |  | 0 | 0
948 | DEL-0016 | TSK-00939 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.5.1.6 | 1.5.5.1 | Client Review & Revisions | Regional Spotify Audio (Paid) | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.5.5.1.5 |  |  | 0 | 0
944 | DEL-0016 | TSK-00935 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.5.1.7 | 1.5.5.1 | Client Review & Revisions | Regional Spotify Audio (Paid) | Client Review & Revisions | Sound Designer | Mid | 5 |  |  | 1.5.5.1.6 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6 | 1.5 | National Pinterest assets (Paid) | National Pinterest assets (Paid) |  |  |  | 16 | 137 | 8 | 1.5.5 |  |  | 195 | 3120
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.1 | 1.5.6 | Quality Check (Specs/Accessibility) | National Pinterest assets (Paid) | Quality Check (Specs/Accessibility) |  |  | 0 | 137 | 3 | 1.5.6 |  |  | 0 | 0
923 | DEL-0016 | TSK-00914 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.1.1 | 1.5.6.1 | Quality Check (Specs/Accessibility) | National Pinterest assets (Paid) | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.5.6.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.2 | 1.5.6 | Internal Review & Critique | National Pinterest assets (Paid) | Internal Review & Critique |  |  | 0 | 140 | 2 | 1.5.6.1.1 |  |  | 0 | 0
921 | DEL-0016 | TSK-00912 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.2.1 | 1.5.6.2 | Internal Review & Critique | National Pinterest assets (Paid) | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.5.6.2 |  |  | 0 | 0
922 | DEL-0016 | TSK-00913 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.2.2 | 1.5.6.2 | Internal Review & Critique | National Pinterest assets (Paid) | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.5.6.2.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.3 | 1.5.6 | Client Review & Revisions | National Pinterest assets (Paid) | Client Review & Revisions |  |  | 0 | 142 | 3 | 1.5.6.2.2 |  |  | 0 | 0
916 | DEL-0016 | TSK-00907 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.3.1 | 1.5.6.3 | Client Review & Revisions | National Pinterest assets (Paid) | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.6.3 |  |  | 0 | 0
917 | DEL-0016 | TSK-00908 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.3.2 | 1.5.6.3 | Client Review & Revisions | National Pinterest assets (Paid) | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.5.6.3.1 |  |  | 0 | 0
918 | DEL-0016 | TSK-00909 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.3.3 | 1.5.6.3 | Client Review & Revisions | National Pinterest assets (Paid) | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.5.6.3.2 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.4 | 1.5.6 | Concept & Layouts (2-3) | National Pinterest assets (Paid) | Concept & Layouts (2-3) |  |  | 0 | 145 | 0 | 1.5.6.3.3 |  |  | 0 | 0
919 | DEL-0016 | TSK-00910 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.4.1 | 1.5.6.4 | Concept & Layouts (2-3) | National Pinterest assets (Paid) | Concept & Layouts (2-3) | Designer | Mid | 7 |  |  | 1.5.6.4 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7 | 1.5 | Regional Pinterest assets (Paid) | Regional Pinterest assets (Paid) |  |  |  | 16 | 137 | 8 | 1.5.6 |  |  | 195 | 3120
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.1 | 1.5.7 | Quality Check (Specs/Accessibility) | Regional Pinterest assets (Paid) | Quality Check (Specs/Accessibility) |  |  | 0 | 137 | 3 | 1.5.7 |  |  | 0 | 0
942 | DEL-0016 | TSK-00933 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.1.1 | 1.5.7.1 | Quality Check (Specs/Accessibility) | Regional Pinterest assets (Paid) | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.5.7.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.2 | 1.5.7 | Internal Review & Critique | Regional Pinterest assets (Paid) | Internal Review & Critique |  |  | 0 | 140 | 2 | 1.5.7.1.1 |  |  | 0 | 0
940 | DEL-0016 | TSK-00931 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.2.1 | 1.5.7.2 | Internal Review & Critique | Regional Pinterest assets (Paid) | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.5.7.2 |  |  | 0 | 0
941 | DEL-0016 | TSK-00932 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.2.2 | 1.5.7.2 | Internal Review & Critique | Regional Pinterest assets (Paid) | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.5.7.2.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.3 | 1.5.7 | Client Review & Revisions | Regional Pinterest assets (Paid) | Client Review & Revisions |  |  | 0 | 142 | 3 | 1.5.7.2.2 |  |  | 0 | 0
935 | DEL-0016 | TSK-00926 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.3.1 | 1.5.7.3 | Client Review & Revisions | Regional Pinterest assets (Paid) | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.7.3 |  |  | 0 | 0
936 | DEL-0016 | TSK-00927 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.3.2 | 1.5.7.3 | Client Review & Revisions | Regional Pinterest assets (Paid) | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.5.7.3.1 |  |  | 0 | 0
937 | DEL-0016 | TSK-00928 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.3.3 | 1.5.7.3 | Client Review & Revisions | Regional Pinterest assets (Paid) | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.5.7.3.2 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.4 | 1.5.7 | Concept & Layouts (2-3) | Regional Pinterest assets (Paid) | Concept & Layouts (2-3) |  |  | 0 | 145 | 0 | 1.5.7.3.3 |  |  | 0 | 0
938 | DEL-0016 | TSK-00929 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.4.1 | 1.5.7.4 | Concept & Layouts (2-3) | Regional Pinterest assets (Paid) | Concept & Layouts (2-3) | Designer | Mid | 7 |  |  | 1.5.7.4 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8 | 1.5 | Resize Assets | Resize Assets |  |  |  | 17 | 137 | 8 | 1.5.7 |  |  | 195 | 3315
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.1 | 1.5.8 | Quality Check (Specs/Accessibility) | Resize Assets | Quality Check (Specs/Accessibility) |  |  | 0 | 137 | 3 | 1.5.8 |  |  | 0 | 0
960 | DEL-0016 | TSK-00951 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.1.1 | 1.5.8.1 | Quality Check (Specs/Accessibility) | Resize Assets | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 6 |  |  | 1.5.8.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.2 | 1.5.8 | Internal Review & Critique | Resize Assets | Internal Review & Critique |  |  | 0 | 140 | 2 | 1.5.8.1.1 |  |  | 0 | 0
958 | DEL-0016 | TSK-00949 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.2.1 | 1.5.8.2 | Internal Review & Critique | Resize Assets | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.5.8.2 |  |  | 0 | 0
959 | DEL-0016 | TSK-00950 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.2.2 | 1.5.8.2 | Internal Review & Critique | Resize Assets | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.5.8.2.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.3 | 1.5.8 | Client Review & Revisions | Resize Assets | Client Review & Revisions |  |  | 0 | 142 | 3 | 1.5.8.2.2 |  |  | 0 | 0
954 | DEL-0016 | TSK-00945 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.3.1 | 1.5.8.3 | Client Review & Revisions | Resize Assets | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.8.3 |  |  | 0 | 0
955 | DEL-0016 | TSK-00946 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.3.2 | 1.5.8.3 | Client Review & Revisions | Resize Assets | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.5.8.3.1 |  |  | 0 | 0
956 | DEL-0016 | TSK-00947 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.3.3 | 1.5.8.3 | Client Review & Revisions | Resize Assets | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.5.8.3.2 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.4 | 1.5.8 | Final Packaging | Resize Assets | Final Packaging |  |  | 0 | 145 | 0 | 1.5.8.3.3 |  |  | 0 | 0
957 | DEL-0016 | TSK-00948 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.4.1 | 1.5.8.4 | Final Packaging | Resize Assets | Final Packaging | Designer | Mid | 5 |  |  | 1.5.8.4 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6 | 1 | Reporting |  |  |  |  | 69 | 145 | 19 | 1.5 |  | Advanced/T2_MediumVolume | 195 | 13455
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.1 | 1.6 | Campaign Reporting (Quarterly) | Campaign Reporting (Quarterly) |  |  |  | 14 | 145 | 4 | 1.6 |  |  | 195 | 2730
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.1.1 | 1.6.1 | Design Polish | Campaign Reporting (Quarterly) | Design Polish |  |  | 0 | 145 | 4 | 1.6.1 |  |  | 0 | 0
1355 | DEL-0032 | TSK-01346 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.1.1.1 | 1.6.1.1 | Design Polish | Campaign Reporting (Quarterly) | Design Polish | Designer | Mid | 3 |  |  | 1.6.1.1 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.1.2 | 1.6.1 | Data Deep Dive | Campaign Reporting (Quarterly) | Data Deep Dive |  |  | 0 | 164 | 0 | 1.6.1.1.1 |  |  | 0 | 0
1353 | DEL-0032 | TSK-01344 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.1.2.1 | 1.6.1.2 | Data Deep Dive | Campaign Reporting (Quarterly) | Data Deep Dive | Analyst | Mid | 3 |  |  | 1.6.1.2 |  |  | 0 | 0
1356 | DEL-0032 | TSK-01347 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.1.2.2 | 1.6.1.2 | Data Deep Dive | Campaign Reporting (Quarterly) | Data Deep Dive | Creative Director | Lead/Director | 2 |  |  | 1.6.1.2.1 |  |  | 0 | 0
1357 | DEL-0032 | TSK-01348 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.1.2.3 | 1.6.1.2 | Data Deep Dive | Campaign Reporting (Quarterly) | Data Deep Dive | Media Strategist | Mid | 3 |  |  | 1.6.1.2.2 |  |  | 0 | 0
1354 | DEL-0032 | TSK-01345 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.1.2.4 | 1.6.1.2 | Data Deep Dive | Campaign Reporting (Quarterly) | Data Deep Dive | QA Specialist | Mid | 3 |  |  | 1.6.1.2.3 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.2 | 1.6 | Campaign Reporting (Bi-Weekly) | Campaign Reporting (Bi-Weekly) |  |  |  | 10 | 149 | 7 | 1.6.1 |  |  | 195 | 1950
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.2.1 | 1.6.2 | Data Refresh & QA | Campaign Reporting (Bi-Weekly) | Data Refresh & QA |  |  | 0 | 149 | 3 | 1.6.2 |  |  | 0 | 0
1350 | DEL-0032 | TSK-01341 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.2.1.1 | 1.6.2.1 | Data Refresh & QA | Campaign Reporting (Bi-Weekly) | Data Refresh & QA | Analyst | Mid | 3 |  |  | 1.6.2.1 |  |  | 0 | 0
1351 | DEL-0032 | TSK-01342 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.2.1.2 | 1.6.2.1 | Data Refresh & QA | Campaign Reporting (Bi-Weekly) | Data Refresh & QA | QA Specialist | Mid | 3 |  |  | 1.6.2.1.1 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.2.2 | 1.6.2 | Client Summary | Campaign Reporting (Bi-Weekly) | Client Summary |  |  | 0 | 156 | 4 | 1.6.2.1.2 |  |  | 0 | 0
1349 | DEL-0032 | TSK-01340 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.2.2.1 | 1.6.2.2 | Client Summary | Campaign Reporting (Bi-Weekly) | Client Summary | Account Manager | Mid | 1 |  |  | 1.6.2.2 |  |  | 0 | 0
1352 | DEL-0032 | TSK-01343 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.2.2.2 | 1.6.2.2 | Client Summary | Campaign Reporting (Bi-Weekly) | Client Summary | Media Strategist | Mid | 3 |  |  | 1.6.2.2.1 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.3 | 1.6 | Campaign Tracking | Campaign Tracking |  |  |  | 8 | 149 | 7 | 1.6.2 |  |  | 195 | 1560
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.3.1 | 1.6.3 | QA Spot Check | Campaign Tracking | QA Spot Check |  |  | 0 | 149 | 3 | 1.6.3 |  |  | 0 | 0
1358 | DEL-0032 | TSK-01349 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.3.1.1 | 1.6.3.1 | QA Spot Check | Campaign Tracking | QA Spot Check | QA Specialist | Mid | 3 |  |  | 1.6.3.1 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.3.2 | 1.6.3 | Tracker Update | Campaign Tracking | Tracker Update |  |  | 0 | 152 | 4 | 1.6.3.1.1 |  |  | 0 | 0
1359 | DEL-0032 | TSK-01350 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.3.2.1 | 1.6.3.2 | Tracker Update | Campaign Tracking | Tracker Update | Analyst | Mid | 5 |  |  | 1.6.3.2 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.4 | 1.6 | Dashboard Analytics | Dashboard Analytics |  |  |  | 9 | 149 | 7 | 1.6.3 |  |  | 195 | 1755
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.4.1 | 1.6.4 | QA & Calc Checks | Dashboard Analytics | QA & Calc Checks |  |  | 0 | 149 | 3 | 1.6.4 |  |  | 0 | 0
1361 | DEL-0032 | TSK-01352 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.4.1.1 | 1.6.4.1 | QA & Calc Checks | Dashboard Analytics | QA & Calc Checks | QA Specialist | Mid | 3 |  |  | 1.6.4.1 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.4.2 | 1.6.4 | Dashboard Build/Refresh | Dashboard Analytics | Dashboard Build/Refresh |  |  | 0 | 156 | 4 | 1.6.4.1.1 |  |  | 0 | 0
1360 | DEL-0032 | TSK-01351 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.4.2.1 | 1.6.4.2 | Dashboard Build/Refresh | Dashboard Analytics | Dashboard Build/Refresh | Analyst | Mid | 6 |  |  | 1.6.4.2 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.5 | 1.6 | Reporting & Ad-Tagging Support | Reporting & Ad-Tagging Support |  |  |  | 8 | 149 | 7 | 1.6.4 |  |  | 195 | 1560
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.5.1 | 1.6.5 | QA | Reporting & Ad-Tagging Support | QA |  |  | 0 | 149 | 3 | 1.6.5 |  |  | 0 | 0
1369 | DEL-0032 | TSK-01360 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.5.1.1 | 1.6.5.1 | QA | Reporting & Ad-Tagging Support | QA | QA Specialist | Mid | 3 |  |  | 1.6.5.1 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.5.2 | 1.6.5 | UTM/Tag Guidance | Reporting & Ad-Tagging Support | UTM/Tag Guidance |  |  | 0 | 152 | 4 | 1.6.5.1.1 |  |  | 0 | 0
1371 | DEL-0032 | TSK-01362 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.5.2.1 | 1.6.5.2 | UTM/Tag Guidance | Reporting & Ad-Tagging Support | UTM/Tag Guidance | Media Strategist | Mid | 3 |  |  | 1.6.5.2 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.5.3 | 1.6.5 | Tagging Support | Reporting & Ad-Tagging Support | Tagging Support |  |  | 0 | 164 | 0 | 1.6.5.2.1 |  |  | 0 | 0
1370 | DEL-0032 | TSK-01361 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.5.3.1 | 1.6.5.3 | Tagging Support | Reporting & Ad-Tagging Support | Tagging Support | Ad Ops / Trafficker | Mid | 2 |  |  | 1.6.5.3 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.6 | 1.6 | Dashboard Maintenance | Dashboard Maintenance |  |  |  | 7 | 156 | 4 | 1.6.5 |  |  | 195 | 1365
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.6.1 | 1.6.6 | Connector Checks & Fixes | Dashboard Maintenance | Connector Checks & Fixes |  |  | 0 | 156 | 4 | 1.6.6 |  |  | 0 | 0
1362 | DEL-0032 | TSK-01353 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.6.1.1 | 1.6.6.1 | Connector Checks & Fixes | Dashboard Maintenance | Connector Checks & Fixes | Analyst | Mid | 6 |  |  | 1.6.6.1 |  |  | 0 | 0
1363 | DEL-0032 | TSK-01354 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.6.1.2 | 1.6.6.1 | Connector Checks & Fixes | Dashboard Maintenance | Connector Checks & Fixes | Project Manager | Mid | 1 |  |  | 1.6.6.1.1 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.7 | 1.6 | Reconcilliation & Media Budget Authorization | Reconcilliation & Media Budget Authorization |  |  |  | 5 | 160 | 2 | 1.6.6 |  |  | 195 | 975
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.7.1 | 1.6.7 | Authorization & Docs | Reconcilliation & Media Budget Authorization | Authorization & Docs |  |  | 0 | 160 | 2 | 1.6.7 |  |  | 0 | 0
1366 | DEL-0032 | TSK-01357 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.7.1.1 | 1.6.7.1 | Authorization & Docs | Reconcilliation & Media Budget Authorization | Authorization & Docs | Account Manager | Mid | 2 |  |  | 1.6.7.1 |  |  | 0 | 0
1368 | DEL-0032 | TSK-01359 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.7.1.2 | 1.6.7.1 | Authorization & Docs | Reconcilliation & Media Budget Authorization | Authorization & Docs | Media Buyer | Mid | 1 |  |  | 1.6.7.1.1 |  |  | 0 | 0
1367 | DEL-0032 | TSK-01358 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.7.1.3 | 1.6.7.1 | Authorization & Docs | Reconcilliation & Media Budget Authorization | Authorization & Docs | Project Manager | Mid | 2 |  |  | 1.6.7.1.2 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.8 | 1.6 | KPI Monitoring | KPI Monitoring |  |  |  | 4 | 162 | 2 | 1.6.7 |  |  | 195 | 780
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.8.1 | 1.6.8 | Weekly KPI Scan | KPI Monitoring | Weekly KPI Scan |  |  | 0 | 162 | 2 | 1.6.8 |  |  | 0 | 0
1365 | DEL-0032 | TSK-01356 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.8.1.1 | 1.6.8.1 | Weekly KPI Scan | KPI Monitoring | Weekly KPI Scan | Analyst | Mid | 1 |  |  | 1.6.8.1 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.8.2 | 1.6.8 | Notes & Flags | KPI Monitoring | Notes & Flags |  |  | 0 | 164 | 0 | 1.6.8.1.1 |  |  | 0 | 0
1364 | DEL-0032 | TSK-01355 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.8.2.1 | 1.6.8.2 | Notes & Flags | KPI Monitoring | Notes & Flags | Media Strategist | Mid | 3 |  |  | 1.6.8.2 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.9 | 1.6 | Ad-Platform Reporting | Ad-Platform Reporting |  |  |  | 4 | 164 | 0 | 1.6.8 |  |  | 195 | 780
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.9.1 | 1.6.9 | Distribution | Ad-Platform Reporting | Distribution |  |  | 0 | 164 | 0 | 1.6.9 |  |  | 0 | 0
1348 | DEL-0032 | TSK-01339 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.9.1.1 | 1.6.9.1 | Distribution | Ad-Platform Reporting | Distribution | Analyst | Mid | 3 |  |  | 1.6.9.1 |  |  | 0 | 0
1347 | DEL-0032 | TSK-01338 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.9.1.2 | 1.6.9.1 | Distribution | Ad-Platform Reporting | Distribution | Project Manager | Mid | 1 |  |  | 1.6.9.1.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7 | 1 | Brand Style & Usage Guidelines |  |  |  |  | 294 | 164 | 11 | 1.6 |  | Advanced/T2_MediumVolume | 195 | 57330
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.1 | 1.7 | Color Palettes | Color Palettes |  |  |  | 16 | 164 | 3 | 1.7 |  |  | 195 | 3120
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.1.1 | 1.7.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions |  |  | 0 | 164 | 3 | 1.7.1 |  |  | 0 | 0
579 | DEL-0009 | TSK-00570 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.1.1.1 | 1.7.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.7.1.1 |  |  | 0 | 0
583 | DEL-0009 | TSK-00574 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.1.1.2 | 1.7.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Art Director | Lead/Director | 2 |  |  | 1.7.1.1.1 |  |  | 0 | 0
580 | DEL-0009 | TSK-00571 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.1.1.3 | 1.7.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Creative Director | Lead/Director | 4 |  |  | 1.7.1.1.2 |  |  | 0 | 0
582 | DEL-0009 | TSK-00573 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.1.1.4 | 1.7.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Designer | Mid | 5 |  |  | 1.7.1.1.3 |  |  | 0 | 0
581 | DEL-0009 | TSK-00572 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.1.1.5 | 1.7.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.7.1.1.4 |  |  | 0 | 0
578 | DEL-0009 | TSK-00569 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.1.1.6 | 1.7.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | QA Specialist | Mid | 3 |  |  | 1.7.1.1.5 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2 | 1.7 | Logo Lock-Ups | Logo Lock-Ups |  |  |  | 33 | 167 | 8 | 1.7.1 |  |  | 195 | 6435
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.1 | 1.7.2 | Quality Check (Specs/Accessibility) | Logo Lock-Ups | Quality Check (Specs/Accessibility) |  |  | 0 | 167 | 3 | 1.7.2 |  |  | 0 | 0
626 | DEL-0009 | TSK-00617 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.1.1 | 1.7.2.1 | Quality Check (Specs/Accessibility) | Logo Lock-Ups | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.7.2.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.2 | 1.7.2 | Internal Review & Critique | Logo Lock-Ups | Internal Review & Critique |  |  | 0 | 170 | 2 | 1.7.2.1.1 |  |  | 0 | 0
622 | DEL-0009 | TSK-00613 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.2.1 | 1.7.2.2 | Internal Review & Critique | Logo Lock-Ups | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.7.2.2 |  |  | 0 | 0
623 | DEL-0009 | TSK-00614 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.2.2 | 1.7.2.2 | Internal Review & Critique | Logo Lock-Ups | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.7.2.2.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.3 | 1.7.2 | Client Review & Revisions | Logo Lock-Ups | Client Review & Revisions |  |  | 0 | 172 | 3 | 1.7.2.2.2 |  |  | 0 | 0
618 | DEL-0009 | TSK-00609 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.3.1 | 1.7.2.3 | Client Review & Revisions | Logo Lock-Ups | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.7.2.3 |  |  | 0 | 0
619 | DEL-0009 | TSK-00610 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.3.2 | 1.7.2.3 | Client Review & Revisions | Logo Lock-Ups | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.7.2.3.1 |  |  | 0 | 0
620 | DEL-0009 | TSK-00611 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.3.3 | 1.7.2.3 | Client Review & Revisions | Logo Lock-Ups | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.7.2.3.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.4 | 1.7.2 | Final Packaging | Logo Lock-Ups | Final Packaging |  |  | 0 | 175 | 0 | 1.7.2.3.3 |  |  | 0 | 0
621 | DEL-0009 | TSK-00612 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.4.1 | 1.7.2.4 | Final Packaging | Logo Lock-Ups | Final Packaging | Designer | Mid | 24 |  |  | 1.7.2.4 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3 | 1.7 | Logo Placement | Logo Placement |  |  |  | 32 | 167 | 8 | 1.7.2 |  |  | 195 | 6240
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3.1 | 1.7.3 | Quality Check (Specs/Accessibility) | Logo Placement | Quality Check (Specs/Accessibility) |  |  | 0 | 167 | 3 | 1.7.3 |  |  | 0 | 0
635 | DEL-0009 | TSK-00626 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3.1.1 | 1.7.3.1 | Quality Check (Specs/Accessibility) | Logo Placement | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.7.3.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3.2 | 1.7.3 | Internal Review & Critique | Logo Placement | Internal Review & Critique |  |  | 0 | 170 | 2 | 1.7.3.1.1 |  |  | 0 | 0
631 | DEL-0009 | TSK-00622 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3.2.1 | 1.7.3.2 | Internal Review & Critique | Logo Placement | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.7.3.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3.3 | 1.7.3 | Client Review & Revisions | Logo Placement | Client Review & Revisions |  |  | 0 | 172 | 3 | 1.7.3.2.1 |  |  | 0 | 0
627 | DEL-0009 | TSK-00618 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3.3.1 | 1.7.3.3 | Client Review & Revisions | Logo Placement | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.7.3.3 |  |  | 0 | 0
628 | DEL-0009 | TSK-00619 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3.3.2 | 1.7.3.3 | Client Review & Revisions | Logo Placement | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.7.3.3.1 |  |  | 0 | 0
629 | DEL-0009 | TSK-00620 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3.3.3 | 1.7.3.3 | Client Review & Revisions | Logo Placement | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.7.3.3.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3.4 | 1.7.3 | Final Packaging | Logo Placement | Final Packaging |  |  | 0 | 175 | 0 | 1.7.3.3.3 |  |  | 0 | 0
630 | DEL-0009 | TSK-00621 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3.4.1 | 1.7.3.4 | Final Packaging | Logo Placement | Final Packaging | Designer | Mid | 24 |  |  | 1.7.3.4 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4 | 1.7 | Brand Do's & Dont's | Brand Do's & Dont's |  |  |  | 39 | 170 | 5 | 1.7.3 |  |  | 195 | 7605
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.1 | 1.7.4 | Internal Review & Critique | Brand Do's & Dont's | Internal Review & Critique |  |  | 0 | 170 | 2 | 1.7.4 |  |  | 0 | 0
573 | DEL-0009 | TSK-00564 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.1.1 | 1.7.4.1 | Internal Review & Critique | Brand Do's & Dont's | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.7.4.1 |  |  | 0 | 0
574 | DEL-0009 | TSK-00565 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.1.2 | 1.7.4.1 | Internal Review & Critique | Brand Do's & Dont's | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.7.4.1.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.2 | 1.7.4 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions |  |  | 0 | 172 | 3 | 1.7.4.1.2 |  |  | 0 | 0
568 | DEL-0009 | TSK-00559 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.2.1 | 1.7.4.2 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.7.4.2 |  |  | 0 | 0
569 | DEL-0009 | TSK-00560 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.2.2 | 1.7.4.2 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.7.4.2.1 |  |  | 0 | 0
570 | DEL-0009 | TSK-00561 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.2.3 | 1.7.4.2 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.7.4.2.2 |  |  | 0 | 0
571 | DEL-0009 | TSK-00562 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.2.4 | 1.7.4.2 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.7.4.2.3 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.3 | 1.7.4 | Outline & Examples | Brand Do's & Dont's | Outline & Examples |  |  | 0 | 175 | 0 | 1.7.4.2.4 |  |  | 0 | 0
575 | DEL-0009 | TSK-00566 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.3.1 | 1.7.4.3 | Outline & Examples | Brand Do's & Dont's | Outline & Examples | Copywriter | Mid | 2 |  |  | 1.7.4.3 |  |  | 0 | 0
572 | DEL-0009 | TSK-00563 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.3.2 | 1.7.4.3 | Outline & Examples | Brand Do's & Dont's | Outline & Examples | Designer | Mid | 30 |  |  | 1.7.4.3.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5 | 1.7 | Design Style Tile | Design Style Tile |  |  |  | 27 | 170 | 5 | 1.7.4 |  |  | 195 | 5265
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5.1 | 1.7.5 | Internal Review & Critique | Design Style Tile | Internal Review & Critique |  |  | 0 | 170 | 2 | 1.7.5 |  |  | 0 | 0
590 | DEL-0009 | TSK-00581 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5.1.1 | 1.7.5.1 | Internal Review & Critique | Design Style Tile | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.7.5.1 |  |  | 0 | 0
591 | DEL-0009 | TSK-00582 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5.1.2 | 1.7.5.1 | Internal Review & Critique | Design Style Tile | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.7.5.1.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5.2 | 1.7.5 | Client Review & Revisions | Design Style Tile | Client Review & Revisions |  |  | 0 | 172 | 3 | 1.7.5.1.2 |  |  | 0 | 0
586 | DEL-0009 | TSK-00577 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5.2.1 | 1.7.5.2 | Client Review & Revisions | Design Style Tile | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.7.5.2 |  |  | 0 | 0
587 | DEL-0009 | TSK-00578 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5.2.2 | 1.7.5.2 | Client Review & Revisions | Design Style Tile | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.7.5.2.1 |  |  | 0 | 0
588 | DEL-0009 | TSK-00579 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5.2.3 | 1.7.5.2 | Client Review & Revisions | Design Style Tile | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.7.5.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5.3 | 1.7.5 | Style Tile Build | Design Style Tile | Style Tile Build |  |  | 0 | 175 | 0 | 1.7.5.2.3 |  |  | 0 | 0
592 | DEL-0009 | TSK-00583 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5.3.1 | 1.7.5.3 | Style Tile Build | Design Style Tile | Style Tile Build | Art Director | Lead/Director | 1 |  |  | 1.7.5.3 |  |  | 0 | 0
589 | DEL-0009 | TSK-00580 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5.3.2 | 1.7.5.3 | Style Tile Build | Design Style Tile | Style Tile Build | Designer | Mid | 20 |  |  | 1.7.5.3.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6 | 1.7 | Image Use Guidance | Image Use Guidance |  |  |  | 27 | 170 | 5 | 1.7.5 |  |  | 195 | 5265
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6.1 | 1.7.6 | Internal Review & Critique | Image Use Guidance | Internal Review & Critique |  |  | 0 | 170 | 2 | 1.7.6 |  |  | 0 | 0
608 | DEL-0009 | TSK-00599 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6.1.1 | 1.7.6.1 | Internal Review & Critique | Image Use Guidance | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.7.6.1 |  |  | 0 | 0
609 | DEL-0009 | TSK-00600 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6.1.2 | 1.7.6.1 | Internal Review & Critique | Image Use Guidance | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.7.6.1.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6.2 | 1.7.6 | Client Review & Revisions | Image Use Guidance | Client Review & Revisions |  |  | 0 | 172 | 3 | 1.7.6.1.2 |  |  | 0 | 0
602 | DEL-0009 | TSK-00593 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6.2.1 | 1.7.6.2 | Client Review & Revisions | Image Use Guidance | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.7.6.2 |  |  | 0 | 0
603 | DEL-0009 | TSK-00594 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6.2.2 | 1.7.6.2 | Client Review & Revisions | Image Use Guidance | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.7.6.2.1 |  |  | 0 | 0
604 | DEL-0009 | TSK-00595 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6.2.3 | 1.7.6.2 | Client Review & Revisions | Image Use Guidance | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.7.6.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6.3 | 1.7.6 | Examples & Callouts | Image Use Guidance | Examples & Callouts |  |  | 0 | 175 | 0 | 1.7.6.2.3 |  |  | 0 | 0
607 | DEL-0009 | TSK-00598 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6.3.1 | 1.7.6.3 | Examples & Callouts | Image Use Guidance | Examples & Callouts | Art Director | Lead/Director | 1 |  |  | 1.7.6.3 |  |  | 0 | 0
605 | DEL-0009 | TSK-00596 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6.3.2 | 1.7.6.3 | Examples & Callouts | Image Use Guidance | Examples & Callouts | Designer | Mid | 20 |  |  | 1.7.6.3.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7 | 1.7 | Imagery Style | Imagery Style |  |  |  | 27 | 170 | 5 | 1.7.6 |  |  | 195 | 5265
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7.1 | 1.7.7 | Internal Review & Critique | Imagery Style | Internal Review & Critique |  |  | 0 | 170 | 2 | 1.7.7 |  |  | 0 | 0
616 | DEL-0009 | TSK-00607 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7.1.1 | 1.7.7.1 | Internal Review & Critique | Imagery Style | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.7.7.1 |  |  | 0 | 0
617 | DEL-0009 | TSK-00608 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7.1.2 | 1.7.7.1 | Internal Review & Critique | Imagery Style | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.7.7.1.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7.2 | 1.7.7 | Client Review & Revisions | Imagery Style | Client Review & Revisions |  |  | 0 | 172 | 3 | 1.7.7.1.2 |  |  | 0 | 0
610 | DEL-0009 | TSK-00601 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7.2.1 | 1.7.7.2 | Client Review & Revisions | Imagery Style | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.7.7.2 |  |  | 0 | 0
611 | DEL-0009 | TSK-00602 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7.2.2 | 1.7.7.2 | Client Review & Revisions | Imagery Style | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.7.7.2.1 |  |  | 0 | 0
612 | DEL-0009 | TSK-00603 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7.2.3 | 1.7.7.2 | Client Review & Revisions | Imagery Style | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.7.7.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7.3 | 1.7.7 | Examples & Callouts | Imagery Style | Examples & Callouts |  |  | 0 | 175 | 0 | 1.7.7.2.3 |  |  | 0 | 0
615 | DEL-0009 | TSK-00606 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7.3.1 | 1.7.7.3 | Examples & Callouts | Imagery Style | Examples & Callouts | Art Director | Lead/Director | 1 |  |  | 1.7.7.3 |  |  | 0 | 0
613 | DEL-0009 | TSK-00604 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7.3.2 | 1.7.7.3 | Examples & Callouts | Imagery Style | Examples & Callouts | Designer | Mid | 20 |  |  | 1.7.7.3.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8 | 1.7 | Photo & Video Direction | Photo & Video Direction |  |  |  | 29 | 170 | 5 | 1.7.7 |  |  | 195 | 5655
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.1 | 1.7.8 | Internal Review & Critique | Photo & Video Direction | Internal Review & Critique |  |  | 0 | 170 | 2 | 1.7.8 |  |  | 0 | 0
642 | DEL-0009 | TSK-00633 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.1.1 | 1.7.8.1 | Internal Review & Critique | Photo & Video Direction | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.7.8.1 |  |  | 0 | 0
643 | DEL-0009 | TSK-00634 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.1.2 | 1.7.8.1 | Internal Review & Critique | Photo & Video Direction | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.7.8.1.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.2 | 1.7.8 | Client Review & Revisions | Photo & Video Direction | Client Review & Revisions |  |  | 0 | 172 | 3 | 1.7.8.1.2 |  |  | 0 | 0
636 | DEL-0009 | TSK-00627 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.2.1 | 1.7.8.2 | Client Review & Revisions | Photo & Video Direction | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.7.8.2 |  |  | 0 | 0
637 | DEL-0009 | TSK-00628 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.2.2 | 1.7.8.2 | Client Review & Revisions | Photo & Video Direction | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.7.8.2.1 |  |  | 0 | 0
638 | DEL-0009 | TSK-00629 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.2.3 | 1.7.8.2 | Client Review & Revisions | Photo & Video Direction | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.7.8.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.3 | 1.7.8 | Direction Pages | Photo & Video Direction | Direction Pages |  |  | 0 | 175 | 0 | 1.7.8.2.3 |  |  | 0 | 0
639 | DEL-0009 | TSK-00630 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.3.1 | 1.7.8.3 | Direction Pages | Photo & Video Direction | Direction Pages | Art Director | Lead/Director | 1 |  |  | 1.7.8.3 |  |  | 0 | 0
640 | DEL-0009 | TSK-00631 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.3.2 | 1.7.8.3 | Direction Pages | Photo & Video Direction | Direction Pages | Creative Director | Lead/Director | 2 |  |  | 1.7.8.3.1 |  |  | 0 | 0
641 | DEL-0009 | TSK-00632 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.3.3 | 1.7.8.3 | Direction Pages | Photo & Video Direction | Direction Pages | Designer | Mid | 20 |  |  | 1.7.8.3.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.9 | 1.7 | Typography | Typography |  |  |  | 21 | 170 | 5 | 1.7.8 |  |  | 195 | 4095
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.9.1 | 1.7.9 | Internal Review & Critique | Typography | Internal Review & Critique |  |  | 0 | 170 | 2 | 1.7.9 |  |  | 0 | 0
649 | DEL-0009 | TSK-00640 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.9.1.1 | 1.7.9.1 | Internal Review & Critique | Typography | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.7.9.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.9.2 | 1.7.9 | Client Review & Revisions | Typography | Client Review & Revisions |  |  | 0 | 172 | 3 | 1.7.9.1.1 |  |  | 0 | 0
645 | DEL-0009 | TSK-00636 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.9.2.1 | 1.7.9.2 | Client Review & Revisions | Typography | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.7.9.2 |  |  | 0 | 0
646 | DEL-0009 | TSK-00637 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.9.2.2 | 1.7.9.2 | Client Review & Revisions | Typography | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.7.9.2.1 |  |  | 0 | 0
647 | DEL-0009 | TSK-00638 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.9.2.3 | 1.7.9.2 | Client Review & Revisions | Typography | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.7.9.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.9.3 | 1.7.9 | Final Packaging | Typography | Final Packaging |  |  | 0 | 175 | 0 | 1.7.9.2.3 |  |  | 0 | 0
648 | DEL-0009 | TSK-00639 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.9.3.1 | 1.7.9.3 | Final Packaging | Typography | Final Packaging | Designer | Mid | 16 |  |  | 1.7.9.3 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.10 | 1.7 | Use Cases | Use Cases |  |  |  | 25 | 170 | 5 | 1.7.9 |  |  | 195 | 4875
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.10.1 | 1.7.10 | Internal Review & Critique | Use Cases | Internal Review & Critique |  |  | 0 | 170 | 2 | 1.7.10 |  |  | 0 | 0
656 | DEL-0009 | TSK-00647 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.10.1.1 | 1.7.10.1 | Internal Review & Critique | Use Cases | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.7.10.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.10.2 | 1.7.10 | Client Review & Revisions | Use Cases | Client Review & Revisions |  |  | 0 | 172 | 3 | 1.7.10.1.1 |  |  | 0 | 0
652 | DEL-0009 | TSK-00643 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.10.2.1 | 1.7.10.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.7.10.2 |  |  | 0 | 0
653 | DEL-0009 | TSK-00644 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.10.2.2 | 1.7.10.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.7.10.2.1 |  |  | 0 | 0
654 | DEL-0009 | TSK-00645 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.10.2.3 | 1.7.10.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.7.10.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.10.3 | 1.7.10 | Final Packaging | Use Cases | Final Packaging |  |  | 0 | 175 | 0 | 1.7.10.2.3 |  |  | 0 | 0
655 | DEL-0009 | TSK-00646 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.10.3.1 | 1.7.10.3 | Final Packaging | Use Cases | Final Packaging | Designer | Mid | 20 |  |  | 1.7.10.3 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.11 | 1.7 | Graphic Treatment Direction | Graphic Treatment Direction |  |  |  | 18 | 175 | 0 | 1.7.10 |  |  | 195 | 3510
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.11.1 | 1.7.11 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions |  |  | 0 | 175 | 0 | 1.7.11 |  |  | 0 | 0
594 | DEL-0009 | TSK-00585 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.11.1.1 | 1.7.11.1 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.7.11.1 |  |  | 0 | 0
598 | DEL-0009 | TSK-00589 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.11.1.2 | 1.7.11.1 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Art Director | Lead/Director | 3 |  |  | 1.7.11.1.1 |  |  | 0 | 0
595 | DEL-0009 | TSK-00586 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.11.1.3 | 1.7.11.1 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Creative Director | Lead/Director | 8 |  |  | 1.7.11.1.2 |  |  | 0 | 0
597 | DEL-0009 | TSK-00588 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.11.1.4 | 1.7.11.1 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.7.11.1.3 |  |  | 0 | 0
596 | DEL-0009 | TSK-00587 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.11.1.5 | 1.7.11.1 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.7.11.1.4 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8 | 1 | Reporting |  |  |  |  | 128 | 175 | 7 | 1.7 |  | Advanced/T2_MediumVolume | 195 | 24960
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.1 | 1.8 | Dashboards | Dashboards |  |  |  | 9 | 175 | 7 | 1.8 |  |  | 195 | 1755
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.1.1 | 1.8.1 | QA | Dashboards | QA |  |  | 0 | 175 | 3 | 1.8.1 |  |  | 0 | 0
1116 | DEL-0024 | TSK-01107 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.1.1.1 | 1.8.1.1 | QA | Dashboards | QA | QA Specialist | Mid | 3 |  |  | 1.8.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.1.2 | 1.8.1 | Dashboard Build/Refresh | Dashboards | Dashboard Build/Refresh |  |  | 0 | 178 | 4 | 1.8.1.1.1 |  |  | 0 | 0
1115 | DEL-0024 | TSK-01106 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.1.2.1 | 1.8.1.2 | Dashboard Build/Refresh | Dashboards | Dashboard Build/Refresh | Analyst | Mid | 6 |  |  | 1.8.1.2 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.2 | 1.8 | Engagement Rate | Engagement Rate |  |  |  | 6 | 175 | 3 | 1.8.1 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.2.1 | 1.8.2 | Data Refresh & Calc Check | Engagement Rate | Data Refresh & Calc Check |  |  | 0 | 175 | 3 | 1.8.2 |  |  | 0 | 0
1119 | DEL-0024 | TSK-01110 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.2.1.1 | 1.8.2.1 | Data Refresh & Calc Check | Engagement Rate | Data Refresh & Calc Check | Analyst | Mid | 3 |  |  | 1.8.2.1 |  |  | 0 | 0
1120 | DEL-0024 | TSK-01111 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.2.1.2 | 1.8.2.1 | Data Refresh & Calc Check | Engagement Rate | Data Refresh & Calc Check | QA Specialist | Mid | 3 |  |  | 1.8.2.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.3 | 1.8 | Emplifi Reports | Emplifi Reports |  |  |  | 7 | 178 | 4 | 1.8.2 |  |  | 195 | 1365
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.3.1 | 1.8.3 | Emplifi Extract & Summary | Emplifi Reports | Emplifi Extract & Summary |  |  | 0 | 178 | 4 | 1.8.3 |  |  | 0 | 0
1117 | DEL-0024 | TSK-01108 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.3.1.1 | 1.8.3.1 | Emplifi Extract & Summary | Emplifi Reports | Emplifi Extract & Summary | Account Manager | Mid | 1 |  |  | 1.8.3.1 |  |  | 0 | 0
1118 | DEL-0024 | TSK-01109 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.3.1.2 | 1.8.3.1 | Emplifi Extract & Summary | Emplifi Reports | Emplifi Extract & Summary | Analyst | Mid | 6 |  |  | 1.8.3.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.4 | 1.8 | Monthly Comprehensive Report | Monthly Comprehensive Report |  |  |  | 11 | 178 | 4 | 1.8.3 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.4.1 | 1.8.4 | Monthly Report | Monthly Comprehensive Report | Monthly Report |  |  | 0 | 178 | 4 | 1.8.4 |  |  | 0 | 0
1127 | DEL-0024 | TSK-01118 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.4.1.1 | 1.8.4.1 | Monthly Report | Monthly Comprehensive Report | Monthly Report | Analyst | Mid | 6 |  |  | 1.8.4.1 |  |  | 0 | 0
1128 | DEL-0024 | TSK-01119 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.4.1.2 | 1.8.4.1 | Monthly Report | Monthly Comprehensive Report | Monthly Report | Designer | Mid | 2 |  |  | 1.8.4.1.1 |  |  | 0 | 0
1129 | DEL-0024 | TSK-01120 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.4.1.3 | 1.8.4.1 | Monthly Report | Monthly Comprehensive Report | Monthly Report | Social Strategist | Mid | 3 |  |  | 1.8.4.1.2 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.5 | 1.8 | Monthly Organic Social Report | Monthly Organic Social Report |  |  |  | 11 | 178 | 4 | 1.8.4 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.5.1 | 1.8.5 | Monthly Organic Report | Monthly Organic Social Report | Monthly Organic Report |  |  | 0 | 178 | 4 | 1.8.5 |  |  | 0 | 0
1130 | DEL-0024 | TSK-01121 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.5.1.1 | 1.8.5.1 | Monthly Organic Report | Monthly Organic Social Report | Monthly Organic Report | Analyst | Mid | 6 |  |  | 1.8.5.1 |  |  | 0 | 0
1131 | DEL-0024 | TSK-01122 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.5.1.2 | 1.8.5.1 | Monthly Organic Report | Monthly Organic Social Report | Monthly Organic Report | Designer | Mid | 2 |  |  | 1.8.5.1.1 |  |  | 0 | 0
1132 | DEL-0024 | TSK-01123 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.5.1.3 | 1.8.5.1 | Monthly Organic Report | Monthly Organic Social Report | Monthly Organic Report | Social Strategist | Mid | 3 |  |  | 1.8.5.1.2 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.6 | 1.8 | Optimization Recommendations Report | Optimization Recommendations Report |  |  |  | 10 | 178 | 4 | 1.8.5 |  |  | 195 | 1950
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.6.1 | 1.8.6 | Recs & Next Steps | Optimization Recommendations Report | Recs & Next Steps |  |  | 0 | 178 | 4 | 1.8.6 |  |  | 0 | 0
1133 | DEL-0024 | TSK-01124 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.6.1.1 | 1.8.6.1 | Recs & Next Steps | Optimization Recommendations Report | Recs & Next Steps | Account Manager | Mid | 1 |  |  | 1.8.6.1 |  |  | 0 | 0
1134 | DEL-0024 | TSK-01125 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.6.1.2 | 1.8.6.1 | Recs & Next Steps | Optimization Recommendations Report | Recs & Next Steps | Analyst | Mid | 6 |  |  | 1.8.6.1.1 |  |  | 0 | 0
1135 | DEL-0024 | TSK-01126 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.6.1.3 | 1.8.6.1 | Recs & Next Steps | Optimization Recommendations Report | Recs & Next Steps | Social Strategist | Mid | 3 |  |  | 1.8.6.1.2 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.7 | 1.8 | Quarterly Ad-Hoc Report | Quarterly Ad-Hoc Report |  |  |  | 9 | 178 | 4 | 1.8.6 |  |  | 195 | 1755
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.7.1 | 1.8.7 | Quarterly Ad-hoc Deep Dive | Quarterly Ad-Hoc Report | Quarterly Ad-hoc Deep Dive |  |  | 0 | 178 | 4 | 1.8.7 |  |  | 0 | 0
1138 | DEL-0024 | TSK-01129 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.7.1.1 | 1.8.7.1 | Quarterly Ad-hoc Deep Dive | Quarterly Ad-Hoc Report | Quarterly Ad-hoc Deep Dive | Analyst | Mid | 6 |  |  | 1.8.7.1 |  |  | 0 | 0
1139 | DEL-0024 | TSK-01130 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.7.1.2 | 1.8.7.1 | Quarterly Ad-hoc Deep Dive | Quarterly Ad-Hoc Report | Quarterly Ad-hoc Deep Dive | QA Specialist | Mid | 3 |  |  | 1.8.7.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.8 | 1.8 | Quarterly Key Learnings & Insights Report | Quarterly Key Learnings & Insights Report |  |  |  | 11 | 178 | 4 | 1.8.7 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.8.1 | 1.8.8 | Quarterly Learnings & Insights | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights |  |  | 0 | 178 | 4 | 1.8.8 |  |  | 0 | 0
1140 | DEL-0024 | TSK-01131 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.8.1.1 | 1.8.8.1 | Quarterly Learnings & Insights | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights | Analyst | Mid | 6 |  |  | 1.8.8.1 |  |  | 0 | 0
1141 | DEL-0024 | TSK-01132 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.8.1.2 | 1.8.8.1 | Quarterly Learnings & Insights | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights | Designer | Mid | 2 |  |  | 1.8.8.1.1 |  |  | 0 | 0
1142 | DEL-0024 | TSK-01133 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.8.1.3 | 1.8.8.1 | Quarterly Learnings & Insights | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights | Social Strategist | Mid | 3 |  |  | 1.8.8.1.2 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.9 | 1.8 | Quarterly Report | Quarterly Report |  |  |  | 11 | 178 | 4 | 1.8.8 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.9.1 | 1.8.9 | Quarterly Report | Quarterly Report | Quarterly Report |  |  | 0 | 178 | 4 | 1.8.9 |  |  | 0 | 0
1143 | DEL-0024 | TSK-01134 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.9.1.1 | 1.8.9.1 | Quarterly Report | Quarterly Report | Quarterly Report | Analyst | Mid | 6 |  |  | 1.8.9.1 |  |  | 0 | 0
1144 | DEL-0024 | TSK-01135 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.9.1.2 | 1.8.9.1 | Quarterly Report | Quarterly Report | Quarterly Report | Designer | Mid | 2 |  |  | 1.8.9.1.1 |  |  | 0 | 0
1145 | DEL-0024 | TSK-01136 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.9.1.3 | 1.8.9.1 | Quarterly Report | Quarterly Report | Quarterly Report | Social Strategist | Mid | 3 |  |  | 1.8.9.1.2 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.10 | 1.8 | Summary overview | Summary overview |  |  |  | 4 | 178 | 4 | 1.8.9 |  |  | 195 | 780
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.10.1 | 1.8.10 | Summary Narrative | Summary overview | Summary Narrative |  |  | 0 | 178 | 4 | 1.8.10 |  |  | 0 | 0
1150 | DEL-0024 | TSK-01141 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.10.1.1 | 1.8.10.1 | Summary Narrative | Summary overview | Summary Narrative | Account Manager | Mid | 1 |  |  | 1.8.10.1 |  |  | 0 | 0
1151 | DEL-0024 | TSK-01142 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.10.1.2 | 1.8.10.1 | Summary Narrative | Summary overview | Summary Narrative | Social Strategist | Mid | 3 |  |  | 1.8.10.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.11 | 1.8 | Weekly Activity Report | Weekly Activity Report |  |  |  | 7 | 178 | 4 | 1.8.10 |  |  | 195 | 1365
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.11.1 | 1.8.11 | Weekly Activity Summary | Weekly Activity Report | Weekly Activity Summary |  |  | 0 | 178 | 4 | 1.8.11 |  |  | 0 | 0
1153 | DEL-0024 | TSK-01144 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.11.1.1 | 1.8.11.1 | Weekly Activity Summary | Weekly Activity Report | Weekly Activity Summary | Account Manager | Mid | 1 |  |  | 1.8.11.1 |  |  | 0 | 0
1154 | DEL-0024 | TSK-01145 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.11.1.2 | 1.8.11.1 | Weekly Activity Summary | Weekly Activity Report | Weekly Activity Summary | Analyst | Mid | 6 |  |  | 1.8.11.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.12 | 1.8 | Follower Growth | Follower Growth |  |  |  | 6 | 182 | 0 | 1.8.11 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.12.1 | 1.8.12 | Metric Pull & Notes | Follower Growth | Metric Pull & Notes |  |  | 0 | 182 | 0 | 1.8.12 |  |  | 0 | 0
1121 | DEL-0024 | TSK-01112 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.12.1.1 | 1.8.12.1 | Metric Pull & Notes | Follower Growth | Metric Pull & Notes | Analyst | Mid | 3 |  |  | 1.8.12.1 |  |  | 0 | 0
1122 | DEL-0024 | TSK-01113 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.12.1.2 | 1.8.12.1 | Metric Pull & Notes | Follower Growth | Metric Pull & Notes | QA Specialist | Mid | 3 |  |  | 1.8.12.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.13 | 1.8 | Impressions | Impressions |  |  |  | 6 | 182 | 0 | 1.8.12 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.13.1 | 1.8.13 | Metric Pull & Notes | Impressions | Metric Pull & Notes |  |  | 0 | 182 | 0 | 1.8.13 |  |  | 0 | 0
1123 | DEL-0024 | TSK-01114 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.13.1.1 | 1.8.13.1 | Metric Pull & Notes | Impressions | Metric Pull & Notes | Analyst | Mid | 3 |  |  | 1.8.13.1 |  |  | 0 | 0
1124 | DEL-0024 | TSK-01115 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.13.1.2 | 1.8.13.1 | Metric Pull & Notes | Impressions | Metric Pull & Notes | QA Specialist | Mid | 3 |  |  | 1.8.13.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.14 | 1.8 | Interactions | Interactions |  |  |  | 5 | 182 | 0 | 1.8.13 |  |  | 195 | 975
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.14.1 | 1.8.14 | Metric Pull & Notes | Interactions | Metric Pull & Notes |  |  | 0 | 182 | 0 | 1.8.14 |  |  | 0 | 0
1125 | DEL-0024 | TSK-01116 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.14.1.1 | 1.8.14.1 | Metric Pull & Notes | Interactions | Metric Pull & Notes | Analyst | Mid | 2 |  |  | 1.8.14.1 |  |  | 0 | 0
1126 | DEL-0024 | TSK-01117 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.14.1.2 | 1.8.14.1 | Metric Pull & Notes | Interactions | Metric Pull & Notes | QA Specialist | Mid | 3 |  |  | 1.8.14.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.15 | 1.8 | Profile Reach | Profile Reach |  |  |  | 5 | 182 | 0 | 1.8.14 |  |  | 195 | 975
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.15.1 | 1.8.15 | Metric Pull & Notes | Profile Reach | Metric Pull & Notes |  |  | 0 | 182 | 0 | 1.8.15 |  |  | 0 | 0
1136 | DEL-0024 | TSK-01127 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.15.1.1 | 1.8.15.1 | Metric Pull & Notes | Profile Reach | Metric Pull & Notes | Analyst | Mid | 2 |  |  | 1.8.15.1 |  |  | 0 | 0
1137 | DEL-0024 | TSK-01128 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.15.1.2 | 1.8.15.1 | Metric Pull & Notes | Profile Reach | Metric Pull & Notes | QA Specialist | Mid | 3 |  |  | 1.8.15.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.16 | 1.8 | Recap Reports | Recap Reports |  |  |  | 4 | 182 | 0 | 1.8.15 |  |  | 195 | 780
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.16.1 | 1.8.16 | Campaign/Period Recaps | Recap Reports | Campaign/Period Recaps |  |  | 0 | 182 | 0 | 1.8.16 |  |  | 0 | 0
1146 | DEL-0024 | TSK-01137 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.16.1.1 | 1.8.16.1 | Campaign/Period Recaps | Recap Reports | Campaign/Period Recaps | Account Manager | Mid | 2 |  |  | 1.8.16.1 |  |  | 0 | 0
1147 | DEL-0024 | TSK-01138 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.16.1.2 | 1.8.16.1 | Campaign/Period Recaps | Recap Reports | Campaign/Period Recaps | Analyst | Mid | 2 |  |  | 1.8.16.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.17 | 1.8 | Social Reporting | Social Reporting |  |  |  | 4 | 182 | 0 | 1.8.16 |  |  | 195 | 780
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.17.1 | 1.8.17 | Ongoing Social Reporting | Social Reporting | Ongoing Social Reporting |  |  | 0 | 182 | 0 | 1.8.17 |  |  | 0 | 0
1148 | DEL-0024 | TSK-01139 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.17.1.1 | 1.8.17.1 | Ongoing Social Reporting | Social Reporting | Ongoing Social Reporting | Account Manager | Mid | 2 |  |  | 1.8.17.1 |  |  | 0 | 0
1149 | DEL-0024 | TSK-01140 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.17.1.2 | 1.8.17.1 | Ongoing Social Reporting | Social Reporting | Ongoing Social Reporting | Analyst | Mid | 2 |  |  | 1.8.17.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.18 | 1.8 | Update/maintain Z/Russia tracker | Update/maintain Z/Russia tracker |  |  |  | 2 | 182 | 0 | 1.8.17 |  |  | 195 | 390
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.18.1 | 1.8.18 | Tracker Update | Update/maintain Z/Russia tracker | Tracker Update |  |  | 0 | 182 | 0 | 1.8.18 |  |  | 0 | 0
1152 | DEL-0024 | TSK-01143 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.18.1.1 | 1.8.18.1 | Tracker Update | Update/maintain Z/Russia tracker | Tracker Update | Analyst | Mid | 2 |  |  | 1.8.18.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9 | 1 | Brand Identity Development |  |  |  |  | 300 | 182 | 15 | 1.8 |  | Advanced/T2_MediumVolume | 195 | 58500
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.1 | 1.9 | Color Palette | Color Palette |  |  |  | 18 | 182 | 3 | 1.9 |  |  | 195 | 3510
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.1.1 | 1.9.1 | Client Review & Revisions | Color Palette | Client Review & Revisions |  |  | 0 | 182 | 3 | 1.9.1 |  |  | 0 | 0
475 | DEL-0008 | TSK-00466 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.1.1.1 | 1.9.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.9.1.1 |  |  | 0 | 0
480 | DEL-0008 | TSK-00471 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.1.1.2 | 1.9.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Art Director | Lead/Director | 2 |  |  | 1.9.1.1.1 |  |  | 0 | 0
476 | DEL-0008 | TSK-00467 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.1.1.3 | 1.9.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Creative Director | Lead/Director | 4 |  |  | 1.9.1.1.2 |  |  | 0 | 0
478 | DEL-0008 | TSK-00469 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.1.1.4 | 1.9.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Designer | Mid | 7 |  |  | 1.9.1.1.3 |  |  | 0 | 0
477 | DEL-0008 | TSK-00468 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.1.1.5 | 1.9.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.9.1.1.4 |  |  | 0 | 0
474 | DEL-0008 | TSK-00465 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.1.1.6 | 1.9.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | QA Specialist | Mid | 3 |  |  | 1.9.1.1.5 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2 | 1.9 | Graphic Mock-Ups | Graphic Mock-Ups |  |  |  | 30 | 185 | 9 | 1.9.1 |  |  | 195 | 5850
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.1 | 1.9.2 | Compositing/Retouch | Graphic Mock-Ups | Compositing/Retouch |  |  | 0 | 185 | 4 | 1.9.2 |  |  | 0 | 0
496 | DEL-0008 | TSK-00487 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.1.1 | 1.9.2.1 | Compositing/Retouch | Graphic Mock-Ups | Compositing/Retouch | Retoucher | Mid | 5 |  |  | 1.9.2.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.2 | 1.9.2 | Internal Review & Critique | Graphic Mock-Ups | Internal Review & Critique |  |  | 0 | 192 | 2 | 1.9.2.1.1 |  |  | 0 | 0
498 | DEL-0008 | TSK-00489 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.2.1 | 1.9.2.2 | Internal Review & Critique | Graphic Mock-Ups | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.9.2.2 |  |  | 0 | 0
499 | DEL-0008 | TSK-00490 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.2.2 | 1.9.2.2 | Internal Review & Critique | Graphic Mock-Ups | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.9.2.2.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.3 | 1.9.2 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions |  |  | 0 | 194 | 3 | 1.9.2.2.2 |  |  | 0 | 0
493 | DEL-0008 | TSK-00484 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.3.1 | 1.9.2.3 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.9.2.3 |  |  | 0 | 0
494 | DEL-0008 | TSK-00485 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.3.2 | 1.9.2.3 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.9.2.3.1 |  |  | 0 | 0
495 | DEL-0008 | TSK-00486 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.3.3 | 1.9.2.3 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.9.2.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.4 | 1.9.2 | Mockup Scenarios (3-4) | Graphic Mock-Ups | Mockup Scenarios (3-4) |  |  | 0 | 197 | 0 | 1.9.2.3.3 |  |  | 0 | 0
500 | DEL-0008 | TSK-00491 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.4.1 | 1.9.2.4 | Mockup Scenarios (3-4) | Graphic Mock-Ups | Mockup Scenarios (3-4) | Art Director | Lead/Director | 3 |  |  | 1.9.2.4 |  |  | 0 | 0
497 | DEL-0008 | TSK-00488 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.4.2 | 1.9.2.4 | Mockup Scenarios (3-4) | Graphic Mock-Ups | Mockup Scenarios (3-4) | Designer | Mid | 16 |  |  | 1.9.2.4.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3 | 1.9 | Logo | Logo |  |  |  | 43 | 189 | 8 | 1.9.2 |  |  | 195 | 8385
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.1 | 1.9.3 | Quality Check (Specs/Accessibility) | Logo | Quality Check (Specs/Accessibility) |  |  | 0 | 189 | 3 | 1.9.3 |  |  | 0 | 0
520 | DEL-0008 | TSK-00511 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.1.1 | 1.9.3.1 | Quality Check (Specs/Accessibility) | Logo | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.9.3.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.2 | 1.9.3 | Internal Review & Critique | Logo | Internal Review & Critique |  |  | 0 | 192 | 2 | 1.9.3.1.1 |  |  | 0 | 0
515 | DEL-0008 | TSK-00506 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.2.1 | 1.9.3.2 | Internal Review & Critique | Logo | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.9.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.3 | 1.9.3 | Client Review & Revisions | Logo | Client Review & Revisions |  |  | 0 | 194 | 3 | 1.9.3.2.1 |  |  | 0 | 0
511 | DEL-0008 | TSK-00502 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.3.1 | 1.9.3.3 | Client Review & Revisions | Logo | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.9.3.3 |  |  | 0 | 0
512 | DEL-0008 | TSK-00503 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.3.2 | 1.9.3.3 | Client Review & Revisions | Logo | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.9.3.3.1 |  |  | 0 | 0
513 | DEL-0008 | TSK-00504 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.3.3 | 1.9.3.3 | Client Review & Revisions | Logo | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.9.3.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.4 | 1.9.3 | Logo Exploration (6-8 dirs) | Logo | Logo Exploration (6-8 dirs) |  |  | 0 | 197 | 0 | 1.9.3.3.3 |  |  | 0 | 0
517 | DEL-0008 | TSK-00508 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.4.1 | 1.9.3.4 | Logo Exploration (6-8 dirs) | Logo | Logo Exploration (6-8 dirs) | Art Director | Lead/Director | 3 |  |  | 1.9.3.4 |  |  | 0 | 0
514 | DEL-0008 | TSK-00505 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.4.2 | 1.9.3.4 | Logo Exploration (6-8 dirs) | Logo | Logo Exploration (6-8 dirs) | Designer | Mid | 32 |  |  | 1.9.3.4.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4 | 1.9 | Typography | Typography |  |  |  | 40 | 189 | 8 | 1.9.3 |  |  | 195 | 7800
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4.1 | 1.9.4 | Quality Check (Specs/Accessibility) | Typography | Quality Check (Specs/Accessibility) |  |  | 0 | 189 | 3 | 1.9.4 |  |  | 0 | 0
556 | DEL-0008 | TSK-00547 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4.1.1 | 1.9.4.1 | Quality Check (Specs/Accessibility) | Typography | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.9.4.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4.2 | 1.9.4 | Internal Review & Critique | Typography | Internal Review & Critique |  |  | 0 | 192 | 2 | 1.9.4.1.1 |  |  | 0 | 0
554 | DEL-0008 | TSK-00545 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4.2.1 | 1.9.4.2 | Internal Review & Critique | Typography | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.9.4.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4.3 | 1.9.4 | Client Review & Revisions | Typography | Client Review & Revisions |  |  | 0 | 194 | 3 | 1.9.4.2.1 |  |  | 0 | 0
549 | DEL-0008 | TSK-00540 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4.3.1 | 1.9.4.3 | Client Review & Revisions | Typography | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.9.4.3 |  |  | 0 | 0
550 | DEL-0008 | TSK-00541 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4.3.2 | 1.9.4.3 | Client Review & Revisions | Typography | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.9.4.3.1 |  |  | 0 | 0
551 | DEL-0008 | TSK-00542 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4.3.3 | 1.9.4.3 | Client Review & Revisions | Typography | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.9.4.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4.4 | 1.9.4 | Final Packaging | Typography | Final Packaging |  |  | 0 | 197 | 0 | 1.9.4.3.3 |  |  | 0 | 0
552 | DEL-0008 | TSK-00543 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4.4.1 | 1.9.4.4 | Final Packaging | Typography | Final Packaging | Designer | Mid | 32 |  |  | 1.9.4.4 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5 | 1.9 | Graphic & Copy Messaging Cornerstones | Graphic & Copy Messaging Cornerstones |  |  |  | 28 | 192 | 5 | 1.9.4 |  |  | 195 | 5460
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.1 | 1.9.5 | Internal Review & Critique | Graphic & Copy Messaging Cornerstones | Internal Review & Critique |  |  | 0 | 192 | 2 | 1.9.5 |  |  | 0 | 0
489 | DEL-0008 | TSK-00480 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.1.1 | 1.9.5.1 | Internal Review & Critique | Graphic & Copy Messaging Cornerstones | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.9.5.1 |  |  | 0 | 0
490 | DEL-0008 | TSK-00481 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.1.2 | 1.9.5.1 | Internal Review & Critique | Graphic & Copy Messaging Cornerstones | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.9.5.1.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.2 | 1.9.5 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions |  |  | 0 | 194 | 3 | 1.9.5.1.2 |  |  | 0 | 0
483 | DEL-0008 | TSK-00474 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.2.1 | 1.9.5.2 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.9.5.2 |  |  | 0 | 0
484 | DEL-0008 | TSK-00475 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.2.2 | 1.9.5.2 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.9.5.2.1 |  |  | 0 | 0
485 | DEL-0008 | TSK-00476 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.2.3 | 1.9.5.2 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.9.5.2.2 |  |  | 0 | 0
486 | DEL-0008 | TSK-00477 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.2.4 | 1.9.5.2 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.9.5.2.3 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.3 | 1.9.5 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft |  |  | 0 | 197 | 0 | 1.9.5.2.4 |  |  | 0 | 0
491 | DEL-0008 | TSK-00482 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.3.1 | 1.9.5.3 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft | Copywriter | Mid | 2 |  |  | 1.9.5.3 |  |  | 0 | 0
492 | DEL-0008 | TSK-00483 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.3.2 | 1.9.5.3 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft | Creative Director | Lead/Director | 3 |  |  | 1.9.5.3.1 |  |  | 0 | 0
487 | DEL-0008 | TSK-00478 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.3.3 | 1.9.5.3 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft | Designer | Mid | 16 |  |  | 1.9.5.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.6 | 1.9 | Iconography | Iconography |  |  |  | 31 | 192 | 5 | 1.9.5 |  |  | 195 | 6045
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.6.1 | 1.9.6 | Internal Review & Critique | Iconography | Internal Review & Critique |  |  | 0 | 192 | 2 | 1.9.6 |  |  | 0 | 0
509 | DEL-0008 | TSK-00500 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.6.1.1 | 1.9.6.1 | Internal Review & Critique | Iconography | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.9.6.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.6.2 | 1.9.6 | Client Review & Revisions | Iconography | Client Review & Revisions |  |  | 0 | 194 | 3 | 1.9.6.1.1 |  |  | 0 | 0
502 | DEL-0008 | TSK-00493 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.6.2.1 | 1.9.6.2 | Client Review & Revisions | Iconography | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.9.6.2 |  |  | 0 | 0
503 | DEL-0008 | TSK-00494 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.6.2.2 | 1.9.6.2 | Client Review & Revisions | Iconography | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.9.6.2.1 |  |  | 0 | 0
504 | DEL-0008 | TSK-00495 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.6.2.3 | 1.9.6.2 | Client Review & Revisions | Iconography | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.9.6.2.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.6.3 | 1.9.6 | Export & Spec | Iconography | Export & Spec |  |  | 0 | 197 | 0 | 1.9.6.2.3 |  |  | 0 | 0
505 | DEL-0008 | TSK-00496 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.6.3.1 | 1.9.6.3 | Export & Spec | Iconography | Export & Spec | Designer | Mid | 24 |  |  | 1.9.6.3 |  |  | 0 | 0
508 | DEL-0008 | TSK-00499 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.6.3.2 | 1.9.6.3 | Export & Spec | Iconography | Export & Spec | Illustrator | Mid | 2 |  |  | 1.9.6.3.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7 | 1.9 | Overarching Moodboard | Overarching Moodboard |  |  |  | 27 | 192 | 5 | 1.9.6 |  |  | 195 | 5265
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.1 | 1.9.7 | Internal Review & Critique | Overarching Moodboard | Internal Review & Critique |  |  | 0 | 192 | 2 | 1.9.7 |  |  | 0 | 0
528 | DEL-0008 | TSK-00519 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.1.1 | 1.9.7.1 | Internal Review & Critique | Overarching Moodboard | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.9.7.1 |  |  | 0 | 0
529 | DEL-0008 | TSK-00520 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.1.2 | 1.9.7.1 | Internal Review & Critique | Overarching Moodboard | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.9.7.1.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.2 | 1.9.7 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions |  |  | 0 | 194 | 3 | 1.9.7.1.2 |  |  | 0 | 0
522 | DEL-0008 | TSK-00513 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.2.1 | 1.9.7.2 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.9.7.2 |  |  | 0 | 0
523 | DEL-0008 | TSK-00514 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.2.2 | 1.9.7.2 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.9.7.2.1 |  |  | 0 | 0
524 | DEL-0008 | TSK-00515 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.2.3 | 1.9.7.2 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.9.7.2.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.3 | 1.9.7 | Curate Moodboard | Overarching Moodboard | Curate Moodboard |  |  | 0 | 197 | 0 | 1.9.7.2.3 |  |  | 0 | 0
526 | DEL-0008 | TSK-00517 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.3.1 | 1.9.7.3 | Curate Moodboard | Overarching Moodboard | Curate Moodboard | Art Director | Lead/Director | 3 |  |  | 1.9.7.3 |  |  | 0 | 0
530 | DEL-0008 | TSK-00521 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.3.2 | 1.9.7.3 | Curate Moodboard | Overarching Moodboard | Curate Moodboard | Copywriter | Mid | 2 |  |  | 1.9.7.3.1 |  |  | 0 | 0
525 | DEL-0008 | TSK-00516 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.3.3 | 1.9.7.3 | Curate Moodboard | Overarching Moodboard | Curate Moodboard | Designer | Mid | 16 |  |  | 1.9.7.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8 | 1.9 | Tagline Copy Bank | Tagline Copy Bank |  |  |  | 22 | 192 | 5 | 1.9.7 |  |  | 195 | 4290
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.1 | 1.9.8 | Internal Review & Critique | Tagline Copy Bank | Internal Review & Critique |  |  | 0 | 192 | 2 | 1.9.8 |  |  | 0 | 0
536 | DEL-0008 | TSK-00527 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.1.1 | 1.9.8.1 | Internal Review & Critique | Tagline Copy Bank | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.9.8.1 |  |  | 0 | 0
537 | DEL-0008 | TSK-00528 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.1.2 | 1.9.8.1 | Internal Review & Critique | Tagline Copy Bank | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.9.8.1.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.2 | 1.9.8 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions |  |  | 0 | 194 | 3 | 1.9.8.1.2 |  |  | 0 | 0
531 | DEL-0008 | TSK-00522 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.2.1 | 1.9.8.2 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.9.8.2 |  |  | 0 | 0
532 | DEL-0008 | TSK-00523 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.2.2 | 1.9.8.2 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.9.8.2.1 |  |  | 0 | 0
533 | DEL-0008 | TSK-00524 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.2.3 | 1.9.8.2 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.9.8.2.2 |  |  | 0 | 0
534 | DEL-0008 | TSK-00525 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.2.4 | 1.9.8.2 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.9.8.2.3 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.3 | 1.9.8 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale |  |  | 0 | 197 | 0 | 1.9.8.2.4 |  |  | 0 | 0
538 | DEL-0008 | TSK-00529 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.3.1 | 1.9.8.3 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale | Copywriter | Mid | 4 |  |  | 1.9.8.3 |  |  | 0 | 0
539 | DEL-0008 | TSK-00530 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.3.2 | 1.9.8.3 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale | Creative Director | Lead/Director | 3 |  |  | 1.9.8.3.1 |  |  | 0 | 0
535 | DEL-0008 | TSK-00526 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.3.3 | 1.9.8.3 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale | Designer | Mid | 8 |  |  | 1.9.8.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.9 | 1.9 | Textures/Patterns/Materials | Textures/Patterns/Materials |  |  |  | 29 | 192 | 5 | 1.9.8 |  |  | 195 | 5655
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.9.1 | 1.9.9 | Internal Review & Critique | Textures/Patterns/Materials | Internal Review & Critique |  |  | 0 | 192 | 2 | 1.9.9 |  |  | 0 | 0
546 | DEL-0008 | TSK-00537 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.9.1.1 | 1.9.9.1 | Internal Review & Critique | Textures/Patterns/Materials | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.9.9.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.9.2 | 1.9.9 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions |  |  | 0 | 194 | 3 | 1.9.9.1.1 |  |  | 0 | 0
542 | DEL-0008 | TSK-00533 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.9.2.1 | 1.9.9.2 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.9.9.2 |  |  | 0 | 0
543 | DEL-0008 | TSK-00534 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.9.2.2 | 1.9.9.2 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.9.9.2.1 |  |  | 0 | 0
544 | DEL-0008 | TSK-00535 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.9.2.3 | 1.9.9.2 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.9.9.2.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.9.3 | 1.9.9 | Build Repeating Tiles | Textures/Patterns/Materials | Build Repeating Tiles |  |  | 0 | 197 | 0 | 1.9.9.2.3 |  |  | 0 | 0
541 | DEL-0008 | TSK-00532 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.9.3.1 | 1.9.9.3 | Build Repeating Tiles | Textures/Patterns/Materials | Build Repeating Tiles | Designer | Mid | 24 |  |  | 1.9.9.3 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.10 | 1.9 | Visual Elements/Comps | Visual Elements/Comps |  |  |  | 32 | 192 | 5 | 1.9.9 |  |  | 195 | 6240
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.10.1 | 1.9.10 | Internal Review & Critique | Visual Elements/Comps | Internal Review & Critique |  |  | 0 | 192 | 2 | 1.9.10 |  |  | 0 | 0
566 | DEL-0008 | TSK-00557 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.10.1.1 | 1.9.10.1 | Internal Review & Critique | Visual Elements/Comps | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.9.10.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.10.2 | 1.9.10 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions |  |  | 0 | 194 | 3 | 1.9.10.1.1 |  |  | 0 | 0
559 | DEL-0008 | TSK-00550 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.10.2.1 | 1.9.10.2 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.9.10.2 |  |  | 0 | 0
560 | DEL-0008 | TSK-00551 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.10.2.2 | 1.9.10.2 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.9.10.2.1 |  |  | 0 | 0
561 | DEL-0008 | TSK-00552 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.10.2.3 | 1.9.10.2 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.9.10.2.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.10.3 | 1.9.10 | Compositions (2-3) | Visual Elements/Comps | Compositions (2-3) |  |  | 0 | 197 | 0 | 1.9.10.2.3 |  |  | 0 | 0
562 | DEL-0008 | TSK-00553 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.10.3.1 | 1.9.10.3 | Compositions (2-3) | Visual Elements/Comps | Compositions (2-3) | Art Director | Lead/Director | 3 |  |  | 1.9.10.3 |  |  | 0 | 0
563 | DEL-0008 | TSK-00554 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.10.3.2 | 1.9.10.3 | Compositions (2-3) | Visual Elements/Comps | Compositions (2-3) | Designer | Mid | 24 |  |  | 1.9.10.3.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10 | 1 | Development |  |  |  |  | 268 | 197 | 26 | 1.9 |  | Advanced/T2_MediumVolume | 195 | 52260
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1 | 1.10 | ADA Compliance | ADA Compliance |  |  |  | 59 | 197 | 18 | 1.10 |  |  | 195 | 11505
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1.1 | 1.10.1 | Accessibility Audit | ADA Compliance | Accessibility Audit |  |  | 0 | 197 | 4 | 1.10.1 |  |  | 0 | 0
1738 | DEL-0044 | TSK-01729 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1.1.1 | 1.10.1.1 | Accessibility Audit | ADA Compliance | Accessibility Audit | Accessibility Specialist | Mid | 2 |  |  | 1.10.1.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1.2 | 1.10.1 | Accessibility QA | ADA Compliance | Accessibility QA |  |  | 0 | 209 | 3 | 1.10.1.1.1 |  |  | 0 | 0
1739 | DEL-0044 | TSK-01730 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1.2.1 | 1.10.1.2 | Accessibility QA | ADA Compliance | Accessibility QA | Accessibility Specialist | Mid | 2 |  |  | 1.10.1.2 |  |  | 0 | 0
1744 | DEL-0044 | TSK-01735 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1.2.2 | 1.10.1.2 | Accessibility QA | ADA Compliance | Accessibility QA | QA Engineer | Mid | 3 |  |  | 1.10.1.2.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1.3 | 1.10.1 | Code Review | ADA Compliance | Code Review |  |  | 0 | 212 | 11 | 1.10.1.2.2 |  |  | 0 | 0
1740 | DEL-0044 | TSK-01731 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1.3.1 | 1.10.1.3 | Code Review | ADA Compliance | Code Review | Backend Engineer | Mid | 12 |  |  | 1.10.1.3 |  |  | 0 | 0
1742 | DEL-0044 | TSK-01733 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1.3.2 | 1.10.1.3 | Code Review | ADA Compliance | Code Review | DevOps Engineer | Mid | 12 |  |  | 1.10.1.3.1 |  |  | 0 | 0
1741 | DEL-0044 | TSK-01732 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1.3.3 | 1.10.1.3 | Code Review | ADA Compliance | Code Review | Frontend Engineer | Mid | 24 |  |  | 1.10.1.3.2 |  |  | 0 | 0
1743 | DEL-0044 | TSK-01734 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1.3.4 | 1.10.1.3 | Code Review | ADA Compliance | Code Review | Project Manager | Mid | 4 |  |  | 1.10.1.3.3 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.2 | 1.10 | Audit & Requirement gathering | Audit & Requirement gathering |  |  |  | 20 | 197 | 4 | 1.10.1 |  |  | 195 | 3900
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.2.1 | 1.10.2 | Analytics Audit | Audit & Requirement gathering | Analytics Audit |  |  | 0 | 197 | 4 | 1.10.2 |  |  | 0 | 0
1750 | DEL-0044 | TSK-01741 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.2.1.1 | 1.10.2.1 | Analytics Audit | Audit & Requirement gathering | Analytics Audit | Business Analyst | Mid | 10 |  |  | 1.10.2.1 |  |  | 0 | 0
1749 | DEL-0044 | TSK-01740 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.2.1.2 | 1.10.2.1 | Analytics Audit | Audit & Requirement gathering | Analytics Audit | Data/Analytics Engineer | Mid | 10 |  |  | 1.10.2.1.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.3 | 1.10 | Audit existing UA Property | Audit existing UA Property |  |  |  | 20 | 197 | 4 | 1.10.2 |  |  | 195 | 3900
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.3.1 | 1.10.3 | Documentation | Audit existing UA Property | Documentation |  |  | 0 | 197 | 4 | 1.10.3 |  |  | 0 | 0
1753 | DEL-0044 | TSK-01744 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.3.1.1 | 1.10.3.1 | Documentation | Audit existing UA Property | Documentation | Business Analyst | Mid | 10 |  |  | 1.10.3.1 |  |  | 0 | 0
1755 | DEL-0044 | TSK-01746 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.3.1.2 | 1.10.3.1 | Documentation | Audit existing UA Property | Documentation | Data/Analytics Engineer | Mid | 10 |  |  | 1.10.3.1.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4 | 1.10 | Footer CTA | Footer CTA |  |  |  | 51 | 201 | 22 | 1.10.3 |  |  | 195 | 9945
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.1 | 1.10.4 | Design Consult | Footer CTA | Design Consult |  |  | 0 | 201 | 8 | 1.10.4 |  |  | 0 | 0
1765 | DEL-0044 | TSK-01756 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.1.1 | 1.10.4.1 | Design Consult | Footer CTA | Design Consult | UI Designer | Mid | 4 |  |  | 1.10.4.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.2 | 1.10.4 | Accessibility QA | Footer CTA | Accessibility QA |  |  | 0 | 209 | 3 | 1.10.4.1.1 |  |  | 0 | 0
1760 | DEL-0044 | TSK-01751 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.2.1 | 1.10.4.2 | Accessibility QA | Footer CTA | Accessibility QA | Accessibility Specialist | Mid | 2 |  |  | 1.10.4.2 |  |  | 0 | 0
1767 | DEL-0044 | TSK-01758 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.2.2 | 1.10.4.2 | Accessibility QA | Footer CTA | Accessibility QA | Frontend Engineer | Mid | 2 |  |  | 1.10.4.2.1 |  |  | 0 | 0
1766 | DEL-0044 | TSK-01757 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.2.3 | 1.10.4.2 | Accessibility QA | Footer CTA | Accessibility QA | QA Engineer | Mid | 3 |  |  | 1.10.4.2.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.3 | 1.10.4 | Code Review | Footer CTA | Code Review |  |  | 0 | 212 | 11 | 1.10.4.2.3 |  |  | 0 | 0
1761 | DEL-0044 | TSK-01752 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.3.1 | 1.10.4.3 | Code Review | Footer CTA | Code Review | Backend Engineer | Mid | 12 |  |  | 1.10.4.3 |  |  | 0 | 0
1763 | DEL-0044 | TSK-01754 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.3.2 | 1.10.4.3 | Code Review | Footer CTA | Code Review | DevOps Engineer | Mid | 12 |  |  | 1.10.4.3.1 |  |  | 0 | 0
1762 | DEL-0044 | TSK-01753 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.3.3 | 1.10.4.3 | Code Review | Footer CTA | Code Review | Frontend Engineer | Mid | 12 |  |  | 1.10.4.3.2 |  |  | 0 | 0
1764 | DEL-0044 | TSK-01755 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.3.4 | 1.10.4.3 | Code Review | Footer CTA | Code Review | Project Manager | Mid | 4 |  |  | 1.10.4.3.3 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5 | 1.10 | Header & Footer Navigation | Header & Footer Navigation |  |  |  | 51 | 201 | 22 | 1.10.4 |  |  | 195 | 9945
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.1 | 1.10.5 | Design Consult | Header & Footer Navigation | Design Consult |  |  | 0 | 201 | 8 | 1.10.5 |  |  | 0 | 0
1773 | DEL-0044 | TSK-01764 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.1.1 | 1.10.5.1 | Design Consult | Header & Footer Navigation | Design Consult | UI Designer | Mid | 4 |  |  | 1.10.5.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.2 | 1.10.5 | Accessibility QA | Header & Footer Navigation | Accessibility QA |  |  | 0 | 209 | 3 | 1.10.5.1.1 |  |  | 0 | 0
1768 | DEL-0044 | TSK-01759 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.2.1 | 1.10.5.2 | Accessibility QA | Header & Footer Navigation | Accessibility QA | Accessibility Specialist | Mid | 2 |  |  | 1.10.5.2 |  |  | 0 | 0
1775 | DEL-0044 | TSK-01766 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.2.2 | 1.10.5.2 | Accessibility QA | Header & Footer Navigation | Accessibility QA | Frontend Engineer | Mid | 2 |  |  | 1.10.5.2.1 |  |  | 0 | 0
1774 | DEL-0044 | TSK-01765 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.2.3 | 1.10.5.2 | Accessibility QA | Header & Footer Navigation | Accessibility QA | QA Engineer | Mid | 3 |  |  | 1.10.5.2.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.3 | 1.10.5 | Code Review | Header & Footer Navigation | Code Review |  |  | 0 | 212 | 11 | 1.10.5.2.3 |  |  | 0 | 0
1769 | DEL-0044 | TSK-01760 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.3.1 | 1.10.5.3 | Code Review | Header & Footer Navigation | Code Review | Backend Engineer | Mid | 12 |  |  | 1.10.5.3 |  |  | 0 | 0
1771 | DEL-0044 | TSK-01762 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.3.2 | 1.10.5.3 | Code Review | Header & Footer Navigation | Code Review | DevOps Engineer | Mid | 12 |  |  | 1.10.5.3.1 |  |  | 0 | 0
1770 | DEL-0044 | TSK-01761 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.3.3 | 1.10.5.3 | Code Review | Header & Footer Navigation | Code Review | Frontend Engineer | Mid | 12 |  |  | 1.10.5.3.2 |  |  | 0 | 0
1772 | DEL-0044 | TSK-01763 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.3.4 | 1.10.5.3 | Code Review | Header & Footer Navigation | Code Review | Project Manager | Mid | 4 |  |  | 1.10.5.3.3 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.6 | 1.10 | Additional Goals Setup | Additional Goals Setup |  |  |  | 8 | 209 | 14 | 1.10.5 |  |  | 195 | 1560
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.6.1 | 1.10.6 | QA Cycle | Additional Goals Setup | QA Cycle |  |  | 0 | 209 | 3 | 1.10.6 |  |  | 0 | 0
1747 | DEL-0044 | TSK-01738 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.6.1.1 | 1.10.6.1 | QA Cycle | Additional Goals Setup | QA Cycle | QA Engineer | Mid | 3 |  |  | 1.10.6.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.6.2 | 1.10.6 | Define & Configure Goals | Additional Goals Setup | Define & Configure Goals |  |  | 0 | 212 | 11 | 1.10.6.1.1 |  |  | 0 | 0
1746 | DEL-0044 | TSK-01737 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.6.2.1 | 1.10.6.2 | Define & Configure Goals | Additional Goals Setup | Define & Configure Goals | Data/Analytics Engineer | Mid | 5 |  |  | 1.10.6.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.7 | 1.10 | Custom Event Tracking | Custom Event Tracking |  |  |  | 8 | 209 | 14 | 1.10.6 |  |  | 195 | 1560
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.7.1 | 1.10.7 | QA Cycle | Custom Event Tracking | QA Cycle |  |  | 0 | 209 | 3 | 1.10.7 |  |  | 0 | 0
1758 | DEL-0044 | TSK-01749 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.7.1.1 | 1.10.7.1 | QA Cycle | Custom Event Tracking | QA Cycle | QA Engineer | Mid | 3 |  |  | 1.10.7.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.7.2 | 1.10.7 | Event Schema & Tagging | Custom Event Tracking | Event Schema & Tagging |  |  | 0 | 212 | 11 | 1.10.7.1.1 |  |  | 0 | 0
1757 | DEL-0044 | TSK-01748 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.7.2.1 | 1.10.7.2 | Event Schema & Tagging | Custom Event Tracking | Event Schema & Tagging | Data/Analytics Engineer | Mid | 5 |  |  | 1.10.7.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.8 | 1.10 | Implement Paid Media Pixel on website w GTM-Google Ads | Implement Paid Media Pixel on website w GTM-Google Ads |  |  |  | 6 | 209 | 14 | 1.10.7 |  |  | 195 | 1170
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.8.1 | 1.10.8 | Spec QA | Implement Paid Media Pixel on website w GTM-Google Ads | Spec QA |  |  | 0 | 209 | 3 | 1.10.8 |  |  | 0 | 0
1777 | DEL-0044 | TSK-01768 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.8.1.1 | 1.10.8.1 | Spec QA | Implement Paid Media Pixel on website w GTM-Google Ads | Spec QA | QA Engineer | Mid | 3 |  |  | 1.10.8.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.8.2 | 1.10.8 | Pixel Setup (GTM) | Implement Paid Media Pixel on website w GTM-Google Ads | Pixel Setup (GTM) |  |  | 0 | 212 | 11 | 1.10.8.1.1 |  |  | 0 | 0
1776 | DEL-0044 | TSK-01767 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.8.2.1 | 1.10.8.2 | Pixel Setup (GTM) | Implement Paid Media Pixel on website w GTM-Google Ads | Pixel Setup (GTM) | Data/Analytics Engineer | Mid | 3 |  |  | 1.10.8.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.9 | 1.10 | Implement goals listed in UA as Conversions in G4 | Implement goals listed in UA as Conversions in G4 |  |  |  | 8 | 209 | 14 | 1.10.8 |  |  | 195 | 1560
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.9.1 | 1.10.9 | QA Cycle | Implement goals listed in UA as Conversions in G4 | QA Cycle |  |  | 0 | 209 | 3 | 1.10.9 |  |  | 0 | 0
1779 | DEL-0044 | TSK-01770 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.9.1.1 | 1.10.9.1 | QA Cycle | Implement goals listed in UA as Conversions in G4 | QA Cycle | QA Engineer | Mid | 3 |  |  | 1.10.9.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.9.2 | 1.10.9 | Migrate UA Goals → GA4 Conversions | Implement goals listed in UA as Conversions in G4 | Migrate UA Goals → GA4 Conversions |  |  | 0 | 212 | 11 | 1.10.9.1.1 |  |  | 0 | 0
1778 | DEL-0044 | TSK-01769 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.9.2.1 | 1.10.9.2 | Migrate UA Goals → GA4 Conversions | Implement goals listed in UA as Conversions in G4 | Migrate UA Goals → GA4 Conversions | Data/Analytics Engineer | Mid | 5 |  |  | 1.10.9.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.10 | 1.10 | Implementation | Implementation |  |  |  | 8 | 209 | 14 | 1.10.9 |  |  | 195 | 1560
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.10.1 | 1.10.10 | QA Cycle | Implementation | QA Cycle |  |  | 0 | 209 | 3 | 1.10.10 |  |  | 0 | 0
1782 | DEL-0044 | TSK-01773 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.10.1.1 | 1.10.10.1 | QA Cycle | Implementation | QA Cycle | QA Engineer | Mid | 3 |  |  | 1.10.10.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.10.2 | 1.10.10 | Implement Tags/Events | Implementation | Implement Tags/Events |  |  | 0 | 212 | 11 | 1.10.10.1.1 |  |  | 0 | 0
1781 | DEL-0044 | TSK-01772 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.10.2.1 | 1.10.10.2 | Implement Tags/Events | Implementation | Implement Tags/Events | Data/Analytics Engineer | Mid | 5 |  |  | 1.10.10.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.11 | 1.10 | Outbound link clicks | Outbound link clicks |  |  |  | 6 | 209 | 14 | 1.10.10 |  |  | 195 | 1170
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.11.1 | 1.10.11 | QA | Outbound link clicks | QA |  |  | 0 | 209 | 3 | 1.10.11 |  |  | 0 | 0
1785 | DEL-0044 | TSK-01776 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.11.1.1 | 1.10.11.1 | QA | Outbound link clicks | QA | QA Engineer | Mid | 3 |  |  | 1.10.11.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.11.2 | 1.10.11 | Event Config | Outbound link clicks | Event Config |  |  | 0 | 212 | 11 | 1.10.11.1.1 |  |  | 0 | 0
1784 | DEL-0044 | TSK-01775 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.11.2.1 | 1.10.11.2 | Event Config | Outbound link clicks | Event Config | Data/Analytics Engineer | Mid | 3 |  |  | 1.10.11.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.12 | 1.10 | Publishing tags, Testing and Auditing | Publishing tags, Testing and Auditing |  |  |  | 5 | 209 | 3 | 1.10.11 |  |  | 195 | 975
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.12.1 | 1.10.12 | Publish & Smoke Test | Publishing tags, Testing and Auditing | Publish & Smoke Test |  |  | 0 | 209 | 3 | 1.10.12 |  |  | 0 | 0
1786 | DEL-0044 | TSK-01777 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.12.1.1 | 1.10.12.1 | Publish & Smoke Test | Publishing tags, Testing and Auditing | Publish & Smoke Test | Data/Analytics Engineer | Mid | 2 |  |  | 1.10.12.1 |  |  | 0 | 0
1787 | DEL-0044 | TSK-01778 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.12.1.2 | 1.10.12.1 | Publish & Smoke Test | Publishing tags, Testing and Auditing | Publish & Smoke Test | QA Engineer | Mid | 3 |  |  | 1.10.12.1.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.13 | 1.10 | Setup cross-domain tracking | Setup cross-domain tracking |  |  |  | 5 | 209 | 14 | 1.10.12 |  |  | 195 | 975
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.13.1 | 1.10.13 | QA | Setup cross-domain tracking | QA |  |  | 0 | 209 | 3 | 1.10.13 |  |  | 0 | 0
1789 | DEL-0044 | TSK-01780 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.13.1.1 | 1.10.13.1 | QA | Setup cross-domain tracking | QA | QA Engineer | Mid | 3 |  |  | 1.10.13.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.13.2 | 1.10.13 | Cross-domain Config | Setup cross-domain tracking | Cross-domain Config |  |  | 0 | 212 | 11 | 1.10.13.1.1 |  |  | 0 | 0
1788 | DEL-0044 | TSK-01779 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.13.2.1 | 1.10.13.2 | Cross-domain Config | Setup cross-domain tracking | Cross-domain Config | Data/Analytics Engineer | Mid | 2 |  |  | 1.10.13.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.14 | 1.10 | Setup eCommerce tracking | Setup eCommerce tracking |  |  |  | 5 | 209 | 14 | 1.10.13 |  |  | 195 | 975
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.14.1 | 1.10.14 | QA | Setup eCommerce tracking | QA |  |  | 0 | 209 | 3 | 1.10.14 |  |  | 0 | 0
1791 | DEL-0044 | TSK-01782 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.14.1.1 | 1.10.14.1 | QA | Setup eCommerce tracking | QA | QA Engineer | Mid | 3 |  |  | 1.10.14.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.14.2 | 1.10.14 | Ecommerce Data Layer | Setup eCommerce tracking | Ecommerce Data Layer |  |  | 0 | 212 | 11 | 1.10.14.1.1 |  |  | 0 | 0
1790 | DEL-0044 | TSK-01781 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.14.2.1 | 1.10.14.2 | Ecommerce Data Layer | Setup eCommerce tracking | Ecommerce Data Layer | Data/Analytics Engineer | Mid | 2 |  |  | 1.10.14.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.15 | 1.10 | Setup new GA4 acct for Caledera House | Setup new GA4 acct for Caledera House |  |  |  | 8 | 209 | 14 | 1.10.14 |  |  | 195 | 1560
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.15.1 | 1.10.15 | QA Cycle | Setup new GA4 acct for Caledera House | QA Cycle |  |  | 0 | 209 | 3 | 1.10.15 |  |  | 0 | 0
1793 | DEL-0044 | TSK-01784 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.15.1.1 | 1.10.15.1 | QA Cycle | Setup new GA4 acct for Caledera House | QA Cycle | QA Engineer | Mid | 3 |  |  | 1.10.15.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.15.2 | 1.10.15 | GA4 Property Setup | Setup new GA4 acct for Caledera House | GA4 Property Setup |  |  | 0 | 212 | 11 | 1.10.15.1.1 |  |  | 0 | 0
1792 | DEL-0044 | TSK-01783 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.15.2.1 | 1.10.15.2 | GA4 Property Setup | Setup new GA4 acct for Caledera House | GA4 Property Setup | Data/Analytics Engineer | Mid | 5 |  |  | 1.10.15.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11 | 1 | Post-Production |  |  |  |  | 222 | 223 | 50 | 1.10 |  | Advanced/T2_MediumVolume | 195 | 43290
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.1 | 1.11 | Content Licensing / Art Buying | Content Licensing / Art Buying |  |  |  | 2 | 223 | 4 | 1.11 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.1.1 | 1.11.1 | Rights/License Research | Content Licensing / Art Buying | Rights/License Research |  |  | 0 | 223 | 4 | 1.11.1 |  |  | 0 | 0
65 | DEL-0003 | TSK-00065 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.1.1.1 | 1.11.1.1 | Rights/License Research | Content Licensing / Art Buying | Rights/License Research | Producer | Mid | 1 |  |  | 1.11.1.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.1.2 | 1.11.1 | Usage Notes | Content Licensing / Art Buying | Usage Notes |  |  | 0 | 273 | 0 | 1.11.1.1.1 |  |  | 0 | 0
66 | DEL-0003 | TSK-00066 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.1.2.1 | 1.11.1.2 | Usage Notes | Content Licensing / Art Buying | Usage Notes | Account Manager | Mid | 1 |  |  | 1.11.1.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.2 | 1.11 | VO Recording Sessions | VO Recording Sessions |  |  |  | 6 | 227 | 5 | 1.11.1 |  |  | 195 | 1170
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.2.1 | 1.11.2 | Script Polish | VO Recording Sessions | Script Polish |  |  | 0 | 227 | 5 | 1.11.2 |  |  | 0 | 0
124 | DEL-0003 | TSK-00124 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.2.1.1 | 1.11.2.1 | Script Polish | VO Recording Sessions | Script Polish | Copywriter | Mid | 2 |  |  | 1.11.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.2.2 | 1.11.2 | VO Session | VO Recording Sessions | VO Session |  |  | 0 | 273 | 0 | 1.11.2.1.1 |  |  | 0 | 0
125 | DEL-0003 | TSK-00125 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.2.2.1 | 1.11.2.2 | VO Session | VO Recording Sessions | VO Session | Producer | Mid | 2 |  |  | 1.11.2.2 |  |  | 0 | 0
126 | DEL-0003 | TSK-00126 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.2.2.2 | 1.11.2.2 | VO Session | VO Recording Sessions | VO Session | Sound Designer | Mid | 2 |  |  | 1.11.2.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.3 | 1.11 | Editing | Editing |  |  |  | 20 | 232 | 6 | 1.11.2 |  |  | 195 | 3900
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.3.1 | 1.11.3 | Client Review & Revisions | Editing | Client Review & Revisions |  |  | 0 | 232 | 6 | 1.11.3 |  |  | 0 | 0
74 | DEL-0003 | TSK-00074 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.3.1.1 | 1.11.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.11.3.1 |  |  | 0 | 0
77 | DEL-0003 | TSK-00077 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.3.1.2 | 1.11.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.11.3.1.1 |  |  | 0 | 0
76 | DEL-0003 | TSK-00076 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.3.1.3 | 1.11.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.11.3.1.2 |  |  | 0 | 0
79 | DEL-0003 | TSK-00079 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.3.1.4 | 1.11.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Editor | Mid | 10 |  |  | 1.11.3.1.3 |  |  | 0 | 0
75 | DEL-0003 | TSK-00075 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.3.1.5 | 1.11.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Producer | Mid | 4 |  |  | 1.11.3.1.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.4 | 1.11 | Video Editing | Video Editing |  |  |  | 30 | 232 | 6 | 1.11.3 |  |  | 195 | 5850
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.4.1 | 1.11.4 | Client Review & Revisions | Video Editing | Client Review & Revisions |  |  | 0 | 232 | 6 | 1.11.4 |  |  | 0 | 0
127 | DEL-0003 | TSK-00127 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.4.1.1 | 1.11.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.11.4.1 |  |  | 0 | 0
131 | DEL-0003 | TSK-00131 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.4.1.2 | 1.11.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.11.4.1.1 |  |  | 0 | 0
129 | DEL-0003 | TSK-00129 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.4.1.3 | 1.11.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.11.4.1.2 |  |  | 0 | 0
130 | DEL-0003 | TSK-00130 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.4.1.4 | 1.11.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Editor | Mid | 20 |  |  | 1.11.4.1.3 |  |  | 0 | 0
128 | DEL-0003 | TSK-00128 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.4.1.5 | 1.11.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Producer | Mid | 4 |  |  | 1.11.4.1.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5 | 1.11 | Voice Over | Voice Over |  |  |  | 20 | 232 | 14 | 1.11.4 |  |  | 195 | 3900
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.1 | 1.11.5 | VO Edit | Voice Over | VO Edit |  |  | 0 | 232 | 6 | 1.11.5 |  |  | 0 | 0
140 | DEL-0003 | TSK-00140 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.1.1 | 1.11.5.1 | VO Edit | Voice Over | VO Edit | Editor | Mid | 10 |  |  | 1.11.5.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.2 | 1.11.5 | Mix | Voice Over | Mix |  |  | 0 | 253 | 3 | 1.11.5.1.1 |  |  | 0 | 0
139 | DEL-0003 | TSK-00139 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.2.1 | 1.11.5.2 | Mix | Voice Over | Mix | Sound Designer | Mid | 3 |  |  | 1.11.5.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.3 | 1.11.5 | Internal Review & Critique | Voice Over | Internal Review & Critique |  |  | 0 | 263 | 2 | 1.11.5.2.1 |  |  | 0 | 0
137 | DEL-0003 | TSK-00137 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.3.1 | 1.11.5.3 | Internal Review & Critique | Voice Over | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.11.5.3 |  |  | 0 | 0
138 | DEL-0003 | TSK-00138 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.3.2 | 1.11.5.3 | Internal Review & Critique | Voice Over | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.11.5.3.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.4 | 1.11.5 | Client Review & Revisions | Voice Over | Client Review & Revisions |  |  | 0 | 265 | 3 | 1.11.5.3.2 |  |  | 0 | 0
134 | DEL-0003 | TSK-00134 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.4.1 | 1.11.5.4 | Client Review & Revisions | Voice Over | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.11.5.4 |  |  | 0 | 0
135 | DEL-0003 | TSK-00135 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.4.2 | 1.11.5.4 | Client Review & Revisions | Voice Over | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.11.5.4.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.5 | 1.11.5 | Final Packaging | Voice Over | Final Packaging |  |  | 0 | 273 | 0 | 1.11.5.4.2 |  |  | 0 | 0
136 | DEL-0003 | TSK-00136 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.5.1 | 1.11.5.5 | Final Packaging | Voice Over | Final Packaging | Designer | Mid | 2 |  |  | 1.11.5.5 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.6 | 1.11 | Motion Design/VFX | Motion Design/VFX |  |  |  | 20 | 238 | 8 | 1.11.5 |  |  | 195 | 3900
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.6.1 | 1.11.6 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions |  |  | 0 | 238 | 8 | 1.11.6 |  |  | 0 | 0
90 | DEL-0003 | TSK-00090 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.6.1.1 | 1.11.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.11.6.1 |  |  | 0 | 0
94 | DEL-0003 | TSK-00094 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.6.1.2 | 1.11.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.11.6.1.1 |  |  | 0 | 0
92 | DEL-0003 | TSK-00092 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.6.1.3 | 1.11.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.11.6.1.2 |  |  | 0 | 0
96 | DEL-0003 | TSK-00096 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.6.1.4 | 1.11.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Editor | Mid | 6 |  |  | 1.11.6.1.3 |  |  | 0 | 0
93 | DEL-0003 | TSK-00093 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.6.1.5 | 1.11.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Motion Designer | Mid | 3 |  |  | 1.11.6.1.4 |  |  | 0 | 0
91 | DEL-0003 | TSK-00091 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.6.1.6 | 1.11.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Producer | Mid | 4 |  |  | 1.11.6.1.5 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.7 | 1.11 | Color Correction | Color Correction |  |  |  | 14 | 246 | 3 | 1.11.6 |  |  | 195 | 2730
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.7.1 | 1.11.7 | Client Review & Revisions | Color Correction | Client Review & Revisions |  |  | 0 | 246 | 3 | 1.11.7 |  |  | 0 | 0
53 | DEL-0003 | TSK-00053 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.7.1.1 | 1.11.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.11.7.1 |  |  | 0 | 0
55 | DEL-0003 | TSK-00055 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.7.1.2 | 1.11.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Colorist | Mid | 6 |  |  | 1.11.7.1.1 |  |  | 0 | 0
57 | DEL-0003 | TSK-00057 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.7.1.3 | 1.11.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.11.7.1.2 |  |  | 0 | 0
56 | DEL-0003 | TSK-00056 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.7.1.4 | 1.11.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.11.7.1.3 |  |  | 0 | 0
54 | DEL-0003 | TSK-00054 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.7.1.5 | 1.11.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.11.7.1.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.8 | 1.11 | Color Grading | Color Grading |  |  |  | 14 | 246 | 3 | 1.11.7 |  |  | 195 | 2730
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.8.1 | 1.11.8 | Client Review & Revisions | Color Grading | Client Review & Revisions |  |  | 0 | 246 | 3 | 1.11.8 |  |  | 0 | 0
59 | DEL-0003 | TSK-00059 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.8.1.1 | 1.11.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.11.8.1 |  |  | 0 | 0
61 | DEL-0003 | TSK-00061 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.8.1.2 | 1.11.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Colorist | Mid | 6 |  |  | 1.11.8.1.1 |  |  | 0 | 0
63 | DEL-0003 | TSK-00063 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.8.1.3 | 1.11.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.11.8.1.2 |  |  | 0 | 0
62 | DEL-0003 | TSK-00062 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.8.1.4 | 1.11.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.11.8.1.3 |  |  | 0 | 0
60 | DEL-0003 | TSK-00060 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.8.1.5 | 1.11.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.11.8.1.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9 | 1.11 | Final Retouched Stills Review | Final Retouched Stills Review |  |  |  | 12 | 249 | 9 | 1.11.8 |  |  | 195 | 2340
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9.1 | 1.11.9 | Retouch | Final Retouched Stills Review | Retouch |  |  | 0 | 249 | 4 | 1.11.9 |  |  | 0 | 0
89 | DEL-0003 | TSK-00089 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9.1.1 | 1.11.9.1 | Retouch | Final Retouched Stills Review | Retouch | Retoucher | Mid | 5 |  |  | 1.11.9.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9.2 | 1.11.9 | Internal Review & Critique | Final Retouched Stills Review | Internal Review & Critique |  |  | 0 | 263 | 2 | 1.11.9.1.1 |  |  | 0 | 0
87 | DEL-0003 | TSK-00087 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9.2.1 | 1.11.9.2 | Internal Review & Critique | Final Retouched Stills Review | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.11.9.2 |  |  | 0 | 0
88 | DEL-0003 | TSK-00088 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9.2.2 | 1.11.9.2 | Internal Review & Critique | Final Retouched Stills Review | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.11.9.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9.3 | 1.11.9 | Client Review & Revisions | Final Retouched Stills Review | Client Review & Revisions |  |  | 0 | 265 | 3 | 1.11.9.2.2 |  |  | 0 | 0
84 | DEL-0003 | TSK-00084 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9.3.1 | 1.11.9.3 | Client Review & Revisions | Final Retouched Stills Review | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.11.9.3 |  |  | 0 | 0
85 | DEL-0003 | TSK-00085 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9.3.2 | 1.11.9.3 | Client Review & Revisions | Final Retouched Stills Review | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.11.9.3.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9.4 | 1.11.9 | Final Packaging | Final Retouched Stills Review | Final Packaging |  |  | 0 | 273 | 0 | 1.11.9.3.2 |  |  | 0 | 0
86 | DEL-0003 | TSK-00086 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9.4.1 | 1.11.9.4 | Final Packaging | Final Retouched Stills Review | Final Packaging | Designer | Mid | 2 |  |  | 1.11.9.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10 | 1.11 | Retouching | Retouching |  |  |  | 12 | 249 | 9 | 1.11.9 |  |  | 195 | 2340
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10.1 | 1.11.10 | Retouch | Retouching | Retouch |  |  | 0 | 249 | 4 | 1.11.10 |  |  | 0 | 0
102 | DEL-0003 | TSK-00102 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10.1.1 | 1.11.10.1 | Retouch | Retouching | Retouch | Retoucher | Mid | 5 |  |  | 1.11.10.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10.2 | 1.11.10 | Internal Review & Critique | Retouching | Internal Review & Critique |  |  | 0 | 263 | 2 | 1.11.10.1.1 |  |  | 0 | 0
100 | DEL-0003 | TSK-00100 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10.2.1 | 1.11.10.2 | Internal Review & Critique | Retouching | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.11.10.2 |  |  | 0 | 0
101 | DEL-0003 | TSK-00101 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10.2.2 | 1.11.10.2 | Internal Review & Critique | Retouching | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.11.10.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10.3 | 1.11.10 | Client Review & Revisions | Retouching | Client Review & Revisions |  |  | 0 | 265 | 3 | 1.11.10.2.2 |  |  | 0 | 0
97 | DEL-0003 | TSK-00097 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10.3.1 | 1.11.10.3 | Client Review & Revisions | Retouching | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.11.10.3 |  |  | 0 | 0
98 | DEL-0003 | TSK-00098 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10.3.2 | 1.11.10.3 | Client Review & Revisions | Retouching | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.11.10.3.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10.4 | 1.11.10 | Final Packaging | Retouching | Final Packaging |  |  | 0 | 273 | 0 | 1.11.10.3.2 |  |  | 0 | 0
99 | DEL-0003 | TSK-00099 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10.4.1 | 1.11.10.4 | Final Packaging | Retouching | Final Packaging | Designer | Mid | 2 |  |  | 1.11.10.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.11 | 1.11 | Sound Mix | Sound Mix |  |  |  | 10 | 253 | 3 | 1.11.10 |  |  | 195 | 1950
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.11.1 | 1.11.11 | Client Review & Revisions | Sound Mix | Client Review & Revisions |  |  | 0 | 253 | 3 | 1.11.11 |  |  | 0 | 0
107 | DEL-0003 | TSK-00107 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.11.1.1 | 1.11.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.11.11.1 |  |  | 0 | 0
110 | DEL-0003 | TSK-00110 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.11.1.2 | 1.11.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.11.11.1.1 |  |  | 0 | 0
109 | DEL-0003 | TSK-00109 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.11.1.3 | 1.11.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.11.11.1.2 |  |  | 0 | 0
108 | DEL-0003 | TSK-00108 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.11.1.4 | 1.11.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.11.11.1.3 |  |  | 0 | 0
112 | DEL-0003 | TSK-00112 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.11.1.5 | 1.11.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Sound Designer | Mid | 2 |  |  | 1.11.11.1.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.12 | 1.11 | Sound Sourcing | Sound Sourcing |  |  |  | 3 | 253 | 3 | 1.11.11 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.12.1 | 1.11.12 | Music Search & License | Sound Sourcing | Music Search & License |  |  | 0 | 253 | 3 | 1.11.12 |  |  | 0 | 0
113 | DEL-0003 | TSK-00113 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.12.1.1 | 1.11.12.1 | Music Search & License | Sound Sourcing | Music Search & License | Producer | Mid | 1 |  |  | 1.11.12.1 |  |  | 0 | 0
114 | DEL-0003 | TSK-00114 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.12.1.2 | 1.11.12.1 | Music Search & License | Sound Sourcing | Music Search & License | Sound Designer | Mid | 2 |  |  | 1.11.12.1.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.13 | 1.11 | Final File Delivery | Final File Delivery |  |  |  | 8 | 256 | 3 | 1.11.12 |  |  | 195 | 1560
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.13.1 | 1.11.13 | QA (Tech & Content) | Final File Delivery | QA (Tech & Content) |  |  | 0 | 256 | 3 | 1.11.13 |  |  | 0 | 0
83 | DEL-0003 | TSK-00083 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.13.1.1 | 1.11.13.1 | QA (Tech & Content) | Final File Delivery | QA (Tech & Content) | QA Specialist | Mid | 3 |  |  | 1.11.13.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.13.2 | 1.11.13 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload |  |  | 0 | 273 | 0 | 1.11.13.1.1 |  |  | 0 | 0
80 | DEL-0003 | TSK-00080 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.13.2.1 | 1.11.13.2 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload | Media Manager / DIT | Mid | 2 |  |  | 1.11.13.2 |  |  | 0 | 0
81 | DEL-0003 | TSK-00081 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.13.2.2 | 1.11.13.2 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload | Producer | Mid | 2 |  |  | 1.11.13.2.1 |  |  | 0 | 0
82 | DEL-0003 | TSK-00082 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.13.2.3 | 1.11.13.2 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload | Project Manager | Mid | 1 |  |  | 1.11.13.2.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14 | 1.11 | True-ups (for vendor costs) | True-ups (for vendor costs) |  |  |  | 11 | 259 | 9 | 1.11.13 |  |  | 195 | 2145
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.1 | 1.11.14 | Change Orders & Tracking | True-ups (for vendor costs) | Change Orders & Tracking |  |  | 0 | 259 | 4 | 1.11.14 |  |  | 0 | 0
116 | DEL-0003 | TSK-00116 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.1.1 | 1.11.14.1 | Change Orders & Tracking | True-ups (for vendor costs) | Change Orders & Tracking | Project Manager | Mid | 1 |  |  | 1.11.14.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.2 | 1.11.14 | Internal Review & Critique | True-ups (for vendor costs) | Internal Review & Critique |  |  | 0 | 263 | 2 | 1.11.14.1.1 |  |  | 0 | 0
120 | DEL-0003 | TSK-00120 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.2.1 | 1.11.14.2 | Internal Review & Critique | True-ups (for vendor costs) | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.11.14.2 |  |  | 0 | 0
121 | DEL-0003 | TSK-00121 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.2.2 | 1.11.14.2 | Internal Review & Critique | True-ups (for vendor costs) | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.11.14.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.3 | 1.11.14 | Client Review & Revisions | True-ups (for vendor costs) | Client Review & Revisions |  |  | 0 | 265 | 3 | 1.11.14.2.2 |  |  | 0 | 0
117 | DEL-0003 | TSK-00117 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.3.1 | 1.11.14.3 | Client Review & Revisions | True-ups (for vendor costs) | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.11.14.3 |  |  | 0 | 0
118 | DEL-0003 | TSK-00118 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.3.2 | 1.11.14.3 | Client Review & Revisions | True-ups (for vendor costs) | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.11.14.3.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.4 | 1.11.14 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation |  |  | 0 | 273 | 0 | 1.11.14.3.2 |  |  | 0 | 0
122 | DEL-0003 | TSK-00122 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.4.1 | 1.11.14.4 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation | Account Manager | Mid | 2 |  |  | 1.11.14.4 |  |  | 0 | 0
119 | DEL-0003 | TSK-00119 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.4.2 | 1.11.14.4 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation | Designer | Mid | 2 |  |  | 1.11.14.4.1 |  |  | 0 | 0
123 | DEL-0003 | TSK-00123 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.4.3 | 1.11.14.4 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation | Producer | Mid | 1 |  |  | 1.11.14.4.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.15 | 1.11 | Cutdowns | Cutdowns |  |  |  | 13 | 263 | 5 | 1.11.14 |  |  | 195 | 2535
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.15.1 | 1.11.15 | Internal Review & Critique | Cutdowns | Internal Review & Critique |  |  | 0 | 263 | 2 | 1.11.15 |  |  | 0 | 0
71 | DEL-0003 | TSK-00071 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.15.1.1 | 1.11.15.1 | Internal Review & Critique | Cutdowns | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.11.15.1 |  |  | 0 | 0
72 | DEL-0003 | TSK-00072 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.15.1.2 | 1.11.15.1 | Internal Review & Critique | Cutdowns | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.11.15.1.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.15.2 | 1.11.15 | Client Review & Revisions | Cutdowns | Client Review & Revisions |  |  | 0 | 265 | 3 | 1.11.15.1.2 |  |  | 0 | 0
67 | DEL-0003 | TSK-00067 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.15.2.1 | 1.11.15.2 | Client Review & Revisions | Cutdowns | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.11.15.2 |  |  | 0 | 0
68 | DEL-0003 | TSK-00068 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.15.2.2 | 1.11.15.2 | Client Review & Revisions | Cutdowns | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.11.15.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.15.3 | 1.11.15 | Cutdowns (2-3) | Cutdowns | Cutdowns (2-3) |  |  | 0 | 273 | 0 | 1.11.15.2.2 |  |  | 0 | 0
70 | DEL-0003 | TSK-00070 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.15.3.1 | 1.11.15.3 | Cutdowns (2-3) | Cutdowns | Cutdowns (2-3) | Designer | Mid | 2 |  |  | 1.11.15.3 |  |  | 0 | 0
69 | DEL-0003 | TSK-00069 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.15.3.2 | 1.11.15.3 | Cutdowns (2-3) | Cutdowns | Cutdowns (2-3) | Editor | Mid | 6 |  |  | 1.11.15.3.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.16 | 1.11 | Client Review | Client Review |  |  |  | 5 | 265 | 3 | 1.11.15 |  |  | 195 | 975
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.16.1 | 1.11.16 | Client Review Coordination | Client Review | Client Review Coordination |  |  | 0 | 265 | 3 | 1.11.16 |  |  | 0 | 0
50 | DEL-0003 | TSK-00050 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.16.1.1 | 1.11.16.1 | Client Review Coordination | Client Review | Client Review Coordination | Account Manager | Mid | 2 |  |  | 1.11.16.1 |  |  | 0 | 0
51 | DEL-0003 | TSK-00051 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.16.1.2 | 1.11.16.1 | Client Review Coordination | Client Review | Client Review Coordination | Producer | Mid | 2 |  |  | 1.11.16.1.1 |  |  | 0 | 0
52 | DEL-0003 | TSK-00052 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.16.1.3 | 1.11.16.1 | Client Review Coordination | Client Review | Client Review Coordination | Project Manager | Mid | 1 |  |  | 1.11.16.1.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.17 | 1.11 | Review & Sign-Off | Review & Sign-Off |  |  |  | 4 | 265 | 5 | 1.11.16 |  |  | 195 | 780
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.17.1 | 1.11.17 | Client Review Coordination | Review & Sign-Off | Client Review Coordination |  |  | 0 | 265 | 3 | 1.11.17 |  |  | 0 | 0
103 | DEL-0003 | TSK-00103 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.17.1.1 | 1.11.17.1 | Client Review Coordination | Review & Sign-Off | Client Review Coordination | Account Manager | Mid | 2 |  |  | 1.11.17.1 |  |  | 0 | 0
104 | DEL-0003 | TSK-00104 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.17.1.2 | 1.11.17.1 | Client Review Coordination | Review & Sign-Off | Client Review Coordination | Producer | Mid | 1 |  |  | 1.11.17.1.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.17.2 | 1.11.17 | Notes Triage | Review & Sign-Off | Notes Triage |  |  | 0 | 271 | 2 | 1.11.17.1.2 |  |  | 0 | 0
105 | DEL-0003 | TSK-00105 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.17.2.1 | 1.11.17.2 | Notes Triage | Review & Sign-Off | Notes Triage | Project Manager | Mid | 1 |  |  | 1.11.17.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.18 | 1.11 | Asset Library | Asset Library |  |  |  | 2 | 268 | 3 | 1.11.17 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.18.1 | 1.11.18 | Post Support | Asset Library | Post Support |  |  | 0 | 268 | 3 | 1.11.18 |  |  | 0 | 0
48 | DEL-0003 | TSK-00048 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.18.1.1 | 1.11.18.1 | Post Support | Asset Library | Post Support | Editor | Mid | 2 |  |  | 1.11.18.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.19 | 1.11 | Capture Library | Capture Library |  |  |  | 2 | 268 | 3 | 1.11.18 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.19.1 | 1.11.19 | Post Support | Capture Library | Post Support |  |  | 0 | 268 | 3 | 1.11.19 |  |  | 0 | 0
49 | DEL-0003 | TSK-00049 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.19.1.1 | 1.11.19.1 | Post Support | Capture Library | Post Support | Editor | Mid | 2 |  |  | 1.11.19.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.20 | 1.11 | Selects Deck | Selects Deck |  |  |  | 2 | 268 | 3 | 1.11.19 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.20.1 | 1.11.20 | Post Support | Selects Deck | Post Support |  |  | 0 | 268 | 3 | 1.11.20 |  |  | 0 | 0
106 | DEL-0003 | TSK-00106 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.20.1.1 | 1.11.20.1 | Post Support | Selects Deck | Post Support | Editor | Mid | 2 |  |  | 1.11.20.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.21 | 1.11 | Delivery | Delivery |  |  |  | 6 | 273 | 0 | 1.11.20 |  |  | 195 | 1170
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.21.1 | 1.11.21 | Post Support | Delivery | Post Support |  |  | 0 | 273 | 0 | 1.11.21 |  |  | 0 | 0
73 | DEL-0003 | TSK-00073 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.21.1.1 | 1.11.21.1 | Post Support | Delivery | Post Support | Editor | Mid | 6 |  |  | 1.11.21.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.22 | 1.11 | Stills/Footage Selection | Stills/Footage Selection |  |  |  | 6 | 273 | 0 | 1.11.21 |  |  | 195 | 1170
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.22.1 | 1.11.22 | Post Support | Stills/Footage Selection | Post Support |  |  | 0 | 273 | 0 | 1.11.22 |  |  | 0 | 0
115 | DEL-0003 | TSK-00115 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.22.1.1 | 1.11.22.1 | Post Support | Stills/Footage Selection | Post Support | Editor | Mid | 6 |  |  | 1.11.22.1 |  |  | 0 | 0

## Scenario B
Row_ID | Deliverable_Code | Task_Code | Service_Department | Deliverable | Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes | Rate_USD | Price_USD
[5 empty] | Casa-Dragones-Digital-MKT-RFP | 1 |  | Casa-Dragones-Digital-MKT-RFP | Project |  |  |  | 0 | 0 |  |  |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1 | 1 | Campaign Strategy |  |  |  |  | 109 | 0 | 15 |  |  | Advanced/T2_MediumVolume | 195 | 21255
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1 | 1.1 | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) |  |  |  | 17 | 0 | 11 | 1.1 |  |  | 195 | 3315
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1 | 1.1.1 | Channel Roles & Cadence | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Channel Roles & Cadence |  |  | 0 | 0 | 6 | 1.1.1 |  |  | 0 | 0
714 | DEL-0011 | TSK-00705 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.1 | 1.1.1.1 | Channel Roles & Cadence | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Channel Roles & Cadence | Creative Director | Lead/Director | 2 |  |  | 1.1.1.1 |  |  | 0 | 0
715 | DEL-0011 | TSK-00706 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.2 | 1.1.1.1 | Channel Roles & Cadence | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Channel Roles & Cadence | Designer | Mid | 9 |  |  | 1.1.1.1.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2 | 1.1.1 | Internal Review & Critique | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.1.1.2 |  |  | 0 | 0
720 | DEL-0011 | TSK-00711 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.1 | 1.1.1.2 | Internal Review & Critique | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.1.2 |  |  | 0 | 0
721 | DEL-0011 | TSK-00712 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.2 | 1.1.1.2 | Internal Review & Critique | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.1.2.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3 | 1.1.1 | Client Review & Revisions | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.1.2.2 |  |  | 0 | 0
716 | DEL-0011 | TSK-00707 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.1 | 1.1.1.3 | Client Review & Revisions | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.1.3 |  |  | 0 | 0
717 | DEL-0011 | TSK-00708 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.2 | 1.1.1.3 | Client Review & Revisions | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.1.3.1 |  |  | 0 | 0
718 | DEL-0011 | TSK-00709 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.3 | 1.1.1.3 | Client Review & Revisions | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.1.3.2 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2 | 1.1 | 10k Ft View | 10k Ft View |  |  |  | 15 | 6 | 9 | 1.1.1 |  |  | 195 | 2925
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.1 | 1.1.2 | Visual Summary | 10k Ft View | Visual Summary |  |  | 0 | 6 | 4 | 1.1.2 |  |  | 0 | 0
705 | DEL-0011 | TSK-00696 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.1.1 | 1.1.2.1 | Visual Summary | 10k Ft View | Visual Summary | Designer | Mid | 2 |  |  | 1.1.2.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.2 | 1.1.2 | Internal Review & Critique | 10k Ft View | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.2.1.1 |  |  | 0 | 0
701 | DEL-0011 | TSK-00692 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.2.1 | 1.1.2.2 | Internal Review & Critique | 10k Ft View | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.2.2 |  |  | 0 | 0
702 | DEL-0011 | TSK-00693 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.2.2 | 1.1.2.2 | Internal Review & Critique | 10k Ft View | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.2.2.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.3 | 1.1.2 | Client Review & Revisions | 10k Ft View | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.2.2.2 |  |  | 0 | 0
696 | DEL-0011 | TSK-00687 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.3.1 | 1.1.2.3 | Client Review & Revisions | 10k Ft View | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.2.3 |  |  | 0 | 0
697 | DEL-0011 | TSK-00688 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.3.2 | 1.1.2.3 | Client Review & Revisions | 10k Ft View | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.1.2.3.1 |  |  | 0 | 0
698 | DEL-0011 | TSK-00689 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.3.3 | 1.1.2.3 | Client Review & Revisions | 10k Ft View | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.2.3.2 |  |  | 0 | 0
699 | DEL-0011 | TSK-00690 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.3.4 | 1.1.2.3 | Client Review & Revisions | 10k Ft View | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.2.3.3 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.4 | 1.1.2 | Narrative Overview | 10k Ft View | Narrative Overview |  |  | 0 | 15 | 0 | 1.1.2.3.4 |  |  | 0 | 0
703 | DEL-0011 | TSK-00694 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.4.1 | 1.1.2.4 | Narrative Overview | 10k Ft View | Narrative Overview | Copywriter | Mid | 2 |  |  | 1.1.2.4 |  |  | 0 | 0
704 | DEL-0011 | TSK-00695 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.4.2 | 1.1.2.4 | Narrative Overview | 10k Ft View | Narrative Overview | Creative Director | Lead/Director | 2 |  |  | 1.1.2.4.1 |  |  | 0 | 0
700 | DEL-0011 | TSK-00691 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.4.3 | 1.1.2.4 | Narrative Overview | 10k Ft View | Narrative Overview | Designer | Mid | 2 |  |  | 1.1.2.4.2 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3 | 1.1 | Image Usage Guidelines | Image Usage Guidelines |  |  |  | 27 | 10 | 5 | 1.1.2 |  |  | 195 | 5265
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.1 | 1.1.3 | Internal Review & Critique | Image Usage Guidelines | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.3 |  |  | 0 | 0
712 | DEL-0011 | TSK-00703 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.1.1 | 1.1.3.1 | Internal Review & Critique | Image Usage Guidelines | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.3.1 |  |  | 0 | 0
713 | DEL-0011 | TSK-00704 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.1.2 | 1.1.3.1 | Internal Review & Critique | Image Usage Guidelines | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.3.1.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.2 | 1.1.3 | Client Review & Revisions | Image Usage Guidelines | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.3.1.2 |  |  | 0 | 0
706 | DEL-0011 | TSK-00697 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.2.1 | 1.1.3.2 | Client Review & Revisions | Image Usage Guidelines | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.3.2 |  |  | 0 | 0
707 | DEL-0011 | TSK-00698 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.2.2 | 1.1.3.2 | Client Review & Revisions | Image Usage Guidelines | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.3.2.1 |  |  | 0 | 0
708 | DEL-0011 | TSK-00699 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.2.3 | 1.1.3.2 | Client Review & Revisions | Image Usage Guidelines | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.3.2.2 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.3 | 1.1.3 | Examples | Image Usage Guidelines | Examples |  |  | 0 | 15 | 0 | 1.1.3.2.3 |  |  | 0 | 0
711 | DEL-0011 | TSK-00702 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.3.1 | 1.1.3.3 | Examples | Image Usage Guidelines | Examples | Art Director | Lead/Director | 1 |  |  | 1.1.3.3 |  |  | 0 | 0
709 | DEL-0011 | TSK-00700 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.3.2 | 1.1.3.3 | Examples | Image Usage Guidelines | Examples | Designer | Mid | 20 |  |  | 1.1.3.3.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4 | 1.1 | Media Assets | Media Assets |  |  |  | 12 | 10 | 5 | 1.1.3 |  |  | 195 | 2340
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.1 | 1.1.4 | Internal Review & Critique | Media Assets | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.4 |  |  | 0 | 0
729 | DEL-0011 | TSK-00720 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.1.1 | 1.1.4.1 | Internal Review & Critique | Media Assets | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.4.1 |  |  | 0 | 0
730 | DEL-0011 | TSK-00721 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.1.2 | 1.1.4.1 | Internal Review & Critique | Media Assets | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.4.1.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.2 | 1.1.4 | Client Review & Revisions | Media Assets | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.4.1.2 |  |  | 0 | 0
725 | DEL-0011 | TSK-00716 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.2.1 | 1.1.4.2 | Client Review & Revisions | Media Assets | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.4.2 |  |  | 0 | 0
726 | DEL-0011 | TSK-00717 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.2.2 | 1.1.4.2 | Client Review & Revisions | Media Assets | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.4.2.1 |  |  | 0 | 0
727 | DEL-0011 | TSK-00718 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.2.3 | 1.1.4.2 | Client Review & Revisions | Media Assets | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.4.2.2 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.3 | 1.1.4 | Asset Matrix | Media Assets | Asset Matrix |  |  | 0 | 15 | 0 | 1.1.4.2.3 |  |  | 0 | 0
723 | DEL-0011 | TSK-00714 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.3.1 | 1.1.4.3 | Asset Matrix | Media Assets | Asset Matrix | Designer | Mid | 5 |  |  | 1.1.4.3 |  |  | 0 | 0
724 | DEL-0011 | TSK-00715 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.3.2 | 1.1.4.3 | Asset Matrix | Media Assets | Asset Matrix | Project Manager | Mid | 1 |  |  | 1.1.4.3.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5 | 1.1 | Photo / Video Direction | Photo / Video Direction |  |  |  | 14 | 10 | 5 | 1.1.4 |  |  | 195 | 2730
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.1 | 1.1.5 | Internal Review & Critique | Photo / Video Direction | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.5 |  |  | 0 | 0
737 | DEL-0011 | TSK-00728 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.1.1 | 1.1.5.1 | Internal Review & Critique | Photo / Video Direction | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.5.1 |  |  | 0 | 0
738 | DEL-0011 | TSK-00729 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.1.2 | 1.1.5.1 | Internal Review & Critique | Photo / Video Direction | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.5.1.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.2 | 1.1.5 | Client Review & Revisions | Photo / Video Direction | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.5.1.2 |  |  | 0 | 0
731 | DEL-0011 | TSK-00722 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.2.1 | 1.1.5.2 | Client Review & Revisions | Photo / Video Direction | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.5.2 |  |  | 0 | 0
732 | DEL-0011 | TSK-00723 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.2.2 | 1.1.5.2 | Client Review & Revisions | Photo / Video Direction | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.5.2.1 |  |  | 0 | 0
733 | DEL-0011 | TSK-00724 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.2.3 | 1.1.5.2 | Client Review & Revisions | Photo / Video Direction | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.5.2.2 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.3 | 1.1.5 | Direction Notes | Photo / Video Direction | Direction Notes |  |  | 0 | 15 | 0 | 1.1.5.2.3 |  |  | 0 | 0
734 | DEL-0011 | TSK-00725 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.3.1 | 1.1.5.3 | Direction Notes | Photo / Video Direction | Direction Notes | Art Director | Lead/Director | 1 |  |  | 1.1.5.3 |  |  | 0 | 0
735 | DEL-0011 | TSK-00726 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.3.2 | 1.1.5.3 | Direction Notes | Photo / Video Direction | Direction Notes | Creative Director | Lead/Director | 2 |  |  | 1.1.5.3.1 |  |  | 0 | 0
736 | DEL-0011 | TSK-00727 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.3.3 | 1.1.5.3 | Direction Notes | Photo / Video Direction | Direction Notes | Designer | Mid | 5 |  |  | 1.1.5.3.2 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6 | 1.1 | Rollout | Rollout |  |  |  | 14 | 10 | 5 | 1.1.5 |  |  | 195 | 2730
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.1 | 1.1.6 | Internal Review & Critique | Rollout | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.6 |  |  | 0 | 0
744 | DEL-0011 | TSK-00735 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.1.1 | 1.1.6.1 | Internal Review & Critique | Rollout | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.6.1 |  |  | 0 | 0
745 | DEL-0011 | TSK-00736 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.1.2 | 1.1.6.1 | Internal Review & Critique | Rollout | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.6.1.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.2 | 1.1.6 | Client Review & Revisions | Rollout | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.6.1.2 |  |  | 0 | 0
740 | DEL-0011 | TSK-00731 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.2.1 | 1.1.6.2 | Client Review & Revisions | Rollout | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.6.2 |  |  | 0 | 0
741 | DEL-0011 | TSK-00732 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.2.2 | 1.1.6.2 | Client Review & Revisions | Rollout | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.6.2.1 |  |  | 0 | 0
742 | DEL-0011 | TSK-00733 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.2.3 | 1.1.6.2 | Client Review & Revisions | Rollout | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.6.2.2 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.3 | 1.1.6 | Phasing & Milestones | Rollout | Phasing & Milestones |  |  | 0 | 15 | 0 | 1.1.6.2.3 |  |  | 0 | 0
746 | DEL-0011 | TSK-00737 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.3.1 | 1.1.6.3 | Phasing & Milestones | Rollout | Phasing & Milestones | Creative Director | Lead/Director | 2 |  |  | 1.1.6.3 |  |  | 0 | 0
743 | DEL-0011 | TSK-00734 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.3.2 | 1.1.6.3 | Phasing & Milestones | Rollout | Phasing & Milestones | Designer | Mid | 5 |  |  | 1.1.6.3.1 |  |  | 0 | 0
747 | DEL-0011 | TSK-00738 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.3.3 | 1.1.6.3 | Phasing & Milestones | Rollout | Phasing & Milestones | Project Manager | Mid | 1 |  |  | 1.1.6.3.2 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7 | 1.1 | Use Cases | Use Cases |  |  |  | 10 | 10 | 5 | 1.1.6 |  |  | 195 | 1950
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.1 | 1.1.7 | Internal Review & Critique | Use Cases | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.7 |  |  | 0 | 0
753 | DEL-0011 | TSK-00744 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.1.1 | 1.1.7.1 | Internal Review & Critique | Use Cases | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.7.1 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.2 | 1.1.7 | Client Review & Revisions | Use Cases | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.7.1.1 |  |  | 0 | 0
749 | DEL-0011 | TSK-00740 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.2.1 | 1.1.7.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.7.2 |  |  | 0 | 0
750 | DEL-0011 | TSK-00741 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.2.2 | 1.1.7.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.7.2.1 |  |  | 0 | 0
751 | DEL-0011 | TSK-00742 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.2.3 | 1.1.7.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.7.2.2 |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.3 | 1.1.7 | Final Packaging | Use Cases | Final Packaging |  |  | 0 | 15 | 0 | 1.1.7.2.3 |  |  | 0 | 0
752 | DEL-0011 | TSK-00743 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.3.1 | 1.1.7.3 | Final Packaging | Use Cases | Final Packaging | Designer | Mid | 5 |  |  | 1.1.7.3 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2 | 1 | Creative Strategy / Campaign Plan Deck |  |  |  |  | 582 | 15 | 28 | 1.1 |  | Advanced/T2_MediumVolume | 195 | 113490
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1 | 1.2 | Activation Ideas | Activation Ideas |  |  |  | 40 | 15 | 11 | 1.2 |  |  | 195 | 7800
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1 | 1.2.1 | Idea Write-Ups | Activation Ideas | Idea Write-Ups |  |  | 0 | 15 | 6 | 1.2.1 |  |  | 0 | 0
1475 | DEL-0036 | TSK-01466 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.1 | 1.2.1.1 | Idea Write-Ups | Activation Ideas | Idea Write-Ups | Copywriter | Mid | 4 |  |  | 1.2.1.1 |  |  | 0 | 0
1477 | DEL-0036 | TSK-01468 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.2 | 1.2.1.1 | Idea Write-Ups | Activation Ideas | Idea Write-Ups | Creative Director | Lead/Director | 3 |  |  | 1.2.1.1.1 |  |  | 0 | 0
1474 | DEL-0036 | TSK-01465 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.3 | 1.2.1.1 | Idea Write-Ups | Activation Ideas | Idea Write-Ups | Designer | Mid | 16 |  |  | 1.2.1.1.2 |  |  | 0 | 0
1476 | DEL-0036 | TSK-01467 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.4 | 1.2.1.1 | Idea Write-Ups | Activation Ideas | Idea Write-Ups | Strategist | Mid | 12 |  |  | 1.2.1.1.3 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.2 | 1.2.1 | Internal Review & Critique | Activation Ideas | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.1.1.4 |  |  | 0 | 0
1479 | DEL-0036 | TSK-01470 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.2.1 | 1.2.1.2 | Internal Review & Critique | Activation Ideas | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.1.2 |  |  | 0 | 0
1480 | DEL-0036 | TSK-01471 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.2.2 | 1.2.1.2 | Internal Review & Critique | Activation Ideas | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.1.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3 | 1.2.1 | Client Review & Revisions | Activation Ideas | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.1.2.2 |  |  | 0 | 0
1471 | DEL-0036 | TSK-01462 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3.1 | 1.2.1.3 | Client Review & Revisions | Activation Ideas | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.1.3 |  |  | 0 | 0
1472 | DEL-0036 | TSK-01463 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3.2 | 1.2.1.3 | Client Review & Revisions | Activation Ideas | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.1.3.1 |  |  | 0 | 0
1473 | DEL-0036 | TSK-01464 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3.3 | 1.2.1.3 | Client Review & Revisions | Activation Ideas | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.1.3.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2 | 1.2 | Art Direction | Art Direction |  |  |  | 29 | 15 | 11 | 1.2.1 |  |  | 195 | 5655
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2.1 | 1.2.2 | Moodboards & References | Art Direction | Moodboards & References |  |  | 0 | 15 | 6 | 1.2.2 |  |  | 0 | 0
1487 | DEL-0036 | TSK-01478 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2.1.1 | 1.2.2.1 | Moodboards & References | Art Direction | Moodboards & References | Creative Director | Lead/Director | 3 |  |  | 1.2.2.1 |  |  | 0 | 0
1484 | DEL-0036 | TSK-01475 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2.1.2 | 1.2.2.1 | Moodboards & References | Art Direction | Moodboards & References | Designer | Mid | 16 |  |  | 1.2.2.1.1 |  |  | 0 | 0
1489 | DEL-0036 | TSK-01480 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2.1.3 | 1.2.2.1 | Moodboards & References | Art Direction | Moodboards & References | Strategist | Mid | 6 |  |  | 1.2.2.1.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2.2 | 1.2.2 | Internal Review & Critique | Art Direction | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.2.1.3 |  |  | 0 | 0
1485 | DEL-0036 | TSK-01476 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2.2.1 | 1.2.2.2 | Internal Review & Critique | Art Direction | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.2.2 |  |  | 0 | 0
1486 | DEL-0036 | TSK-01477 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2.2.2 | 1.2.2.2 | Internal Review & Critique | Art Direction | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.2.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2.3 | 1.2.2 | Client Review & Revisions | Art Direction | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.2.2.2 |  |  | 0 | 0
1482 | DEL-0036 | TSK-01473 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2.3.1 | 1.2.2.3 | Client Review & Revisions | Art Direction | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.2.3 |  |  | 0 | 0
1483 | DEL-0036 | TSK-01474 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.2.3.2 | 1.2.2.3 | Client Review & Revisions | Art Direction | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.2.3.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.3 | 1.2 | Brand Approach for Campaign Period | Brand Approach for Campaign Period |  |  |  | 32 | 15 | 11 | 1.2.2 |  |  | 195 | 6240
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.3.1 | 1.2.3 | Approach Outline | Brand Approach for Campaign Period | Approach Outline |  |  | 0 | 15 | 6 | 1.2.3 |  |  | 0 | 0
1494 | DEL-0036 | TSK-01485 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.3.1.1 | 1.2.3.1 | Approach Outline | Brand Approach for Campaign Period | Approach Outline | Designer | Mid | 16 |  |  | 1.2.3.1 |  |  | 0 | 0
1490 | DEL-0036 | TSK-01481 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.3.1.2 | 1.2.3.1 | Approach Outline | Brand Approach for Campaign Period | Approach Outline | Strategist | Mid | 12 |  |  | 1.2.3.1.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.3.2 | 1.2.3 | Internal Review & Critique | Brand Approach for Campaign Period | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.3.1.2 |  |  | 0 | 0
1495 | DEL-0036 | TSK-01486 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.3.2.1 | 1.2.3.2 | Internal Review & Critique | Brand Approach for Campaign Period | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.3.2 |  |  | 0 | 0
1496 | DEL-0036 | TSK-01487 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.3.2.2 | 1.2.3.2 | Internal Review & Critique | Brand Approach for Campaign Period | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.3.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.3.3 | 1.2.3 | Client Review & Revisions | Brand Approach for Campaign Period | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.3.2.2 |  |  | 0 | 0
1491 | DEL-0036 | TSK-01482 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.3.3.1 | 1.2.3.3 | Client Review & Revisions | Brand Approach for Campaign Period | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.3.3 |  |  | 0 | 0
1492 | DEL-0036 | TSK-01483 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.3.3.2 | 1.2.3.3 | Client Review & Revisions | Brand Approach for Campaign Period | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.3.3.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4 | 1.2 | Campaign Roll-Out/Launch Road Map | Campaign Roll-Out/Launch Road Map |  |  |  | 30 | 15 | 11 | 1.2.3 |  |  | 195 | 5850
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4.1 | 1.2.4 | Phasing & Milestones | Campaign Roll-Out/Launch Road Map | Phasing & Milestones |  |  | 0 | 15 | 6 | 1.2.4 |  |  | 0 | 0
1501 | DEL-0036 | TSK-01492 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4.1.1 | 1.2.4.1 | Phasing & Milestones | Campaign Roll-Out/Launch Road Map | Phasing & Milestones | Designer | Mid | 16 |  |  | 1.2.4.1 |  |  | 0 | 0
1500 | DEL-0036 | TSK-01491 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4.1.2 | 1.2.4.1 | Phasing & Milestones | Campaign Roll-Out/Launch Road Map | Phasing & Milestones | Project Manager | Mid | 4 |  |  | 1.2.4.1.1 |  |  | 0 | 0
1505 | DEL-0036 | TSK-01496 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4.1.3 | 1.2.4.1 | Phasing & Milestones | Campaign Roll-Out/Launch Road Map | Phasing & Milestones | Strategist | Mid | 6 |  |  | 1.2.4.1.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4.2 | 1.2.4 | Internal Review & Critique | Campaign Roll-Out/Launch Road Map | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.4.1.3 |  |  | 0 | 0
1502 | DEL-0036 | TSK-01493 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4.2.1 | 1.2.4.2 | Internal Review & Critique | Campaign Roll-Out/Launch Road Map | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.4.2 |  |  | 0 | 0
1503 | DEL-0036 | TSK-01494 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4.2.2 | 1.2.4.2 | Internal Review & Critique | Campaign Roll-Out/Launch Road Map | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.4.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4.3 | 1.2.4 | Client Review & Revisions | Campaign Roll-Out/Launch Road Map | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.4.2.2 |  |  | 0 | 0
1498 | DEL-0036 | TSK-01489 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4.3.1 | 1.2.4.3 | Client Review & Revisions | Campaign Roll-Out/Launch Road Map | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.4.3 |  |  | 0 | 0
1499 | DEL-0036 | TSK-01490 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.4.3.2 | 1.2.4.3 | Client Review & Revisions | Campaign Roll-Out/Launch Road Map | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.4.3.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5 | 1.2 | Content Plan | Content Plan |  |  |  | 37 | 15 | 11 | 1.2.4 |  |  | 195 | 7215
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.1 | 1.2.5 | Calendar Draft | Content Plan | Calendar Draft |  |  | 0 | 15 | 6 | 1.2.5 |  |  | 0 | 0
1507 | DEL-0036 | TSK-01498 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.1.1 | 1.2.5.1 | Calendar Draft | Content Plan | Calendar Draft | Copywriter | Mid | 8 |  |  | 1.2.5.1 |  |  | 0 | 0
1513 | DEL-0036 | TSK-01504 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.1.2 | 1.2.5.1 | Calendar Draft | Content Plan | Calendar Draft | Designer | Mid | 16 |  |  | 1.2.5.1.1 |  |  | 0 | 0
1508 | DEL-0036 | TSK-01499 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.1.3 | 1.2.5.1 | Calendar Draft | Content Plan | Calendar Draft | Project Manager | Mid | 2 |  |  | 1.2.5.1.2 |  |  | 0 | 0
1517 | DEL-0036 | TSK-01508 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.1.4 | 1.2.5.1 | Calendar Draft | Content Plan | Calendar Draft | Strategist | Mid | 6 |  |  | 1.2.5.1.3 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.2 | 1.2.5 | Internal Review & Critique | Content Plan | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.5.1.4 |  |  | 0 | 0
1515 | DEL-0036 | TSK-01506 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.2.1 | 1.2.5.2 | Internal Review & Critique | Content Plan | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.5.2 |  |  | 0 | 0
1516 | DEL-0036 | TSK-01507 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.2.2 | 1.2.5.2 | Internal Review & Critique | Content Plan | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.5.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.3 | 1.2.5 | Client Review & Revisions | Content Plan | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.5.2.2 |  |  | 0 | 0
1509 | DEL-0036 | TSK-01500 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.3.1 | 1.2.5.3 | Client Review & Revisions | Content Plan | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.5.3 |  |  | 0 | 0
1510 | DEL-0036 | TSK-01501 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.3.2 | 1.2.5.3 | Client Review & Revisions | Content Plan | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.5.3.1 |  |  | 0 | 0
1511 | DEL-0036 | TSK-01502 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.5.3.3 | 1.2.5.3 | Client Review & Revisions | Content Plan | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.5.3.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6 | 1.2 | Content Production Shoot Approach | Content Production Shoot Approach |  |  |  | 26 | 15 | 19 | 1.2.5 |  |  | 195 | 5070
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.1 | 1.2.6 | Final Packaging | Content Production Shoot Approach | Final Packaging |  |  | 0 | 15 | 6 | 1.2.6 |  |  | 0 | 0
1520 | DEL-0036 | TSK-01511 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.1.1 | 1.2.6.1 | Final Packaging | Content Production Shoot Approach | Final Packaging | Designer | Mid | 16 |  |  | 1.2.6.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.2 | 1.2.6 | Shoot Approach & Logistics | Content Production Shoot Approach | Shoot Approach & Logistics |  |  | 0 | 26 | 8 | 1.2.6.1.1 |  |  | 0 | 0
1523 | DEL-0036 | TSK-01514 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.2.1 | 1.2.6.2 | Shoot Approach & Logistics | Content Production Shoot Approach | Shoot Approach & Logistics | Creative Director | Lead/Director | 1 |  |  | 1.2.6.2 |  |  | 0 | 0
1524 | DEL-0036 | TSK-01515 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.2.2 | 1.2.6.2 | Shoot Approach & Logistics | Content Production Shoot Approach | Shoot Approach & Logistics | Project Manager | Mid | 4 |  |  | 1.2.6.2.1 |  |  | 0 | 0
1525 | DEL-0036 | TSK-01516 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.2.3 | 1.2.6.2 | Shoot Approach & Logistics | Content Production Shoot Approach | Shoot Approach & Logistics | Strategist | Mid | 1 |  |  | 1.2.6.2.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.3 | 1.2.6 | Internal Review & Critique | Content Production Shoot Approach | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.6.2.3 |  |  | 0 | 0
1521 | DEL-0036 | TSK-01512 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.3.1 | 1.2.6.3 | Internal Review & Critique | Content Production Shoot Approach | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.6.3 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.4 | 1.2.6 | Client Review & Revisions | Content Production Shoot Approach | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.6.3.1 |  |  | 0 | 0
1518 | DEL-0036 | TSK-01509 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.4.1 | 1.2.6.4 | Client Review & Revisions | Content Production Shoot Approach | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.2.6.4 |  |  | 0 | 0
1519 | DEL-0036 | TSK-01510 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.6.4.2 | 1.2.6.4 | Client Review & Revisions | Content Production Shoot Approach | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.6.4.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7 | 1.2 | Content Types across Full Funnel | Content Types across Full Funnel |  |  |  | 37 | 15 | 11 | 1.2.6 |  |  | 195 | 7215
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.1 | 1.2.7 | Content Type Matrix | Content Types across Full Funnel | Content Type Matrix |  |  | 0 | 15 | 6 | 1.2.7 |  |  | 0 | 0
1537 | DEL-0036 | TSK-01528 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.1.1 | 1.2.7.1 | Content Type Matrix | Content Types across Full Funnel | Content Type Matrix | Copywriter | Mid | 4 |  |  | 1.2.7.1 |  |  | 0 | 0
1538 | DEL-0036 | TSK-01529 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.1.2 | 1.2.7.1 | Content Type Matrix | Content Types across Full Funnel | Content Type Matrix | Designer | Mid | 16 |  |  | 1.2.7.1.1 |  |  | 0 | 0
1539 | DEL-0036 | TSK-01530 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.1.3 | 1.2.7.1 | Content Type Matrix | Content Types across Full Funnel | Content Type Matrix | Strategist | Mid | 12 |  |  | 1.2.7.1.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.2 | 1.2.7 | Internal Review & Critique | Content Types across Full Funnel | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.7.1.3 |  |  | 0 | 0
1542 | DEL-0036 | TSK-01533 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.2.1 | 1.2.7.2 | Internal Review & Critique | Content Types across Full Funnel | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.7.2 |  |  | 0 | 0
1543 | DEL-0036 | TSK-01534 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.2.2 | 1.2.7.2 | Internal Review & Critique | Content Types across Full Funnel | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.7.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.3 | 1.2.7 | Client Review & Revisions | Content Types across Full Funnel | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.7.2.2 |  |  | 0 | 0
1534 | DEL-0036 | TSK-01525 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.3.1 | 1.2.7.3 | Client Review & Revisions | Content Types across Full Funnel | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.7.3 |  |  | 0 | 0
1535 | DEL-0036 | TSK-01526 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.3.2 | 1.2.7.3 | Client Review & Revisions | Content Types across Full Funnel | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.7.3.1 |  |  | 0 | 0
1536 | DEL-0036 | TSK-01527 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.7.3.3 | 1.2.7.3 | Client Review & Revisions | Content Types across Full Funnel | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.7.3.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8 | 1.2 | Copy Bank | Copy Bank |  |  |  | 17 | 15 | 11 | 1.2.7 |  |  | 195 | 3315
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8.1 | 1.2.8 | Copy Examples (Headlines/Captions/CTAs) | Copy Bank | Copy Examples (Headlines/Captions/CTAs) |  |  | 0 | 15 | 6 | 1.2.8 |  |  | 0 | 0
1547 | DEL-0036 | TSK-01538 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8.1.1 | 1.2.8.1 | Copy Examples (Headlines/Captions/CTAs) | Copy Bank | Copy Examples (Headlines/Captions/CTAs) | Copywriter | Mid | 4 |  |  | 1.2.8.1 |  |  | 0 | 0
1548 | DEL-0036 | TSK-01539 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8.1.2 | 1.2.8.1 | Copy Examples (Headlines/Captions/CTAs) | Copy Bank | Copy Examples (Headlines/Captions/CTAs) | Designer | Mid | 8 |  |  | 1.2.8.1.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8.2 | 1.2.8 | Internal Review & Critique | Copy Bank | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.8.1.2 |  |  | 0 | 0
1549 | DEL-0036 | TSK-01540 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8.2.1 | 1.2.8.2 | Internal Review & Critique | Copy Bank | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.8.2 |  |  | 0 | 0
1550 | DEL-0036 | TSK-01541 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8.2.2 | 1.2.8.2 | Internal Review & Critique | Copy Bank | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.8.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8.3 | 1.2.8 | Client Review & Revisions | Copy Bank | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.8.2.2 |  |  | 0 | 0
1544 | DEL-0036 | TSK-01535 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8.3.1 | 1.2.8.3 | Client Review & Revisions | Copy Bank | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.8.3 |  |  | 0 | 0
1545 | DEL-0036 | TSK-01536 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8.3.2 | 1.2.8.3 | Client Review & Revisions | Copy Bank | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.8.3.1 |  |  | 0 | 0
1546 | DEL-0036 | TSK-01537 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.8.3.3 | 1.2.8.3 | Client Review & Revisions | Copy Bank | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.8.3.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.9 | 1.2 | Customer Journey | Customer Journey |  |  |  | 26 | 15 | 11 | 1.2.8 |  |  | 195 | 5070
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.9.1 | 1.2.9 | Journey Mapping | Customer Journey | Journey Mapping |  |  | 0 | 15 | 6 | 1.2.9 |  |  | 0 | 0
1553 | DEL-0036 | TSK-01544 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.9.1.1 | 1.2.9.1 | Journey Mapping | Customer Journey | Journey Mapping | Designer | Mid | 16 |  |  | 1.2.9.1 |  |  | 0 | 0
1557 | DEL-0036 | TSK-01548 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.9.1.2 | 1.2.9.1 | Journey Mapping | Customer Journey | Journey Mapping | Strategist | Mid | 6 |  |  | 1.2.9.1.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.9.2 | 1.2.9 | Internal Review & Critique | Customer Journey | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.9.1.2 |  |  | 0 | 0
1554 | DEL-0036 | TSK-01545 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.9.2.1 | 1.2.9.2 | Internal Review & Critique | Customer Journey | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.9.2 |  |  | 0 | 0
1555 | DEL-0036 | TSK-01546 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.9.2.2 | 1.2.9.2 | Internal Review & Critique | Customer Journey | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.9.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.9.3 | 1.2.9 | Client Review & Revisions | Customer Journey | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.9.2.2 |  |  | 0 | 0
1551 | DEL-0036 | TSK-01542 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.9.3.1 | 1.2.9.3 | Client Review & Revisions | Customer Journey | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.9.3 |  |  | 0 | 0
1552 | DEL-0036 | TSK-01543 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.9.3.2 | 1.2.9.3 | Client Review & Revisions | Customer Journey | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.9.3.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10 | 1.2 | High-Fidelity Organic Social Mock-Ups | High-Fidelity Organic Social Mock-Ups |  |  |  | 28 | 15 | 11 | 1.2.9 |  |  | 195 | 5460
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.1 | 1.2.10 | Concept & Layouts (3-4 ex.) | High-Fidelity Organic Social Mock-Ups | Concept & Layouts (3-4 ex.) |  |  | 0 | 15 | 6 | 1.2.10 |  |  | 0 | 0
1561 | DEL-0036 | TSK-01552 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.1.1 | 1.2.10.1 | Concept & Layouts (3-4 ex.) | High-Fidelity Organic Social Mock-Ups | Concept & Layouts (3-4 ex.) | Copywriter | Mid | 4 |  |  | 1.2.10.1 |  |  | 0 | 0
1562 | DEL-0036 | TSK-01553 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.1.2 | 1.2.10.1 | Concept & Layouts (3-4 ex.) | High-Fidelity Organic Social Mock-Ups | Concept & Layouts (3-4 ex.) | Creative Director | Lead/Director | 3 |  |  | 1.2.10.1.1 |  |  | 0 | 0
1563 | DEL-0036 | TSK-01554 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.1.3 | 1.2.10.1 | Concept & Layouts (3-4 ex.) | High-Fidelity Organic Social Mock-Ups | Concept & Layouts (3-4 ex.) | Designer | Mid | 16 |  |  | 1.2.10.1.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.2 | 1.2.10 | Internal Review & Critique | High-Fidelity Organic Social Mock-Ups | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.10.1.3 |  |  | 0 | 0
1565 | DEL-0036 | TSK-01556 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.2.1 | 1.2.10.2 | Internal Review & Critique | High-Fidelity Organic Social Mock-Ups | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.10.2 |  |  | 0 | 0
1566 | DEL-0036 | TSK-01557 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.2.2 | 1.2.10.2 | Internal Review & Critique | High-Fidelity Organic Social Mock-Ups | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.10.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.3 | 1.2.10 | Client Review & Revisions | High-Fidelity Organic Social Mock-Ups | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.10.2.2 |  |  | 0 | 0
1558 | DEL-0036 | TSK-01549 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.3.1 | 1.2.10.3 | Client Review & Revisions | High-Fidelity Organic Social Mock-Ups | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.10.3 |  |  | 0 | 0
1559 | DEL-0036 | TSK-01550 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.3.2 | 1.2.10.3 | Client Review & Revisions | High-Fidelity Organic Social Mock-Ups | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.10.3.1 |  |  | 0 | 0
1560 | DEL-0036 | TSK-01551 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.10.3.3 | 1.2.10.3 | Client Review & Revisions | High-Fidelity Organic Social Mock-Ups | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.10.3.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11 | 1.2 | High-Fidelity Paid Media Mock-Ups | High-Fidelity Paid Media Mock-Ups |  |  |  | 28 | 15 | 11 | 1.2.10 |  |  | 195 | 5460
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.1 | 1.2.11 | Concept & Layouts (3-4 ex.) | High-Fidelity Paid Media Mock-Ups | Concept & Layouts (3-4 ex.) |  |  | 0 | 15 | 6 | 1.2.11 |  |  | 0 | 0
1570 | DEL-0036 | TSK-01561 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.1.1 | 1.2.11.1 | Concept & Layouts (3-4 ex.) | High-Fidelity Paid Media Mock-Ups | Concept & Layouts (3-4 ex.) | Copywriter | Mid | 4 |  |  | 1.2.11.1 |  |  | 0 | 0
1571 | DEL-0036 | TSK-01562 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.1.2 | 1.2.11.1 | Concept & Layouts (3-4 ex.) | High-Fidelity Paid Media Mock-Ups | Concept & Layouts (3-4 ex.) | Creative Director | Lead/Director | 3 |  |  | 1.2.11.1.1 |  |  | 0 | 0
1572 | DEL-0036 | TSK-01563 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.1.3 | 1.2.11.1 | Concept & Layouts (3-4 ex.) | High-Fidelity Paid Media Mock-Ups | Concept & Layouts (3-4 ex.) | Designer | Mid | 16 |  |  | 1.2.11.1.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.2 | 1.2.11 | Internal Review & Critique | High-Fidelity Paid Media Mock-Ups | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.11.1.3 |  |  | 0 | 0
1574 | DEL-0036 | TSK-01565 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.2.1 | 1.2.11.2 | Internal Review & Critique | High-Fidelity Paid Media Mock-Ups | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.11.2 |  |  | 0 | 0
1575 | DEL-0036 | TSK-01566 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.2.2 | 1.2.11.2 | Internal Review & Critique | High-Fidelity Paid Media Mock-Ups | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.11.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.3 | 1.2.11 | Client Review & Revisions | High-Fidelity Paid Media Mock-Ups | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.11.2.2 |  |  | 0 | 0
1567 | DEL-0036 | TSK-01558 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.3.1 | 1.2.11.3 | Client Review & Revisions | High-Fidelity Paid Media Mock-Ups | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.11.3 |  |  | 0 | 0
1568 | DEL-0036 | TSK-01559 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.3.2 | 1.2.11.3 | Client Review & Revisions | High-Fidelity Paid Media Mock-Ups | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.11.3.1 |  |  | 0 | 0
1569 | DEL-0036 | TSK-01560 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.11.3.3 | 1.2.11.3 | Client Review & Revisions | High-Fidelity Paid Media Mock-Ups | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.11.3.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12 | 1.2 | Influencer Partnership Approach | Influencer Partnership Approach |  |  |  | 31 | 15 | 11 | 1.2.11 |  |  | 195 | 6045
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.1 | 1.2.12 | Outreach & Compensation Framework | Influencer Partnership Approach | Outreach & Compensation Framework |  |  | 0 | 15 | 6 | 1.2.12 |  |  | 0 | 0
1583 | DEL-0036 | TSK-01574 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.1.1 | 1.2.12.1 | Outreach & Compensation Framework | Influencer Partnership Approach | Outreach & Compensation Framework | Account Manager | Mid | 2 |  |  | 1.2.12.1 |  |  | 0 | 0
1579 | DEL-0036 | TSK-01570 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.1.2 | 1.2.12.1 | Outreach & Compensation Framework | Influencer Partnership Approach | Outreach & Compensation Framework | Copywriter | Mid | 4 |  |  | 1.2.12.1.1 |  |  | 0 | 0
1580 | DEL-0036 | TSK-01571 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.1.3 | 1.2.12.1 | Outreach & Compensation Framework | Influencer Partnership Approach | Outreach & Compensation Framework | Designer | Mid | 8 |  |  | 1.2.12.1.2 |  |  | 0 | 0
1584 | DEL-0036 | TSK-01575 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.1.4 | 1.2.12.1 | Outreach & Compensation Framework | Influencer Partnership Approach | Outreach & Compensation Framework | Strategist | Mid | 12 |  |  | 1.2.12.1.3 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.2 | 1.2.12 | Internal Review & Critique | Influencer Partnership Approach | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.12.1.4 |  |  | 0 | 0
1581 | DEL-0036 | TSK-01572 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.2.1 | 1.2.12.2 | Internal Review & Critique | Influencer Partnership Approach | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.12.2 |  |  | 0 | 0
1582 | DEL-0036 | TSK-01573 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.2.2 | 1.2.12.2 | Internal Review & Critique | Influencer Partnership Approach | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.12.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.3 | 1.2.12 | Client Review & Revisions | Influencer Partnership Approach | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.12.2.2 |  |  | 0 | 0
1576 | DEL-0036 | TSK-01567 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.3.1 | 1.2.12.3 | Client Review & Revisions | Influencer Partnership Approach | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.12.3 |  |  | 0 | 0
1577 | DEL-0036 | TSK-01568 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.3.2 | 1.2.12.3 | Client Review & Revisions | Influencer Partnership Approach | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.12.3.1 |  |  | 0 | 0
1578 | DEL-0036 | TSK-01569 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.12.3.3 | 1.2.12.3 | Client Review & Revisions | Influencer Partnership Approach | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.12.3.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13 | 1.2 | Kick-Off Session | Kick-Off Session |  |  |  | 55 | 15 | 11 | 1.2.12 |  |  | 195 | 10725
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.1 | 1.2.13 | Agenda & Materials Prep | Kick-Off Session | Agenda & Materials Prep |  |  | 0 | 15 | 6 | 1.2.13 |  |  | 0 | 0
1586 | DEL-0036 | TSK-01577 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.1.1 | 1.2.13.1 | Agenda & Materials Prep | Kick-Off Session | Agenda & Materials Prep | Account Manager | Mid | 6 |  |  | 1.2.13.1 |  |  | 0 | 0
1593 | DEL-0036 | TSK-01584 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.1.2 | 1.2.13.1 | Agenda & Materials Prep | Kick-Off Session | Agenda & Materials Prep | Creative Director | Lead/Director | 3 |  |  | 1.2.13.1.1 |  |  | 0 | 0
1587 | DEL-0036 | TSK-01578 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.1.3 | 1.2.13.1 | Agenda & Materials Prep | Kick-Off Session | Agenda & Materials Prep | Designer | Mid | 16 |  |  | 1.2.13.1.2 |  |  | 0 | 0
1588 | DEL-0036 | TSK-01579 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.1.4 | 1.2.13.1 | Agenda & Materials Prep | Kick-Off Session | Agenda & Materials Prep | Project Manager | Mid | 2 |  |  | 1.2.13.1.3 |  |  | 0 | 0
1589 | DEL-0036 | TSK-01580 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.1.5 | 1.2.13.1 | Agenda & Materials Prep | Kick-Off Session | Agenda & Materials Prep | Strategist | Mid | 24 |  |  | 1.2.13.1.4 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.2 | 1.2.13 | Internal Review & Critique | Kick-Off Session | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.13.1.5 |  |  | 0 | 0
1596 | DEL-0036 | TSK-01587 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.2.1 | 1.2.13.2 | Internal Review & Critique | Kick-Off Session | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.13.2 |  |  | 0 | 0
1597 | DEL-0036 | TSK-01588 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.2.2 | 1.2.13.2 | Internal Review & Critique | Kick-Off Session | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.13.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.3 | 1.2.13 | Client Review & Revisions | Kick-Off Session | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.13.2.2 |  |  | 0 | 0
1590 | DEL-0036 | TSK-01581 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.3.1 | 1.2.13.3 | Client Review & Revisions | Kick-Off Session | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.13.3 |  |  | 0 | 0
1591 | DEL-0036 | TSK-01582 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.13.3.2 | 1.2.13.3 | Client Review & Revisions | Kick-Off Session | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.13.3.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14 | 1.2 | Messaging Framework (by Audience) | Messaging Framework (by Audience) |  |  |  | 37 | 15 | 11 | 1.2.13 |  |  | 195 | 7215
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.1 | 1.2.14 | Draft Messaging | Messaging Framework (by Audience) | Draft Messaging |  |  | 0 | 15 | 6 | 1.2.14 |  |  | 0 | 0
1605 | DEL-0036 | TSK-01596 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.1.1 | 1.2.14.1 | Draft Messaging | Messaging Framework (by Audience) | Draft Messaging | Copywriter | Mid | 4 |  |  | 1.2.14.1 |  |  | 0 | 0
1604 | DEL-0036 | TSK-01595 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.1.2 | 1.2.14.1 | Draft Messaging | Messaging Framework (by Audience) | Draft Messaging | Designer | Mid | 16 |  |  | 1.2.14.1.1 |  |  | 0 | 0
1606 | DEL-0036 | TSK-01597 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.1.3 | 1.2.14.1 | Draft Messaging | Messaging Framework (by Audience) | Draft Messaging | Strategist | Mid | 12 |  |  | 1.2.14.1.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.2 | 1.2.14 | Internal Review & Critique | Messaging Framework (by Audience) | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.14.1.3 |  |  | 0 | 0
1608 | DEL-0036 | TSK-01599 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.2.1 | 1.2.14.2 | Internal Review & Critique | Messaging Framework (by Audience) | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.14.2 |  |  | 0 | 0
1609 | DEL-0036 | TSK-01600 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.2.2 | 1.2.14.2 | Internal Review & Critique | Messaging Framework (by Audience) | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.14.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.3 | 1.2.14 | Client Review & Revisions | Messaging Framework (by Audience) | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.14.2.2 |  |  | 0 | 0
1601 | DEL-0036 | TSK-01592 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.3.1 | 1.2.14.3 | Client Review & Revisions | Messaging Framework (by Audience) | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.14.3 |  |  | 0 | 0
1602 | DEL-0036 | TSK-01593 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.3.2 | 1.2.14.3 | Client Review & Revisions | Messaging Framework (by Audience) | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.14.3.1 |  |  | 0 | 0
1603 | DEL-0036 | TSK-01594 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.14.3.3 | 1.2.14.3 | Client Review & Revisions | Messaging Framework (by Audience) | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.14.3.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15 | 1.2 | Platform/Channel Approach | Platform/Channel Approach |  |  |  | 29 | 15 | 15 | 1.2.14 |  |  | 195 | 5655
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.1 | 1.2.15 | Baseline KPIs | Platform/Channel Approach | Baseline KPIs |  |  | 0 | 15 | 6 | 1.2.15 |  |  | 0 | 0
1611 | DEL-0036 | TSK-01602 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.1.1 | 1.2.15.1 | Baseline KPIs | Platform/Channel Approach | Baseline KPIs | Analyst | Mid | 3 |  |  | 1.2.15.1 |  |  | 0 | 0
1616 | DEL-0036 | TSK-01607 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.1.2 | 1.2.15.1 | Baseline KPIs | Platform/Channel Approach | Baseline KPIs | Designer | Mid | 8 |  |  | 1.2.15.1.1 |  |  | 0 | 0
1612 | DEL-0036 | TSK-01603 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.1.3 | 1.2.15.1 | Baseline KPIs | Platform/Channel Approach | Baseline KPIs | Strategist | Mid | 12 |  |  | 1.2.15.1.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.2 | 1.2.15 | Summary Slides | Platform/Channel Approach | Summary Slides |  |  | 0 | 34 | 4 | 1.2.15.1.3 |  |  | 0 | 0
1619 | DEL-0036 | TSK-01610 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.2.1 | 1.2.15.2 | Summary Slides | Platform/Channel Approach | Summary Slides | Designer | Mid | 2 |  |  | 1.2.15.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.3 | 1.2.15 | Internal Review & Critique | Platform/Channel Approach | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.15.2.1 |  |  | 0 | 0
1617 | DEL-0036 | TSK-01608 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.3.1 | 1.2.15.3 | Internal Review & Critique | Platform/Channel Approach | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.15.3 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.4 | 1.2.15 | Client Review & Revisions | Platform/Channel Approach | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.15.3.1 |  |  | 0 | 0
1614 | DEL-0036 | TSK-01605 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.4.1 | 1.2.15.4 | Client Review & Revisions | Platform/Channel Approach | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.2.15.4 |  |  | 0 | 0
1615 | DEL-0036 | TSK-01606 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.15.4.2 | 1.2.15.4 | Client Review & Revisions | Platform/Channel Approach | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.15.4.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.16 | 1.2 | Social Templates | Social Templates |  |  |  | 31 | 15 | 11 | 1.2.15 |  |  | 195 | 6045
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.16.1 | 1.2.16 | Template Exploration | Social Templates | Template Exploration |  |  | 0 | 15 | 6 | 1.2.16 |  |  | 0 | 0
1626 | DEL-0036 | TSK-01617 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.16.1.1 | 1.2.16.1 | Template Exploration | Social Templates | Template Exploration | Creative Director | Lead/Director | 3 |  |  | 1.2.16.1 |  |  | 0 | 0
1622 | DEL-0036 | TSK-01613 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.16.1.2 | 1.2.16.1 | Template Exploration | Social Templates | Template Exploration | Designer | Mid | 24 |  |  | 1.2.16.1.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.16.2 | 1.2.16 | Internal Review & Critique | Social Templates | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.16.1.2 |  |  | 0 | 0
1623 | DEL-0036 | TSK-01614 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.16.2.1 | 1.2.16.2 | Internal Review & Critique | Social Templates | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.16.2 |  |  | 0 | 0
1624 | DEL-0036 | TSK-01615 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.16.2.2 | 1.2.16.2 | Internal Review & Critique | Social Templates | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.16.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.16.3 | 1.2.16 | Client Review & Revisions | Social Templates | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.16.2.2 |  |  | 0 | 0
1620 | DEL-0036 | TSK-01611 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.16.3.1 | 1.2.16.3 | Client Review & Revisions | Social Templates | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.16.3 |  |  | 0 | 0
1621 | DEL-0036 | TSK-01612 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.16.3.2 | 1.2.16.3 | Client Review & Revisions | Social Templates | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.16.3.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17 | 1.2 | Visual Approach | Visual Approach |  |  |  | 29 | 15 | 11 | 1.2.16 |  |  | 195 | 5655
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17.1 | 1.2.17 | Moodboards & References | Visual Approach | Moodboards & References |  |  | 0 | 15 | 6 | 1.2.17 |  |  | 0 | 0
1633 | DEL-0036 | TSK-01624 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17.1.1 | 1.2.17.1 | Moodboards & References | Visual Approach | Moodboards & References | Creative Director | Lead/Director | 3 |  |  | 1.2.17.1 |  |  | 0 | 0
1630 | DEL-0036 | TSK-01621 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17.1.2 | 1.2.17.1 | Moodboards & References | Visual Approach | Moodboards & References | Designer | Mid | 16 |  |  | 1.2.17.1.1 |  |  | 0 | 0
1635 | DEL-0036 | TSK-01626 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17.1.3 | 1.2.17.1 | Moodboards & References | Visual Approach | Moodboards & References | Strategist | Mid | 6 |  |  | 1.2.17.1.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17.2 | 1.2.17 | Internal Review & Critique | Visual Approach | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.17.1.3 |  |  | 0 | 0
1631 | DEL-0036 | TSK-01622 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17.2.1 | 1.2.17.2 | Internal Review & Critique | Visual Approach | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.17.2 |  |  | 0 | 0
1632 | DEL-0036 | TSK-01623 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17.2.2 | 1.2.17.2 | Internal Review & Critique | Visual Approach | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.17.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17.3 | 1.2.17 | Client Review & Revisions | Visual Approach | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.17.2.2 |  |  | 0 | 0
1628 | DEL-0036 | TSK-01619 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17.3.1 | 1.2.17.3 | Client Review & Revisions | Visual Approach | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.17.3 |  |  | 0 | 0
1629 | DEL-0036 | TSK-01620 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.17.3.2 | 1.2.17.3 | Client Review & Revisions | Visual Approach | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.17.3.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18 | 1.2 | Voice & Tone | Voice & Tone |  |  |  | 27 | 15 | 11 | 1.2.17 |  |  | 195 | 5265
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.1 | 1.2.18 | Principles Outline | Voice & Tone | Principles Outline |  |  | 0 | 15 | 6 | 1.2.18 |  |  | 0 | 0
1639 | DEL-0036 | TSK-01630 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.1.1 | 1.2.18.1 | Principles Outline | Voice & Tone | Principles Outline | Copywriter | Mid | 8 |  |  | 1.2.18.1 |  |  | 0 | 0
1640 | DEL-0036 | TSK-01631 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.1.2 | 1.2.18.1 | Principles Outline | Voice & Tone | Principles Outline | Designer | Mid | 8 |  |  | 1.2.18.1.1 |  |  | 0 | 0
1644 | DEL-0036 | TSK-01635 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.1.3 | 1.2.18.1 | Principles Outline | Voice & Tone | Principles Outline | Strategist | Mid | 6 |  |  | 1.2.18.1.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.2 | 1.2.18 | Internal Review & Critique | Voice & Tone | Internal Review & Critique |  |  | 0 | 38 | 2 | 1.2.18.1.3 |  |  | 0 | 0
1641 | DEL-0036 | TSK-01632 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.2.1 | 1.2.18.2 | Internal Review & Critique | Voice & Tone | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.18.2 |  |  | 0 | 0
1642 | DEL-0036 | TSK-01633 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.2.2 | 1.2.18.2 | Internal Review & Critique | Voice & Tone | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.18.2.1 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.3 | 1.2.18 | Client Review & Revisions | Voice & Tone | Client Review & Revisions |  |  | 0 | 40 | 3 | 1.2.18.2.2 |  |  | 0 | 0
1636 | DEL-0036 | TSK-01627 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.3.1 | 1.2.18.3 | Client Review & Revisions | Voice & Tone | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.18.3 |  |  | 0 | 0
1637 | DEL-0036 | TSK-01628 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.3.2 | 1.2.18.3 | Client Review & Revisions | Voice & Tone | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.18.3.1 |  |  | 0 | 0
1638 | DEL-0036 | TSK-01629 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.18.3.3 | 1.2.18.3 | Client Review & Revisions | Voice & Tone | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.18.3.2 |  |  | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.19 | 1.2 | Content Production Shot List Review & Guidance | Content Production Shot List Review & Guidance |  |  |  | 13 | 21 | 5 | 1.2.18 |  |  | 195 | 2535
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.19.1 | 1.2.19 | Client Review & Revisions | Content Production Shot List Review & Guidance | Client Review & Revisions |  |  | 0 | 21 | 5 | 1.2.19 |  |  | 0 | 0
1527 | DEL-0036 | TSK-01518 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.19.1.1 | 1.2.19.1 | Client Review & Revisions | Content Production Shot List Review & Guidance | Client Review & Revisions | Account Manager | Mid | 3 |  |  | 1.2.19.1 |  |  | 0 | 0
1530 | DEL-0036 | TSK-01521 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.19.1.2 | 1.2.19.1 | Client Review & Revisions | Content Production Shot List Review & Guidance | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.19.1.1 |  |  | 0 | 0
1529 | DEL-0036 | TSK-01520 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.19.1.3 | 1.2.19.1 | Client Review & Revisions | Content Production Shot List Review & Guidance | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.2.19.1.2 |  |  | 0 | 0
1528 | DEL-0036 | TSK-01519 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.2.19.1.4 | 1.2.19.1 | Client Review & Revisions | Content Production Shot List Review & Guidance | Client Review & Revisions | Strategist | Mid | 6 |  |  | 1.2.19.1.3 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3 | 1 | Paid Media Strategy |  |  |  |  | 162 | 43 | 46 | 1.2 |  | Advanced/T2_MediumVolume | 195 | 31590
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.1 | 1.3 | Audience Research | Audience Research |  |  |  | 13 | 43 | 9 | 1.3 |  |  | 195 | 2535
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.1.1 | 1.3.1 | Audience Build & Rationale | Audience Research | Audience Build & Rationale |  |  | 0 | 43 | 4 | 1.3.1 |  |  | 0 | 0
1266 | DEL-0030 | TSK-01257 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.1.1.1 | 1.3.1.1 | Audience Build & Rationale | Audience Research | Audience Build & Rationale | Analyst | Mid | 5 |  |  | 1.3.1.1 |  |  | 0 | 0
1261 | DEL-0030 | TSK-01252 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.1.1.2 | 1.3.1.1 | Audience Build & Rationale | Audience Research | Audience Build & Rationale | Media Strategist | Mid | 4 |  |  | 1.3.1.1.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.1.2 | 1.3.1 | Internal Review & Critique | Audience Research | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.1.1.2 |  |  | 0 | 0
1264 | DEL-0030 | TSK-01255 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.1.2.1 | 1.3.1.2 | Internal Review & Critique | Audience Research | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.1.2 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.1.3 | 1.3.1 | Client Review & Revisions | Audience Research | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.1.2.1 |  |  | 0 | 0
1262 | DEL-0030 | TSK-01253 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.1.3.1 | 1.3.1.3 | Client Review & Revisions | Audience Research | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.3.1.3 |  |  | 0 | 0
1263 | DEL-0030 | TSK-01254 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.1.3.2 | 1.3.1.3 | Client Review & Revisions | Audience Research | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.1.3.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2 | 1.3 | Keyword List Development | Keyword List Development |  |  |  | 16 | 43 | 20 | 1.3.1 |  |  | 195 | 3120
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2.1 | 1.3.2 | Keyword Discovery | Keyword List Development | Keyword Discovery |  |  | 0 | 43 | 4 | 1.3.2 |  |  | 0 | 0
1290 | DEL-0030 | TSK-01281 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2.1.1 | 1.3.2.1 | Keyword Discovery | Keyword List Development | Keyword Discovery | Analyst | Mid | 5 |  |  | 1.3.2.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2.2 | 1.3.2 | List Development & Grouping | Keyword List Development | List Development & Grouping |  |  | 0 | 71 | 11 | 1.3.2.1.1 |  |  | 0 | 0
1291 | DEL-0030 | TSK-01282 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2.2.1 | 1.3.2.2 | List Development & Grouping | Keyword List Development | List Development & Grouping | Media Strategist | Mid | 7 |  |  | 1.3.2.2 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2.3 | 1.3.2 | Internal Review & Critique | Keyword List Development | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.2.2.1 |  |  | 0 | 0
1288 | DEL-0030 | TSK-01279 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2.3.1 | 1.3.2.3 | Internal Review & Critique | Keyword List Development | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.2.3 |  |  | 0 | 0
1289 | DEL-0030 | TSK-01280 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2.3.2 | 1.3.2.3 | Internal Review & Critique | Keyword List Development | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.2.3.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2.4 | 1.3.2 | Client Review & Revisions | Keyword List Development | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.2.3.2 |  |  | 0 | 0
1286 | DEL-0030 | TSK-01277 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2.4.1 | 1.3.2.4 | Client Review & Revisions | Keyword List Development | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.2.4 |  |  | 0 | 0
1287 | DEL-0030 | TSK-01278 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.2.4.2 | 1.3.2.4 | Client Review & Revisions | Keyword List Development | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.2.4.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3 | 1.3 | Paid Media & Paid Creative Audit | Paid Media & Paid Creative Audit |  |  |  | 23 | 43 | 15 | 1.3.2 |  |  | 195 | 4485
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.1 | 1.3.3 | Platform/Creative Audit | Paid Media & Paid Creative Audit | Platform/Creative Audit |  |  | 0 | 43 | 4 | 1.3.3 |  |  | 0 | 0
1308 | DEL-0030 | TSK-01299 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.1.1 | 1.3.3.1 | Platform/Creative Audit | Paid Media & Paid Creative Audit | Platform/Creative Audit | Analyst | Mid | 5 |  |  | 1.3.3.1 |  |  | 0 | 0
1304 | DEL-0030 | TSK-01295 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.1.2 | 1.3.3.1 | Platform/Creative Audit | Paid Media & Paid Creative Audit | Platform/Creative Audit | Designer | Mid | 3 |  |  | 1.3.3.1.1 |  |  | 0 | 0
1309 | DEL-0030 | TSK-01300 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.1.3 | 1.3.3.1 | Platform/Creative Audit | Paid Media & Paid Creative Audit | Platform/Creative Audit | Media Strategist | Mid | 3 |  |  | 1.3.3.1.2 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.2 | 1.3.3 | Findings Deck | Paid Media & Paid Creative Audit | Findings Deck |  |  | 0 | 47 | 6 | 1.3.3.1.3 |  |  | 0 | 0
1305 | DEL-0030 | TSK-01296 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.2.1 | 1.3.3.2 | Findings Deck | Paid Media & Paid Creative Audit | Findings Deck | Designer | Mid | 8 |  |  | 1.3.3.2 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.3 | 1.3.3 | Internal Review & Critique | Paid Media & Paid Creative Audit | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.3.2.1 |  |  | 0 | 0
1306 | DEL-0030 | TSK-01297 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.3.1 | 1.3.3.3 | Internal Review & Critique | Paid Media & Paid Creative Audit | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.3.3 |  |  | 0 | 0
1307 | DEL-0030 | TSK-01298 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.3.2 | 1.3.3.3 | Internal Review & Critique | Paid Media & Paid Creative Audit | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.3.3.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.4 | 1.3.3 | Client Review & Revisions | Paid Media & Paid Creative Audit | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.3.3.2 |  |  | 0 | 0
1302 | DEL-0030 | TSK-01293 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.4.1 | 1.3.3.4 | Client Review & Revisions | Paid Media & Paid Creative Audit | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.3.4 |  |  | 0 | 0
1303 | DEL-0030 | TSK-01294 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.3.4.2 | 1.3.3.4 | Client Review & Revisions | Paid Media & Paid Creative Audit | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.3.4.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4 | 1.3 | Mock Ad Examples | Mock Ad Examples |  |  |  | 16 | 53 | 17 | 1.3.3 |  |  | 195 | 3120
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.1 | 1.3.4 | Concept & Copy | Mock Ad Examples | Concept & Copy |  |  | 0 | 53 | 4 | 1.3.4 |  |  | 0 | 0
1296 | DEL-0030 | TSK-01287 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.1.1 | 1.3.4.1 | Concept & Copy | Mock Ad Examples | Concept & Copy | Copywriter | Mid | 3 |  |  | 1.3.4.1 |  |  | 0 | 0
1297 | DEL-0030 | TSK-01288 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.1.2 | 1.3.4.1 | Concept & Copy | Mock Ad Examples | Concept & Copy | Creative Director | Lead/Director | 2 |  |  | 1.3.4.1.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.2 | 1.3.4 | Design (3-4 mocks) | Mock Ad Examples | Design (3-4 mocks) |  |  | 0 | 57 | 8 | 1.3.4.1.2 |  |  | 0 | 0
1298 | DEL-0030 | TSK-01289 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.2.1 | 1.3.4.2 | Design (3-4 mocks) | Mock Ad Examples | Design (3-4 mocks) | Designer | Mid | 4 |  |  | 1.3.4.2 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.3 | 1.3.4 | Internal Review & Critique | Mock Ad Examples | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.4.2.1 |  |  | 0 | 0
1300 | DEL-0030 | TSK-01291 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.3.1 | 1.3.4.3 | Internal Review & Critique | Mock Ad Examples | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.4.3 |  |  | 0 | 0
1301 | DEL-0030 | TSK-01292 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.3.2 | 1.3.4.3 | Internal Review & Critique | Mock Ad Examples | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.4.3.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.4 | 1.3.4 | Client Review & Revisions | Mock Ad Examples | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.4.3.2 |  |  | 0 | 0
1293 | DEL-0030 | TSK-01284 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.4.1 | 1.3.4.4 | Client Review & Revisions | Mock Ad Examples | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.4.4 |  |  | 0 | 0
1294 | DEL-0030 | TSK-01285 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.4.2 | 1.3.4.4 | Client Review & Revisions | Mock Ad Examples | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.3.4.4.1 |  |  | 0 | 0
1295 | DEL-0030 | TSK-01286 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.4.3 | 1.3.4.4 | Client Review & Revisions | Mock Ad Examples | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.4.4.2 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.5 | 1.3.4 | Final Packaging | Mock Ad Examples | Final Packaging |  |  | 0 | 89 | 0 | 1.3.4.4.3 |  |  | 0 | 0
1299 | DEL-0030 | TSK-01290 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.4.5.1 | 1.3.4.5 | Final Packaging | Mock Ad Examples | Final Packaging | Designer | Mid | 2 |  |  | 1.3.4.5 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.5 | 1.3 | Campaigns | Campaigns |  |  |  | 24 | 65 | 11 | 1.3.4 |  |  | 195 | 4680
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.5.1 | 1.3.5 | Campaign Architecture | Campaigns | Campaign Architecture |  |  | 0 | 65 | 6 | 1.3.5 |  |  | 0 | 0
1273 | DEL-0030 | TSK-01264 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.5.1.1 | 1.3.5.1 | Campaign Architecture | Campaigns | Campaign Architecture | Media Planner | Mid | 10 |  |  | 1.3.5.1 |  |  | 0 | 0
1274 | DEL-0030 | TSK-01265 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.5.1.2 | 1.3.5.1 | Campaign Architecture | Campaigns | Campaign Architecture | Media Strategist | Mid | 10 |  |  | 1.3.5.1.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.5.2 | 1.3.5 | Internal Review & Critique | Campaigns | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.5.1.2 |  |  | 0 | 0
1277 | DEL-0030 | TSK-01268 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.5.2.1 | 1.3.5.2 | Internal Review & Critique | Campaigns | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.5.2 |  |  | 0 | 0
1278 | DEL-0030 | TSK-01269 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.5.2.2 | 1.3.5.2 | Internal Review & Critique | Campaigns | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.5.2.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.5.3 | 1.3.5 | Client Review & Revisions | Campaigns | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.5.2.2 |  |  | 0 | 0
1275 | DEL-0030 | TSK-01266 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.5.3.1 | 1.3.5.3 | Client Review & Revisions | Campaigns | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.5.3 |  |  | 0 | 0
1276 | DEL-0030 | TSK-01267 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.5.3.2 | 1.3.5.3 | Client Review & Revisions | Campaigns | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.5.3.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.6 | 1.3 | Ad Funnel | Ad Funnel |  |  |  | 16 | 82 | 5 | 1.3.5 |  |  | 195 | 3120
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.6.1 | 1.3.6 | Internal Review & Critique | Ad Funnel | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.6 |  |  | 0 | 0
1257 | DEL-0030 | TSK-01248 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.6.1.1 | 1.3.6.1 | Internal Review & Critique | Ad Funnel | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.6.1 |  |  | 0 | 0
1258 | DEL-0030 | TSK-01249 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.6.1.2 | 1.3.6.1 | Internal Review & Critique | Ad Funnel | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.6.1.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.6.2 | 1.3.6 | Client Review & Revisions | Ad Funnel | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.6.1.2 |  |  | 0 | 0
1253 | DEL-0030 | TSK-01244 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.6.2.1 | 1.3.6.2 | Client Review & Revisions | Ad Funnel | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.6.2 |  |  | 0 | 0
1254 | DEL-0030 | TSK-01245 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.6.2.2 | 1.3.6.2 | Client Review & Revisions | Ad Funnel | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.6.2.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.6.3 | 1.3.6 | Messaging/Asset Mapping | Ad Funnel | Messaging/Asset Mapping |  |  | 0 | 89 | 0 | 1.3.6.2.2 |  |  | 0 | 0
1256 | DEL-0030 | TSK-01247 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.6.3.1 | 1.3.6.3 | Messaging/Asset Mapping | Ad Funnel | Messaging/Asset Mapping | Designer | Mid | 5 |  |  | 1.3.6.3 |  |  | 0 | 0
1255 | DEL-0030 | TSK-01246 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.6.3.2 | 1.3.6.3 | Messaging/Asset Mapping | Ad Funnel | Messaging/Asset Mapping | Media Strategist | Mid | 7 |  |  | 1.3.6.3.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.7 | 1.3 | Budget Distribution | Budget Distribution |  |  |  | 6 | 82 | 7 | 1.3.6 |  |  | 195 | 1170
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.7.1 | 1.3.7 | Internal Review & Critique | Budget Distribution | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.7 |  |  | 0 | 0
1271 | DEL-0030 | TSK-01262 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.7.1.1 | 1.3.7.1 | Internal Review & Critique | Budget Distribution | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.7.1 |  |  | 0 | 0
1272 | DEL-0030 | TSK-01263 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.7.1.2 | 1.3.7.1 | Internal Review & Critique | Budget Distribution | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.7.1.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.7.2 | 1.3.7 | Client Review & Revisions | Budget Distribution | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.7.1.2 |  |  | 0 | 0
1269 | DEL-0030 | TSK-01260 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.7.2.1 | 1.3.7.2 | Client Review & Revisions | Budget Distribution | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.7.2 |  |  | 0 | 0
1270 | DEL-0030 | TSK-01261 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.7.2.2 | 1.3.7.2 | Client Review & Revisions | Budget Distribution | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.7.2.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.7.3 | 1.3.7 | Allocation Modeling | Budget Distribution | Allocation Modeling |  |  | 0 | 87 | 2 | 1.3.7.2.2 |  |  | 0 | 0
1267 | DEL-0030 | TSK-01258 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.7.3.1 | 1.3.7.3 | Allocation Modeling | Budget Distribution | Allocation Modeling | Media Planner | Mid | 1 |  |  | 1.3.7.3 |  |  | 0 | 0
1268 | DEL-0030 | TSK-01259 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.7.3.2 | 1.3.7.3 | Allocation Modeling | Budget Distribution | Allocation Modeling | Media Strategist | Mid | 1 |  |  | 1.3.7.3.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.8 | 1.3 | Identification of Media Needs | Identification of Media Needs |  |  |  | 12 | 82 | 5 | 1.3.7 |  |  | 195 | 2340
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.8.1 | 1.3.8 | Internal Review & Critique | Identification of Media Needs | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.8 |  |  | 0 | 0
1282 | DEL-0030 | TSK-01273 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.8.1.1 | 1.3.8.1 | Internal Review & Critique | Identification of Media Needs | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.8.1 |  |  | 0 | 0
1283 | DEL-0030 | TSK-01274 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.8.1.2 | 1.3.8.1 | Internal Review & Critique | Identification of Media Needs | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.8.1.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.8.2 | 1.3.8 | Client Review & Revisions | Identification of Media Needs | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.8.1.2 |  |  | 0 | 0
1279 | DEL-0030 | TSK-01270 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.8.2.1 | 1.3.8.2 | Client Review & Revisions | Identification of Media Needs | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.8.2 |  |  | 0 | 0
1280 | DEL-0030 | TSK-01271 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.8.2.2 | 1.3.8.2 | Client Review & Revisions | Identification of Media Needs | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.8.2.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.8.3 | 1.3.8 | Needs Matrix (Assets/Specs/Formats) | Identification of Media Needs | Needs Matrix (Assets/Specs/Formats) |  |  | 0 | 89 | 0 | 1.3.8.2.2 |  |  | 0 | 0
1281 | DEL-0030 | TSK-01272 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.8.3.1 | 1.3.8.3 | Needs Matrix (Assets/Specs/Formats) | Identification of Media Needs | Needs Matrix (Assets/Specs/Formats) | Designer | Mid | 5 |  |  | 1.3.8.3 |  |  | 0 | 0
1285 | DEL-0030 | TSK-01276 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.8.3.2 | 1.3.8.3 | Needs Matrix (Assets/Specs/Formats) | Identification of Media Needs | Needs Matrix (Assets/Specs/Formats) | Media Strategist | Mid | 3 |  |  | 1.3.8.3.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9 | 1.3 | Paid Media Recommendations | Paid Media Recommendations |  |  |  | 15 | 82 | 5 | 1.3.8 |  |  | 195 | 2925
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.1 | 1.3.9 | Internal Review & Critique | Paid Media Recommendations | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.9 |  |  | 0 | 0
1313 | DEL-0030 | TSK-01304 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.1.1 | 1.3.9.1 | Internal Review & Critique | Paid Media Recommendations | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.9.1 |  |  | 0 | 0
1314 | DEL-0030 | TSK-01305 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.1.2 | 1.3.9.1 | Internal Review & Critique | Paid Media Recommendations | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.9.1.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.2 | 1.3.9 | Client Review & Revisions | Paid Media Recommendations | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.9.1.2 |  |  | 0 | 0
1310 | DEL-0030 | TSK-01301 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.2.1 | 1.3.9.2 | Client Review & Revisions | Paid Media Recommendations | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.9.2 |  |  | 0 | 0
1311 | DEL-0030 | TSK-01302 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.2.2 | 1.3.9.2 | Client Review & Revisions | Paid Media Recommendations | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.9.2.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.3 | 1.3.9 | Prioritized Recs | Paid Media Recommendations | Prioritized Recs |  |  | 0 | 89 | 0 | 1.3.9.2.2 |  |  | 0 | 0
1312 | DEL-0030 | TSK-01303 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.3.1 | 1.3.9.3 | Prioritized Recs | Paid Media Recommendations | Prioritized Recs | Designer | Mid | 3 |  |  | 1.3.9.3 |  |  | 0 | 0
1315 | DEL-0030 | TSK-01306 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.3.2 | 1.3.9.3 | Prioritized Recs | Paid Media Recommendations | Prioritized Recs | Media Planner | Mid | 4 |  |  | 1.3.9.3.1 |  |  | 0 | 0
1316 | DEL-0030 | TSK-01307 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.3.3 | 1.3.9.3 | Prioritized Recs | Paid Media Recommendations | Prioritized Recs | Media Strategist | Mid | 3 |  |  | 1.3.9.3.2 |  |  | 0 | 0
1317 | DEL-0030 | TSK-01308 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.9.3.4 | 1.3.9.3 | Prioritized Recs | Paid Media Recommendations | Prioritized Recs | Project Manager | Mid | 1 |  |  | 1.3.9.3.3 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.10 | 1.3 | Platform Identification | Platform Identification |  |  |  | 11 | 82 | 5 | 1.3.9 |  |  | 195 | 2145
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.10.1 | 1.3.10 | Internal Review & Critique | Platform Identification | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.10 |  |  | 0 | 0
1320 | DEL-0030 | TSK-01311 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.10.1.1 | 1.3.10.1 | Internal Review & Critique | Platform Identification | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.10.1 |  |  | 0 | 0
1321 | DEL-0030 | TSK-01312 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.10.1.2 | 1.3.10.1 | Internal Review & Critique | Platform Identification | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.10.1.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.10.2 | 1.3.10 | Client Review & Revisions | Platform Identification | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.10.1.2 |  |  | 0 | 0
1318 | DEL-0030 | TSK-01309 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.10.2.1 | 1.3.10.2 | Client Review & Revisions | Platform Identification | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.10.2 |  |  | 0 | 0
1319 | DEL-0030 | TSK-01310 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.10.2.2 | 1.3.10.2 | Client Review & Revisions | Platform Identification | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.10.2.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.10.3 | 1.3.10 | Platform Fit Assessment | Platform Identification | Platform Fit Assessment |  |  | 0 | 89 | 0 | 1.3.10.2.2 |  |  | 0 | 0
1322 | DEL-0030 | TSK-01313 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.10.3.1 | 1.3.10.3 | Platform Fit Assessment | Platform Identification | Platform Fit Assessment | Media Planner | Mid | 4 |  |  | 1.3.10.3 |  |  | 0 | 0
1323 | DEL-0030 | TSK-01314 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.10.3.2 | 1.3.10.3 | Platform Fit Assessment | Platform Identification | Platform Fit Assessment | Media Strategist | Mid | 3 |  |  | 1.3.10.3.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.11 | 1.3 | Target Audience & Demographics | Target Audience & Demographics |  |  |  | 10 | 82 | 5 | 1.3.10 |  |  | 195 | 1950
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.11.1 | 1.3.11 | Internal Review & Critique | Target Audience & Demographics | Internal Review & Critique |  |  | 0 | 82 | 2 | 1.3.11 |  |  | 0 | 0
1328 | DEL-0030 | TSK-01319 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.11.1.1 | 1.3.11.1 | Internal Review & Critique | Target Audience & Demographics | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.11.1 |  |  | 0 | 0
1329 | DEL-0030 | TSK-01320 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.11.1.2 | 1.3.11.1 | Internal Review & Critique | Target Audience & Demographics | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.11.1.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.11.2 | 1.3.11 | Client Review & Revisions | Target Audience & Demographics | Client Review & Revisions |  |  | 0 | 84 | 3 | 1.3.11.1.2 |  |  | 0 | 0
1326 | DEL-0030 | TSK-01317 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.11.2.1 | 1.3.11.2 | Client Review & Revisions | Target Audience & Demographics | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.11.2 |  |  | 0 | 0
1327 | DEL-0030 | TSK-01318 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.11.2.2 | 1.3.11.2 | Client Review & Revisions | Target Audience & Demographics | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.11.2.1 |  |  | 0 | 0
| DEL-0030 |  | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.11.3 | 1.3.11 | Audience Definition | Target Audience & Demographics | Audience Definition |  |  | 0 | 89 | 0 | 1.3.11.2.2 |  |  | 0 | 0
1324 | DEL-0030 | TSK-01315 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.11.3.1 | 1.3.11.3 | Audience Definition | Target Audience & Demographics | Audience Definition | Analyst | Mid | 3 |  |  | 1.3.11.3 |  |  | 0 | 0
1325 | DEL-0030 | TSK-01316 | Paid Media | Paid Media Strategy | Casa-Dragones-Digital-MKT-RFP | 1.3.11.3.2 | 1.3.11.3 | Audience Definition | Target Audience & Demographics | Audience Definition | Media Strategist | Mid | 3 |  |  | 1.3.11.3.1 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4 | 1 | Paid Media Planning |  |  |  |  | 82 | 89 | 33 | 1.3 |  | Advanced/T2_MediumVolume | 195 | 15990
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1 | 1.4 | Media Planning Deck | Media Planning Deck |  |  |  | 19 | 89 | 16 | 1.4 |  |  | 195 | 3705
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.1 | 1.4.1 | Deck Narrative | Media Planning Deck | Deck Narrative |  |  | 0 | 89 | 6 | 1.4.1 |  |  | 0 | 0
1241 | DEL-0029 | TSK-01232 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.1.1 | 1.4.1.1 | Deck Narrative | Media Planning Deck | Deck Narrative | Designer | Mid | 8 |  |  | 1.4.1.1 |  |  | 0 | 0
1240 | DEL-0029 | TSK-01231 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.1.2 | 1.4.1.1 | Deck Narrative | Media Planning Deck | Deck Narrative | Media Strategist | Mid | 4 |  |  | 1.4.1.1.1 |  |  | 0 | 0
1244 | DEL-0029 | TSK-01235 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.1.3 | 1.4.1.1 | Deck Narrative | Media Planning Deck | Deck Narrative | Project Manager | Mid | 2 |  |  | 1.4.1.1.2 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.2 | 1.4.1 | Deck Build | Media Planning Deck | Deck Build |  |  | 0 | 101 | 5 | 1.4.1.1.3 |  |  | 0 | 0
1239 | DEL-0029 | TSK-01230 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.2.1 | 1.4.1.2 | Deck Build | Media Planning Deck | Deck Build | Designer | Mid | 2 |  |  | 1.4.1.2 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.3 | 1.4.1 | Internal Review & Critique | Media Planning Deck | Internal Review & Critique |  |  | 0 | 117 | 2 | 1.4.1.2.1 |  |  | 0 | 0
1242 | DEL-0029 | TSK-01233 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.3.1 | 1.4.1.3 | Internal Review & Critique | Media Planning Deck | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.1.3 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.4 | 1.4.1 | Client Review & Revisions | Media Planning Deck | Client Review & Revisions |  |  | 0 | 119 | 3 | 1.4.1.3.1 |  |  | 0 | 0
1237 | DEL-0029 | TSK-01228 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.4.1 | 1.4.1.4 | Client Review & Revisions | Media Planning Deck | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.4.1.4 |  |  | 0 | 0
1238 | DEL-0029 | TSK-01229 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.1.4.2 | 1.4.1.4 | Client Review & Revisions | Media Planning Deck | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.4.1.4.1 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2 | 1.4 | Paid Media Plan | Paid Media Plan |  |  |  | 29 | 95 | 11 | 1.4.1 |  |  | 195 | 5655
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.1 | 1.4.2 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes |  |  | 0 | 95 | 6 | 1.4.2 |  |  | 0 | 0
1248 | DEL-0029 | TSK-01239 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.1.1 | 1.4.2.1 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes | Designer | Mid | 3 |  |  | 1.4.2.1 |  |  | 0 | 0
1252 | DEL-0029 | TSK-01243 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.1.2 | 1.4.2.1 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes | Media Planner | Mid | 10 |  |  | 1.4.2.1.1 |  |  | 0 | 0
1245 | DEL-0029 | TSK-01236 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.1.3 | 1.4.2.1 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes | Media Strategist | Mid | 10 |  |  | 1.4.2.1.2 |  |  | 0 | 0
1251 | DEL-0029 | TSK-01242 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.1.4 | 1.4.2.1 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes | Project Manager | Mid | 2 |  |  | 1.4.2.1.3 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.2 | 1.4.2 | Internal Review & Critique | Paid Media Plan | Internal Review & Critique |  |  | 0 | 117 | 2 | 1.4.2.1.4 |  |  | 0 | 0
1249 | DEL-0029 | TSK-01240 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.2.1 | 1.4.2.2 | Internal Review & Critique | Paid Media Plan | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.2.2 |  |  | 0 | 0
1250 | DEL-0029 | TSK-01241 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.2.2 | 1.4.2.2 | Internal Review & Critique | Paid Media Plan | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.4.2.2.1 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.3 | 1.4.2 | Client Review & Revisions | Paid Media Plan | Client Review & Revisions |  |  | 0 | 119 | 3 | 1.4.2.2.2 |  |  | 0 | 0
1246 | DEL-0029 | TSK-01237 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.3.1 | 1.4.2.3 | Client Review & Revisions | Paid Media Plan | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.4.2.3 |  |  | 0 | 0
1247 | DEL-0029 | TSK-01238 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.2.3.2 | 1.4.2.3 | Client Review & Revisions | Paid Media Plan | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.4.2.3.1 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3 | 1.4 | Ad Unit & Format POV | Ad Unit & Format POV |  |  |  | 16 | 106 | 16 | 1.4.2 |  |  | 195 | 3120
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.1 | 1.4.3 | Spec Page Build | Ad Unit & Format POV | Spec Page Build |  |  | 0 | 106 | 11 | 1.4.3 |  |  | 0 | 0
1227 | DEL-0029 | TSK-01218 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.1.1 | 1.4.3.1 | Spec Page Build | Ad Unit & Format POV | Spec Page Build | Designer | Mid | 3 |  |  | 1.4.3.1 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.2 | 1.4.3 | Internal Review & Critique | Ad Unit & Format POV | Internal Review & Critique |  |  | 0 | 117 | 2 | 1.4.3.1.1 |  |  | 0 | 0
1223 | DEL-0029 | TSK-01214 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.2.1 | 1.4.3.2 | Internal Review & Critique | Ad Unit & Format POV | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.3.2 |  |  | 0 | 0
1224 | DEL-0029 | TSK-01215 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.2.2 | 1.4.3.2 | Internal Review & Critique | Ad Unit & Format POV | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.4.3.2.1 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.3 | 1.4.3 | Client Review & Revisions | Ad Unit & Format POV | Client Review & Revisions |  |  | 0 | 119 | 3 | 1.4.3.2.2 |  |  | 0 | 0
1220 | DEL-0029 | TSK-01211 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.3.1 | 1.4.3.3 | Client Review & Revisions | Ad Unit & Format POV | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.4.3.3 |  |  | 0 | 0
1221 | DEL-0029 | TSK-01212 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.3.2 | 1.4.3.3 | Client Review & Revisions | Ad Unit & Format POV | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.4.3.3.1 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.4 | 1.4.3 | Spec Matrix & POV | Ad Unit & Format POV | Spec Matrix & POV |  |  | 0 | 122 | 0 | 1.4.3.3.2 |  |  | 0 | 0
1222 | DEL-0029 | TSK-01213 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.4.1 | 1.4.3.4 | Spec Matrix & POV | Ad Unit & Format POV | Spec Matrix & POV | Designer | Mid | 3 |  |  | 1.4.3.4 |  |  | 0 | 0
1225 | DEL-0029 | TSK-01216 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.4.2 | 1.4.3.4 | Spec Matrix & POV | Ad Unit & Format POV | Spec Matrix & POV | Media Planner | Mid | 3 |  |  | 1.4.3.4.1 |  |  | 0 | 0
1226 | DEL-0029 | TSK-01217 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.3.4.3 | 1.4.3.4 | Spec Matrix & POV | Ad Unit & Format POV | Spec Matrix & POV | Media Strategist | Mid | 3 |  |  | 1.4.3.4.2 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4 | 1.4 | Channel & Vendor Evaluation | Channel & Vendor Evaluation |  |  |  | 18 | 117 | 5 | 1.4.3 |  |  | 195 | 3510
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.1 | 1.4.4 | Internal Review & Critique | Channel & Vendor Evaluation | Internal Review & Critique |  |  | 0 | 117 | 2 | 1.4.4 |  |  | 0 | 0
1231 | DEL-0029 | TSK-01222 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.1.1 | 1.4.4.1 | Internal Review & Critique | Channel & Vendor Evaluation | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.4.1 |  |  | 0 | 0
1232 | DEL-0029 | TSK-01223 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.1.2 | 1.4.4.1 | Internal Review & Critique | Channel & Vendor Evaluation | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.4.4.1.1 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.2 | 1.4.4 | Client Review & Revisions | Channel & Vendor Evaluation | Client Review & Revisions |  |  | 0 | 119 | 3 | 1.4.4.1.2 |  |  | 0 | 0
1228 | DEL-0029 | TSK-01219 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.2.1 | 1.4.4.2 | Client Review & Revisions | Channel & Vendor Evaluation | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.4.4.2 |  |  | 0 | 0
1229 | DEL-0029 | TSK-01220 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.2.2 | 1.4.4.2 | Client Review & Revisions | Channel & Vendor Evaluation | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.4.4.2.1 |  |  | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.3 | 1.4.4 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review |  |  | 0 | 122 | 0 | 1.4.4.2.2 |  |  | 0 | 0
1236 | DEL-0029 | TSK-01227 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.3.1 | 1.4.4.3 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review | Account Manager | Mid | 2 |  |  | 1.4.4.3 |  |  | 0 | 0
1230 | DEL-0029 | TSK-01221 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.3.2 | 1.4.4.3 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review | Designer | Mid | 2 |  |  | 1.4.4.3.1 |  |  | 0 | 0
1233 | DEL-0029 | TSK-01224 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.3.3 | 1.4.4.3 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review | Media Planner | Mid | 7 |  |  | 1.4.4.3.2 |  |  | 0 | 0
1234 | DEL-0029 | TSK-01225 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.4.4.3.4 | 1.4.4.3 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review | Media Strategist | Mid | 3 |  |  | 1.4.4.3.3 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5 | 1 | Paid Media Assets |  |  |  |  | 148 | 122 | 23 | 1.4 |  | Advanced/T2_MediumVolume | 195 | 28860
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1 | 1.5 | Awareness Assets (Paid) | Awareness Assets (Paid) |  |  |  | 23 | 122 | 20 | 1.5 |  |  | 195 | 4485
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.1 | 1.5.1 | Concept & Copy | Awareness Assets (Paid) | Concept & Copy |  |  | 0 | 122 | 4 | 1.5.1 |  |  | 0 | 0
897 | DEL-0016 | TSK-00888 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.1.1 | 1.5.1.1 | Concept & Copy | Awareness Assets (Paid) | Concept & Copy | Copywriter | Mid | 3 |  |  | 1.5.1.1 |  |  | 0 | 0
898 | DEL-0016 | TSK-00889 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.1.2 | 1.5.1.1 | Concept & Copy | Awareness Assets (Paid) | Concept & Copy | Creative Director | Lead/Director | 2 |  |  | 1.5.1.1.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.2 | 1.5.1 | Design Explorations (3-4) | Awareness Assets (Paid) | Design Explorations (3-4) |  |  | 0 | 126 | 8 | 1.5.1.1.2 |  |  | 0 | 0
899 | DEL-0016 | TSK-00890 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.2.1 | 1.5.1.2 | Design Explorations (3-4) | Awareness Assets (Paid) | Design Explorations (3-4) | Designer | Mid | 4 |  |  | 1.5.1.2 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.3 | 1.5.1 | Quality Check (Specs/Accessibility) | Awareness Assets (Paid) | Quality Check (Specs/Accessibility) |  |  | 0 | 137 | 3 | 1.5.1.2.1 |  |  | 0 | 0
903 | DEL-0016 | TSK-00894 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.3.1 | 1.5.1.3 | Quality Check (Specs/Accessibility) | Awareness Assets (Paid) | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.5.1.3 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.4 | 1.5.1 | Internal Review & Critique | Awareness Assets (Paid) | Internal Review & Critique |  |  | 0 | 140 | 2 | 1.5.1.3.1 |  |  | 0 | 0
901 | DEL-0016 | TSK-00892 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.4.1 | 1.5.1.4 | Internal Review & Critique | Awareness Assets (Paid) | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.5.1.4 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.5 | 1.5.1 | Client Review & Revisions | Awareness Assets (Paid) | Client Review & Revisions |  |  | 0 | 142 | 3 | 1.5.1.4.1 |  |  | 0 | 0
893 | DEL-0016 | TSK-00884 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.5.1 | 1.5.1.5 | Client Review & Revisions | Awareness Assets (Paid) | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.1.5 |  |  | 0 | 0
894 | DEL-0016 | TSK-00885 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.5.2 | 1.5.1.5 | Client Review & Revisions | Awareness Assets (Paid) | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.5.1.5.1 |  |  | 0 | 0
895 | DEL-0016 | TSK-00886 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.5.3 | 1.5.1.5 | Client Review & Revisions | Awareness Assets (Paid) | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.5.1.5.2 |  |  | 0 | 0
896 | DEL-0016 | TSK-00887 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.5.4 | 1.5.1.5 | Client Review & Revisions | Awareness Assets (Paid) | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.5.1.5.3 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.6 | 1.5.1 | Final Packaging | Awareness Assets (Paid) | Final Packaging |  |  | 0 | 145 | 0 | 1.5.1.5.4 |  |  | 0 | 0
900 | DEL-0016 | TSK-00891 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.1.6.1 | 1.5.1.6 | Final Packaging | Awareness Assets (Paid) | Final Packaging | Designer | Mid | 5 |  |  | 1.5.1.6 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2 | 1.5 | Unique Assets | Unique Assets |  |  |  | 18 | 122 | 12 | 1.5.1 |  |  | 195 | 3510
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.1 | 1.5.2 | Build & Polish | Unique Assets | Build & Polish |  |  | 0 | 122 | 4 | 1.5.2 |  |  | 0 | 0
963 | DEL-0016 | TSK-00954 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.1.1 | 1.5.2.1 | Build & Polish | Unique Assets | Build & Polish | Designer | Mid | 3 |  |  | 1.5.2.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.2 | 1.5.2 | Quality Check (Specs/Accessibility) | Unique Assets | Quality Check (Specs/Accessibility) |  |  | 0 | 137 | 3 | 1.5.2.1.1 |  |  | 0 | 0
972 | DEL-0016 | TSK-00963 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.2.1 | 1.5.2.2 | Quality Check (Specs/Accessibility) | Unique Assets | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.5.2.2 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.3 | 1.5.2 | Internal Review & Critique | Unique Assets | Internal Review & Critique |  |  | 0 | 140 | 2 | 1.5.2.2.1 |  |  | 0 | 0
970 | DEL-0016 | TSK-00961 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.3.1 | 1.5.2.3 | Internal Review & Critique | Unique Assets | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.5.2.3 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.4 | 1.5.2 | Client Review & Revisions | Unique Assets | Client Review & Revisions |  |  | 0 | 142 | 3 | 1.5.2.3.1 |  |  | 0 | 0
964 | DEL-0016 | TSK-00955 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.4.1 | 1.5.2.4 | Client Review & Revisions | Unique Assets | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.2.4 |  |  | 0 | 0
965 | DEL-0016 | TSK-00956 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.4.2 | 1.5.2.4 | Client Review & Revisions | Unique Assets | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.5.2.4.1 |  |  | 0 | 0
966 | DEL-0016 | TSK-00957 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.4.3 | 1.5.2.4 | Client Review & Revisions | Unique Assets | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.5.2.4.2 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.5 | 1.5.2 | Custom Concept | Unique Assets | Custom Concept |  |  | 0 | 145 | 0 | 1.5.2.4.3 |  |  | 0 | 0
967 | DEL-0016 | TSK-00958 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.5.1 | 1.5.2.5 | Custom Concept | Unique Assets | Custom Concept | Copywriter | Mid | 2 |  |  | 1.5.2.5 |  |  | 0 | 0
968 | DEL-0016 | TSK-00959 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.2.5.2 | 1.5.2.5 | Custom Concept | Unique Assets | Custom Concept | Designer | Mid | 5 |  |  | 1.5.2.5.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3 | 1.5 | Conversion Assets (Paid) | Conversion Assets (Paid) |  |  |  | 20 | 126 | 16 | 1.5.2 |  |  | 195 | 3900
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.1 | 1.5.3 | Design Variants (3-4) | Conversion Assets (Paid) | Design Variants (3-4) |  |  | 0 | 126 | 8 | 1.5.3 |  |  | 0 | 0
909 | DEL-0016 | TSK-00900 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.1.1 | 1.5.3.1 | Design Variants (3-4) | Conversion Assets (Paid) | Design Variants (3-4) | Designer | Mid | 4 |  |  | 1.5.3.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.2 | 1.5.3 | Quality Check (Specs/Accessibility) | Conversion Assets (Paid) | Quality Check (Specs/Accessibility) |  |  | 0 | 137 | 3 | 1.5.3.1.1 |  |  | 0 | 0
914 | DEL-0016 | TSK-00905 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.2.1 | 1.5.3.2 | Quality Check (Specs/Accessibility) | Conversion Assets (Paid) | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.5.3.2 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.3 | 1.5.3 | Internal Review & Critique | Conversion Assets (Paid) | Internal Review & Critique |  |  | 0 | 140 | 2 | 1.5.3.2.1 |  |  | 0 | 0
911 | DEL-0016 | TSK-00902 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.3.1 | 1.5.3.3 | Internal Review & Critique | Conversion Assets (Paid) | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.5.3.3 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.4 | 1.5.3 | Client Review & Revisions | Conversion Assets (Paid) | Client Review & Revisions |  |  | 0 | 142 | 3 | 1.5.3.3.1 |  |  | 0 | 0
905 | DEL-0016 | TSK-00896 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.4.1 | 1.5.3.4 | Client Review & Revisions | Conversion Assets (Paid) | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.3.4 |  |  | 0 | 0
906 | DEL-0016 | TSK-00897 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.4.2 | 1.5.3.4 | Client Review & Revisions | Conversion Assets (Paid) | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.5.3.4.1 |  |  | 0 | 0
907 | DEL-0016 | TSK-00898 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.4.3 | 1.5.3.4 | Client Review & Revisions | Conversion Assets (Paid) | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.5.3.4.2 |  |  | 0 | 0
908 | DEL-0016 | TSK-00899 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.4.4 | 1.5.3.4 | Client Review & Revisions | Conversion Assets (Paid) | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.5.3.4.3 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.5 | 1.5.3 | Final Packaging | Conversion Assets (Paid) | Final Packaging |  |  | 0 | 145 | 0 | 1.5.3.4.4 |  |  | 0 | 0
913 | DEL-0016 | TSK-00904 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.5.1 | 1.5.3.5 | Final Packaging | Conversion Assets (Paid) | Final Packaging | Copywriter | Mid | 2 |  |  | 1.5.3.5 |  |  | 0 | 0
910 | DEL-0016 | TSK-00901 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.3.5.2 | 1.5.3.5 | Final Packaging | Conversion Assets (Paid) | Final Packaging | Designer | Mid | 5 |  |  | 1.5.3.5.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.4 | 1.5 | National Spotify Audio (Paid) | National Spotify Audio (Paid) |  |  |  | 19 | 134 | 3 | 1.5.3 |  |  | 195 | 3705
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.4.1 | 1.5.4 | Client Review & Revisions | National Spotify Audio (Paid) | Client Review & Revisions |  |  | 0 | 134 | 3 | 1.5.4 |  |  | 0 | 0
926 | DEL-0016 | TSK-00917 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.4.1.1 | 1.5.4.1 | Client Review & Revisions | National Spotify Audio (Paid) | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.5.4.1 |  |  | 0 | 0
931 | DEL-0016 | TSK-00922 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.4.1.2 | 1.5.4.1 | Client Review & Revisions | National Spotify Audio (Paid) | Client Review & Revisions | Art Director | Lead/Director | 2 |  |  | 1.5.4.1.1 |  |  | 0 | 0
927 | DEL-0016 | TSK-00918 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.4.1.3 | 1.5.4.1 | Client Review & Revisions | National Spotify Audio (Paid) | Client Review & Revisions | Copywriter | Mid | 4 |  |  | 1.5.4.1.2 |  |  | 0 | 0
928 | DEL-0016 | TSK-00919 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.4.1.4 | 1.5.4.1 | Client Review & Revisions | National Spotify Audio (Paid) | Client Review & Revisions | Creative Director | Lead/Director | 4 |  |  | 1.5.4.1.3 |  |  | 0 | 0
930 | DEL-0016 | TSK-00921 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.4.1.5 | 1.5.4.1 | Client Review & Revisions | National Spotify Audio (Paid) | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.5.4.1.4 |  |  | 0 | 0
929 | DEL-0016 | TSK-00920 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.4.1.6 | 1.5.4.1 | Client Review & Revisions | National Spotify Audio (Paid) | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.5.4.1.5 |  |  | 0 | 0
925 | DEL-0016 | TSK-00916 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.4.1.7 | 1.5.4.1 | Client Review & Revisions | National Spotify Audio (Paid) | Client Review & Revisions | Sound Designer | Mid | 5 |  |  | 1.5.4.1.6 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.5 | 1.5 | Regional Spotify Audio (Paid) | Regional Spotify Audio (Paid) |  |  |  | 19 | 134 | 3 | 1.5.4 |  |  | 195 | 3705
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.5.1 | 1.5.5 | Client Review & Revisions | Regional Spotify Audio (Paid) | Client Review & Revisions |  |  | 0 | 134 | 3 | 1.5.5 |  |  | 0 | 0
945 | DEL-0016 | TSK-00936 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.5.1.1 | 1.5.5.1 | Client Review & Revisions | Regional Spotify Audio (Paid) | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.5.5.1 |  |  | 0 | 0
950 | DEL-0016 | TSK-00941 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.5.1.2 | 1.5.5.1 | Client Review & Revisions | Regional Spotify Audio (Paid) | Client Review & Revisions | Art Director | Lead/Director | 2 |  |  | 1.5.5.1.1 |  |  | 0 | 0
946 | DEL-0016 | TSK-00937 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.5.1.3 | 1.5.5.1 | Client Review & Revisions | Regional Spotify Audio (Paid) | Client Review & Revisions | Copywriter | Mid | 4 |  |  | 1.5.5.1.2 |  |  | 0 | 0
947 | DEL-0016 | TSK-00938 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.5.1.4 | 1.5.5.1 | Client Review & Revisions | Regional Spotify Audio (Paid) | Client Review & Revisions | Creative Director | Lead/Director | 4 |  |  | 1.5.5.1.3 |  |  | 0 | 0
949 | DEL-0016 | TSK-00940 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.5.1.5 | 1.5.5.1 | Client Review & Revisions | Regional Spotify Audio (Paid) | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.5.5.1.4 |  |  | 0 | 0
948 | DEL-0016 | TSK-00939 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.5.1.6 | 1.5.5.1 | Client Review & Revisions | Regional Spotify Audio (Paid) | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.5.5.1.5 |  |  | 0 | 0
944 | DEL-0016 | TSK-00935 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.5.1.7 | 1.5.5.1 | Client Review & Revisions | Regional Spotify Audio (Paid) | Client Review & Revisions | Sound Designer | Mid | 5 |  |  | 1.5.5.1.6 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6 | 1.5 | National Pinterest assets (Paid) | National Pinterest assets (Paid) |  |  |  | 16 | 137 | 8 | 1.5.5 |  |  | 195 | 3120
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.1 | 1.5.6 | Quality Check (Specs/Accessibility) | National Pinterest assets (Paid) | Quality Check (Specs/Accessibility) |  |  | 0 | 137 | 3 | 1.5.6 |  |  | 0 | 0
923 | DEL-0016 | TSK-00914 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.1.1 | 1.5.6.1 | Quality Check (Specs/Accessibility) | National Pinterest assets (Paid) | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.5.6.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.2 | 1.5.6 | Internal Review & Critique | National Pinterest assets (Paid) | Internal Review & Critique |  |  | 0 | 140 | 2 | 1.5.6.1.1 |  |  | 0 | 0
921 | DEL-0016 | TSK-00912 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.2.1 | 1.5.6.2 | Internal Review & Critique | National Pinterest assets (Paid) | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.5.6.2 |  |  | 0 | 0
922 | DEL-0016 | TSK-00913 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.2.2 | 1.5.6.2 | Internal Review & Critique | National Pinterest assets (Paid) | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.5.6.2.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.3 | 1.5.6 | Client Review & Revisions | National Pinterest assets (Paid) | Client Review & Revisions |  |  | 0 | 142 | 3 | 1.5.6.2.2 |  |  | 0 | 0
916 | DEL-0016 | TSK-00907 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.3.1 | 1.5.6.3 | Client Review & Revisions | National Pinterest assets (Paid) | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.6.3 |  |  | 0 | 0
917 | DEL-0016 | TSK-00908 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.3.2 | 1.5.6.3 | Client Review & Revisions | National Pinterest assets (Paid) | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.5.6.3.1 |  |  | 0 | 0
918 | DEL-0016 | TSK-00909 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.3.3 | 1.5.6.3 | Client Review & Revisions | National Pinterest assets (Paid) | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.5.6.3.2 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.4 | 1.5.6 | Concept & Layouts (2-3) | National Pinterest assets (Paid) | Concept & Layouts (2-3) |  |  | 0 | 145 | 0 | 1.5.6.3.3 |  |  | 0 | 0
919 | DEL-0016 | TSK-00910 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.6.4.1 | 1.5.6.4 | Concept & Layouts (2-3) | National Pinterest assets (Paid) | Concept & Layouts (2-3) | Designer | Mid | 7 |  |  | 1.5.6.4 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7 | 1.5 | Regional Pinterest assets (Paid) | Regional Pinterest assets (Paid) |  |  |  | 16 | 137 | 8 | 1.5.6 |  |  | 195 | 3120
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.1 | 1.5.7 | Quality Check (Specs/Accessibility) | Regional Pinterest assets (Paid) | Quality Check (Specs/Accessibility) |  |  | 0 | 137 | 3 | 1.5.7 |  |  | 0 | 0
942 | DEL-0016 | TSK-00933 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.1.1 | 1.5.7.1 | Quality Check (Specs/Accessibility) | Regional Pinterest assets (Paid) | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.5.7.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.2 | 1.5.7 | Internal Review & Critique | Regional Pinterest assets (Paid) | Internal Review & Critique |  |  | 0 | 140 | 2 | 1.5.7.1.1 |  |  | 0 | 0
940 | DEL-0016 | TSK-00931 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.2.1 | 1.5.7.2 | Internal Review & Critique | Regional Pinterest assets (Paid) | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.5.7.2 |  |  | 0 | 0
941 | DEL-0016 | TSK-00932 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.2.2 | 1.5.7.2 | Internal Review & Critique | Regional Pinterest assets (Paid) | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.5.7.2.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.3 | 1.5.7 | Client Review & Revisions | Regional Pinterest assets (Paid) | Client Review & Revisions |  |  | 0 | 142 | 3 | 1.5.7.2.2 |  |  | 0 | 0
935 | DEL-0016 | TSK-00926 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.3.1 | 1.5.7.3 | Client Review & Revisions | Regional Pinterest assets (Paid) | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.7.3 |  |  | 0 | 0
936 | DEL-0016 | TSK-00927 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.3.2 | 1.5.7.3 | Client Review & Revisions | Regional Pinterest assets (Paid) | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.5.7.3.1 |  |  | 0 | 0
937 | DEL-0016 | TSK-00928 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.3.3 | 1.5.7.3 | Client Review & Revisions | Regional Pinterest assets (Paid) | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.5.7.3.2 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.4 | 1.5.7 | Concept & Layouts (2-3) | Regional Pinterest assets (Paid) | Concept & Layouts (2-3) |  |  | 0 | 145 | 0 | 1.5.7.3.3 |  |  | 0 | 0
938 | DEL-0016 | TSK-00929 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.7.4.1 | 1.5.7.4 | Concept & Layouts (2-3) | Regional Pinterest assets (Paid) | Concept & Layouts (2-3) | Designer | Mid | 7 |  |  | 1.5.7.4 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8 | 1.5 | Resize Assets | Resize Assets |  |  |  | 17 | 137 | 8 | 1.5.7 |  |  | 195 | 3315
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.1 | 1.5.8 | Quality Check (Specs/Accessibility) | Resize Assets | Quality Check (Specs/Accessibility) |  |  | 0 | 137 | 3 | 1.5.8 |  |  | 0 | 0
960 | DEL-0016 | TSK-00951 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.1.1 | 1.5.8.1 | Quality Check (Specs/Accessibility) | Resize Assets | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 6 |  |  | 1.5.8.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.2 | 1.5.8 | Internal Review & Critique | Resize Assets | Internal Review & Critique |  |  | 0 | 140 | 2 | 1.5.8.1.1 |  |  | 0 | 0
958 | DEL-0016 | TSK-00949 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.2.1 | 1.5.8.2 | Internal Review & Critique | Resize Assets | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.5.8.2 |  |  | 0 | 0
959 | DEL-0016 | TSK-00950 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.2.2 | 1.5.8.2 | Internal Review & Critique | Resize Assets | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.5.8.2.1 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.3 | 1.5.8 | Client Review & Revisions | Resize Assets | Client Review & Revisions |  |  | 0 | 142 | 3 | 1.5.8.2.2 |  |  | 0 | 0
954 | DEL-0016 | TSK-00945 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.3.1 | 1.5.8.3 | Client Review & Revisions | Resize Assets | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.8.3 |  |  | 0 | 0
955 | DEL-0016 | TSK-00946 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.3.2 | 1.5.8.3 | Client Review & Revisions | Resize Assets | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.5.8.3.1 |  |  | 0 | 0
956 | DEL-0016 | TSK-00947 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.3.3 | 1.5.8.3 | Client Review & Revisions | Resize Assets | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.5.8.3.2 |  |  | 0 | 0
| DEL-0016 |  | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.4 | 1.5.8 | Final Packaging | Resize Assets | Final Packaging |  |  | 0 | 145 | 0 | 1.5.8.3.3 |  |  | 0 | 0
957 | DEL-0016 | TSK-00948 | Creative | Paid Media Assets | Casa-Dragones-Digital-MKT-RFP | 1.5.8.4.1 | 1.5.8.4 | Final Packaging | Resize Assets | Final Packaging | Designer | Mid | 5 |  |  | 1.5.8.4 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6 | 1 | Reporting |  |  |  |  | 69 | 145 | 19 | 1.5 |  | Advanced/T2_MediumVolume | 195 | 13455
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.1 | 1.6 | Campaign Reporting (Quarterly) | Campaign Reporting (Quarterly) |  |  |  | 14 | 145 | 4 | 1.6 |  |  | 195 | 2730
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.1.1 | 1.6.1 | Design Polish | Campaign Reporting (Quarterly) | Design Polish |  |  | 0 | 145 | 4 | 1.6.1 |  |  | 0 | 0
1355 | DEL-0032 | TSK-01346 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.1.1.1 | 1.6.1.1 | Design Polish | Campaign Reporting (Quarterly) | Design Polish | Designer | Mid | 3 |  |  | 1.6.1.1 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.1.2 | 1.6.1 | Data Deep Dive | Campaign Reporting (Quarterly) | Data Deep Dive |  |  | 0 | 164 | 0 | 1.6.1.1.1 |  |  | 0 | 0
1353 | DEL-0032 | TSK-01344 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.1.2.1 | 1.6.1.2 | Data Deep Dive | Campaign Reporting (Quarterly) | Data Deep Dive | Analyst | Mid | 3 |  |  | 1.6.1.2 |  |  | 0 | 0
1356 | DEL-0032 | TSK-01347 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.1.2.2 | 1.6.1.2 | Data Deep Dive | Campaign Reporting (Quarterly) | Data Deep Dive | Creative Director | Lead/Director | 2 |  |  | 1.6.1.2.1 |  |  | 0 | 0
1357 | DEL-0032 | TSK-01348 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.1.2.3 | 1.6.1.2 | Data Deep Dive | Campaign Reporting (Quarterly) | Data Deep Dive | Media Strategist | Mid | 3 |  |  | 1.6.1.2.2 |  |  | 0 | 0
1354 | DEL-0032 | TSK-01345 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.1.2.4 | 1.6.1.2 | Data Deep Dive | Campaign Reporting (Quarterly) | Data Deep Dive | QA Specialist | Mid | 3 |  |  | 1.6.1.2.3 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.2 | 1.6 | Campaign Reporting (Bi-Weekly) | Campaign Reporting (Bi-Weekly) |  |  |  | 10 | 149 | 7 | 1.6.1 |  |  | 195 | 1950
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.2.1 | 1.6.2 | Data Refresh & QA | Campaign Reporting (Bi-Weekly) | Data Refresh & QA |  |  | 0 | 149 | 3 | 1.6.2 |  |  | 0 | 0
1350 | DEL-0032 | TSK-01341 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.2.1.1 | 1.6.2.1 | Data Refresh & QA | Campaign Reporting (Bi-Weekly) | Data Refresh & QA | Analyst | Mid | 3 |  |  | 1.6.2.1 |  |  | 0 | 0
1351 | DEL-0032 | TSK-01342 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.2.1.2 | 1.6.2.1 | Data Refresh & QA | Campaign Reporting (Bi-Weekly) | Data Refresh & QA | QA Specialist | Mid | 3 |  |  | 1.6.2.1.1 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.2.2 | 1.6.2 | Client Summary | Campaign Reporting (Bi-Weekly) | Client Summary |  |  | 0 | 156 | 4 | 1.6.2.1.2 |  |  | 0 | 0
1349 | DEL-0032 | TSK-01340 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.2.2.1 | 1.6.2.2 | Client Summary | Campaign Reporting (Bi-Weekly) | Client Summary | Account Manager | Mid | 1 |  |  | 1.6.2.2 |  |  | 0 | 0
1352 | DEL-0032 | TSK-01343 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.2.2.2 | 1.6.2.2 | Client Summary | Campaign Reporting (Bi-Weekly) | Client Summary | Media Strategist | Mid | 3 |  |  | 1.6.2.2.1 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.3 | 1.6 | Campaign Tracking | Campaign Tracking |  |  |  | 8 | 149 | 7 | 1.6.2 |  |  | 195 | 1560
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.3.1 | 1.6.3 | QA Spot Check | Campaign Tracking | QA Spot Check |  |  | 0 | 149 | 3 | 1.6.3 |  |  | 0 | 0
1358 | DEL-0032 | TSK-01349 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.3.1.1 | 1.6.3.1 | QA Spot Check | Campaign Tracking | QA Spot Check | QA Specialist | Mid | 3 |  |  | 1.6.3.1 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.3.2 | 1.6.3 | Tracker Update | Campaign Tracking | Tracker Update |  |  | 0 | 152 | 4 | 1.6.3.1.1 |  |  | 0 | 0
1359 | DEL-0032 | TSK-01350 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.3.2.1 | 1.6.3.2 | Tracker Update | Campaign Tracking | Tracker Update | Analyst | Mid | 5 |  |  | 1.6.3.2 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.4 | 1.6 | Dashboard Analytics | Dashboard Analytics |  |  |  | 9 | 149 | 7 | 1.6.3 |  |  | 195 | 1755
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.4.1 | 1.6.4 | QA & Calc Checks | Dashboard Analytics | QA & Calc Checks |  |  | 0 | 149 | 3 | 1.6.4 |  |  | 0 | 0
1361 | DEL-0032 | TSK-01352 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.4.1.1 | 1.6.4.1 | QA & Calc Checks | Dashboard Analytics | QA & Calc Checks | QA Specialist | Mid | 3 |  |  | 1.6.4.1 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.4.2 | 1.6.4 | Dashboard Build/Refresh | Dashboard Analytics | Dashboard Build/Refresh |  |  | 0 | 156 | 4 | 1.6.4.1.1 |  |  | 0 | 0
1360 | DEL-0032 | TSK-01351 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.4.2.1 | 1.6.4.2 | Dashboard Build/Refresh | Dashboard Analytics | Dashboard Build/Refresh | Analyst | Mid | 6 |  |  | 1.6.4.2 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.5 | 1.6 | Reporting & Ad-Tagging Support | Reporting & Ad-Tagging Support |  |  |  | 8 | 149 | 7 | 1.6.4 |  |  | 195 | 1560
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.5.1 | 1.6.5 | QA | Reporting & Ad-Tagging Support | QA |  |  | 0 | 149 | 3 | 1.6.5 |  |  | 0 | 0
1369 | DEL-0032 | TSK-01360 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.5.1.1 | 1.6.5.1 | QA | Reporting & Ad-Tagging Support | QA | QA Specialist | Mid | 3 |  |  | 1.6.5.1 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.5.2 | 1.6.5 | UTM/Tag Guidance | Reporting & Ad-Tagging Support | UTM/Tag Guidance |  |  | 0 | 152 | 4 | 1.6.5.1.1 |  |  | 0 | 0
1371 | DEL-0032 | TSK-01362 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.5.2.1 | 1.6.5.2 | UTM/Tag Guidance | Reporting & Ad-Tagging Support | UTM/Tag Guidance | Media Strategist | Mid | 3 |  |  | 1.6.5.2 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.5.3 | 1.6.5 | Tagging Support | Reporting & Ad-Tagging Support | Tagging Support |  |  | 0 | 164 | 0 | 1.6.5.2.1 |  |  | 0 | 0
1370 | DEL-0032 | TSK-01361 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.5.3.1 | 1.6.5.3 | Tagging Support | Reporting & Ad-Tagging Support | Tagging Support | Ad Ops / Trafficker | Mid | 2 |  |  | 1.6.5.3 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.6 | 1.6 | Dashboard Maintenance | Dashboard Maintenance |  |  |  | 7 | 156 | 4 | 1.6.5 |  |  | 195 | 1365
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.6.1 | 1.6.6 | Connector Checks & Fixes | Dashboard Maintenance | Connector Checks & Fixes |  |  | 0 | 156 | 4 | 1.6.6 |  |  | 0 | 0
1362 | DEL-0032 | TSK-01353 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.6.1.1 | 1.6.6.1 | Connector Checks & Fixes | Dashboard Maintenance | Connector Checks & Fixes | Analyst | Mid | 6 |  |  | 1.6.6.1 |  |  | 0 | 0
1363 | DEL-0032 | TSK-01354 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.6.1.2 | 1.6.6.1 | Connector Checks & Fixes | Dashboard Maintenance | Connector Checks & Fixes | Project Manager | Mid | 1 |  |  | 1.6.6.1.1 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.7 | 1.6 | Reconcilliation & Media Budget Authorization | Reconcilliation & Media Budget Authorization |  |  |  | 5 | 160 | 2 | 1.6.6 |  |  | 195 | 975
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.7.1 | 1.6.7 | Authorization & Docs | Reconcilliation & Media Budget Authorization | Authorization & Docs |  |  | 0 | 160 | 2 | 1.6.7 |  |  | 0 | 0
1366 | DEL-0032 | TSK-01357 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.7.1.1 | 1.6.7.1 | Authorization & Docs | Reconcilliation & Media Budget Authorization | Authorization & Docs | Account Manager | Mid | 2 |  |  | 1.6.7.1 |  |  | 0 | 0
1368 | DEL-0032 | TSK-01359 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.7.1.2 | 1.6.7.1 | Authorization & Docs | Reconcilliation & Media Budget Authorization | Authorization & Docs | Media Buyer | Mid | 1 |  |  | 1.6.7.1.1 |  |  | 0 | 0
1367 | DEL-0032 | TSK-01358 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.7.1.3 | 1.6.7.1 | Authorization & Docs | Reconcilliation & Media Budget Authorization | Authorization & Docs | Project Manager | Mid | 2 |  |  | 1.6.7.1.2 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.8 | 1.6 | KPI Monitoring | KPI Monitoring |  |  |  | 4 | 162 | 2 | 1.6.7 |  |  | 195 | 780
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.8.1 | 1.6.8 | Weekly KPI Scan | KPI Monitoring | Weekly KPI Scan |  |  | 0 | 162 | 2 | 1.6.8 |  |  | 0 | 0
1365 | DEL-0032 | TSK-01356 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.8.1.1 | 1.6.8.1 | Weekly KPI Scan | KPI Monitoring | Weekly KPI Scan | Analyst | Mid | 1 |  |  | 1.6.8.1 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.8.2 | 1.6.8 | Notes & Flags | KPI Monitoring | Notes & Flags |  |  | 0 | 164 | 0 | 1.6.8.1.1 |  |  | 0 | 0
1364 | DEL-0032 | TSK-01355 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.8.2.1 | 1.6.8.2 | Notes & Flags | KPI Monitoring | Notes & Flags | Media Strategist | Mid | 3 |  |  | 1.6.8.2 |  |  | 0 | 0
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.9 | 1.6 | Ad-Platform Reporting | Ad-Platform Reporting |  |  |  | 4 | 164 | 0 | 1.6.8 |  |  | 195 | 780
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.9.1 | 1.6.9 | Distribution | Ad-Platform Reporting | Distribution |  |  | 0 | 164 | 0 | 1.6.9 |  |  | 0 | 0
1348 | DEL-0032 | TSK-01339 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.9.1.1 | 1.6.9.1 | Distribution | Ad-Platform Reporting | Distribution | Analyst | Mid | 3 |  |  | 1.6.9.1 |  |  | 0 | 0
1347 | DEL-0032 | TSK-01338 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.6.9.1.2 | 1.6.9.1 | Distribution | Ad-Platform Reporting | Distribution | Project Manager | Mid | 1 |  |  | 1.6.9.1.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7 | 1 | Brand Style & Usage Guidelines |  |  |  |  | 294 | 164 | 11 | 1.6 |  | Advanced/T2_MediumVolume | 195 | 57330
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.1 | 1.7 | Color Palettes | Color Palettes |  |  |  | 16 | 164 | 3 | 1.7 |  |  | 195 | 3120
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.1.1 | 1.7.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions |  |  | 0 | 164 | 3 | 1.7.1 |  |  | 0 | 0
579 | DEL-0009 | TSK-00570 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.1.1.1 | 1.7.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.7.1.1 |  |  | 0 | 0
583 | DEL-0009 | TSK-00574 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.1.1.2 | 1.7.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Art Director | Lead/Director | 2 |  |  | 1.7.1.1.1 |  |  | 0 | 0
580 | DEL-0009 | TSK-00571 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.1.1.3 | 1.7.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Creative Director | Lead/Director | 4 |  |  | 1.7.1.1.2 |  |  | 0 | 0
582 | DEL-0009 | TSK-00573 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.1.1.4 | 1.7.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Designer | Mid | 5 |  |  | 1.7.1.1.3 |  |  | 0 | 0
581 | DEL-0009 | TSK-00572 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.1.1.5 | 1.7.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.7.1.1.4 |  |  | 0 | 0
578 | DEL-0009 | TSK-00569 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.1.1.6 | 1.7.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | QA Specialist | Mid | 3 |  |  | 1.7.1.1.5 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2 | 1.7 | Logo Lock-Ups | Logo Lock-Ups |  |  |  | 33 | 167 | 8 | 1.7.1 |  |  | 195 | 6435
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.1 | 1.7.2 | Quality Check (Specs/Accessibility) | Logo Lock-Ups | Quality Check (Specs/Accessibility) |  |  | 0 | 167 | 3 | 1.7.2 |  |  | 0 | 0
626 | DEL-0009 | TSK-00617 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.1.1 | 1.7.2.1 | Quality Check (Specs/Accessibility) | Logo Lock-Ups | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.7.2.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.2 | 1.7.2 | Internal Review & Critique | Logo Lock-Ups | Internal Review & Critique |  |  | 0 | 170 | 2 | 1.7.2.1.1 |  |  | 0 | 0
622 | DEL-0009 | TSK-00613 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.2.1 | 1.7.2.2 | Internal Review & Critique | Logo Lock-Ups | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.7.2.2 |  |  | 0 | 0
623 | DEL-0009 | TSK-00614 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.2.2 | 1.7.2.2 | Internal Review & Critique | Logo Lock-Ups | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.7.2.2.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.3 | 1.7.2 | Client Review & Revisions | Logo Lock-Ups | Client Review & Revisions |  |  | 0 | 172 | 3 | 1.7.2.2.2 |  |  | 0 | 0
618 | DEL-0009 | TSK-00609 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.3.1 | 1.7.2.3 | Client Review & Revisions | Logo Lock-Ups | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.7.2.3 |  |  | 0 | 0
619 | DEL-0009 | TSK-00610 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.3.2 | 1.7.2.3 | Client Review & Revisions | Logo Lock-Ups | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.7.2.3.1 |  |  | 0 | 0
620 | DEL-0009 | TSK-00611 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.3.3 | 1.7.2.3 | Client Review & Revisions | Logo Lock-Ups | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.7.2.3.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.4 | 1.7.2 | Final Packaging | Logo Lock-Ups | Final Packaging |  |  | 0 | 175 | 0 | 1.7.2.3.3 |  |  | 0 | 0
621 | DEL-0009 | TSK-00612 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.2.4.1 | 1.7.2.4 | Final Packaging | Logo Lock-Ups | Final Packaging | Designer | Mid | 24 |  |  | 1.7.2.4 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3 | 1.7 | Logo Placement | Logo Placement |  |  |  | 32 | 167 | 8 | 1.7.2 |  |  | 195 | 6240
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3.1 | 1.7.3 | Quality Check (Specs/Accessibility) | Logo Placement | Quality Check (Specs/Accessibility) |  |  | 0 | 167 | 3 | 1.7.3 |  |  | 0 | 0
635 | DEL-0009 | TSK-00626 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3.1.1 | 1.7.3.1 | Quality Check (Specs/Accessibility) | Logo Placement | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.7.3.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3.2 | 1.7.3 | Internal Review & Critique | Logo Placement | Internal Review & Critique |  |  | 0 | 170 | 2 | 1.7.3.1.1 |  |  | 0 | 0
631 | DEL-0009 | TSK-00622 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3.2.1 | 1.7.3.2 | Internal Review & Critique | Logo Placement | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.7.3.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3.3 | 1.7.3 | Client Review & Revisions | Logo Placement | Client Review & Revisions |  |  | 0 | 172 | 3 | 1.7.3.2.1 |  |  | 0 | 0
627 | DEL-0009 | TSK-00618 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3.3.1 | 1.7.3.3 | Client Review & Revisions | Logo Placement | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.7.3.3 |  |  | 0 | 0
628 | DEL-0009 | TSK-00619 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3.3.2 | 1.7.3.3 | Client Review & Revisions | Logo Placement | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.7.3.3.1 |  |  | 0 | 0
629 | DEL-0009 | TSK-00620 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3.3.3 | 1.7.3.3 | Client Review & Revisions | Logo Placement | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.7.3.3.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3.4 | 1.7.3 | Final Packaging | Logo Placement | Final Packaging |  |  | 0 | 175 | 0 | 1.7.3.3.3 |  |  | 0 | 0
630 | DEL-0009 | TSK-00621 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.3.4.1 | 1.7.3.4 | Final Packaging | Logo Placement | Final Packaging | Designer | Mid | 24 |  |  | 1.7.3.4 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4 | 1.7 | Brand Do's & Dont's | Brand Do's & Dont's |  |  |  | 39 | 170 | 5 | 1.7.3 |  |  | 195 | 7605
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.1 | 1.7.4 | Internal Review & Critique | Brand Do's & Dont's | Internal Review & Critique |  |  | 0 | 170 | 2 | 1.7.4 |  |  | 0 | 0
573 | DEL-0009 | TSK-00564 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.1.1 | 1.7.4.1 | Internal Review & Critique | Brand Do's & Dont's | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.7.4.1 |  |  | 0 | 0
574 | DEL-0009 | TSK-00565 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.1.2 | 1.7.4.1 | Internal Review & Critique | Brand Do's & Dont's | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.7.4.1.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.2 | 1.7.4 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions |  |  | 0 | 172 | 3 | 1.7.4.1.2 |  |  | 0 | 0
568 | DEL-0009 | TSK-00559 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.2.1 | 1.7.4.2 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.7.4.2 |  |  | 0 | 0
569 | DEL-0009 | TSK-00560 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.2.2 | 1.7.4.2 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.7.4.2.1 |  |  | 0 | 0
570 | DEL-0009 | TSK-00561 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.2.3 | 1.7.4.2 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.7.4.2.2 |  |  | 0 | 0
571 | DEL-0009 | TSK-00562 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.2.4 | 1.7.4.2 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.7.4.2.3 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.3 | 1.7.4 | Outline & Examples | Brand Do's & Dont's | Outline & Examples |  |  | 0 | 175 | 0 | 1.7.4.2.4 |  |  | 0 | 0
575 | DEL-0009 | TSK-00566 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.3.1 | 1.7.4.3 | Outline & Examples | Brand Do's & Dont's | Outline & Examples | Copywriter | Mid | 2 |  |  | 1.7.4.3 |  |  | 0 | 0
572 | DEL-0009 | TSK-00563 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.4.3.2 | 1.7.4.3 | Outline & Examples | Brand Do's & Dont's | Outline & Examples | Designer | Mid | 30 |  |  | 1.7.4.3.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5 | 1.7 | Design Style Tile | Design Style Tile |  |  |  | 27 | 170 | 5 | 1.7.4 |  |  | 195 | 5265
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5.1 | 1.7.5 | Internal Review & Critique | Design Style Tile | Internal Review & Critique |  |  | 0 | 170 | 2 | 1.7.5 |  |  | 0 | 0
590 | DEL-0009 | TSK-00581 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5.1.1 | 1.7.5.1 | Internal Review & Critique | Design Style Tile | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.7.5.1 |  |  | 0 | 0
591 | DEL-0009 | TSK-00582 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5.1.2 | 1.7.5.1 | Internal Review & Critique | Design Style Tile | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.7.5.1.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5.2 | 1.7.5 | Client Review & Revisions | Design Style Tile | Client Review & Revisions |  |  | 0 | 172 | 3 | 1.7.5.1.2 |  |  | 0 | 0
586 | DEL-0009 | TSK-00577 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5.2.1 | 1.7.5.2 | Client Review & Revisions | Design Style Tile | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.7.5.2 |  |  | 0 | 0
587 | DEL-0009 | TSK-00578 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5.2.2 | 1.7.5.2 | Client Review & Revisions | Design Style Tile | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.7.5.2.1 |  |  | 0 | 0
588 | DEL-0009 | TSK-00579 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5.2.3 | 1.7.5.2 | Client Review & Revisions | Design Style Tile | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.7.5.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5.3 | 1.7.5 | Style Tile Build | Design Style Tile | Style Tile Build |  |  | 0 | 175 | 0 | 1.7.5.2.3 |  |  | 0 | 0
592 | DEL-0009 | TSK-00583 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5.3.1 | 1.7.5.3 | Style Tile Build | Design Style Tile | Style Tile Build | Art Director | Lead/Director | 1 |  |  | 1.7.5.3 |  |  | 0 | 0
589 | DEL-0009 | TSK-00580 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.5.3.2 | 1.7.5.3 | Style Tile Build | Design Style Tile | Style Tile Build | Designer | Mid | 20 |  |  | 1.7.5.3.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6 | 1.7 | Image Use Guidance | Image Use Guidance |  |  |  | 27 | 170 | 5 | 1.7.5 |  |  | 195 | 5265
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6.1 | 1.7.6 | Internal Review & Critique | Image Use Guidance | Internal Review & Critique |  |  | 0 | 170 | 2 | 1.7.6 |  |  | 0 | 0
608 | DEL-0009 | TSK-00599 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6.1.1 | 1.7.6.1 | Internal Review & Critique | Image Use Guidance | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.7.6.1 |  |  | 0 | 0
609 | DEL-0009 | TSK-00600 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6.1.2 | 1.7.6.1 | Internal Review & Critique | Image Use Guidance | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.7.6.1.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6.2 | 1.7.6 | Client Review & Revisions | Image Use Guidance | Client Review & Revisions |  |  | 0 | 172 | 3 | 1.7.6.1.2 |  |  | 0 | 0
602 | DEL-0009 | TSK-00593 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6.2.1 | 1.7.6.2 | Client Review & Revisions | Image Use Guidance | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.7.6.2 |  |  | 0 | 0
603 | DEL-0009 | TSK-00594 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6.2.2 | 1.7.6.2 | Client Review & Revisions | Image Use Guidance | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.7.6.2.1 |  |  | 0 | 0
604 | DEL-0009 | TSK-00595 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6.2.3 | 1.7.6.2 | Client Review & Revisions | Image Use Guidance | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.7.6.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6.3 | 1.7.6 | Examples & Callouts | Image Use Guidance | Examples & Callouts |  |  | 0 | 175 | 0 | 1.7.6.2.3 |  |  | 0 | 0
607 | DEL-0009 | TSK-00598 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6.3.1 | 1.7.6.3 | Examples & Callouts | Image Use Guidance | Examples & Callouts | Art Director | Lead/Director | 1 |  |  | 1.7.6.3 |  |  | 0 | 0
605 | DEL-0009 | TSK-00596 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.6.3.2 | 1.7.6.3 | Examples & Callouts | Image Use Guidance | Examples & Callouts | Designer | Mid | 20 |  |  | 1.7.6.3.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7 | 1.7 | Imagery Style | Imagery Style |  |  |  | 27 | 170 | 5 | 1.7.6 |  |  | 195 | 5265
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7.1 | 1.7.7 | Internal Review & Critique | Imagery Style | Internal Review & Critique |  |  | 0 | 170 | 2 | 1.7.7 |  |  | 0 | 0
616 | DEL-0009 | TSK-00607 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7.1.1 | 1.7.7.1 | Internal Review & Critique | Imagery Style | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.7.7.1 |  |  | 0 | 0
617 | DEL-0009 | TSK-00608 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7.1.2 | 1.7.7.1 | Internal Review & Critique | Imagery Style | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.7.7.1.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7.2 | 1.7.7 | Client Review & Revisions | Imagery Style | Client Review & Revisions |  |  | 0 | 172 | 3 | 1.7.7.1.2 |  |  | 0 | 0
610 | DEL-0009 | TSK-00601 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7.2.1 | 1.7.7.2 | Client Review & Revisions | Imagery Style | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.7.7.2 |  |  | 0 | 0
611 | DEL-0009 | TSK-00602 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7.2.2 | 1.7.7.2 | Client Review & Revisions | Imagery Style | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.7.7.2.1 |  |  | 0 | 0
612 | DEL-0009 | TSK-00603 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7.2.3 | 1.7.7.2 | Client Review & Revisions | Imagery Style | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.7.7.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7.3 | 1.7.7 | Examples & Callouts | Imagery Style | Examples & Callouts |  |  | 0 | 175 | 0 | 1.7.7.2.3 |  |  | 0 | 0
615 | DEL-0009 | TSK-00606 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7.3.1 | 1.7.7.3 | Examples & Callouts | Imagery Style | Examples & Callouts | Art Director | Lead/Director | 1 |  |  | 1.7.7.3 |  |  | 0 | 0
613 | DEL-0009 | TSK-00604 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.7.3.2 | 1.7.7.3 | Examples & Callouts | Imagery Style | Examples & Callouts | Designer | Mid | 20 |  |  | 1.7.7.3.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8 | 1.7 | Photo & Video Direction | Photo & Video Direction |  |  |  | 29 | 170 | 5 | 1.7.7 |  |  | 195 | 5655
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.1 | 1.7.8 | Internal Review & Critique | Photo & Video Direction | Internal Review & Critique |  |  | 0 | 170 | 2 | 1.7.8 |  |  | 0 | 0
642 | DEL-0009 | TSK-00633 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.1.1 | 1.7.8.1 | Internal Review & Critique | Photo & Video Direction | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.7.8.1 |  |  | 0 | 0
643 | DEL-0009 | TSK-00634 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.1.2 | 1.7.8.1 | Internal Review & Critique | Photo & Video Direction | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.7.8.1.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.2 | 1.7.8 | Client Review & Revisions | Photo & Video Direction | Client Review & Revisions |  |  | 0 | 172 | 3 | 1.7.8.1.2 |  |  | 0 | 0
636 | DEL-0009 | TSK-00627 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.2.1 | 1.7.8.2 | Client Review & Revisions | Photo & Video Direction | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.7.8.2 |  |  | 0 | 0
637 | DEL-0009 | TSK-00628 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.2.2 | 1.7.8.2 | Client Review & Revisions | Photo & Video Direction | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.7.8.2.1 |  |  | 0 | 0
638 | DEL-0009 | TSK-00629 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.2.3 | 1.7.8.2 | Client Review & Revisions | Photo & Video Direction | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.7.8.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.3 | 1.7.8 | Direction Pages | Photo & Video Direction | Direction Pages |  |  | 0 | 175 | 0 | 1.7.8.2.3 |  |  | 0 | 0
639 | DEL-0009 | TSK-00630 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.3.1 | 1.7.8.3 | Direction Pages | Photo & Video Direction | Direction Pages | Art Director | Lead/Director | 1 |  |  | 1.7.8.3 |  |  | 0 | 0
640 | DEL-0009 | TSK-00631 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.3.2 | 1.7.8.3 | Direction Pages | Photo & Video Direction | Direction Pages | Creative Director | Lead/Director | 2 |  |  | 1.7.8.3.1 |  |  | 0 | 0
641 | DEL-0009 | TSK-00632 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.8.3.3 | 1.7.8.3 | Direction Pages | Photo & Video Direction | Direction Pages | Designer | Mid | 20 |  |  | 1.7.8.3.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.9 | 1.7 | Typography | Typography |  |  |  | 21 | 170 | 5 | 1.7.8 |  |  | 195 | 4095
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.9.1 | 1.7.9 | Internal Review & Critique | Typography | Internal Review & Critique |  |  | 0 | 170 | 2 | 1.7.9 |  |  | 0 | 0
649 | DEL-0009 | TSK-00640 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.9.1.1 | 1.7.9.1 | Internal Review & Critique | Typography | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.7.9.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.9.2 | 1.7.9 | Client Review & Revisions | Typography | Client Review & Revisions |  |  | 0 | 172 | 3 | 1.7.9.1.1 |  |  | 0 | 0
645 | DEL-0009 | TSK-00636 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.9.2.1 | 1.7.9.2 | Client Review & Revisions | Typography | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.7.9.2 |  |  | 0 | 0
646 | DEL-0009 | TSK-00637 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.9.2.2 | 1.7.9.2 | Client Review & Revisions | Typography | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.7.9.2.1 |  |  | 0 | 0
647 | DEL-0009 | TSK-00638 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.9.2.3 | 1.7.9.2 | Client Review & Revisions | Typography | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.7.9.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.9.3 | 1.7.9 | Final Packaging | Typography | Final Packaging |  |  | 0 | 175 | 0 | 1.7.9.2.3 |  |  | 0 | 0
648 | DEL-0009 | TSK-00639 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.9.3.1 | 1.7.9.3 | Final Packaging | Typography | Final Packaging | Designer | Mid | 16 |  |  | 1.7.9.3 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.10 | 1.7 | Use Cases | Use Cases |  |  |  | 25 | 170 | 5 | 1.7.9 |  |  | 195 | 4875
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.10.1 | 1.7.10 | Internal Review & Critique | Use Cases | Internal Review & Critique |  |  | 0 | 170 | 2 | 1.7.10 |  |  | 0 | 0
656 | DEL-0009 | TSK-00647 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.10.1.1 | 1.7.10.1 | Internal Review & Critique | Use Cases | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.7.10.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.10.2 | 1.7.10 | Client Review & Revisions | Use Cases | Client Review & Revisions |  |  | 0 | 172 | 3 | 1.7.10.1.1 |  |  | 0 | 0
652 | DEL-0009 | TSK-00643 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.10.2.1 | 1.7.10.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.7.10.2 |  |  | 0 | 0
653 | DEL-0009 | TSK-00644 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.10.2.2 | 1.7.10.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.7.10.2.1 |  |  | 0 | 0
654 | DEL-0009 | TSK-00645 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.10.2.3 | 1.7.10.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.7.10.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.10.3 | 1.7.10 | Final Packaging | Use Cases | Final Packaging |  |  | 0 | 175 | 0 | 1.7.10.2.3 |  |  | 0 | 0
655 | DEL-0009 | TSK-00646 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.10.3.1 | 1.7.10.3 | Final Packaging | Use Cases | Final Packaging | Designer | Mid | 20 |  |  | 1.7.10.3 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.11 | 1.7 | Graphic Treatment Direction | Graphic Treatment Direction |  |  |  | 18 | 175 | 0 | 1.7.10 |  |  | 195 | 3510
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.11.1 | 1.7.11 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions |  |  | 0 | 175 | 0 | 1.7.11 |  |  | 0 | 0
594 | DEL-0009 | TSK-00585 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.11.1.1 | 1.7.11.1 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.7.11.1 |  |  | 0 | 0
598 | DEL-0009 | TSK-00589 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.11.1.2 | 1.7.11.1 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Art Director | Lead/Director | 3 |  |  | 1.7.11.1.1 |  |  | 0 | 0
595 | DEL-0009 | TSK-00586 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.11.1.3 | 1.7.11.1 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Creative Director | Lead/Director | 8 |  |  | 1.7.11.1.2 |  |  | 0 | 0
597 | DEL-0009 | TSK-00588 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.11.1.4 | 1.7.11.1 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.7.11.1.3 |  |  | 0 | 0
596 | DEL-0009 | TSK-00587 | Creative | Brand Style & Usage Guidelines | Casa-Dragones-Digital-MKT-RFP | 1.7.11.1.5 | 1.7.11.1 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.7.11.1.4 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8 | 1 | Reporting |  |  |  |  | 128 | 175 | 7 | 1.7 |  | Advanced/T2_MediumVolume | 195 | 24960
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.1 | 1.8 | Dashboards | Dashboards |  |  |  | 9 | 175 | 7 | 1.8 |  |  | 195 | 1755
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.1.1 | 1.8.1 | QA | Dashboards | QA |  |  | 0 | 175 | 3 | 1.8.1 |  |  | 0 | 0
1116 | DEL-0024 | TSK-01107 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.1.1.1 | 1.8.1.1 | QA | Dashboards | QA | QA Specialist | Mid | 3 |  |  | 1.8.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.1.2 | 1.8.1 | Dashboard Build/Refresh | Dashboards | Dashboard Build/Refresh |  |  | 0 | 178 | 4 | 1.8.1.1.1 |  |  | 0 | 0
1115 | DEL-0024 | TSK-01106 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.1.2.1 | 1.8.1.2 | Dashboard Build/Refresh | Dashboards | Dashboard Build/Refresh | Analyst | Mid | 6 |  |  | 1.8.1.2 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.2 | 1.8 | Engagement Rate | Engagement Rate |  |  |  | 6 | 175 | 3 | 1.8.1 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.2.1 | 1.8.2 | Data Refresh & Calc Check | Engagement Rate | Data Refresh & Calc Check |  |  | 0 | 175 | 3 | 1.8.2 |  |  | 0 | 0
1119 | DEL-0024 | TSK-01110 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.2.1.1 | 1.8.2.1 | Data Refresh & Calc Check | Engagement Rate | Data Refresh & Calc Check | Analyst | Mid | 3 |  |  | 1.8.2.1 |  |  | 0 | 0
1120 | DEL-0024 | TSK-01111 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.2.1.2 | 1.8.2.1 | Data Refresh & Calc Check | Engagement Rate | Data Refresh & Calc Check | QA Specialist | Mid | 3 |  |  | 1.8.2.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.3 | 1.8 | Emplifi Reports | Emplifi Reports |  |  |  | 7 | 178 | 4 | 1.8.2 |  |  | 195 | 1365
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.3.1 | 1.8.3 | Emplifi Extract & Summary | Emplifi Reports | Emplifi Extract & Summary |  |  | 0 | 178 | 4 | 1.8.3 |  |  | 0 | 0
1117 | DEL-0024 | TSK-01108 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.3.1.1 | 1.8.3.1 | Emplifi Extract & Summary | Emplifi Reports | Emplifi Extract & Summary | Account Manager | Mid | 1 |  |  | 1.8.3.1 |  |  | 0 | 0
1118 | DEL-0024 | TSK-01109 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.3.1.2 | 1.8.3.1 | Emplifi Extract & Summary | Emplifi Reports | Emplifi Extract & Summary | Analyst | Mid | 6 |  |  | 1.8.3.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.4 | 1.8 | Monthly Comprehensive Report | Monthly Comprehensive Report |  |  |  | 11 | 178 | 4 | 1.8.3 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.4.1 | 1.8.4 | Monthly Report | Monthly Comprehensive Report | Monthly Report |  |  | 0 | 178 | 4 | 1.8.4 |  |  | 0 | 0
1127 | DEL-0024 | TSK-01118 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.4.1.1 | 1.8.4.1 | Monthly Report | Monthly Comprehensive Report | Monthly Report | Analyst | Mid | 6 |  |  | 1.8.4.1 |  |  | 0 | 0
1128 | DEL-0024 | TSK-01119 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.4.1.2 | 1.8.4.1 | Monthly Report | Monthly Comprehensive Report | Monthly Report | Designer | Mid | 2 |  |  | 1.8.4.1.1 |  |  | 0 | 0
1129 | DEL-0024 | TSK-01120 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.4.1.3 | 1.8.4.1 | Monthly Report | Monthly Comprehensive Report | Monthly Report | Social Strategist | Mid | 3 |  |  | 1.8.4.1.2 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.5 | 1.8 | Monthly Organic Social Report | Monthly Organic Social Report |  |  |  | 11 | 178 | 4 | 1.8.4 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.5.1 | 1.8.5 | Monthly Organic Report | Monthly Organic Social Report | Monthly Organic Report |  |  | 0 | 178 | 4 | 1.8.5 |  |  | 0 | 0
1130 | DEL-0024 | TSK-01121 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.5.1.1 | 1.8.5.1 | Monthly Organic Report | Monthly Organic Social Report | Monthly Organic Report | Analyst | Mid | 6 |  |  | 1.8.5.1 |  |  | 0 | 0
1131 | DEL-0024 | TSK-01122 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.5.1.2 | 1.8.5.1 | Monthly Organic Report | Monthly Organic Social Report | Monthly Organic Report | Designer | Mid | 2 |  |  | 1.8.5.1.1 |  |  | 0 | 0
1132 | DEL-0024 | TSK-01123 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.5.1.3 | 1.8.5.1 | Monthly Organic Report | Monthly Organic Social Report | Monthly Organic Report | Social Strategist | Mid | 3 |  |  | 1.8.5.1.2 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.6 | 1.8 | Optimization Recommendations Report | Optimization Recommendations Report |  |  |  | 10 | 178 | 4 | 1.8.5 |  |  | 195 | 1950
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.6.1 | 1.8.6 | Recs & Next Steps | Optimization Recommendations Report | Recs & Next Steps |  |  | 0 | 178 | 4 | 1.8.6 |  |  | 0 | 0
1133 | DEL-0024 | TSK-01124 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.6.1.1 | 1.8.6.1 | Recs & Next Steps | Optimization Recommendations Report | Recs & Next Steps | Account Manager | Mid | 1 |  |  | 1.8.6.1 |  |  | 0 | 0
1134 | DEL-0024 | TSK-01125 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.6.1.2 | 1.8.6.1 | Recs & Next Steps | Optimization Recommendations Report | Recs & Next Steps | Analyst | Mid | 6 |  |  | 1.8.6.1.1 |  |  | 0 | 0
1135 | DEL-0024 | TSK-01126 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.6.1.3 | 1.8.6.1 | Recs & Next Steps | Optimization Recommendations Report | Recs & Next Steps | Social Strategist | Mid | 3 |  |  | 1.8.6.1.2 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.7 | 1.8 | Quarterly Ad-Hoc Report | Quarterly Ad-Hoc Report |  |  |  | 9 | 178 | 4 | 1.8.6 |  |  | 195 | 1755
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.7.1 | 1.8.7 | Quarterly Ad-hoc Deep Dive | Quarterly Ad-Hoc Report | Quarterly Ad-hoc Deep Dive |  |  | 0 | 178 | 4 | 1.8.7 |  |  | 0 | 0
1138 | DEL-0024 | TSK-01129 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.7.1.1 | 1.8.7.1 | Quarterly Ad-hoc Deep Dive | Quarterly Ad-Hoc Report | Quarterly Ad-hoc Deep Dive | Analyst | Mid | 6 |  |  | 1.8.7.1 |  |  | 0 | 0
1139 | DEL-0024 | TSK-01130 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.7.1.2 | 1.8.7.1 | Quarterly Ad-hoc Deep Dive | Quarterly Ad-Hoc Report | Quarterly Ad-hoc Deep Dive | QA Specialist | Mid | 3 |  |  | 1.8.7.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.8 | 1.8 | Quarterly Key Learnings & Insights Report | Quarterly Key Learnings & Insights Report |  |  |  | 11 | 178 | 4 | 1.8.7 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.8.1 | 1.8.8 | Quarterly Learnings & Insights | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights |  |  | 0 | 178 | 4 | 1.8.8 |  |  | 0 | 0
1140 | DEL-0024 | TSK-01131 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.8.1.1 | 1.8.8.1 | Quarterly Learnings & Insights | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights | Analyst | Mid | 6 |  |  | 1.8.8.1 |  |  | 0 | 0
1141 | DEL-0024 | TSK-01132 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.8.1.2 | 1.8.8.1 | Quarterly Learnings & Insights | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights | Designer | Mid | 2 |  |  | 1.8.8.1.1 |  |  | 0 | 0
1142 | DEL-0024 | TSK-01133 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.8.1.3 | 1.8.8.1 | Quarterly Learnings & Insights | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights | Social Strategist | Mid | 3 |  |  | 1.8.8.1.2 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.9 | 1.8 | Quarterly Report | Quarterly Report |  |  |  | 11 | 178 | 4 | 1.8.8 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.9.1 | 1.8.9 | Quarterly Report | Quarterly Report | Quarterly Report |  |  | 0 | 178 | 4 | 1.8.9 |  |  | 0 | 0
1143 | DEL-0024 | TSK-01134 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.9.1.1 | 1.8.9.1 | Quarterly Report | Quarterly Report | Quarterly Report | Analyst | Mid | 6 |  |  | 1.8.9.1 |  |  | 0 | 0
1144 | DEL-0024 | TSK-01135 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.9.1.2 | 1.8.9.1 | Quarterly Report | Quarterly Report | Quarterly Report | Designer | Mid | 2 |  |  | 1.8.9.1.1 |  |  | 0 | 0
1145 | DEL-0024 | TSK-01136 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.9.1.3 | 1.8.9.1 | Quarterly Report | Quarterly Report | Quarterly Report | Social Strategist | Mid | 3 |  |  | 1.8.9.1.2 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.10 | 1.8 | Summary overview | Summary overview |  |  |  | 4 | 178 | 4 | 1.8.9 |  |  | 195 | 780
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.10.1 | 1.8.10 | Summary Narrative | Summary overview | Summary Narrative |  |  | 0 | 178 | 4 | 1.8.10 |  |  | 0 | 0
1150 | DEL-0024 | TSK-01141 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.10.1.1 | 1.8.10.1 | Summary Narrative | Summary overview | Summary Narrative | Account Manager | Mid | 1 |  |  | 1.8.10.1 |  |  | 0 | 0
1151 | DEL-0024 | TSK-01142 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.10.1.2 | 1.8.10.1 | Summary Narrative | Summary overview | Summary Narrative | Social Strategist | Mid | 3 |  |  | 1.8.10.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.11 | 1.8 | Weekly Activity Report | Weekly Activity Report |  |  |  | 7 | 178 | 4 | 1.8.10 |  |  | 195 | 1365
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.11.1 | 1.8.11 | Weekly Activity Summary | Weekly Activity Report | Weekly Activity Summary |  |  | 0 | 178 | 4 | 1.8.11 |  |  | 0 | 0
1153 | DEL-0024 | TSK-01144 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.11.1.1 | 1.8.11.1 | Weekly Activity Summary | Weekly Activity Report | Weekly Activity Summary | Account Manager | Mid | 1 |  |  | 1.8.11.1 |  |  | 0 | 0
1154 | DEL-0024 | TSK-01145 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.11.1.2 | 1.8.11.1 | Weekly Activity Summary | Weekly Activity Report | Weekly Activity Summary | Analyst | Mid | 6 |  |  | 1.8.11.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.12 | 1.8 | Follower Growth | Follower Growth |  |  |  | 6 | 182 | 0 | 1.8.11 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.12.1 | 1.8.12 | Metric Pull & Notes | Follower Growth | Metric Pull & Notes |  |  | 0 | 182 | 0 | 1.8.12 |  |  | 0 | 0
1121 | DEL-0024 | TSK-01112 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.12.1.1 | 1.8.12.1 | Metric Pull & Notes | Follower Growth | Metric Pull & Notes | Analyst | Mid | 3 |  |  | 1.8.12.1 |  |  | 0 | 0
1122 | DEL-0024 | TSK-01113 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.12.1.2 | 1.8.12.1 | Metric Pull & Notes | Follower Growth | Metric Pull & Notes | QA Specialist | Mid | 3 |  |  | 1.8.12.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.13 | 1.8 | Impressions | Impressions |  |  |  | 6 | 182 | 0 | 1.8.12 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.13.1 | 1.8.13 | Metric Pull & Notes | Impressions | Metric Pull & Notes |  |  | 0 | 182 | 0 | 1.8.13 |  |  | 0 | 0
1123 | DEL-0024 | TSK-01114 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.13.1.1 | 1.8.13.1 | Metric Pull & Notes | Impressions | Metric Pull & Notes | Analyst | Mid | 3 |  |  | 1.8.13.1 |  |  | 0 | 0
1124 | DEL-0024 | TSK-01115 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.13.1.2 | 1.8.13.1 | Metric Pull & Notes | Impressions | Metric Pull & Notes | QA Specialist | Mid | 3 |  |  | 1.8.13.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.14 | 1.8 | Interactions | Interactions |  |  |  | 5 | 182 | 0 | 1.8.13 |  |  | 195 | 975
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.14.1 | 1.8.14 | Metric Pull & Notes | Interactions | Metric Pull & Notes |  |  | 0 | 182 | 0 | 1.8.14 |  |  | 0 | 0
1125 | DEL-0024 | TSK-01116 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.14.1.1 | 1.8.14.1 | Metric Pull & Notes | Interactions | Metric Pull & Notes | Analyst | Mid | 2 |  |  | 1.8.14.1 |  |  | 0 | 0
1126 | DEL-0024 | TSK-01117 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.14.1.2 | 1.8.14.1 | Metric Pull & Notes | Interactions | Metric Pull & Notes | QA Specialist | Mid | 3 |  |  | 1.8.14.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.15 | 1.8 | Profile Reach | Profile Reach |  |  |  | 5 | 182 | 0 | 1.8.14 |  |  | 195 | 975
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.15.1 | 1.8.15 | Metric Pull & Notes | Profile Reach | Metric Pull & Notes |  |  | 0 | 182 | 0 | 1.8.15 |  |  | 0 | 0
1136 | DEL-0024 | TSK-01127 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.15.1.1 | 1.8.15.1 | Metric Pull & Notes | Profile Reach | Metric Pull & Notes | Analyst | Mid | 2 |  |  | 1.8.15.1 |  |  | 0 | 0
1137 | DEL-0024 | TSK-01128 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.15.1.2 | 1.8.15.1 | Metric Pull & Notes | Profile Reach | Metric Pull & Notes | QA Specialist | Mid | 3 |  |  | 1.8.15.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.16 | 1.8 | Recap Reports | Recap Reports |  |  |  | 4 | 182 | 0 | 1.8.15 |  |  | 195 | 780
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.16.1 | 1.8.16 | Campaign/Period Recaps | Recap Reports | Campaign/Period Recaps |  |  | 0 | 182 | 0 | 1.8.16 |  |  | 0 | 0
1146 | DEL-0024 | TSK-01137 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.16.1.1 | 1.8.16.1 | Campaign/Period Recaps | Recap Reports | Campaign/Period Recaps | Account Manager | Mid | 2 |  |  | 1.8.16.1 |  |  | 0 | 0
1147 | DEL-0024 | TSK-01138 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.16.1.2 | 1.8.16.1 | Campaign/Period Recaps | Recap Reports | Campaign/Period Recaps | Analyst | Mid | 2 |  |  | 1.8.16.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.17 | 1.8 | Social Reporting | Social Reporting |  |  |  | 4 | 182 | 0 | 1.8.16 |  |  | 195 | 780
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.17.1 | 1.8.17 | Ongoing Social Reporting | Social Reporting | Ongoing Social Reporting |  |  | 0 | 182 | 0 | 1.8.17 |  |  | 0 | 0
1148 | DEL-0024 | TSK-01139 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.17.1.1 | 1.8.17.1 | Ongoing Social Reporting | Social Reporting | Ongoing Social Reporting | Account Manager | Mid | 2 |  |  | 1.8.17.1 |  |  | 0 | 0
1149 | DEL-0024 | TSK-01140 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.17.1.2 | 1.8.17.1 | Ongoing Social Reporting | Social Reporting | Ongoing Social Reporting | Analyst | Mid | 2 |  |  | 1.8.17.1.1 |  |  | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.18 | 1.8 | Update/maintain Z/Russia tracker | Update/maintain Z/Russia tracker |  |  |  | 2 | 182 | 0 | 1.8.17 |  |  | 195 | 390
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.18.1 | 1.8.18 | Tracker Update | Update/maintain Z/Russia tracker | Tracker Update |  |  | 0 | 182 | 0 | 1.8.18 |  |  | 0 | 0
1152 | DEL-0024 | TSK-01143 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.8.18.1.1 | 1.8.18.1 | Tracker Update | Update/maintain Z/Russia tracker | Tracker Update | Analyst | Mid | 2 |  |  | 1.8.18.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9 | 1 | Brand Identity Development |  |  |  |  | 300 | 182 | 15 | 1.8 |  | Advanced/T2_MediumVolume | 195 | 58500
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.1 | 1.9 | Color Palette | Color Palette |  |  |  | 18 | 182 | 3 | 1.9 |  |  | 195 | 3510
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.1.1 | 1.9.1 | Client Review & Revisions | Color Palette | Client Review & Revisions |  |  | 0 | 182 | 3 | 1.9.1 |  |  | 0 | 0
475 | DEL-0008 | TSK-00466 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.1.1.1 | 1.9.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.9.1.1 |  |  | 0 | 0
480 | DEL-0008 | TSK-00471 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.1.1.2 | 1.9.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Art Director | Lead/Director | 2 |  |  | 1.9.1.1.1 |  |  | 0 | 0
476 | DEL-0008 | TSK-00467 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.1.1.3 | 1.9.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Creative Director | Lead/Director | 4 |  |  | 1.9.1.1.2 |  |  | 0 | 0
478 | DEL-0008 | TSK-00469 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.1.1.4 | 1.9.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Designer | Mid | 7 |  |  | 1.9.1.1.3 |  |  | 0 | 0
477 | DEL-0008 | TSK-00468 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.1.1.5 | 1.9.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.9.1.1.4 |  |  | 0 | 0
474 | DEL-0008 | TSK-00465 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.1.1.6 | 1.9.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | QA Specialist | Mid | 3 |  |  | 1.9.1.1.5 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2 | 1.9 | Graphic Mock-Ups | Graphic Mock-Ups |  |  |  | 30 | 185 | 9 | 1.9.1 |  |  | 195 | 5850
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.1 | 1.9.2 | Compositing/Retouch | Graphic Mock-Ups | Compositing/Retouch |  |  | 0 | 185 | 4 | 1.9.2 |  |  | 0 | 0
496 | DEL-0008 | TSK-00487 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.1.1 | 1.9.2.1 | Compositing/Retouch | Graphic Mock-Ups | Compositing/Retouch | Retoucher | Mid | 5 |  |  | 1.9.2.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.2 | 1.9.2 | Internal Review & Critique | Graphic Mock-Ups | Internal Review & Critique |  |  | 0 | 192 | 2 | 1.9.2.1.1 |  |  | 0 | 0
498 | DEL-0008 | TSK-00489 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.2.1 | 1.9.2.2 | Internal Review & Critique | Graphic Mock-Ups | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.9.2.2 |  |  | 0 | 0
499 | DEL-0008 | TSK-00490 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.2.2 | 1.9.2.2 | Internal Review & Critique | Graphic Mock-Ups | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.9.2.2.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.3 | 1.9.2 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions |  |  | 0 | 194 | 3 | 1.9.2.2.2 |  |  | 0 | 0
493 | DEL-0008 | TSK-00484 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.3.1 | 1.9.2.3 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.9.2.3 |  |  | 0 | 0
494 | DEL-0008 | TSK-00485 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.3.2 | 1.9.2.3 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.9.2.3.1 |  |  | 0 | 0
495 | DEL-0008 | TSK-00486 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.3.3 | 1.9.2.3 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.9.2.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.4 | 1.9.2 | Mockup Scenarios (3-4) | Graphic Mock-Ups | Mockup Scenarios (3-4) |  |  | 0 | 197 | 0 | 1.9.2.3.3 |  |  | 0 | 0
500 | DEL-0008 | TSK-00491 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.4.1 | 1.9.2.4 | Mockup Scenarios (3-4) | Graphic Mock-Ups | Mockup Scenarios (3-4) | Art Director | Lead/Director | 3 |  |  | 1.9.2.4 |  |  | 0 | 0
497 | DEL-0008 | TSK-00488 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.2.4.2 | 1.9.2.4 | Mockup Scenarios (3-4) | Graphic Mock-Ups | Mockup Scenarios (3-4) | Designer | Mid | 16 |  |  | 1.9.2.4.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3 | 1.9 | Logo | Logo |  |  |  | 43 | 189 | 8 | 1.9.2 |  |  | 195 | 8385
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.1 | 1.9.3 | Quality Check (Specs/Accessibility) | Logo | Quality Check (Specs/Accessibility) |  |  | 0 | 189 | 3 | 1.9.3 |  |  | 0 | 0
520 | DEL-0008 | TSK-00511 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.1.1 | 1.9.3.1 | Quality Check (Specs/Accessibility) | Logo | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.9.3.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.2 | 1.9.3 | Internal Review & Critique | Logo | Internal Review & Critique |  |  | 0 | 192 | 2 | 1.9.3.1.1 |  |  | 0 | 0
515 | DEL-0008 | TSK-00506 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.2.1 | 1.9.3.2 | Internal Review & Critique | Logo | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.9.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.3 | 1.9.3 | Client Review & Revisions | Logo | Client Review & Revisions |  |  | 0 | 194 | 3 | 1.9.3.2.1 |  |  | 0 | 0
511 | DEL-0008 | TSK-00502 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.3.1 | 1.9.3.3 | Client Review & Revisions | Logo | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.9.3.3 |  |  | 0 | 0
512 | DEL-0008 | TSK-00503 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.3.2 | 1.9.3.3 | Client Review & Revisions | Logo | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.9.3.3.1 |  |  | 0 | 0
513 | DEL-0008 | TSK-00504 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.3.3 | 1.9.3.3 | Client Review & Revisions | Logo | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.9.3.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.4 | 1.9.3 | Logo Exploration (6-8 dirs) | Logo | Logo Exploration (6-8 dirs) |  |  | 0 | 197 | 0 | 1.9.3.3.3 |  |  | 0 | 0
517 | DEL-0008 | TSK-00508 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.4.1 | 1.9.3.4 | Logo Exploration (6-8 dirs) | Logo | Logo Exploration (6-8 dirs) | Art Director | Lead/Director | 3 |  |  | 1.9.3.4 |  |  | 0 | 0
514 | DEL-0008 | TSK-00505 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.3.4.2 | 1.9.3.4 | Logo Exploration (6-8 dirs) | Logo | Logo Exploration (6-8 dirs) | Designer | Mid | 32 |  |  | 1.9.3.4.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4 | 1.9 | Typography | Typography |  |  |  | 40 | 189 | 8 | 1.9.3 |  |  | 195 | 7800
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4.1 | 1.9.4 | Quality Check (Specs/Accessibility) | Typography | Quality Check (Specs/Accessibility) |  |  | 0 | 189 | 3 | 1.9.4 |  |  | 0 | 0
556 | DEL-0008 | TSK-00547 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4.1.1 | 1.9.4.1 | Quality Check (Specs/Accessibility) | Typography | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.9.4.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4.2 | 1.9.4 | Internal Review & Critique | Typography | Internal Review & Critique |  |  | 0 | 192 | 2 | 1.9.4.1.1 |  |  | 0 | 0
554 | DEL-0008 | TSK-00545 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4.2.1 | 1.9.4.2 | Internal Review & Critique | Typography | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.9.4.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4.3 | 1.9.4 | Client Review & Revisions | Typography | Client Review & Revisions |  |  | 0 | 194 | 3 | 1.9.4.2.1 |  |  | 0 | 0
549 | DEL-0008 | TSK-00540 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4.3.1 | 1.9.4.3 | Client Review & Revisions | Typography | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.9.4.3 |  |  | 0 | 0
550 | DEL-0008 | TSK-00541 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4.3.2 | 1.9.4.3 | Client Review & Revisions | Typography | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.9.4.3.1 |  |  | 0 | 0
551 | DEL-0008 | TSK-00542 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4.3.3 | 1.9.4.3 | Client Review & Revisions | Typography | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.9.4.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4.4 | 1.9.4 | Final Packaging | Typography | Final Packaging |  |  | 0 | 197 | 0 | 1.9.4.3.3 |  |  | 0 | 0
552 | DEL-0008 | TSK-00543 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.4.4.1 | 1.9.4.4 | Final Packaging | Typography | Final Packaging | Designer | Mid | 32 |  |  | 1.9.4.4 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5 | 1.9 | Graphic & Copy Messaging Cornerstones | Graphic & Copy Messaging Cornerstones |  |  |  | 28 | 192 | 5 | 1.9.4 |  |  | 195 | 5460
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.1 | 1.9.5 | Internal Review & Critique | Graphic & Copy Messaging Cornerstones | Internal Review & Critique |  |  | 0 | 192 | 2 | 1.9.5 |  |  | 0 | 0
489 | DEL-0008 | TSK-00480 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.1.1 | 1.9.5.1 | Internal Review & Critique | Graphic & Copy Messaging Cornerstones | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.9.5.1 |  |  | 0 | 0
490 | DEL-0008 | TSK-00481 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.1.2 | 1.9.5.1 | Internal Review & Critique | Graphic & Copy Messaging Cornerstones | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.9.5.1.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.2 | 1.9.5 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions |  |  | 0 | 194 | 3 | 1.9.5.1.2 |  |  | 0 | 0
483 | DEL-0008 | TSK-00474 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.2.1 | 1.9.5.2 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.9.5.2 |  |  | 0 | 0
484 | DEL-0008 | TSK-00475 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.2.2 | 1.9.5.2 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.9.5.2.1 |  |  | 0 | 0
485 | DEL-0008 | TSK-00476 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.2.3 | 1.9.5.2 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.9.5.2.2 |  |  | 0 | 0
486 | DEL-0008 | TSK-00477 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.2.4 | 1.9.5.2 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.9.5.2.3 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.3 | 1.9.5 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft |  |  | 0 | 197 | 0 | 1.9.5.2.4 |  |  | 0 | 0
491 | DEL-0008 | TSK-00482 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.3.1 | 1.9.5.3 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft | Copywriter | Mid | 2 |  |  | 1.9.5.3 |  |  | 0 | 0
492 | DEL-0008 | TSK-00483 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.3.2 | 1.9.5.3 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft | Creative Director | Lead/Director | 3 |  |  | 1.9.5.3.1 |  |  | 0 | 0
487 | DEL-0008 | TSK-00478 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.5.3.3 | 1.9.5.3 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft | Designer | Mid | 16 |  |  | 1.9.5.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.6 | 1.9 | Iconography | Iconography |  |  |  | 31 | 192 | 5 | 1.9.5 |  |  | 195 | 6045
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.6.1 | 1.9.6 | Internal Review & Critique | Iconography | Internal Review & Critique |  |  | 0 | 192 | 2 | 1.9.6 |  |  | 0 | 0
509 | DEL-0008 | TSK-00500 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.6.1.1 | 1.9.6.1 | Internal Review & Critique | Iconography | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.9.6.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.6.2 | 1.9.6 | Client Review & Revisions | Iconography | Client Review & Revisions |  |  | 0 | 194 | 3 | 1.9.6.1.1 |  |  | 0 | 0
502 | DEL-0008 | TSK-00493 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.6.2.1 | 1.9.6.2 | Client Review & Revisions | Iconography | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.9.6.2 |  |  | 0 | 0
503 | DEL-0008 | TSK-00494 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.6.2.2 | 1.9.6.2 | Client Review & Revisions | Iconography | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.9.6.2.1 |  |  | 0 | 0
504 | DEL-0008 | TSK-00495 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.6.2.3 | 1.9.6.2 | Client Review & Revisions | Iconography | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.9.6.2.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.6.3 | 1.9.6 | Export & Spec | Iconography | Export & Spec |  |  | 0 | 197 | 0 | 1.9.6.2.3 |  |  | 0 | 0
505 | DEL-0008 | TSK-00496 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.6.3.1 | 1.9.6.3 | Export & Spec | Iconography | Export & Spec | Designer | Mid | 24 |  |  | 1.9.6.3 |  |  | 0 | 0
508 | DEL-0008 | TSK-00499 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.6.3.2 | 1.9.6.3 | Export & Spec | Iconography | Export & Spec | Illustrator | Mid | 2 |  |  | 1.9.6.3.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7 | 1.9 | Overarching Moodboard | Overarching Moodboard |  |  |  | 27 | 192 | 5 | 1.9.6 |  |  | 195 | 5265
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.1 | 1.9.7 | Internal Review & Critique | Overarching Moodboard | Internal Review & Critique |  |  | 0 | 192 | 2 | 1.9.7 |  |  | 0 | 0
528 | DEL-0008 | TSK-00519 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.1.1 | 1.9.7.1 | Internal Review & Critique | Overarching Moodboard | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.9.7.1 |  |  | 0 | 0
529 | DEL-0008 | TSK-00520 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.1.2 | 1.9.7.1 | Internal Review & Critique | Overarching Moodboard | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.9.7.1.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.2 | 1.9.7 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions |  |  | 0 | 194 | 3 | 1.9.7.1.2 |  |  | 0 | 0
522 | DEL-0008 | TSK-00513 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.2.1 | 1.9.7.2 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.9.7.2 |  |  | 0 | 0
523 | DEL-0008 | TSK-00514 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.2.2 | 1.9.7.2 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.9.7.2.1 |  |  | 0 | 0
524 | DEL-0008 | TSK-00515 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.2.3 | 1.9.7.2 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.9.7.2.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.3 | 1.9.7 | Curate Moodboard | Overarching Moodboard | Curate Moodboard |  |  | 0 | 197 | 0 | 1.9.7.2.3 |  |  | 0 | 0
526 | DEL-0008 | TSK-00517 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.3.1 | 1.9.7.3 | Curate Moodboard | Overarching Moodboard | Curate Moodboard | Art Director | Lead/Director | 3 |  |  | 1.9.7.3 |  |  | 0 | 0
530 | DEL-0008 | TSK-00521 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.3.2 | 1.9.7.3 | Curate Moodboard | Overarching Moodboard | Curate Moodboard | Copywriter | Mid | 2 |  |  | 1.9.7.3.1 |  |  | 0 | 0
525 | DEL-0008 | TSK-00516 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.7.3.3 | 1.9.7.3 | Curate Moodboard | Overarching Moodboard | Curate Moodboard | Designer | Mid | 16 |  |  | 1.9.7.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8 | 1.9 | Tagline Copy Bank | Tagline Copy Bank |  |  |  | 22 | 192 | 5 | 1.9.7 |  |  | 195 | 4290
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.1 | 1.9.8 | Internal Review & Critique | Tagline Copy Bank | Internal Review & Critique |  |  | 0 | 192 | 2 | 1.9.8 |  |  | 0 | 0
536 | DEL-0008 | TSK-00527 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.1.1 | 1.9.8.1 | Internal Review & Critique | Tagline Copy Bank | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.9.8.1 |  |  | 0 | 0
537 | DEL-0008 | TSK-00528 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.1.2 | 1.9.8.1 | Internal Review & Critique | Tagline Copy Bank | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.9.8.1.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.2 | 1.9.8 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions |  |  | 0 | 194 | 3 | 1.9.8.1.2 |  |  | 0 | 0
531 | DEL-0008 | TSK-00522 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.2.1 | 1.9.8.2 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.9.8.2 |  |  | 0 | 0
532 | DEL-0008 | TSK-00523 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.2.2 | 1.9.8.2 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.9.8.2.1 |  |  | 0 | 0
533 | DEL-0008 | TSK-00524 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.2.3 | 1.9.8.2 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.9.8.2.2 |  |  | 0 | 0
534 | DEL-0008 | TSK-00525 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.2.4 | 1.9.8.2 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.9.8.2.3 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.3 | 1.9.8 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale |  |  | 0 | 197 | 0 | 1.9.8.2.4 |  |  | 0 | 0
538 | DEL-0008 | TSK-00529 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.3.1 | 1.9.8.3 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale | Copywriter | Mid | 4 |  |  | 1.9.8.3 |  |  | 0 | 0
539 | DEL-0008 | TSK-00530 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.3.2 | 1.9.8.3 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale | Creative Director | Lead/Director | 3 |  |  | 1.9.8.3.1 |  |  | 0 | 0
535 | DEL-0008 | TSK-00526 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.8.3.3 | 1.9.8.3 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale | Designer | Mid | 8 |  |  | 1.9.8.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.9 | 1.9 | Textures/Patterns/Materials | Textures/Patterns/Materials |  |  |  | 29 | 192 | 5 | 1.9.8 |  |  | 195 | 5655
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.9.1 | 1.9.9 | Internal Review & Critique | Textures/Patterns/Materials | Internal Review & Critique |  |  | 0 | 192 | 2 | 1.9.9 |  |  | 0 | 0
546 | DEL-0008 | TSK-00537 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.9.1.1 | 1.9.9.1 | Internal Review & Critique | Textures/Patterns/Materials | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.9.9.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.9.2 | 1.9.9 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions |  |  | 0 | 194 | 3 | 1.9.9.1.1 |  |  | 0 | 0
542 | DEL-0008 | TSK-00533 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.9.2.1 | 1.9.9.2 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.9.9.2 |  |  | 0 | 0
543 | DEL-0008 | TSK-00534 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.9.2.2 | 1.9.9.2 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.9.9.2.1 |  |  | 0 | 0
544 | DEL-0008 | TSK-00535 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.9.2.3 | 1.9.9.2 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.9.9.2.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.9.3 | 1.9.9 | Build Repeating Tiles | Textures/Patterns/Materials | Build Repeating Tiles |  |  | 0 | 197 | 0 | 1.9.9.2.3 |  |  | 0 | 0
541 | DEL-0008 | TSK-00532 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.9.3.1 | 1.9.9.3 | Build Repeating Tiles | Textures/Patterns/Materials | Build Repeating Tiles | Designer | Mid | 24 |  |  | 1.9.9.3 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.10 | 1.9 | Visual Elements/Comps | Visual Elements/Comps |  |  |  | 32 | 192 | 5 | 1.9.9 |  |  | 195 | 6240
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.10.1 | 1.9.10 | Internal Review & Critique | Visual Elements/Comps | Internal Review & Critique |  |  | 0 | 192 | 2 | 1.9.10 |  |  | 0 | 0
566 | DEL-0008 | TSK-00557 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.10.1.1 | 1.9.10.1 | Internal Review & Critique | Visual Elements/Comps | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.9.10.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.10.2 | 1.9.10 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions |  |  | 0 | 194 | 3 | 1.9.10.1.1 |  |  | 0 | 0
559 | DEL-0008 | TSK-00550 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.10.2.1 | 1.9.10.2 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.9.10.2 |  |  | 0 | 0
560 | DEL-0008 | TSK-00551 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.10.2.2 | 1.9.10.2 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.9.10.2.1 |  |  | 0 | 0
561 | DEL-0008 | TSK-00552 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.10.2.3 | 1.9.10.2 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.9.10.2.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.10.3 | 1.9.10 | Compositions (2-3) | Visual Elements/Comps | Compositions (2-3) |  |  | 0 | 197 | 0 | 1.9.10.2.3 |  |  | 0 | 0
562 | DEL-0008 | TSK-00553 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.10.3.1 | 1.9.10.3 | Compositions (2-3) | Visual Elements/Comps | Compositions (2-3) | Art Director | Lead/Director | 3 |  |  | 1.9.10.3 |  |  | 0 | 0
563 | DEL-0008 | TSK-00554 | Creative | Brand Identity Development | Casa-Dragones-Digital-MKT-RFP | 1.9.10.3.2 | 1.9.10.3 | Compositions (2-3) | Visual Elements/Comps | Compositions (2-3) | Designer | Mid | 24 |  |  | 1.9.10.3.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10 | 1 | Development |  |  |  |  | 268 | 197 | 26 | 1.9 |  | Advanced/T2_MediumVolume | 195 | 52260
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1 | 1.10 | ADA Compliance | ADA Compliance |  |  |  | 59 | 197 | 18 | 1.10 |  |  | 195 | 11505
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1.1 | 1.10.1 | Accessibility Audit | ADA Compliance | Accessibility Audit |  |  | 0 | 197 | 4 | 1.10.1 |  |  | 0 | 0
1738 | DEL-0044 | TSK-01729 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1.1.1 | 1.10.1.1 | Accessibility Audit | ADA Compliance | Accessibility Audit | Accessibility Specialist | Mid | 2 |  |  | 1.10.1.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1.2 | 1.10.1 | Accessibility QA | ADA Compliance | Accessibility QA |  |  | 0 | 209 | 3 | 1.10.1.1.1 |  |  | 0 | 0
1739 | DEL-0044 | TSK-01730 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1.2.1 | 1.10.1.2 | Accessibility QA | ADA Compliance | Accessibility QA | Accessibility Specialist | Mid | 2 |  |  | 1.10.1.2 |  |  | 0 | 0
1744 | DEL-0044 | TSK-01735 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1.2.2 | 1.10.1.2 | Accessibility QA | ADA Compliance | Accessibility QA | QA Engineer | Mid | 3 |  |  | 1.10.1.2.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1.3 | 1.10.1 | Code Review | ADA Compliance | Code Review |  |  | 0 | 212 | 11 | 1.10.1.2.2 |  |  | 0 | 0
1740 | DEL-0044 | TSK-01731 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1.3.1 | 1.10.1.3 | Code Review | ADA Compliance | Code Review | Backend Engineer | Mid | 12 |  |  | 1.10.1.3 |  |  | 0 | 0
1742 | DEL-0044 | TSK-01733 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1.3.2 | 1.10.1.3 | Code Review | ADA Compliance | Code Review | DevOps Engineer | Mid | 12 |  |  | 1.10.1.3.1 |  |  | 0 | 0
1741 | DEL-0044 | TSK-01732 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1.3.3 | 1.10.1.3 | Code Review | ADA Compliance | Code Review | Frontend Engineer | Mid | 24 |  |  | 1.10.1.3.2 |  |  | 0 | 0
1743 | DEL-0044 | TSK-01734 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.1.3.4 | 1.10.1.3 | Code Review | ADA Compliance | Code Review | Project Manager | Mid | 4 |  |  | 1.10.1.3.3 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.2 | 1.10 | Audit & Requirement gathering | Audit & Requirement gathering |  |  |  | 20 | 197 | 4 | 1.10.1 |  |  | 195 | 3900
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.2.1 | 1.10.2 | Analytics Audit | Audit & Requirement gathering | Analytics Audit |  |  | 0 | 197 | 4 | 1.10.2 |  |  | 0 | 0
1750 | DEL-0044 | TSK-01741 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.2.1.1 | 1.10.2.1 | Analytics Audit | Audit & Requirement gathering | Analytics Audit | Business Analyst | Mid | 10 |  |  | 1.10.2.1 |  |  | 0 | 0
1749 | DEL-0044 | TSK-01740 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.2.1.2 | 1.10.2.1 | Analytics Audit | Audit & Requirement gathering | Analytics Audit | Data/Analytics Engineer | Mid | 10 |  |  | 1.10.2.1.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.3 | 1.10 | Audit existing UA Property | Audit existing UA Property |  |  |  | 20 | 197 | 4 | 1.10.2 |  |  | 195 | 3900
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.3.1 | 1.10.3 | Documentation | Audit existing UA Property | Documentation |  |  | 0 | 197 | 4 | 1.10.3 |  |  | 0 | 0
1753 | DEL-0044 | TSK-01744 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.3.1.1 | 1.10.3.1 | Documentation | Audit existing UA Property | Documentation | Business Analyst | Mid | 10 |  |  | 1.10.3.1 |  |  | 0 | 0
1755 | DEL-0044 | TSK-01746 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.3.1.2 | 1.10.3.1 | Documentation | Audit existing UA Property | Documentation | Data/Analytics Engineer | Mid | 10 |  |  | 1.10.3.1.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4 | 1.10 | Footer CTA | Footer CTA |  |  |  | 51 | 201 | 22 | 1.10.3 |  |  | 195 | 9945
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.1 | 1.10.4 | Design Consult | Footer CTA | Design Consult |  |  | 0 | 201 | 8 | 1.10.4 |  |  | 0 | 0
1765 | DEL-0044 | TSK-01756 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.1.1 | 1.10.4.1 | Design Consult | Footer CTA | Design Consult | UI Designer | Mid | 4 |  |  | 1.10.4.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.2 | 1.10.4 | Accessibility QA | Footer CTA | Accessibility QA |  |  | 0 | 209 | 3 | 1.10.4.1.1 |  |  | 0 | 0
1760 | DEL-0044 | TSK-01751 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.2.1 | 1.10.4.2 | Accessibility QA | Footer CTA | Accessibility QA | Accessibility Specialist | Mid | 2 |  |  | 1.10.4.2 |  |  | 0 | 0
1767 | DEL-0044 | TSK-01758 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.2.2 | 1.10.4.2 | Accessibility QA | Footer CTA | Accessibility QA | Frontend Engineer | Mid | 2 |  |  | 1.10.4.2.1 |  |  | 0 | 0
1766 | DEL-0044 | TSK-01757 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.2.3 | 1.10.4.2 | Accessibility QA | Footer CTA | Accessibility QA | QA Engineer | Mid | 3 |  |  | 1.10.4.2.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.3 | 1.10.4 | Code Review | Footer CTA | Code Review |  |  | 0 | 212 | 11 | 1.10.4.2.3 |  |  | 0 | 0
1761 | DEL-0044 | TSK-01752 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.3.1 | 1.10.4.3 | Code Review | Footer CTA | Code Review | Backend Engineer | Mid | 12 |  |  | 1.10.4.3 |  |  | 0 | 0
1763 | DEL-0044 | TSK-01754 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.3.2 | 1.10.4.3 | Code Review | Footer CTA | Code Review | DevOps Engineer | Mid | 12 |  |  | 1.10.4.3.1 |  |  | 0 | 0
1762 | DEL-0044 | TSK-01753 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.3.3 | 1.10.4.3 | Code Review | Footer CTA | Code Review | Frontend Engineer | Mid | 12 |  |  | 1.10.4.3.2 |  |  | 0 | 0
1764 | DEL-0044 | TSK-01755 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.4.3.4 | 1.10.4.3 | Code Review | Footer CTA | Code Review | Project Manager | Mid | 4 |  |  | 1.10.4.3.3 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5 | 1.10 | Header & Footer Navigation | Header & Footer Navigation |  |  |  | 51 | 201 | 22 | 1.10.4 |  |  | 195 | 9945
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.1 | 1.10.5 | Design Consult | Header & Footer Navigation | Design Consult |  |  | 0 | 201 | 8 | 1.10.5 |  |  | 0 | 0
1773 | DEL-0044 | TSK-01764 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.1.1 | 1.10.5.1 | Design Consult | Header & Footer Navigation | Design Consult | UI Designer | Mid | 4 |  |  | 1.10.5.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.2 | 1.10.5 | Accessibility QA | Header & Footer Navigation | Accessibility QA |  |  | 0 | 209 | 3 | 1.10.5.1.1 |  |  | 0 | 0
1768 | DEL-0044 | TSK-01759 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.2.1 | 1.10.5.2 | Accessibility QA | Header & Footer Navigation | Accessibility QA | Accessibility Specialist | Mid | 2 |  |  | 1.10.5.2 |  |  | 0 | 0
1775 | DEL-0044 | TSK-01766 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.2.2 | 1.10.5.2 | Accessibility QA | Header & Footer Navigation | Accessibility QA | Frontend Engineer | Mid | 2 |  |  | 1.10.5.2.1 |  |  | 0 | 0
1774 | DEL-0044 | TSK-01765 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.2.3 | 1.10.5.2 | Accessibility QA | Header & Footer Navigation | Accessibility QA | QA Engineer | Mid | 3 |  |  | 1.10.5.2.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.3 | 1.10.5 | Code Review | Header & Footer Navigation | Code Review |  |  | 0 | 212 | 11 | 1.10.5.2.3 |  |  | 0 | 0
1769 | DEL-0044 | TSK-01760 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.3.1 | 1.10.5.3 | Code Review | Header & Footer Navigation | Code Review | Backend Engineer | Mid | 12 |  |  | 1.10.5.3 |  |  | 0 | 0
1771 | DEL-0044 | TSK-01762 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.3.2 | 1.10.5.3 | Code Review | Header & Footer Navigation | Code Review | DevOps Engineer | Mid | 12 |  |  | 1.10.5.3.1 |  |  | 0 | 0
1770 | DEL-0044 | TSK-01761 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.3.3 | 1.10.5.3 | Code Review | Header & Footer Navigation | Code Review | Frontend Engineer | Mid | 12 |  |  | 1.10.5.3.2 |  |  | 0 | 0
1772 | DEL-0044 | TSK-01763 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.5.3.4 | 1.10.5.3 | Code Review | Header & Footer Navigation | Code Review | Project Manager | Mid | 4 |  |  | 1.10.5.3.3 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.6 | 1.10 | Additional Goals Setup | Additional Goals Setup |  |  |  | 8 | 209 | 14 | 1.10.5 |  |  | 195 | 1560
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.6.1 | 1.10.6 | QA Cycle | Additional Goals Setup | QA Cycle |  |  | 0 | 209 | 3 | 1.10.6 |  |  | 0 | 0
1747 | DEL-0044 | TSK-01738 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.6.1.1 | 1.10.6.1 | QA Cycle | Additional Goals Setup | QA Cycle | QA Engineer | Mid | 3 |  |  | 1.10.6.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.6.2 | 1.10.6 | Define & Configure Goals | Additional Goals Setup | Define & Configure Goals |  |  | 0 | 212 | 11 | 1.10.6.1.1 |  |  | 0 | 0
1746 | DEL-0044 | TSK-01737 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.6.2.1 | 1.10.6.2 | Define & Configure Goals | Additional Goals Setup | Define & Configure Goals | Data/Analytics Engineer | Mid | 5 |  |  | 1.10.6.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.7 | 1.10 | Custom Event Tracking | Custom Event Tracking |  |  |  | 8 | 209 | 14 | 1.10.6 |  |  | 195 | 1560
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.7.1 | 1.10.7 | QA Cycle | Custom Event Tracking | QA Cycle |  |  | 0 | 209 | 3 | 1.10.7 |  |  | 0 | 0
1758 | DEL-0044 | TSK-01749 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.7.1.1 | 1.10.7.1 | QA Cycle | Custom Event Tracking | QA Cycle | QA Engineer | Mid | 3 |  |  | 1.10.7.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.7.2 | 1.10.7 | Event Schema & Tagging | Custom Event Tracking | Event Schema & Tagging |  |  | 0 | 212 | 11 | 1.10.7.1.1 |  |  | 0 | 0
1757 | DEL-0044 | TSK-01748 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.7.2.1 | 1.10.7.2 | Event Schema & Tagging | Custom Event Tracking | Event Schema & Tagging | Data/Analytics Engineer | Mid | 5 |  |  | 1.10.7.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.8 | 1.10 | Implement Paid Media Pixel on website w GTM-Google Ads | Implement Paid Media Pixel on website w GTM-Google Ads |  |  |  | 6 | 209 | 14 | 1.10.7 |  |  | 195 | 1170
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.8.1 | 1.10.8 | Spec QA | Implement Paid Media Pixel on website w GTM-Google Ads | Spec QA |  |  | 0 | 209 | 3 | 1.10.8 |  |  | 0 | 0
1777 | DEL-0044 | TSK-01768 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.8.1.1 | 1.10.8.1 | Spec QA | Implement Paid Media Pixel on website w GTM-Google Ads | Spec QA | QA Engineer | Mid | 3 |  |  | 1.10.8.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.8.2 | 1.10.8 | Pixel Setup (GTM) | Implement Paid Media Pixel on website w GTM-Google Ads | Pixel Setup (GTM) |  |  | 0 | 212 | 11 | 1.10.8.1.1 |  |  | 0 | 0
1776 | DEL-0044 | TSK-01767 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.8.2.1 | 1.10.8.2 | Pixel Setup (GTM) | Implement Paid Media Pixel on website w GTM-Google Ads | Pixel Setup (GTM) | Data/Analytics Engineer | Mid | 3 |  |  | 1.10.8.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.9 | 1.10 | Implement goals listed in UA as Conversions in G4 | Implement goals listed in UA as Conversions in G4 |  |  |  | 8 | 209 | 14 | 1.10.8 |  |  | 195 | 1560
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.9.1 | 1.10.9 | QA Cycle | Implement goals listed in UA as Conversions in G4 | QA Cycle |  |  | 0 | 209 | 3 | 1.10.9 |  |  | 0 | 0
1779 | DEL-0044 | TSK-01770 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.9.1.1 | 1.10.9.1 | QA Cycle | Implement goals listed in UA as Conversions in G4 | QA Cycle | QA Engineer | Mid | 3 |  |  | 1.10.9.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.9.2 | 1.10.9 | Migrate UA Goals → GA4 Conversions | Implement goals listed in UA as Conversions in G4 | Migrate UA Goals → GA4 Conversions |  |  | 0 | 212 | 11 | 1.10.9.1.1 |  |  | 0 | 0
1778 | DEL-0044 | TSK-01769 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.9.2.1 | 1.10.9.2 | Migrate UA Goals → GA4 Conversions | Implement goals listed in UA as Conversions in G4 | Migrate UA Goals → GA4 Conversions | Data/Analytics Engineer | Mid | 5 |  |  | 1.10.9.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.10 | 1.10 | Implementation | Implementation |  |  |  | 8 | 209 | 14 | 1.10.9 |  |  | 195 | 1560
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.10.1 | 1.10.10 | QA Cycle | Implementation | QA Cycle |  |  | 0 | 209 | 3 | 1.10.10 |  |  | 0 | 0
1782 | DEL-0044 | TSK-01773 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.10.1.1 | 1.10.10.1 | QA Cycle | Implementation | QA Cycle | QA Engineer | Mid | 3 |  |  | 1.10.10.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.10.2 | 1.10.10 | Implement Tags/Events | Implementation | Implement Tags/Events |  |  | 0 | 212 | 11 | 1.10.10.1.1 |  |  | 0 | 0
1781 | DEL-0044 | TSK-01772 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.10.2.1 | 1.10.10.2 | Implement Tags/Events | Implementation | Implement Tags/Events | Data/Analytics Engineer | Mid | 5 |  |  | 1.10.10.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.11 | 1.10 | Outbound link clicks | Outbound link clicks |  |  |  | 6 | 209 | 14 | 1.10.10 |  |  | 195 | 1170
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.11.1 | 1.10.11 | QA | Outbound link clicks | QA |  |  | 0 | 209 | 3 | 1.10.11 |  |  | 0 | 0
1785 | DEL-0044 | TSK-01776 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.11.1.1 | 1.10.11.1 | QA | Outbound link clicks | QA | QA Engineer | Mid | 3 |  |  | 1.10.11.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.11.2 | 1.10.11 | Event Config | Outbound link clicks | Event Config |  |  | 0 | 212 | 11 | 1.10.11.1.1 |  |  | 0 | 0
1784 | DEL-0044 | TSK-01775 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.11.2.1 | 1.10.11.2 | Event Config | Outbound link clicks | Event Config | Data/Analytics Engineer | Mid | 3 |  |  | 1.10.11.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.12 | 1.10 | Publishing tags, Testing and Auditing | Publishing tags, Testing and Auditing |  |  |  | 5 | 209 | 3 | 1.10.11 |  |  | 195 | 975
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.12.1 | 1.10.12 | Publish & Smoke Test | Publishing tags, Testing and Auditing | Publish & Smoke Test |  |  | 0 | 209 | 3 | 1.10.12 |  |  | 0 | 0
1786 | DEL-0044 | TSK-01777 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.12.1.1 | 1.10.12.1 | Publish & Smoke Test | Publishing tags, Testing and Auditing | Publish & Smoke Test | Data/Analytics Engineer | Mid | 2 |  |  | 1.10.12.1 |  |  | 0 | 0
1787 | DEL-0044 | TSK-01778 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.12.1.2 | 1.10.12.1 | Publish & Smoke Test | Publishing tags, Testing and Auditing | Publish & Smoke Test | QA Engineer | Mid | 3 |  |  | 1.10.12.1.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.13 | 1.10 | Setup cross-domain tracking | Setup cross-domain tracking |  |  |  | 5 | 209 | 14 | 1.10.12 |  |  | 195 | 975
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.13.1 | 1.10.13 | QA | Setup cross-domain tracking | QA |  |  | 0 | 209 | 3 | 1.10.13 |  |  | 0 | 0
1789 | DEL-0044 | TSK-01780 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.13.1.1 | 1.10.13.1 | QA | Setup cross-domain tracking | QA | QA Engineer | Mid | 3 |  |  | 1.10.13.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.13.2 | 1.10.13 | Cross-domain Config | Setup cross-domain tracking | Cross-domain Config |  |  | 0 | 212 | 11 | 1.10.13.1.1 |  |  | 0 | 0
1788 | DEL-0044 | TSK-01779 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.13.2.1 | 1.10.13.2 | Cross-domain Config | Setup cross-domain tracking | Cross-domain Config | Data/Analytics Engineer | Mid | 2 |  |  | 1.10.13.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.14 | 1.10 | Setup eCommerce tracking | Setup eCommerce tracking |  |  |  | 5 | 209 | 14 | 1.10.13 |  |  | 195 | 975
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.14.1 | 1.10.14 | QA | Setup eCommerce tracking | QA |  |  | 0 | 209 | 3 | 1.10.14 |  |  | 0 | 0
1791 | DEL-0044 | TSK-01782 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.14.1.1 | 1.10.14.1 | QA | Setup eCommerce tracking | QA | QA Engineer | Mid | 3 |  |  | 1.10.14.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.14.2 | 1.10.14 | Ecommerce Data Layer | Setup eCommerce tracking | Ecommerce Data Layer |  |  | 0 | 212 | 11 | 1.10.14.1.1 |  |  | 0 | 0
1790 | DEL-0044 | TSK-01781 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.14.2.1 | 1.10.14.2 | Ecommerce Data Layer | Setup eCommerce tracking | Ecommerce Data Layer | Data/Analytics Engineer | Mid | 2 |  |  | 1.10.14.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.15 | 1.10 | Setup new GA4 acct for Caledera House | Setup new GA4 acct for Caledera House |  |  |  | 8 | 209 | 14 | 1.10.14 |  |  | 195 | 1560
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.15.1 | 1.10.15 | QA Cycle | Setup new GA4 acct for Caledera House | QA Cycle |  |  | 0 | 209 | 3 | 1.10.15 |  |  | 0 | 0
1793 | DEL-0044 | TSK-01784 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.15.1.1 | 1.10.15.1 | QA Cycle | Setup new GA4 acct for Caledera House | QA Cycle | QA Engineer | Mid | 3 |  |  | 1.10.15.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.15.2 | 1.10.15 | GA4 Property Setup | Setup new GA4 acct for Caledera House | GA4 Property Setup |  |  | 0 | 212 | 11 | 1.10.15.1.1 |  |  | 0 | 0
1792 | DEL-0044 | TSK-01783 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.10.15.2.1 | 1.10.15.2 | GA4 Property Setup | Setup new GA4 acct for Caledera House | GA4 Property Setup | Data/Analytics Engineer | Mid | 5 |  |  | 1.10.15.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11 | 1 | Post-Production |  |  |  |  | 222 | 223 | 50 | 1.10 |  | Advanced/T2_MediumVolume | 195 | 43290
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.1 | 1.11 | Content Licensing / Art Buying | Content Licensing / Art Buying |  |  |  | 2 | 223 | 4 | 1.11 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.1.1 | 1.11.1 | Rights/License Research | Content Licensing / Art Buying | Rights/License Research |  |  | 0 | 223 | 4 | 1.11.1 |  |  | 0 | 0
65 | DEL-0003 | TSK-00065 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.1.1.1 | 1.11.1.1 | Rights/License Research | Content Licensing / Art Buying | Rights/License Research | Producer | Mid | 1 |  |  | 1.11.1.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.1.2 | 1.11.1 | Usage Notes | Content Licensing / Art Buying | Usage Notes |  |  | 0 | 273 | 0 | 1.11.1.1.1 |  |  | 0 | 0
66 | DEL-0003 | TSK-00066 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.1.2.1 | 1.11.1.2 | Usage Notes | Content Licensing / Art Buying | Usage Notes | Account Manager | Mid | 1 |  |  | 1.11.1.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.2 | 1.11 | VO Recording Sessions | VO Recording Sessions |  |  |  | 6 | 227 | 5 | 1.11.1 |  |  | 195 | 1170
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.2.1 | 1.11.2 | Script Polish | VO Recording Sessions | Script Polish |  |  | 0 | 227 | 5 | 1.11.2 |  |  | 0 | 0
124 | DEL-0003 | TSK-00124 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.2.1.1 | 1.11.2.1 | Script Polish | VO Recording Sessions | Script Polish | Copywriter | Mid | 2 |  |  | 1.11.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.2.2 | 1.11.2 | VO Session | VO Recording Sessions | VO Session |  |  | 0 | 273 | 0 | 1.11.2.1.1 |  |  | 0 | 0
125 | DEL-0003 | TSK-00125 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.2.2.1 | 1.11.2.2 | VO Session | VO Recording Sessions | VO Session | Producer | Mid | 2 |  |  | 1.11.2.2 |  |  | 0 | 0
126 | DEL-0003 | TSK-00126 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.2.2.2 | 1.11.2.2 | VO Session | VO Recording Sessions | VO Session | Sound Designer | Mid | 2 |  |  | 1.11.2.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.3 | 1.11 | Editing | Editing |  |  |  | 20 | 232 | 6 | 1.11.2 |  |  | 195 | 3900
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.3.1 | 1.11.3 | Client Review & Revisions | Editing | Client Review & Revisions |  |  | 0 | 232 | 6 | 1.11.3 |  |  | 0 | 0
74 | DEL-0003 | TSK-00074 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.3.1.1 | 1.11.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.11.3.1 |  |  | 0 | 0
77 | DEL-0003 | TSK-00077 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.3.1.2 | 1.11.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.11.3.1.1 |  |  | 0 | 0
76 | DEL-0003 | TSK-00076 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.3.1.3 | 1.11.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.11.3.1.2 |  |  | 0 | 0
79 | DEL-0003 | TSK-00079 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.3.1.4 | 1.11.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Editor | Mid | 10 |  |  | 1.11.3.1.3 |  |  | 0 | 0
75 | DEL-0003 | TSK-00075 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.3.1.5 | 1.11.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Producer | Mid | 4 |  |  | 1.11.3.1.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.4 | 1.11 | Video Editing | Video Editing |  |  |  | 30 | 232 | 6 | 1.11.3 |  |  | 195 | 5850
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.4.1 | 1.11.4 | Client Review & Revisions | Video Editing | Client Review & Revisions |  |  | 0 | 232 | 6 | 1.11.4 |  |  | 0 | 0
127 | DEL-0003 | TSK-00127 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.4.1.1 | 1.11.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.11.4.1 |  |  | 0 | 0
131 | DEL-0003 | TSK-00131 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.4.1.2 | 1.11.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.11.4.1.1 |  |  | 0 | 0
129 | DEL-0003 | TSK-00129 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.4.1.3 | 1.11.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.11.4.1.2 |  |  | 0 | 0
130 | DEL-0003 | TSK-00130 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.4.1.4 | 1.11.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Editor | Mid | 20 |  |  | 1.11.4.1.3 |  |  | 0 | 0
128 | DEL-0003 | TSK-00128 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.4.1.5 | 1.11.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Producer | Mid | 4 |  |  | 1.11.4.1.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5 | 1.11 | Voice Over | Voice Over |  |  |  | 20 | 232 | 14 | 1.11.4 |  |  | 195 | 3900
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.1 | 1.11.5 | VO Edit | Voice Over | VO Edit |  |  | 0 | 232 | 6 | 1.11.5 |  |  | 0 | 0
140 | DEL-0003 | TSK-00140 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.1.1 | 1.11.5.1 | VO Edit | Voice Over | VO Edit | Editor | Mid | 10 |  |  | 1.11.5.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.2 | 1.11.5 | Mix | Voice Over | Mix |  |  | 0 | 253 | 3 | 1.11.5.1.1 |  |  | 0 | 0
139 | DEL-0003 | TSK-00139 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.2.1 | 1.11.5.2 | Mix | Voice Over | Mix | Sound Designer | Mid | 3 |  |  | 1.11.5.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.3 | 1.11.5 | Internal Review & Critique | Voice Over | Internal Review & Critique |  |  | 0 | 263 | 2 | 1.11.5.2.1 |  |  | 0 | 0
137 | DEL-0003 | TSK-00137 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.3.1 | 1.11.5.3 | Internal Review & Critique | Voice Over | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.11.5.3 |  |  | 0 | 0
138 | DEL-0003 | TSK-00138 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.3.2 | 1.11.5.3 | Internal Review & Critique | Voice Over | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.11.5.3.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.4 | 1.11.5 | Client Review & Revisions | Voice Over | Client Review & Revisions |  |  | 0 | 265 | 3 | 1.11.5.3.2 |  |  | 0 | 0
134 | DEL-0003 | TSK-00134 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.4.1 | 1.11.5.4 | Client Review & Revisions | Voice Over | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.11.5.4 |  |  | 0 | 0
135 | DEL-0003 | TSK-00135 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.4.2 | 1.11.5.4 | Client Review & Revisions | Voice Over | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.11.5.4.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.5 | 1.11.5 | Final Packaging | Voice Over | Final Packaging |  |  | 0 | 273 | 0 | 1.11.5.4.2 |  |  | 0 | 0
136 | DEL-0003 | TSK-00136 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.5.5.1 | 1.11.5.5 | Final Packaging | Voice Over | Final Packaging | Designer | Mid | 2 |  |  | 1.11.5.5 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.6 | 1.11 | Motion Design/VFX | Motion Design/VFX |  |  |  | 20 | 238 | 8 | 1.11.5 |  |  | 195 | 3900
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.6.1 | 1.11.6 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions |  |  | 0 | 238 | 8 | 1.11.6 |  |  | 0 | 0
90 | DEL-0003 | TSK-00090 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.6.1.1 | 1.11.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.11.6.1 |  |  | 0 | 0
94 | DEL-0003 | TSK-00094 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.6.1.2 | 1.11.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.11.6.1.1 |  |  | 0 | 0
92 | DEL-0003 | TSK-00092 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.6.1.3 | 1.11.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.11.6.1.2 |  |  | 0 | 0
96 | DEL-0003 | TSK-00096 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.6.1.4 | 1.11.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Editor | Mid | 6 |  |  | 1.11.6.1.3 |  |  | 0 | 0
93 | DEL-0003 | TSK-00093 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.6.1.5 | 1.11.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Motion Designer | Mid | 3 |  |  | 1.11.6.1.4 |  |  | 0 | 0
91 | DEL-0003 | TSK-00091 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.6.1.6 | 1.11.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Producer | Mid | 4 |  |  | 1.11.6.1.5 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.7 | 1.11 | Color Correction | Color Correction |  |  |  | 14 | 246 | 3 | 1.11.6 |  |  | 195 | 2730
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.7.1 | 1.11.7 | Client Review & Revisions | Color Correction | Client Review & Revisions |  |  | 0 | 246 | 3 | 1.11.7 |  |  | 0 | 0
53 | DEL-0003 | TSK-00053 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.7.1.1 | 1.11.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.11.7.1 |  |  | 0 | 0
55 | DEL-0003 | TSK-00055 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.7.1.2 | 1.11.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Colorist | Mid | 6 |  |  | 1.11.7.1.1 |  |  | 0 | 0
57 | DEL-0003 | TSK-00057 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.7.1.3 | 1.11.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.11.7.1.2 |  |  | 0 | 0
56 | DEL-0003 | TSK-00056 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.7.1.4 | 1.11.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.11.7.1.3 |  |  | 0 | 0
54 | DEL-0003 | TSK-00054 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.7.1.5 | 1.11.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.11.7.1.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.8 | 1.11 | Color Grading | Color Grading |  |  |  | 14 | 246 | 3 | 1.11.7 |  |  | 195 | 2730
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.8.1 | 1.11.8 | Client Review & Revisions | Color Grading | Client Review & Revisions |  |  | 0 | 246 | 3 | 1.11.8 |  |  | 0 | 0
59 | DEL-0003 | TSK-00059 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.8.1.1 | 1.11.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.11.8.1 |  |  | 0 | 0
61 | DEL-0003 | TSK-00061 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.8.1.2 | 1.11.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Colorist | Mid | 6 |  |  | 1.11.8.1.1 |  |  | 0 | 0
63 | DEL-0003 | TSK-00063 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.8.1.3 | 1.11.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.11.8.1.2 |  |  | 0 | 0
62 | DEL-0003 | TSK-00062 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.8.1.4 | 1.11.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.11.8.1.3 |  |  | 0 | 0
60 | DEL-0003 | TSK-00060 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.8.1.5 | 1.11.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.11.8.1.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9 | 1.11 | Final Retouched Stills Review | Final Retouched Stills Review |  |  |  | 12 | 249 | 9 | 1.11.8 |  |  | 195 | 2340
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9.1 | 1.11.9 | Retouch | Final Retouched Stills Review | Retouch |  |  | 0 | 249 | 4 | 1.11.9 |  |  | 0 | 0
89 | DEL-0003 | TSK-00089 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9.1.1 | 1.11.9.1 | Retouch | Final Retouched Stills Review | Retouch | Retoucher | Mid | 5 |  |  | 1.11.9.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9.2 | 1.11.9 | Internal Review & Critique | Final Retouched Stills Review | Internal Review & Critique |  |  | 0 | 263 | 2 | 1.11.9.1.1 |  |  | 0 | 0
87 | DEL-0003 | TSK-00087 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9.2.1 | 1.11.9.2 | Internal Review & Critique | Final Retouched Stills Review | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.11.9.2 |  |  | 0 | 0
88 | DEL-0003 | TSK-00088 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9.2.2 | 1.11.9.2 | Internal Review & Critique | Final Retouched Stills Review | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.11.9.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9.3 | 1.11.9 | Client Review & Revisions | Final Retouched Stills Review | Client Review & Revisions |  |  | 0 | 265 | 3 | 1.11.9.2.2 |  |  | 0 | 0
84 | DEL-0003 | TSK-00084 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9.3.1 | 1.11.9.3 | Client Review & Revisions | Final Retouched Stills Review | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.11.9.3 |  |  | 0 | 0
85 | DEL-0003 | TSK-00085 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9.3.2 | 1.11.9.3 | Client Review & Revisions | Final Retouched Stills Review | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.11.9.3.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9.4 | 1.11.9 | Final Packaging | Final Retouched Stills Review | Final Packaging |  |  | 0 | 273 | 0 | 1.11.9.3.2 |  |  | 0 | 0
86 | DEL-0003 | TSK-00086 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.9.4.1 | 1.11.9.4 | Final Packaging | Final Retouched Stills Review | Final Packaging | Designer | Mid | 2 |  |  | 1.11.9.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10 | 1.11 | Retouching | Retouching |  |  |  | 12 | 249 | 9 | 1.11.9 |  |  | 195 | 2340
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10.1 | 1.11.10 | Retouch | Retouching | Retouch |  |  | 0 | 249 | 4 | 1.11.10 |  |  | 0 | 0
102 | DEL-0003 | TSK-00102 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10.1.1 | 1.11.10.1 | Retouch | Retouching | Retouch | Retoucher | Mid | 5 |  |  | 1.11.10.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10.2 | 1.11.10 | Internal Review & Critique | Retouching | Internal Review & Critique |  |  | 0 | 263 | 2 | 1.11.10.1.1 |  |  | 0 | 0
100 | DEL-0003 | TSK-00100 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10.2.1 | 1.11.10.2 | Internal Review & Critique | Retouching | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.11.10.2 |  |  | 0 | 0
101 | DEL-0003 | TSK-00101 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10.2.2 | 1.11.10.2 | Internal Review & Critique | Retouching | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.11.10.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10.3 | 1.11.10 | Client Review & Revisions | Retouching | Client Review & Revisions |  |  | 0 | 265 | 3 | 1.11.10.2.2 |  |  | 0 | 0
97 | DEL-0003 | TSK-00097 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10.3.1 | 1.11.10.3 | Client Review & Revisions | Retouching | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.11.10.3 |  |  | 0 | 0
98 | DEL-0003 | TSK-00098 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10.3.2 | 1.11.10.3 | Client Review & Revisions | Retouching | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.11.10.3.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10.4 | 1.11.10 | Final Packaging | Retouching | Final Packaging |  |  | 0 | 273 | 0 | 1.11.10.3.2 |  |  | 0 | 0
99 | DEL-0003 | TSK-00099 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.10.4.1 | 1.11.10.4 | Final Packaging | Retouching | Final Packaging | Designer | Mid | 2 |  |  | 1.11.10.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.11 | 1.11 | Sound Mix | Sound Mix |  |  |  | 10 | 253 | 3 | 1.11.10 |  |  | 195 | 1950
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.11.1 | 1.11.11 | Client Review & Revisions | Sound Mix | Client Review & Revisions |  |  | 0 | 253 | 3 | 1.11.11 |  |  | 0 | 0
107 | DEL-0003 | TSK-00107 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.11.1.1 | 1.11.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.11.11.1 |  |  | 0 | 0
110 | DEL-0003 | TSK-00110 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.11.1.2 | 1.11.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.11.11.1.1 |  |  | 0 | 0
109 | DEL-0003 | TSK-00109 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.11.1.3 | 1.11.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.11.11.1.2 |  |  | 0 | 0
108 | DEL-0003 | TSK-00108 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.11.1.4 | 1.11.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.11.11.1.3 |  |  | 0 | 0
112 | DEL-0003 | TSK-00112 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.11.1.5 | 1.11.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Sound Designer | Mid | 2 |  |  | 1.11.11.1.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.12 | 1.11 | Sound Sourcing | Sound Sourcing |  |  |  | 3 | 253 | 3 | 1.11.11 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.12.1 | 1.11.12 | Music Search & License | Sound Sourcing | Music Search & License |  |  | 0 | 253 | 3 | 1.11.12 |  |  | 0 | 0
113 | DEL-0003 | TSK-00113 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.12.1.1 | 1.11.12.1 | Music Search & License | Sound Sourcing | Music Search & License | Producer | Mid | 1 |  |  | 1.11.12.1 |  |  | 0 | 0
114 | DEL-0003 | TSK-00114 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.12.1.2 | 1.11.12.1 | Music Search & License | Sound Sourcing | Music Search & License | Sound Designer | Mid | 2 |  |  | 1.11.12.1.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.13 | 1.11 | Final File Delivery | Final File Delivery |  |  |  | 8 | 256 | 3 | 1.11.12 |  |  | 195 | 1560
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.13.1 | 1.11.13 | QA (Tech & Content) | Final File Delivery | QA (Tech & Content) |  |  | 0 | 256 | 3 | 1.11.13 |  |  | 0 | 0
83 | DEL-0003 | TSK-00083 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.13.1.1 | 1.11.13.1 | QA (Tech & Content) | Final File Delivery | QA (Tech & Content) | QA Specialist | Mid | 3 |  |  | 1.11.13.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.13.2 | 1.11.13 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload |  |  | 0 | 273 | 0 | 1.11.13.1.1 |  |  | 0 | 0
80 | DEL-0003 | TSK-00080 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.13.2.1 | 1.11.13.2 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload | Media Manager / DIT | Mid | 2 |  |  | 1.11.13.2 |  |  | 0 | 0
81 | DEL-0003 | TSK-00081 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.13.2.2 | 1.11.13.2 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload | Producer | Mid | 2 |  |  | 1.11.13.2.1 |  |  | 0 | 0
82 | DEL-0003 | TSK-00082 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.13.2.3 | 1.11.13.2 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload | Project Manager | Mid | 1 |  |  | 1.11.13.2.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14 | 1.11 | True-ups (for vendor costs) | True-ups (for vendor costs) |  |  |  | 11 | 259 | 9 | 1.11.13 |  |  | 195 | 2145
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.1 | 1.11.14 | Change Orders & Tracking | True-ups (for vendor costs) | Change Orders & Tracking |  |  | 0 | 259 | 4 | 1.11.14 |  |  | 0 | 0
116 | DEL-0003 | TSK-00116 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.1.1 | 1.11.14.1 | Change Orders & Tracking | True-ups (for vendor costs) | Change Orders & Tracking | Project Manager | Mid | 1 |  |  | 1.11.14.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.2 | 1.11.14 | Internal Review & Critique | True-ups (for vendor costs) | Internal Review & Critique |  |  | 0 | 263 | 2 | 1.11.14.1.1 |  |  | 0 | 0
120 | DEL-0003 | TSK-00120 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.2.1 | 1.11.14.2 | Internal Review & Critique | True-ups (for vendor costs) | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.11.14.2 |  |  | 0 | 0
121 | DEL-0003 | TSK-00121 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.2.2 | 1.11.14.2 | Internal Review & Critique | True-ups (for vendor costs) | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.11.14.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.3 | 1.11.14 | Client Review & Revisions | True-ups (for vendor costs) | Client Review & Revisions |  |  | 0 | 265 | 3 | 1.11.14.2.2 |  |  | 0 | 0
117 | DEL-0003 | TSK-00117 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.3.1 | 1.11.14.3 | Client Review & Revisions | True-ups (for vendor costs) | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.11.14.3 |  |  | 0 | 0
118 | DEL-0003 | TSK-00118 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.3.2 | 1.11.14.3 | Client Review & Revisions | True-ups (for vendor costs) | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.11.14.3.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.4 | 1.11.14 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation |  |  | 0 | 273 | 0 | 1.11.14.3.2 |  |  | 0 | 0
122 | DEL-0003 | TSK-00122 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.4.1 | 1.11.14.4 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation | Account Manager | Mid | 2 |  |  | 1.11.14.4 |  |  | 0 | 0
119 | DEL-0003 | TSK-00119 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.4.2 | 1.11.14.4 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation | Designer | Mid | 2 |  |  | 1.11.14.4.1 |  |  | 0 | 0
123 | DEL-0003 | TSK-00123 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.14.4.3 | 1.11.14.4 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation | Producer | Mid | 1 |  |  | 1.11.14.4.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.15 | 1.11 | Cutdowns | Cutdowns |  |  |  | 13 | 263 | 5 | 1.11.14 |  |  | 195 | 2535
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.15.1 | 1.11.15 | Internal Review & Critique | Cutdowns | Internal Review & Critique |  |  | 0 | 263 | 2 | 1.11.15 |  |  | 0 | 0
71 | DEL-0003 | TSK-00071 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.15.1.1 | 1.11.15.1 | Internal Review & Critique | Cutdowns | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.11.15.1 |  |  | 0 | 0
72 | DEL-0003 | TSK-00072 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.15.1.2 | 1.11.15.1 | Internal Review & Critique | Cutdowns | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.11.15.1.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.15.2 | 1.11.15 | Client Review & Revisions | Cutdowns | Client Review & Revisions |  |  | 0 | 265 | 3 | 1.11.15.1.2 |  |  | 0 | 0
67 | DEL-0003 | TSK-00067 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.15.2.1 | 1.11.15.2 | Client Review & Revisions | Cutdowns | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.11.15.2 |  |  | 0 | 0
68 | DEL-0003 | TSK-00068 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.15.2.2 | 1.11.15.2 | Client Review & Revisions | Cutdowns | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.11.15.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.15.3 | 1.11.15 | Cutdowns (2-3) | Cutdowns | Cutdowns (2-3) |  |  | 0 | 273 | 0 | 1.11.15.2.2 |  |  | 0 | 0
70 | DEL-0003 | TSK-00070 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.15.3.1 | 1.11.15.3 | Cutdowns (2-3) | Cutdowns | Cutdowns (2-3) | Designer | Mid | 2 |  |  | 1.11.15.3 |  |  | 0 | 0
69 | DEL-0003 | TSK-00069 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.15.3.2 | 1.11.15.3 | Cutdowns (2-3) | Cutdowns | Cutdowns (2-3) | Editor | Mid | 6 |  |  | 1.11.15.3.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.16 | 1.11 | Client Review | Client Review |  |  |  | 5 | 265 | 3 | 1.11.15 |  |  | 195 | 975
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.16.1 | 1.11.16 | Client Review Coordination | Client Review | Client Review Coordination |  |  | 0 | 265 | 3 | 1.11.16 |  |  | 0 | 0
50 | DEL-0003 | TSK-00050 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.16.1.1 | 1.11.16.1 | Client Review Coordination | Client Review | Client Review Coordination | Account Manager | Mid | 2 |  |  | 1.11.16.1 |  |  | 0 | 0
51 | DEL-0003 | TSK-00051 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.16.1.2 | 1.11.16.1 | Client Review Coordination | Client Review | Client Review Coordination | Producer | Mid | 2 |  |  | 1.11.16.1.1 |  |  | 0 | 0
52 | DEL-0003 | TSK-00052 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.16.1.3 | 1.11.16.1 | Client Review Coordination | Client Review | Client Review Coordination | Project Manager | Mid | 1 |  |  | 1.11.16.1.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.17 | 1.11 | Review & Sign-Off | Review & Sign-Off |  |  |  | 4 | 265 | 5 | 1.11.16 |  |  | 195 | 780
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.17.1 | 1.11.17 | Client Review Coordination | Review & Sign-Off | Client Review Coordination |  |  | 0 | 265 | 3 | 1.11.17 |  |  | 0 | 0
103 | DEL-0003 | TSK-00103 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.17.1.1 | 1.11.17.1 | Client Review Coordination | Review & Sign-Off | Client Review Coordination | Account Manager | Mid | 2 |  |  | 1.11.17.1 |  |  | 0 | 0
104 | DEL-0003 | TSK-00104 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.17.1.2 | 1.11.17.1 | Client Review Coordination | Review & Sign-Off | Client Review Coordination | Producer | Mid | 1 |  |  | 1.11.17.1.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.17.2 | 1.11.17 | Notes Triage | Review & Sign-Off | Notes Triage |  |  | 0 | 271 | 2 | 1.11.17.1.2 |  |  | 0 | 0
105 | DEL-0003 | TSK-00105 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.17.2.1 | 1.11.17.2 | Notes Triage | Review & Sign-Off | Notes Triage | Project Manager | Mid | 1 |  |  | 1.11.17.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.18 | 1.11 | Asset Library | Asset Library |  |  |  | 2 | 268 | 3 | 1.11.17 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.18.1 | 1.11.18 | Post Support | Asset Library | Post Support |  |  | 0 | 268 | 3 | 1.11.18 |  |  | 0 | 0
48 | DEL-0003 | TSK-00048 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.18.1.1 | 1.11.18.1 | Post Support | Asset Library | Post Support | Editor | Mid | 2 |  |  | 1.11.18.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.19 | 1.11 | Capture Library | Capture Library |  |  |  | 2 | 268 | 3 | 1.11.18 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.19.1 | 1.11.19 | Post Support | Capture Library | Post Support |  |  | 0 | 268 | 3 | 1.11.19 |  |  | 0 | 0
49 | DEL-0003 | TSK-00049 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.19.1.1 | 1.11.19.1 | Post Support | Capture Library | Post Support | Editor | Mid | 2 |  |  | 1.11.19.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.20 | 1.11 | Selects Deck | Selects Deck |  |  |  | 2 | 268 | 3 | 1.11.19 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.20.1 | 1.11.20 | Post Support | Selects Deck | Post Support |  |  | 0 | 268 | 3 | 1.11.20 |  |  | 0 | 0
106 | DEL-0003 | TSK-00106 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.20.1.1 | 1.11.20.1 | Post Support | Selects Deck | Post Support | Editor | Mid | 2 |  |  | 1.11.20.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.21 | 1.11 | Delivery | Delivery |  |  |  | 6 | 273 | 0 | 1.11.20 |  |  | 195 | 1170
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.21.1 | 1.11.21 | Post Support | Delivery | Post Support |  |  | 0 | 273 | 0 | 1.11.21 |  |  | 0 | 0
73 | DEL-0003 | TSK-00073 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.21.1.1 | 1.11.21.1 | Post Support | Delivery | Post Support | Editor | Mid | 6 |  |  | 1.11.21.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.22 | 1.11 | Stills/Footage Selection | Stills/Footage Selection |  |  |  | 6 | 273 | 0 | 1.11.21 |  |  | 195 | 1170
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.22.1 | 1.11.22 | Post Support | Stills/Footage Selection | Post Support |  |  | 0 | 273 | 0 | 1.11.22 |  |  | 0 | 0
115 | DEL-0003 | TSK-00115 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.11.22.1.1 | 1.11.22.1 | Post Support | Stills/Footage Selection | Post Support | Editor | Mid | 6 |  |  | 1.11.22.1 |  |  | 0 | 0