## Sheet1
Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Deliverable | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes
RFP_154542403_Digital_Marketing_Services | 1.1 | 1 | Development | Development |  |  |  |  | 347.75 | 0 | 28 |  |  | Advanced / T1_LargeVolume
RFP_154542403_Digital_Marketing_Services | 1.1.1 | 1.1 | research | Development |  | research |  |  |  |  | 4
RFP_154542403_Digital_Marketing_Services | 1.1.2 | 1.1 | design_prod | Development |  | design_prod |  |  |  |  | 9
RFP_154542403_Digital_Marketing_Services | 1.1.3 | 1.1 | qa | Development |  | qa |  |  |  |  | 3
RFP_154542403_Digital_Marketing_Services | 1.1.4 | 1.1 | development | Development |  | development |  |  |  |  | 12
RFP_154542403_Digital_Marketing_Services | 1.2 | 1 | Reporting | Reporting |  |  |  |  | 166.4 | 0 | 7 |  |  | Advanced / T1_LargeVolume
RFP_154542403_Digital_Marketing_Services | 1.2.1 | 1.2 | qa | Reporting |  | qa |  |  |  |  | 3
RFP_154542403_Digital_Marketing_Services | 1.2.2 | 1.2 | reporting | Reporting |  | reporting |  |  |  |  | 4
RFP_154542403_Digital_Marketing_Services | 1.2.3 | 1.2 | general | Reporting |  | general |  |  |  |  | 0
RFP_154542403_Digital_Marketing_Services | 1.3 | 1 | Reporting | Reporting |  |  |  |  | 89.38 | 0 | 19 |  |  | Advanced / T1_LargeVolume
RFP_154542403_Digital_Marketing_Services | 1.3.1 | 1.3 | copywriting | Reporting |  | copywriting |  |  |  |  | 4
RFP_154542403_Digital_Marketing_Services | 1.3.2 | 1.3 | qa | Reporting |  | qa |  |  |  |  | 3
RFP_154542403_Digital_Marketing_Services | 1.3.3 | 1.3 | analytics_tagging | Reporting |  | analytics_tagging |  |  |  |  | 4
RFP_154542403_Digital_Marketing_Services | 1.3.4 | 1.3 | reporting | Reporting |  | reporting |  |  |  |  | 4
RFP_154542403_Digital_Marketing_Services | 1.3.5 | 1.3 | pm_admin | Reporting |  | pm_admin |  |  |  |  | 2
RFP_154542403_Digital_Marketing_Services | 1.3.6 | 1.3 | status_meeting | Reporting |  | status_meeting |  |  |  |  | 2
RFP_154542403_Digital_Marketing_Services | 1.3.7 | 1.3 | general | Reporting |  | general |  |  |  |  | 0
RFP_154542403_Digital_Marketing_Services | 1.4 | 1 | Paid Media Assets | Paid Media Assets |  |  |  |  | 193.11 | 0 | 24 |  |  | Advanced / T1_LargeVolume
RFP_154542403_Digital_Marketing_Services | 1.4.1 | 1.4 | copywriting | Paid Media Assets |  | copywriting |  |  |  |  | 4
RFP_154542403_Digital_Marketing_Services | 1.4.2 | 1.4 | design_prod | Paid Media Assets |  | design_prod |  |  |  |  | 9
RFP_154542403_Digital_Marketing_Services | 1.4.3 | 1.4 | sound | Paid Media Assets |  | sound |  |  |  |  | 3
RFP_154542403_Digital_Marketing_Services | 1.4.4 | 1.4 | qa | Paid Media Assets |  | qa |  |  |  |  | 3
RFP_154542403_Digital_Marketing_Services | 1.4.5 | 1.4 | internal_review | Paid Media Assets |  | internal_review |  |  |  |  | 2
RFP_154542403_Digital_Marketing_Services | 1.4.6 | 1.4 | client_review | Paid Media Assets |  | client_review |  |  |  |  | 3
RFP_154542403_Digital_Marketing_Services | 1.4.7 | 1.4 | general | Paid Media Assets |  | general |  |  |  |  | 0
RFP_154542403_Digital_Marketing_Services | 1.5 | 1 | Brand Style & Usage Guidelines | Brand Style & Usage Guidelines |  |  |  |  | 382.29 | 0 | 11 |  |  | Advanced / T1_LargeVolume
RFP_154542403_Digital_Marketing_Services | 1.5.1 | 1.5 | color | Brand Style & Usage Guidelines |  | color |  |  |  |  | 3
RFP_154542403_Digital_Marketing_Services | 1.5.2 | 1.5 | qa | Brand Style & Usage Guidelines |  | qa |  |  |  |  | 3
RFP_154542403_Digital_Marketing_Services | 1.5.3 | 1.5 | internal_review | Brand Style & Usage Guidelines |  | internal_review |  |  |  |  | 2
RFP_154542403_Digital_Marketing_Services | 1.5.4 | 1.5 | client_review | Brand Style & Usage Guidelines |  | client_review |  |  |  |  | 3
RFP_154542403_Digital_Marketing_Services | 1.5.5 | 1.5 | brand_identity | Brand Style & Usage Guidelines |  | brand_identity |  |  |  |  | 0
RFP_154542403_Digital_Marketing_Services | 1.5.6 | 1.5 | style_guide | Brand Style & Usage Guidelines |  | style_guide |  |  |  |  | 0
RFP_154542403_Digital_Marketing_Services | 1.5.7 | 1.5 | treatment | Brand Style & Usage Guidelines |  | treatment |  |  |  |  | 0
RFP_154542403_Digital_Marketing_Services | 1.6 | 1 | Post-Production | Post-Production |  |  |  |  | 288.3 | 0 | 51 |  |  | Advanced / T1_LargeVolume
RFP_154542403_Digital_Marketing_Services | 1.6.1 | 1.6 | research | Post-Production |  | research |  |  |  |  | 4
RFP_154542403_Digital_Marketing_Services | 1.6.2 | 1.6 | prepro_docs | Post-Production |  | prepro_docs |  |  |  |  | 5
RFP_154542403_Digital_Marketing_Services | 1.6.3 | 1.6 | edit | Post-Production |  | edit |  |  |  |  | 6
RFP_154542403_Digital_Marketing_Services | 1.6.4 | 1.6 | motion | Post-Production |  | motion |  |  |  |  | 9
RFP_154542403_Digital_Marketing_Services | 1.6.5 | 1.6 | color | Post-Production |  | color |  |  |  |  | 3
RFP_154542403_Digital_Marketing_Services | 1.6.6 | 1.6 | retouch | Post-Production |  | retouch |  |  |  |  | 4
RFP_154542403_Digital_Marketing_Services | 1.6.7 | 1.6 | sound | Post-Production |  | sound |  |  |  |  | 3
RFP_154542403_Digital_Marketing_Services | 1.6.8 | 1.6 | qa | Post-Production |  | qa |  |  |  |  | 3
RFP_154542403_Digital_Marketing_Services | 1.6.9 | 1.6 | analytics_tagging | Post-Production |  | analytics_tagging |  |  |  |  | 4
RFP_154542403_Digital_Marketing_Services | 1.6.10 | 1.6 | internal_review | Post-Production |  | internal_review |  |  |  |  | 2
RFP_154542403_Digital_Marketing_Services | 1.6.11 | 1.6 | client_review | Post-Production |  | client_review |  |  |  |  | 3
RFP_154542403_Digital_Marketing_Services | 1.6.12 | 1.6 | library | Post-Production |  | library |  |  |  |  | 3
RFP_154542403_Digital_Marketing_Services | 1.6.13 | 1.6 | notes_triage | Post-Production |  | notes_triage |  |  |  |  | 2
RFP_154542403_Digital_Marketing_Services | 1.6.14 | 1.6 | general | Post-Production |  | general |  |  |  |  | 0
RFP_154542403_Digital_Marketing_Services | 1.7 | 1 | Brand Identity Development | Brand Identity Development |  |  |  |  | 390.74 | 0 | 15 |  |  | Advanced / T1_LargeVolume
RFP_154542403_Digital_Marketing_Services | 1.7.1 | 1.7 | color | Brand Identity Development |  | color |  |  |  |  | 3
RFP_154542403_Digital_Marketing_Services | 1.7.2 | 1.7 | retouch | Brand Identity Development |  | retouch |  |  |  |  | 4
RFP_154542403_Digital_Marketing_Services | 1.7.3 | 1.7 | qa | Brand Identity Development |  | qa |  |  |  |  | 3
RFP_154542403_Digital_Marketing_Services | 1.7.4 | 1.7 | internal_review | Brand Identity Development |  | internal_review |  |  |  |  | 2
RFP_154542403_Digital_Marketing_Services | 1.7.5 | 1.7 | client_review | Brand Identity Development |  | client_review |  |  |  |  | 3
RFP_154542403_Digital_Marketing_Services | 1.7.6 | 1.7 | brand_identity | Brand Identity Development |  | brand_identity |  |  |  |  | 0
RFP_154542403_Digital_Marketing_Services | 1.8 | 1 | Paid Media Strategy | Paid Media Strategy |  |  |  |  | 211.36 | 0 | 48 |  |  | Advanced / T1_LargeVolume
RFP_154542403_Digital_Marketing_Services | 1.8.1 | 1.8 | research | Paid Media Strategy |  | research |  |  |  |  | 4
RFP_154542403_Digital_Marketing_Services | 1.8.2 | 1.8 | deck_build | Paid Media Strategy |  | deck_build |  |  |  |  | 6
RFP_154542403_Digital_Marketing_Services | 1.8.3 | 1.8 | copywriting | Paid Media Strategy |  | copywriting |  |  |  |  | 4
RFP_154542403_Digital_Marketing_Services | 1.8.4 | 1.8 | design_prod | Paid Media Strategy |  | design_prod |  |  |  |  | 9
RFP_154542403_Digital_Marketing_Services | 1.8.5 | 1.8 | media_planning | Paid Media Strategy |  | media_planning |  |  |  |  | 6
RFP_154542403_Digital_Marketing_Services | 1.8.6 | 1.8 | development | Paid Media Strategy |  | development |  |  |  |  | 12
RFP_154542403_Digital_Marketing_Services | 1.8.7 | 1.8 | internal_review | Paid Media Strategy |  | internal_review |  |  |  |  | 2
RFP_154542403_Digital_Marketing_Services | 1.8.8 | 1.8 | client_review | Paid Media Strategy |  | client_review |  |  |  |  | 3
RFP_154542403_Digital_Marketing_Services | 1.8.9 | 1.8 | pm_admin | Paid Media Strategy |  | pm_admin |  |  |  |  | 2
RFP_154542403_Digital_Marketing_Services | 1.8.10 | 1.8 | general | Paid Media Strategy |  | general |  |  |  |  | 0