## Scenario A
Row_ID | Deliverable_Code | Task_Code | Service_Department | Deliverable | Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes | Rate_USD | Price_USD
[5 empty] | Vascano Tequila - RFP Creative Services 2022 (8) | 1 |  | Vascano Tequila - RFP Creative Services 2022 (8) | Project |  |  |  | 0 | 0 |  |  |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1 | 1 | Development |  |  |  |  | 227 | 0 | 22 |  |  | Core/T2_MediumVolume | 195 | 44265
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1 | 1.1 | ADA Compliance | ADA Compliance |  |  |  | 50 | 0 | 15 | 1.1 |  |  | 195 | 9750
1738 | DEL-0044 | TSK-01729 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.1 | 1.1.1 | Accessibility Audit | ADA Compliance | Accessibility Audit | Accessibility Specialist | Mid | 2 | 0 | 3 | 1.1.1 |  |  | 195 | 390
1739 | DEL-0044 | TSK-01730 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.2 | 1.1.1 | Accessibility QA | ADA Compliance | Accessibility QA | QA Engineer | Mid | 4 | 10 | 2 | 1.1.1.1 |  |  | 195 | 780
1740 | DEL-0044 | TSK-01731 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.3 | 1.1.1 | Code Review | ADA Compliance | Code Review | Frontend Engineer | Mid | 44 | 12 | 10 | 1.1.1.2 |  |  | 195 | 8580
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2 | 1.1 | Audit & Requirement gathering | Audit & Requirement gathering |  |  |  | 17 | 0 | 3 | 1.1.1 |  |  | 195 | 3315
1749 | DEL-0044 | TSK-01740 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.1 | 1.1.2 | Analytics Audit | Audit & Requirement gathering | Analytics Audit | Business Analyst | Mid | 17 | 0 | 3 | 1.1.2 |  |  | 195 | 3315
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3 | 1.1 | Audit existing UA Property | Audit existing UA Property |  |  |  | 17 | 0 | 3 | 1.1.2 |  |  | 195 | 3315
1753 | DEL-0044 | TSK-01744 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.1 | 1.1.3 | Documentation | Audit existing UA Property | Documentation | Business Analyst | Mid | 17 | 0 | 3 | 1.1.3 |  |  | 195 | 3315
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4 | 1.1 | Footer CTA | Footer CTA |  |  |  | 43 | 3 | 19 | 1.1.3 |  |  | 195 | 8385
1765 | DEL-0044 | TSK-01756 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.1 | 1.1.4 | Design Consult | Footer CTA | Design Consult | UI Designer | Mid | 3 | 3 | 7 | 1.1.4 |  |  | 195 | 585
1760 | DEL-0044 | TSK-01751 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.2 | 1.1.4 | Accessibility QA | Footer CTA | Accessibility QA | QA Engineer | Mid | 6 | 10 | 2 | 1.1.4.1 |  |  | 195 | 1170
1761 | DEL-0044 | TSK-01752 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.3 | 1.1.4 | Code Review | Footer CTA | Code Review | Backend Engineer | Mid | 34 | 12 | 10 | 1.1.4.2 |  |  | 195 | 6630
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5 | 1.1 | Header & Footer Navigation | Header & Footer Navigation |  |  |  | 43 | 3 | 19 | 1.1.4 |  |  | 195 | 8385
1773 | DEL-0044 | TSK-01764 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.1 | 1.1.5 | Design Consult | Header & Footer Navigation | Design Consult | UI Designer | Mid | 3 | 3 | 7 | 1.1.5 |  |  | 195 | 585
1768 | DEL-0044 | TSK-01759 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.2 | 1.1.5 | Accessibility QA | Header & Footer Navigation | Accessibility QA | QA Engineer | Mid | 6 | 10 | 2 | 1.1.5.1 |  |  | 195 | 1170
1769 | DEL-0044 | TSK-01760 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.3 | 1.1.5 | Code Review | Header & Footer Navigation | Code Review | Backend Engineer | Mid | 34 | 12 | 10 | 1.1.5.2 |  |  | 195 | 6630
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6 | 1.1 | Additional Goals Setup | Additional Goals Setup |  |  |  | 7 | 10 | 12 | 1.1.5 |  |  | 195 | 1365
1747 | DEL-0044 | TSK-01738 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.1 | 1.1.6 | QA Cycle | Additional Goals Setup | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.6 |  |  | 195 | 585
1746 | DEL-0044 | TSK-01737 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.2 | 1.1.6 | Define & Configure Goals | Additional Goals Setup | Define & Configure Goals | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.6.1 |  |  | 195 | 780
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7 | 1.1 | Custom Event Tracking | Custom Event Tracking |  |  |  | 7 | 10 | 12 | 1.1.6 |  |  | 195 | 1365
1758 | DEL-0044 | TSK-01749 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.1 | 1.1.7 | QA Cycle | Custom Event Tracking | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.7 |  |  | 195 | 585
1757 | DEL-0044 | TSK-01748 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.2 | 1.1.7 | Event Schema & Tagging | Custom Event Tracking | Event Schema & Tagging | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.7.1 |  |  | 195 | 780
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8 | 1.1 | Implement Paid Media Pixel on website w GTM-Google Ads | Implement Paid Media Pixel on website w GTM-Google Ads |  |  |  | 5 | 10 | 12 | 1.1.7 |  |  | 195 | 975
1777 | DEL-0044 | TSK-01768 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.1 | 1.1.8 | Spec QA | Implement Paid Media Pixel on website w GTM-Google Ads | Spec QA | QA Engineer | Mid | 3 | 10 | 2 | 1.1.8 |  |  | 195 | 585
1776 | DEL-0044 | TSK-01767 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.2 | 1.1.8 | Pixel Setup (GTM) | Implement Paid Media Pixel on website w GTM-Google Ads | Pixel Setup (GTM) | Data/Analytics Engineer | Mid | 2 | 12 | 10 | 1.1.8.1 |  |  | 195 | 390
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9 | 1.1 | Implement goals listed in UA as Conversions in G4 | Implement goals listed in UA as Conversions in G4 |  |  |  | 7 | 10 | 12 | 1.1.8 |  |  | 195 | 1365
1779 | DEL-0044 | TSK-01770 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.1 | 1.1.9 | QA Cycle | Implement goals listed in UA as Conversions in G4 | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.9 |  |  | 195 | 585
1778 | DEL-0044 | TSK-01769 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.2 | 1.1.9 | Migrate UA Goals → GA4 Conversions | Implement goals listed in UA as Conversions in G4 | Migrate UA Goals → GA4 Conversions | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.9.1 |  |  | 195 | 780
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10 | 1.1 | Implementation | Implementation |  |  |  | 7 | 10 | 12 | 1.1.9 |  |  | 195 | 1365
1782 | DEL-0044 | TSK-01773 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.1 | 1.1.10 | QA Cycle | Implementation | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.10 |  |  | 195 | 585
1781 | DEL-0044 | TSK-01772 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.2 | 1.1.10 | Implement Tags/Events | Implementation | Implement Tags/Events | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.10.1 |  |  | 195 | 780
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11 | 1.1 | Outbound link clicks | Outbound link clicks |  |  |  | 5 | 10 | 12 | 1.1.10 |  |  | 195 | 975
1785 | DEL-0044 | TSK-01776 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11.1 | 1.1.11 | QA | Outbound link clicks | QA | QA Engineer | Mid | 3 | 10 | 2 | 1.1.11 |  |  | 195 | 585
1784 | DEL-0044 | TSK-01775 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11.2 | 1.1.11 | Event Config | Outbound link clicks | Event Config | Data/Analytics Engineer | Mid | 2 | 12 | 10 | 1.1.11.1 |  |  | 195 | 390
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.12 | 1.1 | Publishing tags, Testing and Auditing | Publishing tags, Testing and Auditing |  |  |  | 4 | 10 | 2 | 1.1.11 |  |  | 195 | 780
1786 | DEL-0044 | TSK-01777 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.12.1 | 1.1.12 | Publish & Smoke Test | Publishing tags, Testing and Auditing | Publish & Smoke Test | QA Engineer | Mid | 4 | 10 | 2 | 1.1.12 |  |  | 195 | 780
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.13 | 1.1 | Setup cross-domain tracking | Setup cross-domain tracking |  |  |  | 4 | 10 | 12 | 1.1.12 |  |  | 195 | 780
1789 | DEL-0044 | TSK-01780 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.13.1 | 1.1.13 | QA | Setup cross-domain tracking | QA | QA Engineer | Mid | 2 | 10 | 2 | 1.1.13 |  |  | 195 | 390
1788 | DEL-0044 | TSK-01779 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.13.2 | 1.1.13 | Cross-domain Config | Setup cross-domain tracking | Cross-domain Config | Data/Analytics Engineer | Mid | 2 | 12 | 10 | 1.1.13.1 |  |  | 195 | 390
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.14 | 1.1 | Setup eCommerce tracking | Setup eCommerce tracking |  |  |  | 4 | 10 | 12 | 1.1.13 |  |  | 195 | 780
1791 | DEL-0044 | TSK-01782 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.14.1 | 1.1.14 | QA | Setup eCommerce tracking | QA | QA Engineer | Mid | 2 | 10 | 2 | 1.1.14 |  |  | 195 | 390
1790 | DEL-0044 | TSK-01781 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.14.2 | 1.1.14 | Ecommerce Data Layer | Setup eCommerce tracking | Ecommerce Data Layer | Data/Analytics Engineer | Mid | 2 | 12 | 10 | 1.1.14.1 |  |  | 195 | 390
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.15 | 1.1 | Setup new GA4 acct for Caledera House | Setup new GA4 acct for Caledera House |  |  |  | 7 | 10 | 12 | 1.1.14 |  |  | 195 | 1365
1793 | DEL-0044 | TSK-01784 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.15.1 | 1.1.15 | QA Cycle | Setup new GA4 acct for Caledera House | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.15 |  |  | 195 | 585
1792 | DEL-0044 | TSK-01783 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.15.2 | 1.1.15 | GA4 Property Setup | Setup new GA4 acct for Caledera House | GA4 Property Setup | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.15.1 |  |  | 195 | 780
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2 | 1 | Post-Production |  |  |  |  | 188 | 22 | 41 | 1.1 |  | Core/T2_MediumVolume | 195 | 36660
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1 | 1.2 | Content Licensing / Art Buying | Content Licensing / Art Buying |  |  |  | 2 | 22 | 3 | 1.2 |  |  | 195 | 390
65 | DEL-0003 | TSK-00065 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1.1 | 1.2.1 | Rights/License Research | Content Licensing / Art Buying | Rights/License Research | Producer | Mid | 1 | 22 | 3 | 1.2.1 |  |  | 195 | 195
66 | DEL-0003 | TSK-00066 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1.2 | 1.2.1 | Usage Notes | Content Licensing / Art Buying | Usage Notes | Account Manager | Mid | 1 | 63 | 0 | 1.2.1.1 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2 | 1.2 | VO Recording Sessions | VO Recording Sessions |  |  |  | 5 | 25 | 4 | 1.2.1 |  |  | 195 | 975
124 | DEL-0003 | TSK-00124 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.1 | 1.2.2 | Script Polish | VO Recording Sessions | Script Polish | Copywriter | Mid | 1 | 25 | 4 | 1.2.2 |  |  | 195 | 195
125 | DEL-0003 | TSK-00125 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.2 | 1.2.2 | VO Session | VO Recording Sessions | VO Session | Sound Designer | Mid | 4 | 63 | 0 | 1.2.2.1 |  |  | 195 | 780
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3 | 1.2 | Editing | Editing |  |  |  | 17 | 29 | 5 | 1.2.2 |  |  | 195 | 3315
74 | DEL-0003 | TSK-00074 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.1 | 1.2.3 | Client Review & Revisions | Editing | Client Review & Revisions | Editor | Mid | 17 | 29 | 5 | 1.2.3 |  |  | 195 | 3315
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4 | 1.2 | Video Editing | Video Editing |  |  |  | 25 | 29 | 5 | 1.2.3 |  |  | 195 | 4875
127 | DEL-0003 | TSK-00127 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.1 | 1.2.4 | Client Review & Revisions | Video Editing | Client Review & Revisions | Editor | Mid | 25 | 29 | 5 | 1.2.4 |  |  | 195 | 4875
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5 | 1.2 | Voice Over | Voice Over |  |  |  | 17 | 29 | 12 | 1.2.4 |  |  | 195 | 3315
140 | DEL-0003 | TSK-00140 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.1 | 1.2.5 | VO Edit | Voice Over | VO Edit | Editor | Mid | 9 | 29 | 5 | 1.2.5 |  |  | 195 | 1755
139 | DEL-0003 | TSK-00139 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.2 | 1.2.5 | Mix | Voice Over | Mix | Sound Designer | Mid | 2 | 46 | 2 | 1.2.5.1 |  |  | 195 | 390
137 | DEL-0003 | TSK-00137 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.3 | 1.2.5 | Internal Review & Critique | Voice Over | Internal Review & Critique | Producer | Mid | 1 | 53 | 2 | 1.2.5.2 |  |  | 195 | 195
134 | DEL-0003 | TSK-00134 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.4 | 1.2.5 | Client Review & Revisions | Voice Over | Client Review & Revisions | Account Manager | Mid | 3 | 55 | 3 | 1.2.5.3 |  |  | 195 | 585
136 | DEL-0003 | TSK-00136 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.5 | 1.2.5 | Final Packaging | Voice Over | Final Packaging | Designer | Mid | 2 | 63 | 0 | 1.2.5.4 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6 | 1.2 | Motion Design/VFX | Motion Design/VFX |  |  |  | 17 | 34 | 7 | 1.2.5 |  |  | 195 | 3315
90 | DEL-0003 | TSK-00090 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.1 | 1.2.6 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Editor | Mid | 17 | 34 | 7 | 1.2.6 |  |  | 195 | 3315
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7 | 1.2 | Color Correction | Color Correction |  |  |  | 11 | 41 | 2 | 1.2.6 |  |  | 195 | 2145
53 | DEL-0003 | TSK-00053 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.1 | 1.2.7 | Client Review & Revisions | Color Correction | Client Review & Revisions | Colorist | Mid | 11 | 41 | 2 | 1.2.7 |  |  | 195 | 2145
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8 | 1.2 | Color Grading | Color Grading |  |  |  | 11 | 41 | 2 | 1.2.7 |  |  | 195 | 2145
59 | DEL-0003 | TSK-00059 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.1 | 1.2.8 | Client Review & Revisions | Color Grading | Client Review & Revisions | Colorist | Mid | 11 | 41 | 2 | 1.2.8 |  |  | 195 | 2145
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9 | 1.2 | Final Retouched Stills Review | Final Retouched Stills Review |  |  |  | 10 | 43 | 8 | 1.2.8 |  |  | 195 | 1950
89 | DEL-0003 | TSK-00089 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.1 | 1.2.9 | Retouch | Final Retouched Stills Review | Retouch | Retoucher | Mid | 4 | 43 | 3 | 1.2.9 |  |  | 195 | 780
87 | DEL-0003 | TSK-00087 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.2 | 1.2.9 | Internal Review & Critique | Final Retouched Stills Review | Internal Review & Critique | Producer | Mid | 1 | 53 | 2 | 1.2.9.1 |  |  | 195 | 195
84 | DEL-0003 | TSK-00084 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.3 | 1.2.9 | Client Review & Revisions | Final Retouched Stills Review | Client Review & Revisions | Account Manager | Mid | 3 | 55 | 3 | 1.2.9.2 |  |  | 195 | 585
86 | DEL-0003 | TSK-00086 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.4 | 1.2.9 | Final Packaging | Final Retouched Stills Review | Final Packaging | Designer | Mid | 2 | 63 | 0 | 1.2.9.3 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10 | 1.2 | Retouching | Retouching |  |  |  | 10 | 43 | 8 | 1.2.9 |  |  | 195 | 1950
102 | DEL-0003 | TSK-00102 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.1 | 1.2.10 | Retouch | Retouching | Retouch | Retoucher | Mid | 4 | 43 | 3 | 1.2.10 |  |  | 195 | 780
100 | DEL-0003 | TSK-00100 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.2 | 1.2.10 | Internal Review & Critique | Retouching | Internal Review & Critique | Producer | Mid | 1 | 53 | 2 | 1.2.10.1 |  |  | 195 | 195
97 | DEL-0003 | TSK-00097 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.3 | 1.2.10 | Client Review & Revisions | Retouching | Client Review & Revisions | Account Manager | Mid | 3 | 55 | 3 | 1.2.10.2 |  |  | 195 | 585
99 | DEL-0003 | TSK-00099 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.4 | 1.2.10 | Final Packaging | Retouching | Final Packaging | Designer | Mid | 2 | 63 | 0 | 1.2.10.3 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.11 | 1.2 | Sound Mix | Sound Mix |  |  |  | 9 | 46 | 2 | 1.2.10 |  |  | 195 | 1755
107 | DEL-0003 | TSK-00107 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.11.1 | 1.2.11 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Designer | Mid | 9 | 46 | 2 | 1.2.11 |  |  | 195 | 1755
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.12 | 1.2 | Sound Sourcing | Sound Sourcing |  |  |  | 3 | 46 | 2 | 1.2.11 |  |  | 195 | 585
113 | DEL-0003 | TSK-00113 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.12.1 | 1.2.12 | Music Search & License | Sound Sourcing | Music Search & License | Sound Designer | Mid | 3 | 46 | 2 | 1.2.12 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.13 | 1.2 | Final File Delivery | Final File Delivery |  |  |  | 7 | 48 | 2 | 1.2.12 |  |  | 195 | 1365
83 | DEL-0003 | TSK-00083 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.13.1 | 1.2.13 | QA (Tech & Content) | Final File Delivery | QA (Tech & Content) | QA Specialist | Mid | 3 | 48 | 2 | 1.2.13 |  |  | 195 | 585
80 | DEL-0003 | TSK-00080 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.13.2 | 1.2.13 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload | Media Manager / DIT | Mid | 4 | 63 | 0 | 1.2.13.1 |  |  | 195 | 780
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.14 | 1.2 | True-ups (for vendor costs) | True-ups (for vendor costs) |  |  |  | 10 | 50 | 8 | 1.2.13 |  |  | 195 | 1950
116 | DEL-0003 | TSK-00116 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.14.1 | 1.2.14 | Change Orders & Tracking | True-ups (for vendor costs) | Change Orders & Tracking | Project Manager | Mid | 1 | 50 | 3 | 1.2.14 |  |  | 195 | 195
120 | DEL-0003 | TSK-00120 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.14.2 | 1.2.14 | Internal Review & Critique | True-ups (for vendor costs) | Internal Review & Critique | Producer | Mid | 1 | 53 | 2 | 1.2.14.1 |  |  | 195 | 195
117 | DEL-0003 | TSK-00117 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.14.3 | 1.2.14 | Client Review & Revisions | True-ups (for vendor costs) | Client Review & Revisions | Account Manager | Mid | 3 | 55 | 3 | 1.2.14.2 |  |  | 195 | 585
119 | DEL-0003 | TSK-00119 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.14.4 | 1.2.14 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation | Designer | Mid | 5 | 63 | 0 | 1.2.14.3 |  |  | 195 | 975
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.15 | 1.2 | Cutdowns | Cutdowns |  |  |  | 11 | 53 | 5 | 1.2.14 |  |  | 195 | 2145
71 | DEL-0003 | TSK-00071 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.15.1 | 1.2.15 | Internal Review & Critique | Cutdowns | Internal Review & Critique | Producer | Mid | 1 | 53 | 2 | 1.2.15 |  |  | 195 | 195
67 | DEL-0003 | TSK-00067 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.15.2 | 1.2.15 | Client Review & Revisions | Cutdowns | Client Review & Revisions | Account Manager | Mid | 3 | 55 | 3 | 1.2.15.1 |  |  | 195 | 585
69 | DEL-0003 | TSK-00069 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.15.3 | 1.2.15 | Cutdowns (2-3) | Cutdowns | Cutdowns (2-3) | Editor | Mid | 7 | 63 | 0 | 1.2.15.2 |  |  | 195 | 1365
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.16 | 1.2 | Client Review | Client Review |  |  |  | 4 | 55 | 3 | 1.2.15 |  |  | 195 | 780
50 | DEL-0003 | TSK-00050 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.16.1 | 1.2.16 | Client Review Coordination | Client Review | Client Review Coordination | Account Manager | Mid | 4 | 55 | 3 | 1.2.16 |  |  | 195 | 780
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.17 | 1.2 | Review & Sign-Off | Review & Sign-Off |  |  |  | 3 | 55 | 5 | 1.2.16 |  |  | 195 | 585
103 | DEL-0003 | TSK-00103 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.17.1 | 1.2.17 | Client Review Coordination | Review & Sign-Off | Client Review Coordination | Account Manager | Mid | 2 | 55 | 3 | 1.2.17 |  |  | 195 | 390
105 | DEL-0003 | TSK-00105 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.17.2 | 1.2.17 | Notes Triage | Review & Sign-Off | Notes Triage | Project Manager | Mid | 1 | 61 | 2 | 1.2.17.1 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.18 | 1.2 | Asset Library | Asset Library |  |  |  | 2 | 58 | 3 | 1.2.17 |  |  | 195 | 390
48 | DEL-0003 | TSK-00048 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.18.1 | 1.2.18 | Post Support | Asset Library | Post Support | Editor | Mid | 2 | 58 | 3 | 1.2.18 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.19 | 1.2 | Capture Library | Capture Library |  |  |  | 2 | 58 | 3 | 1.2.18 |  |  | 195 | 390
49 | DEL-0003 | TSK-00049 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.19.1 | 1.2.19 | Post Support | Capture Library | Post Support | Editor | Mid | 2 | 58 | 3 | 1.2.19 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.20 | 1.2 | Selects Deck | Selects Deck |  |  |  | 2 | 58 | 3 | 1.2.19 |  |  | 195 | 390
106 | DEL-0003 | TSK-00106 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.20.1 | 1.2.20 | Post Support | Selects Deck | Post Support | Editor | Mid | 2 | 58 | 3 | 1.2.20 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.21 | 1.2 | Delivery | Delivery |  |  |  | 5 | 63 | 0 | 1.2.20 |  |  | 195 | 975
73 | DEL-0003 | TSK-00073 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.21.1 | 1.2.21 | Post Support | Delivery | Post Support | Editor | Mid | 5 | 63 | 0 | 1.2.21 |  |  | 195 | 975
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.22 | 1.2 | Stills/Footage Selection | Stills/Footage Selection |  |  |  | 5 | 63 | 0 | 1.2.21 |  |  | 195 | 975
115 | DEL-0003 | TSK-00115 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.22.1 | 1.2.22 | Post Support | Stills/Footage Selection | Post Support | Editor | Mid | 5 | 63 | 0 | 1.2.22 |  |  | 195 | 975
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3 | 1 | Pre-Production |  |  |  |  | 396 | 63 | 57 | 1.2 |  | Core/T2_MediumVolume | 195 | 77220
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1 | 1.3 | Wardrobe | Wardrobe |  |  |  | 12 | 63 | 7 | 1.3 |  |  | 195 | 2340
361 | DEL-0004 | TSK-00352 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.1 | 1.3.1 | Wardrobe Brief | Wardrobe | Wardrobe Brief | Art Director | Lead/Director | 3 | 63 | 2 | 1.3.1 |  |  | 195 | 585
358 | DEL-0004 | TSK-00349 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.2 | 1.3.1 | Internal Review & Critique | Wardrobe | Internal Review & Critique | Producer | Mid | 1 | 113 | 2 | 1.3.1.1 |  |  | 195 | 195
354 | DEL-0004 | TSK-00345 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.3 | 1.3.1 | Client Review & Revisions | Wardrobe | Client Review & Revisions | Account Manager | Mid | 3 | 115 | 3 | 1.3.1.2 |  |  | 195 | 585
356 | DEL-0004 | TSK-00347 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.4 | 1.3.1 | Final Packaging | Wardrobe | Final Packaging | Designer | Mid | 5 | 120 | 0 | 1.3.1.3 |  |  | 195 | 975
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2 | 1.3 | Pre-Production Deck | Pre-Production Deck |  |  |  | 26 | 65 | 14 | 1.3.1 |  |  | 195 | 5070
214 | DEL-0004 | TSK-00214 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2.1 | 1.3.2 | Content Draft | Pre-Production Deck | Content Draft | Strategist | Mid | 21 | 65 | 5 | 1.3.2 |  |  | 195 | 4095
216 | DEL-0004 | TSK-00216 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2.2 | 1.3.2 | Deck Build | Pre-Production Deck | Deck Build | Designer | Mid | 1 | 77 | 4 | 1.3.2.1 |  |  | 195 | 195
218 | DEL-0004 | TSK-00218 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2.3 | 1.3.2 | Internal Review & Critique | Pre-Production Deck | Internal Review & Critique | Producer | Mid | 1 | 113 | 2 | 1.3.2.2 |  |  | 195 | 195
212 | DEL-0004 | TSK-00212 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2.4 | 1.3.2 | Client Review & Revisions | Pre-Production Deck | Client Review & Revisions | Account Manager | Mid | 3 | 115 | 3 | 1.3.2.3 |  |  | 195 | 585
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3 | 1.3 | File Naming Convention & Storage | File Naming Convention & Storage |  |  |  | 12 | 70 | 12 | 1.3.2 |  |  | 195 | 2340
186 | DEL-0004 | TSK-00186 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3.1 | 1.3.3 | Schema Design | File Naming Convention & Storage | Schema Design | Media Manager / DIT | Mid | 3 | 70 | 7 | 1.3.3 |  |  | 195 | 585
184 | DEL-0004 | TSK-00184 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3.2 | 1.3.3 | Internal Review & Critique | File Naming Convention & Storage | Internal Review & Critique | Producer | Mid | 1 | 113 | 2 | 1.3.3.1 |  |  | 195 | 195
179 | DEL-0004 | TSK-00179 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3.3 | 1.3.3 | Client Review & Revisions | File Naming Convention & Storage | Client Review & Revisions | Account Manager | Mid | 3 | 115 | 3 | 1.3.3.2 |  |  | 195 | 585
181 | DEL-0004 | TSK-00181 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3.4 | 1.3.3 | Distribution & Notes | File Naming Convention & Storage | Distribution & Notes | Designer | Mid | 5 | 120 | 0 | 1.3.3.3 |  |  | 195 | 975
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4 | 1.3 | R1 Pre-Production Deck/Shot List | R1 Pre-Production Deck/Shot List |  |  |  | 17 | 77 | 4 | 1.3.3 |  |  | 195 | 3315
230 | DEL-0004 | TSK-00230 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.1 | 1.3.4 | Client Review & Revisions | R1 Pre-Production Deck/Shot List | Client Review & Revisions | Producer | Mid | 17 | 77 | 4 | 1.3.4 |  |  | 195 | 3315
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5 | 1.3 | R2 Pre-Production Deck/Shot List | R2 Pre-Production Deck/Shot List |  |  |  | 17 | 77 | 4 | 1.3.4 |  |  | 195 | 3315
238 | DEL-0004 | TSK-00238 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.1 | 1.3.5 | Client Review & Revisions | R2 Pre-Production Deck/Shot List | Client Review & Revisions | Producer | Mid | 17 | 77 | 4 | 1.3.5 |  |  | 195 | 3315
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.6 | 1.3 | Run of Show & Call Sheet | Run of Show & Call Sheet |  |  |  | 23 | 77 | 4 | 1.3.5 |  |  | 195 | 4485
246 | DEL-0004 | TSK-00246 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.6.1 | 1.3.6 | Client Review & Revisions | Run of Show & Call Sheet | Client Review & Revisions | Producer | Mid | 23 | 77 | 4 | 1.3.6 |  |  | 195 | 4485
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.7 | 1.3 | Script & Storyboards | Script & Storyboards |  |  |  | 31 | 77 | 4 | 1.3.6 |  |  | 195 | 6045
256 | DEL-0004 | TSK-00256 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.7.1 | 1.3.7 | Client Review & Revisions | Script & Storyboards | Client Review & Revisions | Producer | Mid | 31 | 77 | 4 | 1.3.7 |  |  | 195 | 6045
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8 | 1.3 | Shoot Oversight & Direction | Shoot Oversight & Direction |  |  |  | 12 | 77 | 6 | 1.3.7 |  |  | 195 | 2340
280 | DEL-0004 | TSK-00271 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8.1 | 1.3.8 | Schedule Management | Shoot Oversight & Direction | Schedule Management | Producer | Mid | 3 | 77 | 4 | 1.3.8 |  |  | 195 | 585
279 | DEL-0004 | TSK-00270 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8.2 | 1.3.8 | Quality Check (QC) | Shoot Oversight & Direction | Quality Check (QC) | QA Specialist | Mid | 2 | 93 | 2 | 1.3.8.1 |  |  | 195 | 390
274 | DEL-0004 | TSK-00265 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8.3 | 1.3.8 | Daily Wrap Notes | Shoot Oversight & Direction | Daily Wrap Notes | Creative Director | Lead/Director | 7 | 120 | 0 | 1.3.8.2 |  |  | 195 | 1365
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.9 | 1.3 | Shot List | Shot List |  |  |  | 20 | 77 | 4 | 1.3.8 |  |  | 195 | 3900
281 | DEL-0004 | TSK-00272 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.9.1 | 1.3.9 | Client Review & Revisions | Shot List | Client Review & Revisions | Producer | Mid | 20 | 77 | 4 | 1.3.9 |  |  | 195 | 3900
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.10 | 1.3 | Storyboard Review | Storyboard Review |  |  |  | 4 | 77 | 4 | 1.3.9 |  |  | 195 | 780
291 | DEL-0004 | TSK-00282 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.10.1 | 1.3.10 | Internal Crit | Storyboard Review | Internal Crit | Art Director | Lead/Director | 4 | 77 | 4 | 1.3.10 |  |  | 195 | 780
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.11 | 1.3 | Storyboards & Script Writing | Storyboards & Script Writing |  |  |  | 15 | 77 | 4 | 1.3.10 |  |  | 195 | 2925
294 | DEL-0004 | TSK-00285 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.11.1 | 1.3.11 | Client Review & Revisions | Storyboards & Script Writing | Client Review & Revisions | Producer | Mid | 15 | 77 | 4 | 1.3.11 |  |  | 195 | 2925
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.12 | 1.3 | Casting | Casting |  |  |  | 13 | 81 | 7 | 1.3.11 |  |  | 195 | 2535
150 | DEL-0004 | TSK-00150 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.12.1 | 1.3.12 | Approvals/Holds | Casting | Approvals/Holds | Producer | Mid | 13 | 81 | 7 | 1.3.12 |  |  | 195 | 2535
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.13 | 1.3 | Load In & Pre-Lighting | Load In & Pre-Lighting |  |  |  | 25 | 81 | 7 | 1.3.12 |  |  | 195 | 4875
188 | DEL-0004 | TSK-00188 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.13.1 | 1.3.13 | Client Review & Revisions | Load In & Pre-Lighting | Client Review & Revisions | Producer | Mid | 25 | 81 | 7 | 1.3.13 |  |  | 195 | 4875
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.14 | 1.3 | Talent Casting | Talent Casting |  |  |  | 25 | 81 | 7 | 1.3.13 |  |  | 195 | 4875
303 | DEL-0004 | TSK-00294 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.14.1 | 1.3.14 | Approvals & Holds | Talent Casting | Approvals & Holds | Producer | Mid | 25 | 81 | 7 | 1.3.14 |  |  | 195 | 4875
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15 | 1.3 | Post Production Plan & Timeline | Post Production Plan & Timeline |  |  |  | 21 | 88 | 10 | 1.3.14 |  |  | 195 | 4095
203 | DEL-0004 | TSK-00203 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15.1 | 1.3.15 | Editorial Milestones | Post Production Plan & Timeline | Editorial Milestones | Editor | Mid | 10 | 88 | 5 | 1.3.15 |  |  | 195 | 1950
206 | DEL-0004 | TSK-00206 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15.2 | 1.3.15 | Internal Review & Critique | Post Production Plan & Timeline | Internal Review & Critique | Producer | Mid | 1 | 113 | 2 | 1.3.15.1 |  |  | 195 | 195
198 | DEL-0004 | TSK-00198 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15.3 | 1.3.15 | Client Review & Revisions | Post Production Plan & Timeline | Client Review & Revisions | Account Manager | Mid | 4 | 115 | 3 | 1.3.15.2 |  |  | 195 | 780
201 | DEL-0004 | TSK-00201 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15.4 | 1.3.15 | Delivery Timeline | Post Production Plan & Timeline | Delivery Timeline | Producer | Mid | 6 | 120 | 0 | 1.3.15.3 |  |  | 195 | 1170
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.16 | 1.3 | Concept Development | Concept Development |  |  |  | 17 | 95 | 15 | 1.3.15 |  |  | 195 | 3315
158 | DEL-0004 | TSK-00158 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.16.1 | 1.3.16 | Ideation Sprint | Concept Development | Ideation Sprint | Designer | Mid | 12 | 95 | 10 | 1.3.16 |  |  | 195 | 2340
163 | DEL-0004 | TSK-00163 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.16.2 | 1.3.16 | Internal Review & Critique | Concept Development | Internal Review & Critique | Producer | Mid | 2 | 113 | 2 | 1.3.16.1 |  |  | 195 | 390
155 | DEL-0004 | TSK-00155 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.16.3 | 1.3.16 | Client Review & Revisions | Concept Development | Client Review & Revisions | Account Manager | Mid | 3 | 115 | 3 | 1.3.16.2 |  |  | 195 | 585
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.17 | 1.3 | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) |  |  |  | 10 | 105 | 8 | 1.3.16 |  |  | 195 | 1950
228 | DEL-0004 | TSK-00228 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.17.1 | 1.3.17 | Inventory & Tracking | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Inventory & Tracking | Producer | Mid | 1 | 105 | 3 | 1.3.17 |  |  | 195 | 195
226 | DEL-0004 | TSK-00226 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.17.2 | 1.3.17 | Internal Review & Critique | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Internal Review & Critique | Producer | Mid | 1 | 113 | 2 | 1.3.17.1 |  |  | 195 | 195
223 | DEL-0004 | TSK-00223 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.17.3 | 1.3.17 | Client Review & Revisions | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Client Review & Revisions | Account Manager | Mid | 3 | 115 | 3 | 1.3.17.2 |  |  | 195 | 585
222 | DEL-0004 | TSK-00222 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.17.4 | 1.3.17 | Chain of Custody | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Chain of Custody | Designer | Mid | 5 | 120 | 0 | 1.3.17.3 |  |  | 195 | 975
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.18 | 1.3 | Vendor Deal Memos & Contracts | Vendor Deal Memos & Contracts |  |  |  | 3 | 105 | 3 | 1.3.17 |  |  | 195 | 585
333 | DEL-0004 | TSK-00324 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.18.1 | 1.3.18 | Filing & Tracking | Vendor Deal Memos & Contracts | Filing & Tracking | Project Manager | Mid | 1 | 105 | 3 | 1.3.18 |  |  | 195 | 195
331 | DEL-0004 | TSK-00322 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.18.2 | 1.3.18 | Deal Memos & Contracts | Vendor Deal Memos & Contracts | Deal Memos & Contracts | Account Manager | Mid | 2 | 120 | 0 | 1.3.18.1 |  |  | 195 | 390
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.19 | 1.3 | Vendor Engagement | Vendor Engagement |  |  |  | 13 | 108 | 10 | 1.3.18 |  |  | 195 | 2535
334 | DEL-0004 | TSK-00325 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.19.1 | 1.3.19 | Briefing Docs | Vendor Engagement | Briefing Docs | Designer | Mid | 9 | 108 | 5 | 1.3.19 |  |  | 195 | 1755
342 | DEL-0004 | TSK-00333 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.19.2 | 1.3.19 | Internal Review & Critique | Vendor Engagement | Internal Review & Critique | Producer | Mid | 1 | 113 | 2 | 1.3.19.1 |  |  | 195 | 195
336 | DEL-0004 | TSK-00327 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.19.3 | 1.3.19 | Client Review & Revisions | Vendor Engagement | Client Review & Revisions | Account Manager | Mid | 3 | 115 | 3 | 1.3.19.2 |  |  | 195 | 585
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.20 | 1.3 | Art Direction | Art Direction |  |  |  | 19 | 113 | 5 | 1.3.19 |  |  | 195 | 3705
144 | DEL-0004 | TSK-00144 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.20.1 | 1.3.20 | Internal Review & Critique | Art Direction | Internal Review & Critique | Producer | Mid | 1 | 113 | 2 | 1.3.20 |  |  | 195 | 195
141 | DEL-0004 | TSK-00141 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.20.2 | 1.3.20 | Client Review & Revisions | Art Direction | Client Review & Revisions | Account Manager | Mid | 3 | 115 | 3 | 1.3.20.1 |  |  | 195 | 585
143 | DEL-0004 | TSK-00143 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.20.3 | 1.3.20 | Look Dev & References | Art Direction | Look Dev & References | Designer | Mid | 5 | 120 | 0 | 1.3.20.2 |  |  | 195 | 975
148 | DEL-0004 | TSK-00148 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.20.4 | 1.3.20 | Style Guide (lite) | Art Direction | Style Guide (lite) | Designer | Mid | 10 | 120 | 0 | 1.3.20.3 |  |  | 195 | 1950
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.21 | 1.3 | Concepting | Concepting |  |  |  | 21 | 113 | 5 | 1.3.20 |  |  | 195 | 4095
175 | DEL-0004 | TSK-00175 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.21.1 | 1.3.21 | Internal Review & Critique | Concepting | Internal Review & Critique | Producer | Mid | 2 | 113 | 2 | 1.3.21 |  |  | 195 | 390
166 | DEL-0004 | TSK-00166 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.21.2 | 1.3.21 | Client Review & Revisions | Concepting | Client Review & Revisions | Account Manager | Mid | 3 | 115 | 3 | 1.3.21.1 |  |  | 195 | 585
169 | DEL-0004 | TSK-00169 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.21.3 | 1.3.21 | Ideation Sprint | Concepting | Ideation Sprint | Strategist | Mid | 16 | 120 | 0 | 1.3.21.2 |  |  | 195 | 3120
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.22 | 1.3 | Vendor Contracting | Vendor Contracting |  |  |  | 12 | 113 | 5 | 1.3.21 |  |  | 195 | 2340
319 | DEL-0004 | TSK-00310 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.22.1 | 1.3.22 | Internal Review & Critique | Vendor Contracting | Internal Review & Critique | Producer | Mid | 1 | 113 | 2 | 1.3.22 |  |  | 195 | 195
313 | DEL-0004 | TSK-00304 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.22.2 | 1.3.22 | Client Review & Revisions | Vendor Contracting | Client Review & Revisions | Account Manager | Mid | 4 | 115 | 3 | 1.3.22.1 |  |  | 195 | 780
316 | DEL-0004 | TSK-00307 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.22.3 | 1.3.22 | SOW/CO Draft & Negotiate | Vendor Contracting | SOW/CO Draft & Negotiate | Account Manager | Mid | 7 | 120 | 0 | 1.3.22.2 |  |  | 195 | 1365
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.23 | 1.3 | Vendor Deal Memos | Vendor Deal Memos |  |  |  | 10 | 113 | 5 | 1.3.22 |  |  | 195 | 1950
329 | DEL-0004 | TSK-00320 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.23.1 | 1.3.23 | Internal Review & Critique | Vendor Deal Memos | Internal Review & Critique | Producer | Mid | 1 | 113 | 2 | 1.3.23 |  |  | 195 | 195
323 | DEL-0004 | TSK-00314 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.23.2 | 1.3.23 | Client Review & Revisions | Vendor Deal Memos | Client Review & Revisions | Account Manager | Mid | 3 | 115 | 3 | 1.3.23.1 |  |  | 195 | 585
325 | DEL-0004 | TSK-00316 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.23.3 | 1.3.23 | Distribution & Confirmation | Vendor Deal Memos | Distribution & Confirmation | Producer | Mid | 6 | 120 | 0 | 1.3.23.2 |  |  | 195 | 1170
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.24 | 1.3 | Vendor Pre-Production Meetings | Vendor Pre-Production Meetings |  |  |  | 13 | 113 | 7 | 1.3.23 |  |  | 195 | 2535
349 | DEL-0004 | TSK-00340 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.24.1 | 1.3.24 | Internal Review & Critique | Vendor Pre-Production Meetings | Internal Review & Critique | Producer | Mid | 1 | 113 | 2 | 1.3.24 |  |  | 195 | 195
346 | DEL-0004 | TSK-00337 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.24.2 | 1.3.24 | Client Review & Revisions | Vendor Pre-Production Meetings | Client Review & Revisions | Account Manager | Mid | 2 | 115 | 3 | 1.3.24.1 |  |  | 195 | 390
351 | DEL-0004 | TSK-00342 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.24.3 | 1.3.24 | Run Meeting & Notes | Vendor Pre-Production Meetings | Run Meeting & Notes | Creative Director | Lead/Director | 3 | 118 | 2 | 1.3.24.2 |  |  | 195 | 585
344 | DEL-0004 | TSK-00335 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.24.4 | 1.3.24 | Agenda & Materials | Vendor Pre-Production Meetings | Agenda & Materials | Designer | Mid | 7 | 120 | 0 | 1.3.24.3 |  |  | 195 | 1365
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.25 | 1.3 | Pre-Interview Talent Calls | Pre-Interview Talent Calls |  |  |  | 4 | 120 | 0 | 1.3.24 |  |  | 195 | 780
209 | DEL-0004 | TSK-00209 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.25.1 | 1.3.25 | Notes & Shareout | Pre-Interview Talent Calls | Notes & Shareout | Producer | Mid | 4 | 120 | 0 | 1.3.25 |  |  | 195 | 780
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.26 | 1.3 | Wrap & File Organization | Wrap & File Organization |  |  |  | 1 | 120 | 0 | 1.3.25 |  |  | 195 | 195
363 | DEL-0004 | TSK-00354 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.26.1 | 1.3.26 | Pre-Production Support | Wrap & File Organization | Pre-Production Support | Producer | Mid | 1 | 120 | 0 | 1.3.26 |  |  | 195 | 195
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4 | 1 | Brand Identity Development |  |  |  |  | 255 | 120 | 12 | 1.3 |  | Core/T2_MediumVolume | 195 | 49725
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1 | 1.4 | Color Palette | Color Palette |  |  |  | 15 | 120 | 2 | 1.4 |  |  | 195 | 2925
474 | DEL-0008 | TSK-00465 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.1 | 1.4.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Designer | Mid | 15 | 120 | 2 | 1.4.1 |  |  | 195 | 2925
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2 | 1.4 | Graphic Mock-Ups | Graphic Mock-Ups |  |  |  | 25 | 122 | 8 | 1.4.1 |  |  | 195 | 4875
496 | DEL-0008 | TSK-00487 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.1 | 1.4.2 | Compositing/Retouch | Graphic Mock-Ups | Compositing/Retouch | Retoucher | Mid | 4 | 122 | 3 | 1.4.2 |  |  | 195 | 780
498 | DEL-0008 | TSK-00489 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.2 | 1.4.2 | Internal Review & Critique | Graphic Mock-Ups | Internal Review & Critique | Art Director | Lead/Director | 1 | 127 | 2 | 1.4.2.1 |  |  | 195 | 195
493 | DEL-0008 | TSK-00484 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.3 | 1.4.2 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions | Account Manager | Mid | 4 | 129 | 3 | 1.4.2.2 |  |  | 195 | 780
497 | DEL-0008 | TSK-00488 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.4 | 1.4.2 | Mockup Scenarios (3-4) | Graphic Mock-Ups | Mockup Scenarios (3-4) | Designer | Mid | 16 | 132 | 0 | 1.4.2.3 |  |  | 195 | 3120
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3 | 1.4 | Logo | Logo |  |  |  | 37 | 125 | 7 | 1.4.2 |  |  | 195 | 7215
520 | DEL-0008 | TSK-00511 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.1 | 1.4.3 | Quality Check (Specs/Accessibility) | Logo | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 | 125 | 2 | 1.4.3 |  |  | 195 | 585
515 | DEL-0008 | TSK-00506 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.2 | 1.4.3 | Internal Review & Critique | Logo | Internal Review & Critique | Art Director | Lead/Director | 1 | 127 | 2 | 1.4.3.1 |  |  | 195 | 195
511 | DEL-0008 | TSK-00502 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.3 | 1.4.3 | Client Review & Revisions | Logo | Client Review & Revisions | Account Manager | Mid | 3 | 129 | 3 | 1.4.3.2 |  |  | 195 | 585
514 | DEL-0008 | TSK-00505 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.4 | 1.4.3 | Logo Exploration (6-8 dirs) | Logo | Logo Exploration (6-8 dirs) | Designer | Mid | 30 | 132 | 0 | 1.4.3.3 |  |  | 195 | 5850
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4 | 1.4 | Typography | Typography |  |  |  | 34 | 125 | 7 | 1.4.3 |  |  | 195 | 6630
556 | DEL-0008 | TSK-00547 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.1 | 1.4.4 | Quality Check (Specs/Accessibility) | Typography | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 | 125 | 2 | 1.4.4 |  |  | 195 | 585
554 | DEL-0008 | TSK-00545 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.2 | 1.4.4 | Internal Review & Critique | Typography | Internal Review & Critique | Art Director | Lead/Director | 1 | 127 | 2 | 1.4.4.1 |  |  | 195 | 195
549 | DEL-0008 | TSK-00540 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.3 | 1.4.4 | Client Review & Revisions | Typography | Client Review & Revisions | Account Manager | Mid | 3 | 129 | 3 | 1.4.4.2 |  |  | 195 | 585
552 | DEL-0008 | TSK-00543 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.4 | 1.4.4 | Final Packaging | Typography | Final Packaging | Designer | Mid | 27 | 132 | 0 | 1.4.4.3 |  |  | 195 | 5265
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5 | 1.4 | Graphic & Copy Messaging Cornerstones | Graphic & Copy Messaging Cornerstones |  |  |  | 23 | 127 | 5 | 1.4.4 |  |  | 195 | 4485
489 | DEL-0008 | TSK-00480 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.1 | 1.4.5 | Internal Review & Critique | Graphic & Copy Messaging Cornerstones | Internal Review & Critique | Art Director | Lead/Director | 1 | 127 | 2 | 1.4.5 |  |  | 195 | 195
483 | DEL-0008 | TSK-00474 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.2 | 1.4.5 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Account Manager | Mid | 4 | 129 | 3 | 1.4.5.1 |  |  | 195 | 780
487 | DEL-0008 | TSK-00478 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.3 | 1.4.5 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft | Designer | Mid | 18 | 132 | 0 | 1.4.5.2 |  |  | 195 | 3510
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6 | 1.4 | Iconography | Iconography |  |  |  | 27 | 127 | 5 | 1.4.5 |  |  | 195 | 5265
509 | DEL-0008 | TSK-00500 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.1 | 1.4.6 | Internal Review & Critique | Iconography | Internal Review & Critique | Art Director | Lead/Director | 1 | 127 | 2 | 1.4.6 |  |  | 195 | 195
502 | DEL-0008 | TSK-00493 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.2 | 1.4.6 | Client Review & Revisions | Iconography | Client Review & Revisions | Account Manager | Mid | 4 | 129 | 3 | 1.4.6.1 |  |  | 195 | 780
505 | DEL-0008 | TSK-00496 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.3 | 1.4.6 | Export & Spec | Iconography | Export & Spec | Designer | Mid | 22 | 132 | 0 | 1.4.6.2 |  |  | 195 | 4290
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7 | 1.4 | Overarching Moodboard | Overarching Moodboard |  |  |  | 23 | 127 | 5 | 1.4.6 |  |  | 195 | 4485
528 | DEL-0008 | TSK-00519 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.1 | 1.4.7 | Internal Review & Critique | Overarching Moodboard | Internal Review & Critique | Art Director | Lead/Director | 1 | 127 | 2 | 1.4.7 |  |  | 195 | 195
522 | DEL-0008 | TSK-00513 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.2 | 1.4.7 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions | Account Manager | Mid | 4 | 129 | 3 | 1.4.7.1 |  |  | 195 | 780
525 | DEL-0008 | TSK-00516 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.3 | 1.4.7 | Curate Moodboard | Overarching Moodboard | Curate Moodboard | Designer | Mid | 18 | 132 | 0 | 1.4.7.2 |  |  | 195 | 3510
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8 | 1.4 | Tagline Copy Bank | Tagline Copy Bank |  |  |  | 18 | 127 | 5 | 1.4.7 |  |  | 195 | 3510
536 | DEL-0008 | TSK-00527 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.1 | 1.4.8 | Internal Review & Critique | Tagline Copy Bank | Internal Review & Critique | Art Director | Lead/Director | 1 | 127 | 2 | 1.4.8 |  |  | 195 | 195
531 | DEL-0008 | TSK-00522 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.2 | 1.4.8 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Account Manager | Mid | 4 | 129 | 3 | 1.4.8.1 |  |  | 195 | 780
535 | DEL-0008 | TSK-00526 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.3 | 1.4.8 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale | Designer | Mid | 13 | 132 | 0 | 1.4.8.2 |  |  | 195 | 2535
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9 | 1.4 | Textures/Patterns/Materials | Textures/Patterns/Materials |  |  |  | 25 | 127 | 5 | 1.4.8 |  |  | 195 | 4875
546 | DEL-0008 | TSK-00537 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.1 | 1.4.9 | Internal Review & Critique | Textures/Patterns/Materials | Internal Review & Critique | Art Director | Lead/Director | 1 | 127 | 2 | 1.4.9 |  |  | 195 | 195
542 | DEL-0008 | TSK-00533 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.2 | 1.4.9 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions | Account Manager | Mid | 4 | 129 | 3 | 1.4.9.1 |  |  | 195 | 780
541 | DEL-0008 | TSK-00532 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.3 | 1.4.9 | Build Repeating Tiles | Textures/Patterns/Materials | Build Repeating Tiles | Designer | Mid | 20 | 132 | 0 | 1.4.9.2 |  |  | 195 | 3900
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10 | 1.4 | Visual Elements/Comps | Visual Elements/Comps |  |  |  | 28 | 127 | 5 | 1.4.9 |  |  | 195 | 5460
566 | DEL-0008 | TSK-00557 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10.1 | 1.4.10 | Internal Review & Critique | Visual Elements/Comps | Internal Review & Critique | Art Director | Lead/Director | 1 | 127 | 2 | 1.4.10 |  |  | 195 | 195
559 | DEL-0008 | TSK-00550 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10.2 | 1.4.10 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions | Account Manager | Mid | 4 | 129 | 3 | 1.4.10.1 |  |  | 195 | 780
562 | DEL-0008 | TSK-00553 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10.3 | 1.4.10 | Compositions (2-3) | Visual Elements/Comps | Compositions (2-3) | Designer | Mid | 23 | 132 | 0 | 1.4.10.2 |  |  | 195 | 4485
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5 | 1 | Brand Style & Usage Guidelines |  |  |  |  | 250 | 132 | 9 | 1.4 |  | Core/T2_MediumVolume | 195 | 48750
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.1 | 1.5 | Color Palettes | Color Palettes |  |  |  | 13 | 132 | 2 | 1.5 |  |  | 195 | 2535
578 | DEL-0009 | TSK-00569 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.1.1 | 1.5.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Designer | Mid | 13 | 132 | 2 | 1.5.1 |  |  | 195 | 2535
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2 | 1.5 | Logo Lock-Ups | Logo Lock-Ups |  |  |  | 28 | 134 | 7 | 1.5.1 |  |  | 195 | 5460
626 | DEL-0009 | TSK-00617 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.1 | 1.5.2 | Quality Check (Specs/Accessibility) | Logo Lock-Ups | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 | 134 | 2 | 1.5.2 |  |  | 195 | 585
622 | DEL-0009 | TSK-00613 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.2 | 1.5.2 | Internal Review & Critique | Logo Lock-Ups | Internal Review & Critique | Art Director | Lead/Director | 1 | 136 | 2 | 1.5.2.1 |  |  | 195 | 195
618 | DEL-0009 | TSK-00609 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.3 | 1.5.2 | Client Review & Revisions | Logo Lock-Ups | Client Review & Revisions | Account Manager | Mid | 3 | 138 | 3 | 1.5.2.2 |  |  | 195 | 585
621 | DEL-0009 | TSK-00612 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.4 | 1.5.2 | Final Packaging | Logo Lock-Ups | Final Packaging | Designer | Mid | 21 | 141 | 0 | 1.5.2.3 |  |  | 195 | 4095
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3 | 1.5 | Logo Placement | Logo Placement |  |  |  | 27 | 134 | 7 | 1.5.2 |  |  | 195 | 5265
635 | DEL-0009 | TSK-00626 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.1 | 1.5.3 | Quality Check (Specs/Accessibility) | Logo Placement | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 | 134 | 2 | 1.5.3 |  |  | 195 | 585
631 | DEL-0009 | TSK-00622 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.2 | 1.5.3 | Internal Review & Critique | Logo Placement | Internal Review & Critique | Art Director | Lead/Director | 1 | 136 | 2 | 1.5.3.1 |  |  | 195 | 195
627 | DEL-0009 | TSK-00618 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.3 | 1.5.3 | Client Review & Revisions | Logo Placement | Client Review & Revisions | Account Manager | Mid | 3 | 138 | 3 | 1.5.3.2 |  |  | 195 | 585
630 | DEL-0009 | TSK-00621 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.4 | 1.5.3 | Final Packaging | Logo Placement | Final Packaging | Designer | Mid | 20 | 141 | 0 | 1.5.3.3 |  |  | 195 | 3900
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4 | 1.5 | Brand Do's & Dont's | Brand Do's & Dont's |  |  |  | 33 | 136 | 5 | 1.5.3 |  |  | 195 | 6435
573 | DEL-0009 | TSK-00564 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.1 | 1.5.4 | Internal Review & Critique | Brand Do's & Dont's | Internal Review & Critique | Art Director | Lead/Director | 1 | 136 | 2 | 1.5.4 |  |  | 195 | 195
568 | DEL-0009 | TSK-00559 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.2 | 1.5.4 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions | Account Manager | Mid | 4 | 138 | 3 | 1.5.4.1 |  |  | 195 | 780
572 | DEL-0009 | TSK-00563 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.3 | 1.5.4 | Outline & Examples | Brand Do's & Dont's | Outline & Examples | Designer | Mid | 28 | 141 | 0 | 1.5.4.2 |  |  | 195 | 5460
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5 | 1.5 | Design Style Tile | Design Style Tile |  |  |  | 23 | 136 | 5 | 1.5.4 |  |  | 195 | 4485
590 | DEL-0009 | TSK-00581 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.1 | 1.5.5 | Internal Review & Critique | Design Style Tile | Internal Review & Critique | Art Director | Lead/Director | 1 | 136 | 2 | 1.5.5 |  |  | 195 | 195
586 | DEL-0009 | TSK-00577 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.2 | 1.5.5 | Client Review & Revisions | Design Style Tile | Client Review & Revisions | Account Manager | Mid | 4 | 138 | 3 | 1.5.5.1 |  |  | 195 | 780
589 | DEL-0009 | TSK-00580 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.3 | 1.5.5 | Style Tile Build | Design Style Tile | Style Tile Build | Designer | Mid | 18 | 141 | 0 | 1.5.5.2 |  |  | 195 | 3510
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6 | 1.5 | Image Use Guidance | Image Use Guidance |  |  |  | 23 | 136 | 5 | 1.5.5 |  |  | 195 | 4485
608 | DEL-0009 | TSK-00599 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.1 | 1.5.6 | Internal Review & Critique | Image Use Guidance | Internal Review & Critique | Art Director | Lead/Director | 1 | 136 | 2 | 1.5.6 |  |  | 195 | 195
602 | DEL-0009 | TSK-00593 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.2 | 1.5.6 | Client Review & Revisions | Image Use Guidance | Client Review & Revisions | Account Manager | Mid | 4 | 138 | 3 | 1.5.6.1 |  |  | 195 | 780
605 | DEL-0009 | TSK-00596 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.3 | 1.5.6 | Examples & Callouts | Image Use Guidance | Examples & Callouts | Designer | Mid | 18 | 141 | 0 | 1.5.6.2 |  |  | 195 | 3510
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7 | 1.5 | Imagery Style | Imagery Style |  |  |  | 23 | 136 | 5 | 1.5.6 |  |  | 195 | 4485
616 | DEL-0009 | TSK-00607 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.1 | 1.5.7 | Internal Review & Critique | Imagery Style | Internal Review & Critique | Art Director | Lead/Director | 1 | 136 | 2 | 1.5.7 |  |  | 195 | 195
610 | DEL-0009 | TSK-00601 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.2 | 1.5.7 | Client Review & Revisions | Imagery Style | Client Review & Revisions | Account Manager | Mid | 4 | 138 | 3 | 1.5.7.1 |  |  | 195 | 780
613 | DEL-0009 | TSK-00604 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.3 | 1.5.7 | Examples & Callouts | Imagery Style | Examples & Callouts | Designer | Mid | 18 | 141 | 0 | 1.5.7.2 |  |  | 195 | 3510
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8 | 1.5 | Photo & Video Direction | Photo & Video Direction |  |  |  | 25 | 136 | 5 | 1.5.7 |  |  | 195 | 4875
642 | DEL-0009 | TSK-00633 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.1 | 1.5.8 | Internal Review & Critique | Photo & Video Direction | Internal Review & Critique | Art Director | Lead/Director | 1 | 136 | 2 | 1.5.8 |  |  | 195 | 195
636 | DEL-0009 | TSK-00627 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.2 | 1.5.8 | Client Review & Revisions | Photo & Video Direction | Client Review & Revisions | Account Manager | Mid | 4 | 138 | 3 | 1.5.8.1 |  |  | 195 | 780
639 | DEL-0009 | TSK-00630 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.3 | 1.5.8 | Direction Pages | Photo & Video Direction | Direction Pages | Designer | Mid | 20 | 141 | 0 | 1.5.8.2 |  |  | 195 | 3900
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9 | 1.5 | Typography | Typography |  |  |  | 18 | 136 | 5 | 1.5.8 |  |  | 195 | 3510
649 | DEL-0009 | TSK-00640 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.1 | 1.5.9 | Internal Review & Critique | Typography | Internal Review & Critique | Art Director | Lead/Director | 1 | 136 | 2 | 1.5.9 |  |  | 195 | 195
645 | DEL-0009 | TSK-00636 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.2 | 1.5.9 | Client Review & Revisions | Typography | Client Review & Revisions | Account Manager | Mid | 3 | 138 | 3 | 1.5.9.1 |  |  | 195 | 585
648 | DEL-0009 | TSK-00639 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.3 | 1.5.9 | Final Packaging | Typography | Final Packaging | Designer | Mid | 14 | 141 | 0 | 1.5.9.2 |  |  | 195 | 2730
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10 | 1.5 | Use Cases | Use Cases |  |  |  | 22 | 136 | 5 | 1.5.9 |  |  | 195 | 4290
656 | DEL-0009 | TSK-00647 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.1 | 1.5.10 | Internal Review & Critique | Use Cases | Internal Review & Critique | Art Director | Lead/Director | 1 | 136 | 2 | 1.5.10 |  |  | 195 | 195
652 | DEL-0009 | TSK-00643 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.2 | 1.5.10 | Client Review & Revisions | Use Cases | Client Review & Revisions | Account Manager | Mid | 4 | 138 | 3 | 1.5.10.1 |  |  | 195 | 780
655 | DEL-0009 | TSK-00646 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.3 | 1.5.10 | Final Packaging | Use Cases | Final Packaging | Designer | Mid | 17 | 141 | 0 | 1.5.10.2 |  |  | 195 | 3315
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.11 | 1.5 | Graphic Treatment Direction | Graphic Treatment Direction |  |  |  | 15 | 141 | 0 | 1.5.10 |  |  | 195 | 2925
594 | DEL-0009 | TSK-00585 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.11.1 | 1.5.11 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Creative Director | Lead/Director | 15 | 141 | 0 | 1.5.11 |  |  | 195 | 2925

## Scenario B
Row_ID | Deliverable_Code | Task_Code | Service_Department | Deliverable | Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes | Rate_USD | Price_USD
[5 empty] | Vascano Tequila - RFP Creative Services 2022 (8) | 1 |  | Vascano Tequila - RFP Creative Services 2022 (8) | Project |  |  |  | 0 | 0 |  |  |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1 | 1 | Development |  |  |  |  | 348 | 0 | 28 |  |  | Advanced/T1_LargeVolume | 195 | 67860
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1 | 1.1 | ADA Compliance | ADA Compliance |  |  |  | 77 | 0 | 19 | 1.1 |  |  | 195 | 15015
1738 | DEL-0044 | TSK-01729 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.1 | 1.1.1 | Accessibility Audit | ADA Compliance | Accessibility Audit | Accessibility Specialist | Mid | 3 | 0 | 4 | 1.1.1 |  |  | 195 | 585
1739 | DEL-0044 | TSK-01730 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.2 | 1.1.1 | Accessibility QA | ADA Compliance | Accessibility QA | QA Engineer | Mid | 6 | 13 | 3 | 1.1.1.1 |  |  | 195 | 1170
1740 | DEL-0044 | TSK-01731 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.3 | 1.1.1 | Code Review | ADA Compliance | Code Review | Frontend Engineer | Mid | 68 | 16 | 12 | 1.1.1.2 |  |  | 195 | 13260
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2 | 1.1 | Audit & Requirement gathering | Audit & Requirement gathering |  |  |  | 26 | 0 | 4 | 1.1.1 |  |  | 195 | 5070
1749 | DEL-0044 | TSK-01740 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.1 | 1.1.2 | Analytics Audit | Audit & Requirement gathering | Analytics Audit | Business Analyst | Mid | 26 | 0 | 4 | 1.1.2 |  |  | 195 | 5070
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3 | 1.1 | Audit existing UA Property | Audit existing UA Property |  |  |  | 26 | 0 | 4 | 1.1.2 |  |  | 195 | 5070
1753 | DEL-0044 | TSK-01744 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.1 | 1.1.3 | Documentation | Audit existing UA Property | Documentation | Business Analyst | Mid | 26 | 0 | 4 | 1.1.3 |  |  | 195 | 5070
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4 | 1.1 | Footer CTA | Footer CTA |  |  |  | 66 | 4 | 24 | 1.1.3 |  |  | 195 | 12870
1765 | DEL-0044 | TSK-01756 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.1 | 1.1.4 | Design Consult | Footer CTA | Design Consult | UI Designer | Mid | 5 | 4 | 9 | 1.1.4 |  |  | 195 | 975
1760 | DEL-0044 | TSK-01751 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.2 | 1.1.4 | Accessibility QA | Footer CTA | Accessibility QA | QA Engineer | Mid | 9 | 13 | 3 | 1.1.4.1 |  |  | 195 | 1755
1761 | DEL-0044 | TSK-01752 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.3 | 1.1.4 | Code Review | Footer CTA | Code Review | Backend Engineer | Mid | 52 | 16 | 12 | 1.1.4.2 |  |  | 195 | 10140
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5 | 1.1 | Header & Footer Navigation | Header & Footer Navigation |  |  |  | 66 | 4 | 24 | 1.1.4 |  |  | 195 | 12870
1773 | DEL-0044 | TSK-01764 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.1 | 1.1.5 | Design Consult | Header & Footer Navigation | Design Consult | UI Designer | Mid | 5 | 4 | 9 | 1.1.5 |  |  | 195 | 975
1768 | DEL-0044 | TSK-01759 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.2 | 1.1.5 | Accessibility QA | Header & Footer Navigation | Accessibility QA | QA Engineer | Mid | 9 | 13 | 3 | 1.1.5.1 |  |  | 195 | 1755
1769 | DEL-0044 | TSK-01760 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.3 | 1.1.5 | Code Review | Header & Footer Navigation | Code Review | Backend Engineer | Mid | 52 | 16 | 12 | 1.1.5.2 |  |  | 195 | 10140
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6 | 1.1 | Additional Goals Setup | Additional Goals Setup |  |  |  | 11 | 13 | 15 | 1.1.5 |  |  | 195 | 2145
1747 | DEL-0044 | TSK-01738 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.1 | 1.1.6 | QA Cycle | Additional Goals Setup | QA Cycle | QA Engineer | Mid | 4 | 13 | 3 | 1.1.6 |  |  | 195 | 780
1746 | DEL-0044 | TSK-01737 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.2 | 1.1.6 | Define & Configure Goals | Additional Goals Setup | Define & Configure Goals | Data/Analytics Engineer | Mid | 7 | 16 | 12 | 1.1.6.1 |  |  | 195 | 1365
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7 | 1.1 | Custom Event Tracking | Custom Event Tracking |  |  |  | 11 | 13 | 15 | 1.1.6 |  |  | 195 | 2145
1758 | DEL-0044 | TSK-01749 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.1 | 1.1.7 | QA Cycle | Custom Event Tracking | QA Cycle | QA Engineer | Mid | 4 | 13 | 3 | 1.1.7 |  |  | 195 | 780
1757 | DEL-0044 | TSK-01748 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.2 | 1.1.7 | Event Schema & Tagging | Custom Event Tracking | Event Schema & Tagging | Data/Analytics Engineer | Mid | 7 | 16 | 12 | 1.1.7.1 |  |  | 195 | 1365
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8 | 1.1 | Implement Paid Media Pixel on website w GTM-Google Ads | Implement Paid Media Pixel on website w GTM-Google Ads |  |  |  | 7 | 13 | 15 | 1.1.7 |  |  | 195 | 1365
1777 | DEL-0044 | TSK-01768 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.1 | 1.1.8 | Spec QA | Implement Paid Media Pixel on website w GTM-Google Ads | Spec QA | QA Engineer | Mid | 4 | 13 | 3 | 1.1.8 |  |  | 195 | 780
1776 | DEL-0044 | TSK-01767 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.2 | 1.1.8 | Pixel Setup (GTM) | Implement Paid Media Pixel on website w GTM-Google Ads | Pixel Setup (GTM) | Data/Analytics Engineer | Mid | 3 | 16 | 12 | 1.1.8.1 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9 | 1.1 | Implement goals listed in UA as Conversions in G4 | Implement goals listed in UA as Conversions in G4 |  |  |  | 10 | 13 | 15 | 1.1.8 |  |  | 195 | 1950
1779 | DEL-0044 | TSK-01770 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.1 | 1.1.9 | QA Cycle | Implement goals listed in UA as Conversions in G4 | QA Cycle | QA Engineer | Mid | 4 | 13 | 3 | 1.1.9 |  |  | 195 | 780
1778 | DEL-0044 | TSK-01769 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.2 | 1.1.9 | Migrate UA Goals → GA4 Conversions | Implement goals listed in UA as Conversions in G4 | Migrate UA Goals → GA4 Conversions | Data/Analytics Engineer | Mid | 6 | 16 | 12 | 1.1.9.1 |  |  | 195 | 1170
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10 | 1.1 | Implementation | Implementation |  |  |  | 10 | 13 | 15 | 1.1.9 |  |  | 195 | 1950
1782 | DEL-0044 | TSK-01773 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.1 | 1.1.10 | QA Cycle | Implementation | QA Cycle | QA Engineer | Mid | 4 | 13 | 3 | 1.1.10 |  |  | 195 | 780
1781 | DEL-0044 | TSK-01772 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.2 | 1.1.10 | Implement Tags/Events | Implementation | Implement Tags/Events | Data/Analytics Engineer | Mid | 6 | 16 | 12 | 1.1.10.1 |  |  | 195 | 1170
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11 | 1.1 | Outbound link clicks | Outbound link clicks |  |  |  | 7 | 13 | 15 | 1.1.10 |  |  | 195 | 1365
1785 | DEL-0044 | TSK-01776 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11.1 | 1.1.11 | QA | Outbound link clicks | QA | QA Engineer | Mid | 4 | 13 | 3 | 1.1.11 |  |  | 195 | 780
1784 | DEL-0044 | TSK-01775 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11.2 | 1.1.11 | Event Config | Outbound link clicks | Event Config | Data/Analytics Engineer | Mid | 3 | 16 | 12 | 1.1.11.1 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.12 | 1.1 | Publishing tags, Testing and Auditing | Publishing tags, Testing and Auditing |  |  |  | 7 | 13 | 3 | 1.1.11 |  |  | 195 | 1365
1786 | DEL-0044 | TSK-01777 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.12.1 | 1.1.12 | Publish & Smoke Test | Publishing tags, Testing and Auditing | Publish & Smoke Test | QA Engineer | Mid | 7 | 13 | 3 | 1.1.12 |  |  | 195 | 1365
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.13 | 1.1 | Setup cross-domain tracking | Setup cross-domain tracking |  |  |  | 7 | 13 | 15 | 1.1.12 |  |  | 195 | 1365
1789 | DEL-0044 | TSK-01780 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.13.1 | 1.1.13 | QA | Setup cross-domain tracking | QA | QA Engineer | Mid | 4 | 13 | 3 | 1.1.13 |  |  | 195 | 780
1788 | DEL-0044 | TSK-01779 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.13.2 | 1.1.13 | Cross-domain Config | Setup cross-domain tracking | Cross-domain Config | Data/Analytics Engineer | Mid | 3 | 16 | 12 | 1.1.13.1 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.14 | 1.1 | Setup eCommerce tracking | Setup eCommerce tracking |  |  |  | 7 | 13 | 15 | 1.1.13 |  |  | 195 | 1365
1791 | DEL-0044 | TSK-01782 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.14.1 | 1.1.14 | QA | Setup eCommerce tracking | QA | QA Engineer | Mid | 4 | 13 | 3 | 1.1.14 |  |  | 195 | 780
1790 | DEL-0044 | TSK-01781 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.14.2 | 1.1.14 | Ecommerce Data Layer | Setup eCommerce tracking | Ecommerce Data Layer | Data/Analytics Engineer | Mid | 3 | 16 | 12 | 1.1.14.1 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.15 | 1.1 | Setup new GA4 acct for Caledera House | Setup new GA4 acct for Caledera House |  |  |  | 10 | 13 | 15 | 1.1.14 |  |  | 195 | 1950
1793 | DEL-0044 | TSK-01784 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.15.1 | 1.1.15 | QA Cycle | Setup new GA4 acct for Caledera House | QA Cycle | QA Engineer | Mid | 4 | 13 | 3 | 1.1.15 |  |  | 195 | 780
1792 | DEL-0044 | TSK-01783 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.15.2 | 1.1.15 | GA4 Property Setup | Setup new GA4 acct for Caledera House | GA4 Property Setup | Data/Analytics Engineer | Mid | 6 | 16 | 12 | 1.1.15.1 |  |  | 195 | 1170
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2 | 1 | Post-Production |  |  |  |  | 288 | 28 | 51 | 1.1 |  | Advanced/T1_LargeVolume | 195 | 56160
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1 | 1.2 | Content Licensing / Art Buying | Content Licensing / Art Buying |  |  |  | 3 | 28 | 4 | 1.2 |  |  | 195 | 585
65 | DEL-0003 | TSK-00065 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1.1 | 1.2.1 | Rights/License Research | Content Licensing / Art Buying | Rights/License Research | Producer | Mid | 1 | 28 | 4 | 1.2.1 |  |  | 195 | 195
66 | DEL-0003 | TSK-00066 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1.2 | 1.2.1 | Usage Notes | Content Licensing / Art Buying | Usage Notes | Account Manager | Mid | 2 | 79 | 0 | 1.2.1.1 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2 | 1.2 | VO Recording Sessions | VO Recording Sessions |  |  |  | 7 | 32 | 5 | 1.2.1 |  |  | 195 | 1365
124 | DEL-0003 | TSK-00124 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.1 | 1.2.2 | Script Polish | VO Recording Sessions | Script Polish | Copywriter | Mid | 2 | 32 | 5 | 1.2.2 |  |  | 195 | 390
125 | DEL-0003 | TSK-00125 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.2 | 1.2.2 | VO Session | VO Recording Sessions | VO Session | Sound Designer | Mid | 5 | 79 | 0 | 1.2.2.1 |  |  | 195 | 975
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3 | 1.2 | Editing | Editing |  |  |  | 26 | 37 | 6 | 1.2.2 |  |  | 195 | 5070
74 | DEL-0003 | TSK-00074 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.1 | 1.2.3 | Client Review & Revisions | Editing | Client Review & Revisions | Editor | Mid | 26 | 37 | 6 | 1.2.3 |  |  | 195 | 5070
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4 | 1.2 | Video Editing | Video Editing |  |  |  | 39 | 37 | 6 | 1.2.3 |  |  | 195 | 7605
127 | DEL-0003 | TSK-00127 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.1 | 1.2.4 | Client Review & Revisions | Video Editing | Client Review & Revisions | Editor | Mid | 39 | 37 | 6 | 1.2.4 |  |  | 195 | 7605
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5 | 1.2 | Voice Over | Voice Over |  |  |  | 26 | 37 | 14 | 1.2.4 |  |  | 195 | 5070
140 | DEL-0003 | TSK-00140 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.1 | 1.2.5 | VO Edit | Voice Over | VO Edit | Editor | Mid | 13 | 37 | 6 | 1.2.5 |  |  | 195 | 2535
139 | DEL-0003 | TSK-00139 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.2 | 1.2.5 | Mix | Voice Over | Mix | Sound Designer | Mid | 3 | 59 | 3 | 1.2.5.1 |  |  | 195 | 585
137 | DEL-0003 | TSK-00137 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.3 | 1.2.5 | Internal Review & Critique | Voice Over | Internal Review & Critique | Producer | Mid | 3 | 69 | 2 | 1.2.5.2 |  |  | 195 | 585
134 | DEL-0003 | TSK-00134 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.4 | 1.2.5 | Client Review & Revisions | Voice Over | Client Review & Revisions | Account Manager | Mid | 4 | 71 | 3 | 1.2.5.3 |  |  | 195 | 780
136 | DEL-0003 | TSK-00136 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.5 | 1.2.5 | Final Packaging | Voice Over | Final Packaging | Designer | Mid | 3 | 79 | 0 | 1.2.5.4 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6 | 1.2 | Motion Design/VFX | Motion Design/VFX |  |  |  | 26 | 43 | 9 | 1.2.5 |  |  | 195 | 5070
90 | DEL-0003 | TSK-00090 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.1 | 1.2.6 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Editor | Mid | 26 | 43 | 9 | 1.2.6 |  |  | 195 | 5070
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7 | 1.2 | Color Correction | Color Correction |  |  |  | 17 | 52 | 3 | 1.2.6 |  |  | 195 | 3315
53 | DEL-0003 | TSK-00053 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.1 | 1.2.7 | Client Review & Revisions | Color Correction | Client Review & Revisions | Colorist | Mid | 17 | 52 | 3 | 1.2.7 |  |  | 195 | 3315
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8 | 1.2 | Color Grading | Color Grading |  |  |  | 17 | 52 | 3 | 1.2.7 |  |  | 195 | 3315
59 | DEL-0003 | TSK-00059 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.1 | 1.2.8 | Client Review & Revisions | Color Grading | Client Review & Revisions | Colorist | Mid | 17 | 52 | 3 | 1.2.8 |  |  | 195 | 3315
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9 | 1.2 | Final Retouched Stills Review | Final Retouched Stills Review |  |  |  | 16 | 55 | 9 | 1.2.8 |  |  | 195 | 3120
89 | DEL-0003 | TSK-00089 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.1 | 1.2.9 | Retouch | Final Retouched Stills Review | Retouch | Retoucher | Mid | 7 | 55 | 4 | 1.2.9 |  |  | 195 | 1365
87 | DEL-0003 | TSK-00087 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.2 | 1.2.9 | Internal Review & Critique | Final Retouched Stills Review | Internal Review & Critique | Producer | Mid | 2 | 69 | 2 | 1.2.9.1 |  |  | 195 | 390
84 | DEL-0003 | TSK-00084 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.3 | 1.2.9 | Client Review & Revisions | Final Retouched Stills Review | Client Review & Revisions | Account Manager | Mid | 4 | 71 | 3 | 1.2.9.2 |  |  | 195 | 780
86 | DEL-0003 | TSK-00086 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.4 | 1.2.9 | Final Packaging | Final Retouched Stills Review | Final Packaging | Designer | Mid | 3 | 79 | 0 | 1.2.9.3 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10 | 1.2 | Retouching | Retouching |  |  |  | 16 | 55 | 9 | 1.2.9 |  |  | 195 | 3120
102 | DEL-0003 | TSK-00102 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.1 | 1.2.10 | Retouch | Retouching | Retouch | Retoucher | Mid | 7 | 55 | 4 | 1.2.10 |  |  | 195 | 1365
100 | DEL-0003 | TSK-00100 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.2 | 1.2.10 | Internal Review & Critique | Retouching | Internal Review & Critique | Producer | Mid | 2 | 69 | 2 | 1.2.10.1 |  |  | 195 | 390
97 | DEL-0003 | TSK-00097 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.3 | 1.2.10 | Client Review & Revisions | Retouching | Client Review & Revisions | Account Manager | Mid | 4 | 71 | 3 | 1.2.10.2 |  |  | 195 | 780
99 | DEL-0003 | TSK-00099 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.4 | 1.2.10 | Final Packaging | Retouching | Final Packaging | Designer | Mid | 3 | 79 | 0 | 1.2.10.3 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.11 | 1.2 | Sound Mix | Sound Mix |  |  |  | 13 | 59 | 3 | 1.2.10 |  |  | 195 | 2535
107 | DEL-0003 | TSK-00107 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.11.1 | 1.2.11 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Designer | Mid | 13 | 59 | 3 | 1.2.11 |  |  | 195 | 2535
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.12 | 1.2 | Sound Sourcing | Sound Sourcing |  |  |  | 4 | 59 | 3 | 1.2.11 |  |  | 195 | 780
113 | DEL-0003 | TSK-00113 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.12.1 | 1.2.12 | Music Search & License | Sound Sourcing | Music Search & License | Sound Designer | Mid | 4 | 59 | 3 | 1.2.12 |  |  | 195 | 780
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.13 | 1.2 | Final File Delivery | Final File Delivery |  |  |  | 10 | 62 | 3 | 1.2.12 |  |  | 195 | 1950
83 | DEL-0003 | TSK-00083 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.13.1 | 1.2.13 | QA (Tech & Content) | Final File Delivery | QA (Tech & Content) | QA Specialist | Mid | 4 | 62 | 3 | 1.2.13 |  |  | 195 | 780
80 | DEL-0003 | TSK-00080 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.13.2 | 1.2.13 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload | Media Manager / DIT | Mid | 6 | 79 | 0 | 1.2.13.1 |  |  | 195 | 1170
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.14 | 1.2 | True-ups (for vendor costs) | True-ups (for vendor costs) |  |  |  | 15 | 65 | 9 | 1.2.13 |  |  | 195 | 2925
116 | DEL-0003 | TSK-00116 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.14.1 | 1.2.14 | Change Orders & Tracking | True-ups (for vendor costs) | Change Orders & Tracking | Project Manager | Mid | 1 | 65 | 4 | 1.2.14 |  |  | 195 | 195
120 | DEL-0003 | TSK-00120 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.14.2 | 1.2.14 | Internal Review & Critique | True-ups (for vendor costs) | Internal Review & Critique | Producer | Mid | 3 | 69 | 2 | 1.2.14.1 |  |  | 195 | 585
117 | DEL-0003 | TSK-00117 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.14.3 | 1.2.14 | Client Review & Revisions | True-ups (for vendor costs) | Client Review & Revisions | Account Manager | Mid | 4 | 71 | 3 | 1.2.14.2 |  |  | 195 | 780
119 | DEL-0003 | TSK-00119 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.14.4 | 1.2.14 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation | Designer | Mid | 7 | 79 | 0 | 1.2.14.3 |  |  | 195 | 1365
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.15 | 1.2 | Cutdowns | Cutdowns |  |  |  | 17 | 69 | 5 | 1.2.14 |  |  | 195 | 3315
71 | DEL-0003 | TSK-00071 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.15.1 | 1.2.15 | Internal Review & Critique | Cutdowns | Internal Review & Critique | Producer | Mid | 2 | 69 | 2 | 1.2.15 |  |  | 195 | 390
67 | DEL-0003 | TSK-00067 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.15.2 | 1.2.15 | Client Review & Revisions | Cutdowns | Client Review & Revisions | Account Manager | Mid | 4 | 71 | 3 | 1.2.15.1 |  |  | 195 | 780
69 | DEL-0003 | TSK-00069 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.15.3 | 1.2.15 | Cutdowns (2-3) | Cutdowns | Cutdowns (2-3) | Editor | Mid | 11 | 79 | 0 | 1.2.15.2 |  |  | 195 | 2145
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.16 | 1.2 | Client Review | Client Review |  |  |  | 6 | 71 | 3 | 1.2.15 |  |  | 195 | 1170
50 | DEL-0003 | TSK-00050 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.16.1 | 1.2.16 | Client Review Coordination | Client Review | Client Review Coordination | Account Manager | Mid | 6 | 71 | 3 | 1.2.16 |  |  | 195 | 1170
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.17 | 1.2 | Review & Sign-Off | Review & Sign-Off |  |  |  | 5 | 71 | 5 | 1.2.16 |  |  | 195 | 975
103 | DEL-0003 | TSK-00103 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.17.1 | 1.2.17 | Client Review Coordination | Review & Sign-Off | Client Review Coordination | Account Manager | Mid | 4 | 71 | 3 | 1.2.17 |  |  | 195 | 780
105 | DEL-0003 | TSK-00105 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.17.2 | 1.2.17 | Notes Triage | Review & Sign-Off | Notes Triage | Project Manager | Mid | 1 | 77 | 2 | 1.2.17.1 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.18 | 1.2 | Asset Library | Asset Library |  |  |  | 3 | 74 | 3 | 1.2.17 |  |  | 195 | 585
48 | DEL-0003 | TSK-00048 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.18.1 | 1.2.18 | Post Support | Asset Library | Post Support | Editor | Mid | 3 | 74 | 3 | 1.2.18 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.19 | 1.2 | Capture Library | Capture Library |  |  |  | 3 | 74 | 3 | 1.2.18 |  |  | 195 | 585
49 | DEL-0003 | TSK-00049 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.19.1 | 1.2.19 | Post Support | Capture Library | Post Support | Editor | Mid | 3 | 74 | 3 | 1.2.19 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.20 | 1.2 | Selects Deck | Selects Deck |  |  |  | 3 | 74 | 3 | 1.2.19 |  |  | 195 | 585
106 | DEL-0003 | TSK-00106 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.20.1 | 1.2.20 | Post Support | Selects Deck | Post Support | Editor | Mid | 3 | 74 | 3 | 1.2.20 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.21 | 1.2 | Delivery | Delivery |  |  |  | 8 | 79 | 0 | 1.2.20 |  |  | 195 | 1560
73 | DEL-0003 | TSK-00073 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.21.1 | 1.2.21 | Post Support | Delivery | Post Support | Editor | Mid | 8 | 79 | 0 | 1.2.21 |  |  | 195 | 1560
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.22 | 1.2 | Stills/Footage Selection | Stills/Footage Selection |  |  |  | 8 | 79 | 0 | 1.2.21 |  |  | 195 | 1560
115 | DEL-0003 | TSK-00115 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.22.1 | 1.2.22 | Post Support | Stills/Footage Selection | Post Support | Editor | Mid | 8 | 79 | 0 | 1.2.22 |  |  | 195 | 1560
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3 | 1 | Pre-Production |  |  |  |  | 606 | 79 | 69 | 1.2 |  | Advanced/T1_LargeVolume | 195 | 118170
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1 | 1.3 | Wardrobe | Wardrobe |  |  |  | 19 | 79 | 8 | 1.3 |  |  | 195 | 3705
361 | DEL-0004 | TSK-00352 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.1 | 1.3.1 | Wardrobe Brief | Wardrobe | Wardrobe Brief | Art Director | Lead/Director | 4 | 79 | 3 | 1.3.1 |  |  | 195 | 780
358 | DEL-0004 | TSK-00349 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.2 | 1.3.1 | Internal Review & Critique | Wardrobe | Internal Review & Critique | Producer | Mid | 2 | 141 | 2 | 1.3.1.1 |  |  | 195 | 390
354 | DEL-0004 | TSK-00345 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.3 | 1.3.1 | Client Review & Revisions | Wardrobe | Client Review & Revisions | Account Manager | Mid | 4 | 143 | 3 | 1.3.1.2 |  |  | 195 | 780
356 | DEL-0004 | TSK-00347 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.4 | 1.3.1 | Final Packaging | Wardrobe | Final Packaging | Designer | Mid | 9 | 148 | 0 | 1.3.1.3 |  |  | 195 | 1755
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2 | 1.3 | Pre-Production Deck | Pre-Production Deck |  |  |  | 39 | 82 | 16 | 1.3.1 |  |  | 195 | 7605
214 | DEL-0004 | TSK-00214 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2.1 | 1.3.2 | Content Draft | Pre-Production Deck | Content Draft | Strategist | Mid | 31 | 82 | 6 | 1.3.2 |  |  | 195 | 6045
216 | DEL-0004 | TSK-00216 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2.2 | 1.3.2 | Deck Build | Pre-Production Deck | Deck Build | Designer | Mid | 2 | 97 | 5 | 1.3.2.1 |  |  | 195 | 390
218 | DEL-0004 | TSK-00218 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2.3 | 1.3.2 | Internal Review & Critique | Pre-Production Deck | Internal Review & Critique | Producer | Mid | 2 | 141 | 2 | 1.3.2.2 |  |  | 195 | 390
212 | DEL-0004 | TSK-00212 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2.4 | 1.3.2 | Client Review & Revisions | Pre-Production Deck | Client Review & Revisions | Account Manager | Mid | 4 | 143 | 3 | 1.3.2.3 |  |  | 195 | 780
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3 | 1.3 | File Naming Convention & Storage | File Naming Convention & Storage |  |  |  | 18 | 88 | 14 | 1.3.2 |  |  | 195 | 3510
186 | DEL-0004 | TSK-00186 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3.1 | 1.3.3 | Schema Design | File Naming Convention & Storage | Schema Design | Media Manager / DIT | Mid | 4 | 88 | 9 | 1.3.3 |  |  | 195 | 780
184 | DEL-0004 | TSK-00184 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3.2 | 1.3.3 | Internal Review & Critique | File Naming Convention & Storage | Internal Review & Critique | Producer | Mid | 2 | 141 | 2 | 1.3.3.1 |  |  | 195 | 390
179 | DEL-0004 | TSK-00179 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3.3 | 1.3.3 | Client Review & Revisions | File Naming Convention & Storage | Client Review & Revisions | Account Manager | Mid | 4 | 143 | 3 | 1.3.3.2 |  |  | 195 | 780
181 | DEL-0004 | TSK-00181 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3.4 | 1.3.3 | Distribution & Notes | File Naming Convention & Storage | Distribution & Notes | Designer | Mid | 8 | 148 | 0 | 1.3.3.3 |  |  | 195 | 1560
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4 | 1.3 | R1 Pre-Production Deck/Shot List | R1 Pre-Production Deck/Shot List |  |  |  | 25 | 97 | 5 | 1.3.3 |  |  | 195 | 4875
230 | DEL-0004 | TSK-00230 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.1 | 1.3.4 | Client Review & Revisions | R1 Pre-Production Deck/Shot List | Client Review & Revisions | Producer | Mid | 25 | 97 | 5 | 1.3.4 |  |  | 195 | 4875
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5 | 1.3 | R2 Pre-Production Deck/Shot List | R2 Pre-Production Deck/Shot List |  |  |  | 25 | 97 | 5 | 1.3.4 |  |  | 195 | 4875
238 | DEL-0004 | TSK-00238 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.1 | 1.3.5 | Client Review & Revisions | R2 Pre-Production Deck/Shot List | Client Review & Revisions | Producer | Mid | 25 | 97 | 5 | 1.3.5 |  |  | 195 | 4875
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.6 | 1.3 | Run of Show & Call Sheet | Run of Show & Call Sheet |  |  |  | 35 | 97 | 5 | 1.3.5 |  |  | 195 | 6825
246 | DEL-0004 | TSK-00246 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.6.1 | 1.3.6 | Client Review & Revisions | Run of Show & Call Sheet | Client Review & Revisions | Producer | Mid | 35 | 97 | 5 | 1.3.6 |  |  | 195 | 6825
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.7 | 1.3 | Script & Storyboards | Script & Storyboards |  |  |  | 47 | 97 | 5 | 1.3.6 |  |  | 195 | 9165
256 | DEL-0004 | TSK-00256 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.7.1 | 1.3.7 | Client Review & Revisions | Script & Storyboards | Client Review & Revisions | Producer | Mid | 47 | 97 | 5 | 1.3.7 |  |  | 195 | 9165
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8 | 1.3 | Shoot Oversight & Direction | Shoot Oversight & Direction |  |  |  | 18 | 97 | 8 | 1.3.7 |  |  | 195 | 3510
280 | DEL-0004 | TSK-00271 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8.1 | 1.3.8 | Schedule Management | Shoot Oversight & Direction | Schedule Management | Producer | Mid | 4 | 97 | 5 | 1.3.8 |  |  | 195 | 780
279 | DEL-0004 | TSK-00270 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8.2 | 1.3.8 | Quality Check (QC) | Shoot Oversight & Direction | Quality Check (QC) | QA Specialist | Mid | 4 | 116 | 3 | 1.3.8.1 |  |  | 195 | 780
274 | DEL-0004 | TSK-00265 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8.3 | 1.3.8 | Daily Wrap Notes | Shoot Oversight & Direction | Daily Wrap Notes | Creative Director | Lead/Director | 10 | 148 | 0 | 1.3.8.2 |  |  | 195 | 1950
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.9 | 1.3 | Shot List | Shot List |  |  |  | 31 | 97 | 5 | 1.3.8 |  |  | 195 | 6045
281 | DEL-0004 | TSK-00272 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.9.1 | 1.3.9 | Client Review & Revisions | Shot List | Client Review & Revisions | Producer | Mid | 31 | 97 | 5 | 1.3.9 |  |  | 195 | 6045
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.10 | 1.3 | Storyboard Review | Storyboard Review |  |  |  | 6 | 97 | 5 | 1.3.9 |  |  | 195 | 1170
291 | DEL-0004 | TSK-00282 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.10.1 | 1.3.10 | Internal Crit | Storyboard Review | Internal Crit | Art Director | Lead/Director | 6 | 97 | 5 | 1.3.10 |  |  | 195 | 1170
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.11 | 1.3 | Storyboards & Script Writing | Storyboards & Script Writing |  |  |  | 23 | 97 | 5 | 1.3.10 |  |  | 195 | 4485
294 | DEL-0004 | TSK-00285 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.11.1 | 1.3.11 | Client Review & Revisions | Storyboards & Script Writing | Client Review & Revisions | Producer | Mid | 23 | 97 | 5 | 1.3.11 |  |  | 195 | 4485
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.12 | 1.3 | Casting | Casting |  |  |  | 20 | 102 | 8 | 1.3.11 |  |  | 195 | 3900
150 | DEL-0004 | TSK-00150 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.12.1 | 1.3.12 | Approvals/Holds | Casting | Approvals/Holds | Producer | Mid | 20 | 102 | 8 | 1.3.12 |  |  | 195 | 3900
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.13 | 1.3 | Load In & Pre-Lighting | Load In & Pre-Lighting |  |  |  | 38 | 102 | 8 | 1.3.12 |  |  | 195 | 7410
188 | DEL-0004 | TSK-00188 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.13.1 | 1.3.13 | Client Review & Revisions | Load In & Pre-Lighting | Client Review & Revisions | Producer | Mid | 38 | 102 | 8 | 1.3.13 |  |  | 195 | 7410
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.14 | 1.3 | Talent Casting | Talent Casting |  |  |  | 38 | 102 | 8 | 1.3.13 |  |  | 195 | 7410
303 | DEL-0004 | TSK-00294 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.14.1 | 1.3.14 | Approvals & Holds | Talent Casting | Approvals & Holds | Producer | Mid | 38 | 102 | 8 | 1.3.14 |  |  | 195 | 7410
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15 | 1.3 | Post Production Plan & Timeline | Post Production Plan & Timeline |  |  |  | 33 | 110 | 11 | 1.3.14 |  |  | 195 | 6435
203 | DEL-0004 | TSK-00203 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15.1 | 1.3.15 | Editorial Milestones | Post Production Plan & Timeline | Editorial Milestones | Editor | Mid | 16 | 110 | 6 | 1.3.15 |  |  | 195 | 3120
206 | DEL-0004 | TSK-00206 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15.2 | 1.3.15 | Internal Review & Critique | Post Production Plan & Timeline | Internal Review & Critique | Producer | Mid | 2 | 141 | 2 | 1.3.15.1 |  |  | 195 | 390
198 | DEL-0004 | TSK-00198 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15.3 | 1.3.15 | Client Review & Revisions | Post Production Plan & Timeline | Client Review & Revisions | Account Manager | Mid | 6 | 143 | 3 | 1.3.15.2 |  |  | 195 | 1170
201 | DEL-0004 | TSK-00201 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15.4 | 1.3.15 | Delivery Timeline | Post Production Plan & Timeline | Delivery Timeline | Producer | Mid | 9 | 148 | 0 | 1.3.15.3 |  |  | 195 | 1755
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.16 | 1.3 | Concept Development | Concept Development |  |  |  | 26 | 119 | 17 | 1.3.15 |  |  | 195 | 5070
158 | DEL-0004 | TSK-00158 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.16.1 | 1.3.16 | Ideation Sprint | Concept Development | Ideation Sprint | Designer | Mid | 19 | 119 | 12 | 1.3.16 |  |  | 195 | 3705
163 | DEL-0004 | TSK-00163 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.16.2 | 1.3.16 | Internal Review & Critique | Concept Development | Internal Review & Critique | Producer | Mid | 2 | 141 | 2 | 1.3.16.1 |  |  | 195 | 390
155 | DEL-0004 | TSK-00155 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.16.3 | 1.3.16 | Client Review & Revisions | Concept Development | Client Review & Revisions | Account Manager | Mid | 5 | 143 | 3 | 1.3.16.2 |  |  | 195 | 975
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.17 | 1.3 | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) |  |  |  | 15 | 131 | 9 | 1.3.16 |  |  | 195 | 2925
228 | DEL-0004 | TSK-00228 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.17.1 | 1.3.17 | Inventory & Tracking | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Inventory & Tracking | Producer | Mid | 1 | 131 | 4 | 1.3.17 |  |  | 195 | 195
226 | DEL-0004 | TSK-00226 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.17.2 | 1.3.17 | Internal Review & Critique | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Internal Review & Critique | Producer | Mid | 3 | 141 | 2 | 1.3.17.1 |  |  | 195 | 585
223 | DEL-0004 | TSK-00223 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.17.3 | 1.3.17 | Client Review & Revisions | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Client Review & Revisions | Account Manager | Mid | 4 | 143 | 3 | 1.3.17.2 |  |  | 195 | 780
222 | DEL-0004 | TSK-00222 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.17.4 | 1.3.17 | Chain of Custody | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Chain of Custody | Designer | Mid | 7 | 148 | 0 | 1.3.17.3 |  |  | 195 | 1365
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.18 | 1.3 | Vendor Deal Memos & Contracts | Vendor Deal Memos & Contracts |  |  |  | 5 | 131 | 4 | 1.3.17 |  |  | 195 | 975
333 | DEL-0004 | TSK-00324 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.18.1 | 1.3.18 | Filing & Tracking | Vendor Deal Memos & Contracts | Filing & Tracking | Project Manager | Mid | 1 | 131 | 4 | 1.3.18 |  |  | 195 | 195
331 | DEL-0004 | TSK-00322 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.18.2 | 1.3.18 | Deal Memos & Contracts | Vendor Deal Memos & Contracts | Deal Memos & Contracts | Account Manager | Mid | 4 | 148 | 0 | 1.3.18.1 |  |  | 195 | 780
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.19 | 1.3 | Vendor Engagement | Vendor Engagement |  |  |  | 21 | 135 | 11 | 1.3.18 |  |  | 195 | 4095
334 | DEL-0004 | TSK-00325 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.19.1 | 1.3.19 | Briefing Docs | Vendor Engagement | Briefing Docs | Designer | Mid | 15 | 135 | 6 | 1.3.19 |  |  | 195 | 2925
342 | DEL-0004 | TSK-00333 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.19.2 | 1.3.19 | Internal Review & Critique | Vendor Engagement | Internal Review & Critique | Producer | Mid | 2 | 141 | 2 | 1.3.19.1 |  |  | 195 | 390
336 | DEL-0004 | TSK-00327 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.19.3 | 1.3.19 | Client Review & Revisions | Vendor Engagement | Client Review & Revisions | Account Manager | Mid | 4 | 143 | 3 | 1.3.19.2 |  |  | 195 | 780
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.20 | 1.3 | Art Direction | Art Direction |  |  |  | 30 | 141 | 5 | 1.3.19 |  |  | 195 | 5850
144 | DEL-0004 | TSK-00144 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.20.1 | 1.3.20 | Internal Review & Critique | Art Direction | Internal Review & Critique | Producer | Mid | 2 | 141 | 2 | 1.3.20 |  |  | 195 | 390
141 | DEL-0004 | TSK-00141 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.20.2 | 1.3.20 | Client Review & Revisions | Art Direction | Client Review & Revisions | Account Manager | Mid | 4 | 143 | 3 | 1.3.20.1 |  |  | 195 | 780
143 | DEL-0004 | TSK-00143 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.20.3 | 1.3.20 | Look Dev & References | Art Direction | Look Dev & References | Designer | Mid | 9 | 148 | 0 | 1.3.20.2 |  |  | 195 | 1755
148 | DEL-0004 | TSK-00148 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.20.4 | 1.3.20 | Style Guide (lite) | Art Direction | Style Guide (lite) | Designer | Mid | 15 | 148 | 0 | 1.3.20.3 |  |  | 195 | 2925
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.21 | 1.3 | Concepting | Concepting |  |  |  | 32 | 141 | 5 | 1.3.20 |  |  | 195 | 6240
175 | DEL-0004 | TSK-00175 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.21.1 | 1.3.21 | Internal Review & Critique | Concepting | Internal Review & Critique | Producer | Mid | 2 | 141 | 2 | 1.3.21 |  |  | 195 | 390
166 | DEL-0004 | TSK-00166 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.21.2 | 1.3.21 | Client Review & Revisions | Concepting | Client Review & Revisions | Account Manager | Mid | 5 | 143 | 3 | 1.3.21.1 |  |  | 195 | 975
169 | DEL-0004 | TSK-00169 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.21.3 | 1.3.21 | Ideation Sprint | Concepting | Ideation Sprint | Strategist | Mid | 25 | 148 | 0 | 1.3.21.2 |  |  | 195 | 4875
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.22 | 1.3 | Vendor Contracting | Vendor Contracting |  |  |  | 19 | 141 | 5 | 1.3.21 |  |  | 195 | 3705
319 | DEL-0004 | TSK-00310 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.22.1 | 1.3.22 | Internal Review & Critique | Vendor Contracting | Internal Review & Critique | Producer | Mid | 2 | 141 | 2 | 1.3.22 |  |  | 195 | 390
313 | DEL-0004 | TSK-00304 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.22.2 | 1.3.22 | Client Review & Revisions | Vendor Contracting | Client Review & Revisions | Account Manager | Mid | 6 | 143 | 3 | 1.3.22.1 |  |  | 195 | 1170
316 | DEL-0004 | TSK-00307 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.22.3 | 1.3.22 | SOW/CO Draft & Negotiate | Vendor Contracting | SOW/CO Draft & Negotiate | Account Manager | Mid | 11 | 148 | 0 | 1.3.22.2 |  |  | 195 | 2145
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.23 | 1.3 | Vendor Deal Memos | Vendor Deal Memos |  |  |  | 15 | 141 | 5 | 1.3.22 |  |  | 195 | 2925
329 | DEL-0004 | TSK-00320 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.23.1 | 1.3.23 | Internal Review & Critique | Vendor Deal Memos | Internal Review & Critique | Producer | Mid | 2 | 141 | 2 | 1.3.23 |  |  | 195 | 390
323 | DEL-0004 | TSK-00314 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.23.2 | 1.3.23 | Client Review & Revisions | Vendor Deal Memos | Client Review & Revisions | Account Manager | Mid | 4 | 143 | 3 | 1.3.23.1 |  |  | 195 | 780
325 | DEL-0004 | TSK-00316 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.23.3 | 1.3.23 | Distribution & Confirmation | Vendor Deal Memos | Distribution & Confirmation | Producer | Mid | 9 | 148 | 0 | 1.3.23.2 |  |  | 195 | 1755
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.24 | 1.3 | Vendor Pre-Production Meetings | Vendor Pre-Production Meetings |  |  |  | 20 | 141 | 7 | 1.3.23 |  |  | 195 | 3900
349 | DEL-0004 | TSK-00340 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.24.1 | 1.3.24 | Internal Review & Critique | Vendor Pre-Production Meetings | Internal Review & Critique | Producer | Mid | 2 | 141 | 2 | 1.3.24 |  |  | 195 | 390
346 | DEL-0004 | TSK-00337 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.24.2 | 1.3.24 | Client Review & Revisions | Vendor Pre-Production Meetings | Client Review & Revisions | Account Manager | Mid | 4 | 143 | 3 | 1.3.24.1 |  |  | 195 | 780
351 | DEL-0004 | TSK-00342 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.24.3 | 1.3.24 | Run Meeting & Notes | Vendor Pre-Production Meetings | Run Meeting & Notes | Creative Director | Lead/Director | 4 | 146 | 2 | 1.3.24.2 |  |  | 195 | 780
344 | DEL-0004 | TSK-00335 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.24.4 | 1.3.24 | Agenda & Materials | Vendor Pre-Production Meetings | Agenda & Materials | Designer | Mid | 10 | 148 | 0 | 1.3.24.3 |  |  | 195 | 1950
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.25 | 1.3 | Pre-Interview Talent Calls | Pre-Interview Talent Calls |  |  |  | 6 | 148 | 0 | 1.3.24 |  |  | 195 | 1170
209 | DEL-0004 | TSK-00209 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.25.1 | 1.3.25 | Notes & Shareout | Pre-Interview Talent Calls | Notes & Shareout | Producer | Mid | 6 | 148 | 0 | 1.3.25 |  |  | 195 | 1170
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.26 | 1.3 | Wrap & File Organization | Wrap & File Organization |  |  |  | 2 | 148 | 0 | 1.3.25 |  |  | 195 | 390
363 | DEL-0004 | TSK-00354 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.26.1 | 1.3.26 | Pre-Production Support | Wrap & File Organization | Pre-Production Support | Producer | Mid | 2 | 148 | 0 | 1.3.26 |  |  | 195 | 390
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4 | 1 | Brand Identity Development |  |  |  |  | 391 | 148 | 15 | 1.3 |  | Advanced/T1_LargeVolume | 195 | 76245
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1 | 1.4 | Color Palette | Color Palette |  |  |  | 23 | 148 | 3 | 1.4 |  |  | 195 | 4485
474 | DEL-0008 | TSK-00465 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.1 | 1.4.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Designer | Mid | 23 | 148 | 3 | 1.4.1 |  |  | 195 | 4485
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2 | 1.4 | Graphic Mock-Ups | Graphic Mock-Ups |  |  |  | 38 | 151 | 9 | 1.4.1 |  |  | 195 | 7410
496 | DEL-0008 | TSK-00487 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.1 | 1.4.2 | Compositing/Retouch | Graphic Mock-Ups | Compositing/Retouch | Retoucher | Mid | 6 | 151 | 4 | 1.4.2 |  |  | 195 | 1170
498 | DEL-0008 | TSK-00489 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.2 | 1.4.2 | Internal Review & Critique | Graphic Mock-Ups | Internal Review & Critique | Art Director | Lead/Director | 2 | 158 | 2 | 1.4.2.1 |  |  | 195 | 390
493 | DEL-0008 | TSK-00484 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.3 | 1.4.2 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions | Account Manager | Mid | 5 | 160 | 3 | 1.4.2.2 |  |  | 195 | 975
497 | DEL-0008 | TSK-00488 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.4 | 1.4.2 | Mockup Scenarios (3-4) | Graphic Mock-Ups | Mockup Scenarios (3-4) | Designer | Mid | 25 | 163 | 0 | 1.4.2.3 |  |  | 195 | 4875
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3 | 1.4 | Logo | Logo |  |  |  | 57 | 155 | 8 | 1.4.2 |  |  | 195 | 11115
520 | DEL-0008 | TSK-00511 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.1 | 1.4.3 | Quality Check (Specs/Accessibility) | Logo | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 4 | 155 | 3 | 1.4.3 |  |  | 195 | 780
515 | DEL-0008 | TSK-00506 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.2 | 1.4.3 | Internal Review & Critique | Logo | Internal Review & Critique | Art Director | Lead/Director | 2 | 158 | 2 | 1.4.3.1 |  |  | 195 | 390
511 | DEL-0008 | TSK-00502 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.3 | 1.4.3 | Client Review & Revisions | Logo | Client Review & Revisions | Account Manager | Mid | 5 | 160 | 3 | 1.4.3.2 |  |  | 195 | 975
514 | DEL-0008 | TSK-00505 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.4 | 1.4.3 | Logo Exploration (6-8 dirs) | Logo | Logo Exploration (6-8 dirs) | Designer | Mid | 46 | 163 | 0 | 1.4.3.3 |  |  | 195 | 8970
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4 | 1.4 | Typography | Typography |  |  |  | 53 | 155 | 8 | 1.4.3 |  |  | 195 | 10335
556 | DEL-0008 | TSK-00547 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.1 | 1.4.4 | Quality Check (Specs/Accessibility) | Typography | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 4 | 155 | 3 | 1.4.4 |  |  | 195 | 780
554 | DEL-0008 | TSK-00545 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.2 | 1.4.4 | Internal Review & Critique | Typography | Internal Review & Critique | Art Director | Lead/Director | 2 | 158 | 2 | 1.4.4.1 |  |  | 195 | 390
549 | DEL-0008 | TSK-00540 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.3 | 1.4.4 | Client Review & Revisions | Typography | Client Review & Revisions | Account Manager | Mid | 5 | 160 | 3 | 1.4.4.2 |  |  | 195 | 975
552 | DEL-0008 | TSK-00543 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.4 | 1.4.4 | Final Packaging | Typography | Final Packaging | Designer | Mid | 42 | 163 | 0 | 1.4.4.3 |  |  | 195 | 8190
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5 | 1.4 | Graphic & Copy Messaging Cornerstones | Graphic & Copy Messaging Cornerstones |  |  |  | 36 | 158 | 5 | 1.4.4 |  |  | 195 | 7020
489 | DEL-0008 | TSK-00480 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.1 | 1.4.5 | Internal Review & Critique | Graphic & Copy Messaging Cornerstones | Internal Review & Critique | Art Director | Lead/Director | 2 | 158 | 2 | 1.4.5 |  |  | 195 | 390
483 | DEL-0008 | TSK-00474 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.2 | 1.4.5 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Account Manager | Mid | 7 | 160 | 3 | 1.4.5.1 |  |  | 195 | 1365
487 | DEL-0008 | TSK-00478 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.3 | 1.4.5 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft | Designer | Mid | 27 | 163 | 0 | 1.4.5.2 |  |  | 195 | 5265
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6 | 1.4 | Iconography | Iconography |  |  |  | 41 | 158 | 5 | 1.4.5 |  |  | 195 | 7995
509 | DEL-0008 | TSK-00500 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.1 | 1.4.6 | Internal Review & Critique | Iconography | Internal Review & Critique | Art Director | Lead/Director | 2 | 158 | 2 | 1.4.6 |  |  | 195 | 390
502 | DEL-0008 | TSK-00493 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.2 | 1.4.6 | Client Review & Revisions | Iconography | Client Review & Revisions | Account Manager | Mid | 5 | 160 | 3 | 1.4.6.1 |  |  | 195 | 975
505 | DEL-0008 | TSK-00496 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.3 | 1.4.6 | Export & Spec | Iconography | Export & Spec | Designer | Mid | 34 | 163 | 0 | 1.4.6.2 |  |  | 195 | 6630
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7 | 1.4 | Overarching Moodboard | Overarching Moodboard |  |  |  | 35 | 158 | 5 | 1.4.6 |  |  | 195 | 6825
528 | DEL-0008 | TSK-00519 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.1 | 1.4.7 | Internal Review & Critique | Overarching Moodboard | Internal Review & Critique | Art Director | Lead/Director | 2 | 158 | 2 | 1.4.7 |  |  | 195 | 390
522 | DEL-0008 | TSK-00513 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.2 | 1.4.7 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions | Account Manager | Mid | 5 | 160 | 3 | 1.4.7.1 |  |  | 195 | 975
525 | DEL-0008 | TSK-00516 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.3 | 1.4.7 | Curate Moodboard | Overarching Moodboard | Curate Moodboard | Designer | Mid | 28 | 163 | 0 | 1.4.7.2 |  |  | 195 | 5460
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8 | 1.4 | Tagline Copy Bank | Tagline Copy Bank |  |  |  | 28 | 158 | 5 | 1.4.7 |  |  | 195 | 5460
536 | DEL-0008 | TSK-00527 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.1 | 1.4.8 | Internal Review & Critique | Tagline Copy Bank | Internal Review & Critique | Art Director | Lead/Director | 2 | 158 | 2 | 1.4.8 |  |  | 195 | 390
531 | DEL-0008 | TSK-00522 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.2 | 1.4.8 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Account Manager | Mid | 6 | 160 | 3 | 1.4.8.1 |  |  | 195 | 1170
535 | DEL-0008 | TSK-00526 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.3 | 1.4.8 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale | Designer | Mid | 20 | 163 | 0 | 1.4.8.2 |  |  | 195 | 3900
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9 | 1.4 | Textures/Patterns/Materials | Textures/Patterns/Materials |  |  |  | 38 | 158 | 5 | 1.4.8 |  |  | 195 | 7410
546 | DEL-0008 | TSK-00537 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.1 | 1.4.9 | Internal Review & Critique | Textures/Patterns/Materials | Internal Review & Critique | Art Director | Lead/Director | 2 | 158 | 2 | 1.4.9 |  |  | 195 | 390
542 | DEL-0008 | TSK-00533 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.2 | 1.4.9 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions | Account Manager | Mid | 5 | 160 | 3 | 1.4.9.1 |  |  | 195 | 975
541 | DEL-0008 | TSK-00532 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.3 | 1.4.9 | Build Repeating Tiles | Textures/Patterns/Materials | Build Repeating Tiles | Designer | Mid | 31 | 163 | 0 | 1.4.9.2 |  |  | 195 | 6045
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10 | 1.4 | Visual Elements/Comps | Visual Elements/Comps |  |  |  | 42 | 158 | 5 | 1.4.9 |  |  | 195 | 8190
566 | DEL-0008 | TSK-00557 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10.1 | 1.4.10 | Internal Review & Critique | Visual Elements/Comps | Internal Review & Critique | Art Director | Lead/Director | 2 | 158 | 2 | 1.4.10 |  |  | 195 | 390
559 | DEL-0008 | TSK-00550 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10.2 | 1.4.10 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions | Account Manager | Mid | 5 | 160 | 3 | 1.4.10.1 |  |  | 195 | 975
562 | DEL-0008 | TSK-00553 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10.3 | 1.4.10 | Compositions (2-3) | Visual Elements/Comps | Compositions (2-3) | Designer | Mid | 35 | 163 | 0 | 1.4.10.2 |  |  | 195 | 6825
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5 | 1 | Brand Style & Usage Guidelines |  |  |  |  | 382 | 163 | 11 | 1.4 |  | Advanced/T1_LargeVolume | 195 | 74490
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.1 | 1.5 | Color Palettes | Color Palettes |  |  |  | 20 | 163 | 3 | 1.5 |  |  | 195 | 3900
578 | DEL-0009 | TSK-00569 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.1.1 | 1.5.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Designer | Mid | 20 | 163 | 3 | 1.5.1 |  |  | 195 | 3900
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2 | 1.5 | Logo Lock-Ups | Logo Lock-Ups |  |  |  | 42 | 166 | 8 | 1.5.1 |  |  | 195 | 8190
626 | DEL-0009 | TSK-00617 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.1 | 1.5.2 | Quality Check (Specs/Accessibility) | Logo Lock-Ups | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 4 | 166 | 3 | 1.5.2 |  |  | 195 | 780
622 | DEL-0009 | TSK-00613 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.2 | 1.5.2 | Internal Review & Critique | Logo Lock-Ups | Internal Review & Critique | Art Director | Lead/Director | 2 | 169 | 2 | 1.5.2.1 |  |  | 195 | 390
618 | DEL-0009 | TSK-00609 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.3 | 1.5.2 | Client Review & Revisions | Logo Lock-Ups | Client Review & Revisions | Account Manager | Mid | 5 | 171 | 3 | 1.5.2.2 |  |  | 195 | 975
621 | DEL-0009 | TSK-00612 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.4 | 1.5.2 | Final Packaging | Logo Lock-Ups | Final Packaging | Designer | Mid | 31 | 174 | 0 | 1.5.2.3 |  |  | 195 | 6045
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3 | 1.5 | Logo Placement | Logo Placement |  |  |  | 42 | 166 | 8 | 1.5.2 |  |  | 195 | 8190
635 | DEL-0009 | TSK-00626 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.1 | 1.5.3 | Quality Check (Specs/Accessibility) | Logo Placement | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 4 | 166 | 3 | 1.5.3 |  |  | 195 | 780
631 | DEL-0009 | TSK-00622 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.2 | 1.5.3 | Internal Review & Critique | Logo Placement | Internal Review & Critique | Art Director | Lead/Director | 2 | 169 | 2 | 1.5.3.1 |  |  | 195 | 390
627 | DEL-0009 | TSK-00618 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.3 | 1.5.3 | Client Review & Revisions | Logo Placement | Client Review & Revisions | Account Manager | Mid | 5 | 171 | 3 | 1.5.3.2 |  |  | 195 | 975
630 | DEL-0009 | TSK-00621 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.4 | 1.5.3 | Final Packaging | Logo Placement | Final Packaging | Designer | Mid | 31 | 174 | 0 | 1.5.3.3 |  |  | 195 | 6045
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4 | 1.5 | Brand Do's & Dont's | Brand Do's & Dont's |  |  |  | 50 | 169 | 5 | 1.5.3 |  |  | 195 | 9750
573 | DEL-0009 | TSK-00564 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.1 | 1.5.4 | Internal Review & Critique | Brand Do's & Dont's | Internal Review & Critique | Art Director | Lead/Director | 2 | 169 | 2 | 1.5.4 |  |  | 195 | 390
568 | DEL-0009 | TSK-00559 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.2 | 1.5.4 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions | Account Manager | Mid | 6 | 171 | 3 | 1.5.4.1 |  |  | 195 | 1170
572 | DEL-0009 | TSK-00563 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.3 | 1.5.4 | Outline & Examples | Brand Do's & Dont's | Outline & Examples | Designer | Mid | 42 | 174 | 0 | 1.5.4.2 |  |  | 195 | 8190
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5 | 1.5 | Design Style Tile | Design Style Tile |  |  |  | 35 | 169 | 5 | 1.5.4 |  |  | 195 | 6825
590 | DEL-0009 | TSK-00581 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.1 | 1.5.5 | Internal Review & Critique | Design Style Tile | Internal Review & Critique | Art Director | Lead/Director | 2 | 169 | 2 | 1.5.5 |  |  | 195 | 390
586 | DEL-0009 | TSK-00577 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.2 | 1.5.5 | Client Review & Revisions | Design Style Tile | Client Review & Revisions | Account Manager | Mid | 5 | 171 | 3 | 1.5.5.1 |  |  | 195 | 975
589 | DEL-0009 | TSK-00580 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.3 | 1.5.5 | Style Tile Build | Design Style Tile | Style Tile Build | Designer | Mid | 28 | 174 | 0 | 1.5.5.2 |  |  | 195 | 5460
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6 | 1.5 | Image Use Guidance | Image Use Guidance |  |  |  | 35 | 169 | 5 | 1.5.5 |  |  | 195 | 6825
608 | DEL-0009 | TSK-00599 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.1 | 1.5.6 | Internal Review & Critique | Image Use Guidance | Internal Review & Critique | Art Director | Lead/Director | 2 | 169 | 2 | 1.5.6 |  |  | 195 | 390
602 | DEL-0009 | TSK-00593 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.2 | 1.5.6 | Client Review & Revisions | Image Use Guidance | Client Review & Revisions | Account Manager | Mid | 5 | 171 | 3 | 1.5.6.1 |  |  | 195 | 975
605 | DEL-0009 | TSK-00596 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.3 | 1.5.6 | Examples & Callouts | Image Use Guidance | Examples & Callouts | Designer | Mid | 28 | 174 | 0 | 1.5.6.2 |  |  | 195 | 5460
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7 | 1.5 | Imagery Style | Imagery Style |  |  |  | 35 | 169 | 5 | 1.5.6 |  |  | 195 | 6825
616 | DEL-0009 | TSK-00607 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.1 | 1.5.7 | Internal Review & Critique | Imagery Style | Internal Review & Critique | Art Director | Lead/Director | 2 | 169 | 2 | 1.5.7 |  |  | 195 | 390
610 | DEL-0009 | TSK-00601 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.2 | 1.5.7 | Client Review & Revisions | Imagery Style | Client Review & Revisions | Account Manager | Mid | 5 | 171 | 3 | 1.5.7.1 |  |  | 195 | 975
613 | DEL-0009 | TSK-00604 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.3 | 1.5.7 | Examples & Callouts | Imagery Style | Examples & Callouts | Designer | Mid | 28 | 174 | 0 | 1.5.7.2 |  |  | 195 | 5460
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8 | 1.5 | Photo & Video Direction | Photo & Video Direction |  |  |  | 38 | 169 | 5 | 1.5.7 |  |  | 195 | 7410
642 | DEL-0009 | TSK-00633 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.1 | 1.5.8 | Internal Review & Critique | Photo & Video Direction | Internal Review & Critique | Art Director | Lead/Director | 2 | 169 | 2 | 1.5.8 |  |  | 195 | 390
636 | DEL-0009 | TSK-00627 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.2 | 1.5.8 | Client Review & Revisions | Photo & Video Direction | Client Review & Revisions | Account Manager | Mid | 5 | 171 | 3 | 1.5.8.1 |  |  | 195 | 975
639 | DEL-0009 | TSK-00630 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.3 | 1.5.8 | Direction Pages | Photo & Video Direction | Direction Pages | Designer | Mid | 31 | 174 | 0 | 1.5.8.2 |  |  | 195 | 6045
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9 | 1.5 | Typography | Typography |  |  |  | 28 | 169 | 5 | 1.5.8 |  |  | 195 | 5460
649 | DEL-0009 | TSK-00640 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.1 | 1.5.9 | Internal Review & Critique | Typography | Internal Review & Critique | Art Director | Lead/Director | 2 | 169 | 2 | 1.5.9 |  |  | 195 | 390
645 | DEL-0009 | TSK-00636 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.2 | 1.5.9 | Client Review & Revisions | Typography | Client Review & Revisions | Account Manager | Mid | 5 | 171 | 3 | 1.5.9.1 |  |  | 195 | 975
648 | DEL-0009 | TSK-00639 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.3 | 1.5.9 | Final Packaging | Typography | Final Packaging | Designer | Mid | 21 | 174 | 0 | 1.5.9.2 |  |  | 195 | 4095
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10 | 1.5 | Use Cases | Use Cases |  |  |  | 33 | 169 | 5 | 1.5.9 |  |  | 195 | 6435
656 | DEL-0009 | TSK-00647 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.1 | 1.5.10 | Internal Review & Critique | Use Cases | Internal Review & Critique | Art Director | Lead/Director | 2 | 169 | 2 | 1.5.10 |  |  | 195 | 390
652 | DEL-0009 | TSK-00643 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.2 | 1.5.10 | Client Review & Revisions | Use Cases | Client Review & Revisions | Account Manager | Mid | 5 | 171 | 3 | 1.5.10.1 |  |  | 195 | 975
655 | DEL-0009 | TSK-00646 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.3 | 1.5.10 | Final Packaging | Use Cases | Final Packaging | Designer | Mid | 26 | 174 | 0 | 1.5.10.2 |  |  | 195 | 5070
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.11 | 1.5 | Graphic Treatment Direction | Graphic Treatment Direction |  |  |  | 24 | 174 | 0 | 1.5.10 |  |  | 195 | 4680
594 | DEL-0009 | TSK-00585 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.11.1 | 1.5.11 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Creative Director | Lead/Director | 24 | 174 | 0 | 1.5.11 |  |  | 195 | 4680