## Sheet1
Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Deliverable | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1 | 1 | Post-Production | Post-Production |  |  |  |  | 288.3 | 0 | 51 |  |  | Advanced / T1_LargeVolume
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1 | 1.1 | research | Post-Production |  | research |  |  |  |  | 4
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2 | 1.1 | prepro_docs | Post-Production |  | prepro_docs |  |  |  |  | 5
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3 | 1.1 | edit | Post-Production |  | edit |  |  |  |  | 6
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4 | 1.1 | motion | Post-Production |  | motion |  |  |  |  | 9
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5 | 1.1 | color | Post-Production |  | color |  |  |  |  | 3
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6 | 1.1 | retouch | Post-Production |  | retouch |  |  |  |  | 4
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.7 | 1.1 | sound | Post-Production |  | sound |  |  |  |  | 3
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.8 | 1.1 | qa | Post-Production |  | qa |  |  |  |  | 3
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.9 | 1.1 | analytics_tagging | Post-Production |  | analytics_tagging |  |  |  |  | 4
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.10 | 1.1 | internal_review | Post-Production |  | internal_review |  |  |  |  | 2
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.11 | 1.1 | client_review | Post-Production |  | client_review |  |  |  |  | 3
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.12 | 1.1 | library | Post-Production |  | library |  |  |  |  | 3
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.13 | 1.1 | notes_triage | Post-Production |  | notes_triage |  |  |  |  | 2
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.14 | 1.1 | general | Post-Production |  | general |  |  |  |  | 0
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2 | 1 | Development | Development |  |  |  |  | 347.75 | 0 | 28 |  |  | Advanced / T1_LargeVolume
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1 | 1.2 | research | Development |  | research |  |  |  |  | 4
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2 | 1.2 | design_prod | Development |  | design_prod |  |  |  |  | 9
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3 | 1.2 | qa | Development |  | qa |  |  |  |  | 3
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4 | 1.2 | development | Development |  | development |  |  |  |  | 12