## Sheet1
Row_ID | Deliverable_Code | Task_Code | Service_Department | Deliverable | Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes | Rate_USD | Price_USD
[5 empty] | RFP_Brief_ First on SoundCloud 2021 Campaign | 1 |  | RFP_Brief_ First on SoundCloud 2021 Campaign | Project |  |  |  | 0 | 0 |  |  |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1 | 1 | Campaign Strategy |  |  |  |  | 109 | 0 | 15 |  |  | Advanced/T2_MediumVolume | 195 | 21255
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1 | 1.1 | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) |  |  |  | 17 | 0 | 11 | 1.1 |  |  | 195 | 3315
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.1 | 1.1.1 | Channel Roles & Cadence | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Channel Roles & Cadence |  |  | 0 | 0 | 6 | 1.1.1 |  |  | 0 | 0
714 | DEL-0011 | TSK-00705 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.1.1 | 1.1.1.1 | Channel Roles & Cadence | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Channel Roles & Cadence | Creative Director | Lead/Director | 2 |  |  | 1.1.1.1 |  |  | 195 | 390
715 | DEL-0011 | TSK-00706 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.1.2 | 1.1.1.1 | Channel Roles & Cadence | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Channel Roles & Cadence | Designer | Mid | 9 |  |  | 1.1.1.1.1 |  |  | 195 | 1755
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.2 | 1.1.1 | Internal Review & Critique | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.1.1.2 |  |  | 0 | 0
720 | DEL-0011 | TSK-00711 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.2.1 | 1.1.1.2 | Internal Review & Critique | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.1.2 |  |  | 195 | 195
721 | DEL-0011 | TSK-00712 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.2.2 | 1.1.1.2 | Internal Review & Critique | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.1.2.1 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.3 | 1.1.1 | Client Review & Revisions | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.1.2.2 |  |  | 0 | 0
716 | DEL-0011 | TSK-00707 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.3.1 | 1.1.1.3 | Client Review & Revisions | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.1.3 |  |  | 195 | 390
717 | DEL-0011 | TSK-00708 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.3.2 | 1.1.1.3 | Client Review & Revisions | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.1.3.1 |  |  | 195 | 195
718 | DEL-0011 | TSK-00709 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.3.3 | 1.1.1.3 | Client Review & Revisions | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.1.3.2 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2 | 1.1 | 10k Ft View | 10k Ft View |  |  |  | 15 | 6 | 9 | 1.1.1 |  |  | 195 | 2925
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.1 | 1.1.2 | Visual Summary | 10k Ft View | Visual Summary |  |  | 0 | 6 | 4 | 1.1.2 |  |  | 0 | 0
705 | DEL-0011 | TSK-00696 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.1.1 | 1.1.2.1 | Visual Summary | 10k Ft View | Visual Summary | Designer | Mid | 2 |  |  | 1.1.2.1 |  |  | 195 | 390
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.2 | 1.1.2 | Internal Review & Critique | 10k Ft View | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.2.1.1 |  |  | 0 | 0
701 | DEL-0011 | TSK-00692 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.2.1 | 1.1.2.2 | Internal Review & Critique | 10k Ft View | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.2.2 |  |  | 195 | 195
702 | DEL-0011 | TSK-00693 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.2.2 | 1.1.2.2 | Internal Review & Critique | 10k Ft View | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.2.2.1 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.3 | 1.1.2 | Client Review & Revisions | 10k Ft View | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.2.2.2 |  |  | 0 | 0
696 | DEL-0011 | TSK-00687 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.3.1 | 1.1.2.3 | Client Review & Revisions | 10k Ft View | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.2.3 |  |  | 195 | 390
697 | DEL-0011 | TSK-00688 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.3.2 | 1.1.2.3 | Client Review & Revisions | 10k Ft View | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.1.2.3.1 |  |  | 195 | 195
698 | DEL-0011 | TSK-00689 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.3.3 | 1.1.2.3 | Client Review & Revisions | 10k Ft View | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.2.3.2 |  |  | 195 | 195
699 | DEL-0011 | TSK-00690 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.3.4 | 1.1.2.3 | Client Review & Revisions | 10k Ft View | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.2.3.3 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.4 | 1.1.2 | Narrative Overview | 10k Ft View | Narrative Overview |  |  | 0 | 15 | 0 | 1.1.2.3.4 |  |  | 0 | 0
703 | DEL-0011 | TSK-00694 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.4.1 | 1.1.2.4 | Narrative Overview | 10k Ft View | Narrative Overview | Copywriter | Mid | 2 |  |  | 1.1.2.4 |  |  | 195 | 390
704 | DEL-0011 | TSK-00695 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.4.2 | 1.1.2.4 | Narrative Overview | 10k Ft View | Narrative Overview | Creative Director | Lead/Director | 2 |  |  | 1.1.2.4.1 |  |  | 195 | 390
700 | DEL-0011 | TSK-00691 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.4.3 | 1.1.2.4 | Narrative Overview | 10k Ft View | Narrative Overview | Designer | Mid | 2 |  |  | 1.1.2.4.2 |  |  | 195 | 390
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3 | 1.1 | Image Usage Guidelines | Image Usage Guidelines |  |  |  | 27 | 10 | 5 | 1.1.2 |  |  | 195 | 5265
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.1 | 1.1.3 | Internal Review & Critique | Image Usage Guidelines | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.3 |  |  | 0 | 0
712 | DEL-0011 | TSK-00703 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.1.1 | 1.1.3.1 | Internal Review & Critique | Image Usage Guidelines | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.3.1 |  |  | 195 | 195
713 | DEL-0011 | TSK-00704 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.1.2 | 1.1.3.1 | Internal Review & Critique | Image Usage Guidelines | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.3.1.1 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.2 | 1.1.3 | Client Review & Revisions | Image Usage Guidelines | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.3.1.2 |  |  | 0 | 0
706 | DEL-0011 | TSK-00697 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.2.1 | 1.1.3.2 | Client Review & Revisions | Image Usage Guidelines | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.3.2 |  |  | 195 | 390
707 | DEL-0011 | TSK-00698 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.2.2 | 1.1.3.2 | Client Review & Revisions | Image Usage Guidelines | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.3.2.1 |  |  | 195 | 195
708 | DEL-0011 | TSK-00699 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.2.3 | 1.1.3.2 | Client Review & Revisions | Image Usage Guidelines | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.3.2.2 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.3 | 1.1.3 | Examples | Image Usage Guidelines | Examples |  |  | 0 | 15 | 0 | 1.1.3.2.3 |  |  | 0 | 0
711 | DEL-0011 | TSK-00702 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.3.1 | 1.1.3.3 | Examples | Image Usage Guidelines | Examples | Art Director | Lead/Director | 1 |  |  | 1.1.3.3 |  |  | 195 | 195
709 | DEL-0011 | TSK-00700 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.3.2 | 1.1.3.3 | Examples | Image Usage Guidelines | Examples | Designer | Mid | 20 |  |  | 1.1.3.3.1 |  |  | 195 | 3900
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4 | 1.1 | Media Assets | Media Assets |  |  |  | 12 | 10 | 5 | 1.1.3 |  |  | 195 | 2340
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.1 | 1.1.4 | Internal Review & Critique | Media Assets | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.4 |  |  | 0 | 0
729 | DEL-0011 | TSK-00720 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.1.1 | 1.1.4.1 | Internal Review & Critique | Media Assets | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.4.1 |  |  | 195 | 195
730 | DEL-0011 | TSK-00721 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.1.2 | 1.1.4.1 | Internal Review & Critique | Media Assets | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.4.1.1 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.2 | 1.1.4 | Client Review & Revisions | Media Assets | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.4.1.2 |  |  | 0 | 0
725 | DEL-0011 | TSK-00716 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.2.1 | 1.1.4.2 | Client Review & Revisions | Media Assets | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.4.2 |  |  | 195 | 390
726 | DEL-0011 | TSK-00717 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.2.2 | 1.1.4.2 | Client Review & Revisions | Media Assets | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.4.2.1 |  |  | 195 | 195
727 | DEL-0011 | TSK-00718 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.2.3 | 1.1.4.2 | Client Review & Revisions | Media Assets | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.4.2.2 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.3 | 1.1.4 | Asset Matrix | Media Assets | Asset Matrix |  |  | 0 | 15 | 0 | 1.1.4.2.3 |  |  | 0 | 0
723 | DEL-0011 | TSK-00714 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.3.1 | 1.1.4.3 | Asset Matrix | Media Assets | Asset Matrix | Designer | Mid | 5 |  |  | 1.1.4.3 |  |  | 195 | 975
724 | DEL-0011 | TSK-00715 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.3.2 | 1.1.4.3 | Asset Matrix | Media Assets | Asset Matrix | Project Manager | Mid | 1 |  |  | 1.1.4.3.1 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5 | 1.1 | Photo / Video Direction | Photo / Video Direction |  |  |  | 14 | 10 | 5 | 1.1.4 |  |  | 195 | 2730
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.1 | 1.1.5 | Internal Review & Critique | Photo / Video Direction | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.5 |  |  | 0 | 0
737 | DEL-0011 | TSK-00728 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.1.1 | 1.1.5.1 | Internal Review & Critique | Photo / Video Direction | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.5.1 |  |  | 195 | 195
738 | DEL-0011 | TSK-00729 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.1.2 | 1.1.5.1 | Internal Review & Critique | Photo / Video Direction | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.5.1.1 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.2 | 1.1.5 | Client Review & Revisions | Photo / Video Direction | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.5.1.2 |  |  | 0 | 0
731 | DEL-0011 | TSK-00722 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.2.1 | 1.1.5.2 | Client Review & Revisions | Photo / Video Direction | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.5.2 |  |  | 195 | 390
732 | DEL-0011 | TSK-00723 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.2.2 | 1.1.5.2 | Client Review & Revisions | Photo / Video Direction | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.5.2.1 |  |  | 195 | 195
733 | DEL-0011 | TSK-00724 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.2.3 | 1.1.5.2 | Client Review & Revisions | Photo / Video Direction | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.5.2.2 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.3 | 1.1.5 | Direction Notes | Photo / Video Direction | Direction Notes |  |  | 0 | 15 | 0 | 1.1.5.2.3 |  |  | 0 | 0
734 | DEL-0011 | TSK-00725 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.3.1 | 1.1.5.3 | Direction Notes | Photo / Video Direction | Direction Notes | Art Director | Lead/Director | 1 |  |  | 1.1.5.3 |  |  | 195 | 195
735 | DEL-0011 | TSK-00726 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.3.2 | 1.1.5.3 | Direction Notes | Photo / Video Direction | Direction Notes | Creative Director | Lead/Director | 2 |  |  | 1.1.5.3.1 |  |  | 195 | 390
736 | DEL-0011 | TSK-00727 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.3.3 | 1.1.5.3 | Direction Notes | Photo / Video Direction | Direction Notes | Designer | Mid | 5 |  |  | 1.1.5.3.2 |  |  | 195 | 975
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6 | 1.1 | Rollout | Rollout |  |  |  | 14 | 10 | 5 | 1.1.5 |  |  | 195 | 2730
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.1 | 1.1.6 | Internal Review & Critique | Rollout | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.6 |  |  | 0 | 0
744 | DEL-0011 | TSK-00735 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.1.1 | 1.1.6.1 | Internal Review & Critique | Rollout | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.6.1 |  |  | 195 | 195
745 | DEL-0011 | TSK-00736 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.1.2 | 1.1.6.1 | Internal Review & Critique | Rollout | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.6.1.1 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.2 | 1.1.6 | Client Review & Revisions | Rollout | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.6.1.2 |  |  | 0 | 0
740 | DEL-0011 | TSK-00731 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.2.1 | 1.1.6.2 | Client Review & Revisions | Rollout | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.6.2 |  |  | 195 | 390
741 | DEL-0011 | TSK-00732 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.2.2 | 1.1.6.2 | Client Review & Revisions | Rollout | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.6.2.1 |  |  | 195 | 195
742 | DEL-0011 | TSK-00733 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.2.3 | 1.1.6.2 | Client Review & Revisions | Rollout | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.6.2.2 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.3 | 1.1.6 | Phasing & Milestones | Rollout | Phasing & Milestones |  |  | 0 | 15 | 0 | 1.1.6.2.3 |  |  | 0 | 0
746 | DEL-0011 | TSK-00737 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.3.1 | 1.1.6.3 | Phasing & Milestones | Rollout | Phasing & Milestones | Creative Director | Lead/Director | 2 |  |  | 1.1.6.3 |  |  | 195 | 390
743 | DEL-0011 | TSK-00734 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.3.2 | 1.1.6.3 | Phasing & Milestones | Rollout | Phasing & Milestones | Designer | Mid | 5 |  |  | 1.1.6.3.1 |  |  | 195 | 975
747 | DEL-0011 | TSK-00738 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.3.3 | 1.1.6.3 | Phasing & Milestones | Rollout | Phasing & Milestones | Project Manager | Mid | 1 |  |  | 1.1.6.3.2 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.7 | 1.1 | Use Cases | Use Cases |  |  |  | 10 | 10 | 5 | 1.1.6 |  |  | 195 | 1950
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.7.1 | 1.1.7 | Internal Review & Critique | Use Cases | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.7 |  |  | 0 | 0
753 | DEL-0011 | TSK-00744 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.7.1.1 | 1.1.7.1 | Internal Review & Critique | Use Cases | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.7.1 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.7.2 | 1.1.7 | Client Review & Revisions | Use Cases | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.7.1.1 |  |  | 0 | 0
749 | DEL-0011 | TSK-00740 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.7.2.1 | 1.1.7.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.7.2 |  |  | 195 | 390
750 | DEL-0011 | TSK-00741 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.7.2.2 | 1.1.7.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.7.2.1 |  |  | 195 | 195
751 | DEL-0011 | TSK-00742 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.7.2.3 | 1.1.7.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.7.2.2 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.7.3 | 1.1.7 | Final Packaging | Use Cases | Final Packaging |  |  | 0 | 15 | 0 | 1.1.7.2.3 |  |  | 0 | 0
752 | DEL-0011 | TSK-00743 | Creative | Campaign Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.7.3.1 | 1.1.7.3 | Final Packaging | Use Cases | Final Packaging | Designer | Mid | 5 |  |  | 1.1.7.3 |  |  | 195 | 975
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2 | 1 | Paid Media Planning |  |  |  |  | 82 | 15 | 33 | 1.1 |  | Advanced/T2_MediumVolume | 195 | 15990
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1 | 1.2 | Media Planning Deck | Media Planning Deck |  |  |  | 19 | 15 | 16 | 1.2 |  |  | 195 | 3705
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.1 | 1.2.1 | Deck Narrative | Media Planning Deck | Deck Narrative |  |  | 0 | 15 | 6 | 1.2.1 |  |  | 0 | 0
1241 | DEL-0029 | TSK-01232 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.1.1 | 1.2.1.1 | Deck Narrative | Media Planning Deck | Deck Narrative | Designer | Mid | 8 |  |  | 1.2.1.1 |  |  | 195 | 1560
1240 | DEL-0029 | TSK-01231 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.1.2 | 1.2.1.1 | Deck Narrative | Media Planning Deck | Deck Narrative | Media Strategist | Mid | 4 |  |  | 1.2.1.1.1 |  |  | 195 | 780
1244 | DEL-0029 | TSK-01235 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.1.3 | 1.2.1.1 | Deck Narrative | Media Planning Deck | Deck Narrative | Project Manager | Mid | 2 |  |  | 1.2.1.1.2 |  |  | 195 | 390
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.2 | 1.2.1 | Deck Build | Media Planning Deck | Deck Build |  |  | 0 | 27 | 5 | 1.2.1.1.3 |  |  | 0 | 0
1239 | DEL-0029 | TSK-01230 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.2.1 | 1.2.1.2 | Deck Build | Media Planning Deck | Deck Build | Designer | Mid | 2 |  |  | 1.2.1.2 |  |  | 195 | 390
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.3 | 1.2.1 | Internal Review & Critique | Media Planning Deck | Internal Review & Critique |  |  | 0 | 43 | 2 | 1.2.1.2.1 |  |  | 0 | 0
1242 | DEL-0029 | TSK-01233 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.3.1 | 1.2.1.3 | Internal Review & Critique | Media Planning Deck | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.1.3 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.4 | 1.2.1 | Client Review & Revisions | Media Planning Deck | Client Review & Revisions |  |  | 0 | 45 | 3 | 1.2.1.3.1 |  |  | 0 | 0
1237 | DEL-0029 | TSK-01228 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.4.1 | 1.2.1.4 | Client Review & Revisions | Media Planning Deck | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.1.4 |  |  | 195 | 195
1238 | DEL-0029 | TSK-01229 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.4.2 | 1.2.1.4 | Client Review & Revisions | Media Planning Deck | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.2.1.4.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2 | 1.2 | Paid Media Plan | Paid Media Plan |  |  |  | 29 | 21 | 11 | 1.2.1 |  |  | 195 | 5655
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.1 | 1.2.2 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes |  |  | 0 | 21 | 6 | 1.2.2 |  |  | 0 | 0
1248 | DEL-0029 | TSK-01239 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.1.1 | 1.2.2.1 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes | Designer | Mid | 3 |  |  | 1.2.2.1 |  |  | 195 | 585
1252 | DEL-0029 | TSK-01243 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.1.2 | 1.2.2.1 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes | Media Planner | Mid | 10 |  |  | 1.2.2.1.1 |  |  | 195 | 1950
1245 | DEL-0029 | TSK-01236 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.1.3 | 1.2.2.1 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes | Media Strategist | Mid | 10 |  |  | 1.2.2.1.2 |  |  | 195 | 1950
1251 | DEL-0029 | TSK-01242 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.1.4 | 1.2.2.1 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes | Project Manager | Mid | 2 |  |  | 1.2.2.1.3 |  |  | 195 | 390
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.2 | 1.2.2 | Internal Review & Critique | Paid Media Plan | Internal Review & Critique |  |  | 0 | 43 | 2 | 1.2.2.1.4 |  |  | 0 | 0
1249 | DEL-0029 | TSK-01240 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.2.1 | 1.2.2.2 | Internal Review & Critique | Paid Media Plan | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.2.2 |  |  | 195 | 195
1250 | DEL-0029 | TSK-01241 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.2.2 | 1.2.2.2 | Internal Review & Critique | Paid Media Plan | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.2.2.2.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.3 | 1.2.2 | Client Review & Revisions | Paid Media Plan | Client Review & Revisions |  |  | 0 | 45 | 3 | 1.2.2.2.2 |  |  | 0 | 0
1246 | DEL-0029 | TSK-01237 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.3.1 | 1.2.2.3 | Client Review & Revisions | Paid Media Plan | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.2.3 |  |  | 195 | 195
1247 | DEL-0029 | TSK-01238 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.3.2 | 1.2.2.3 | Client Review & Revisions | Paid Media Plan | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.2.2.3.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3 | 1.2 | Ad Unit & Format POV | Ad Unit & Format POV |  |  |  | 16 | 32 | 16 | 1.2.2 |  |  | 195 | 3120
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.1 | 1.2.3 | Spec Page Build | Ad Unit & Format POV | Spec Page Build |  |  | 0 | 32 | 11 | 1.2.3 |  |  | 0 | 0
1227 | DEL-0029 | TSK-01218 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.1.1 | 1.2.3.1 | Spec Page Build | Ad Unit & Format POV | Spec Page Build | Designer | Mid | 3 |  |  | 1.2.3.1 |  |  | 195 | 585
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.2 | 1.2.3 | Internal Review & Critique | Ad Unit & Format POV | Internal Review & Critique |  |  | 0 | 43 | 2 | 1.2.3.1.1 |  |  | 0 | 0
1223 | DEL-0029 | TSK-01214 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.2.1 | 1.2.3.2 | Internal Review & Critique | Ad Unit & Format POV | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.3.2 |  |  | 195 | 195
1224 | DEL-0029 | TSK-01215 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.2.2 | 1.2.3.2 | Internal Review & Critique | Ad Unit & Format POV | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.2.3.2.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.3 | 1.2.3 | Client Review & Revisions | Ad Unit & Format POV | Client Review & Revisions |  |  | 0 | 45 | 3 | 1.2.3.2.2 |  |  | 0 | 0
1220 | DEL-0029 | TSK-01211 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.3.1 | 1.2.3.3 | Client Review & Revisions | Ad Unit & Format POV | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.3.3 |  |  | 195 | 195
1221 | DEL-0029 | TSK-01212 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.3.2 | 1.2.3.3 | Client Review & Revisions | Ad Unit & Format POV | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.2.3.3.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.4 | 1.2.3 | Spec Matrix & POV | Ad Unit & Format POV | Spec Matrix & POV |  |  | 0 | 48 | 0 | 1.2.3.3.2 |  |  | 0 | 0
1222 | DEL-0029 | TSK-01213 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.4.1 | 1.2.3.4 | Spec Matrix & POV | Ad Unit & Format POV | Spec Matrix & POV | Designer | Mid | 3 |  |  | 1.2.3.4 |  |  | 195 | 585
1225 | DEL-0029 | TSK-01216 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.4.2 | 1.2.3.4 | Spec Matrix & POV | Ad Unit & Format POV | Spec Matrix & POV | Media Planner | Mid | 3 |  |  | 1.2.3.4.1 |  |  | 195 | 585
1226 | DEL-0029 | TSK-01217 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.4.3 | 1.2.3.4 | Spec Matrix & POV | Ad Unit & Format POV | Spec Matrix & POV | Media Strategist | Mid | 3 |  |  | 1.2.3.4.2 |  |  | 195 | 585
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4 | 1.2 | Channel & Vendor Evaluation | Channel & Vendor Evaluation |  |  |  | 18 | 43 | 5 | 1.2.3 |  |  | 195 | 3510
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.1 | 1.2.4 | Internal Review & Critique | Channel & Vendor Evaluation | Internal Review & Critique |  |  | 0 | 43 | 2 | 1.2.4 |  |  | 0 | 0
1231 | DEL-0029 | TSK-01222 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.1.1 | 1.2.4.1 | Internal Review & Critique | Channel & Vendor Evaluation | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.4.1 |  |  | 195 | 195
1232 | DEL-0029 | TSK-01223 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.1.2 | 1.2.4.1 | Internal Review & Critique | Channel & Vendor Evaluation | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.2.4.1.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.2 | 1.2.4 | Client Review & Revisions | Channel & Vendor Evaluation | Client Review & Revisions |  |  | 0 | 45 | 3 | 1.2.4.1.2 |  |  | 0 | 0
1228 | DEL-0029 | TSK-01219 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.2.1 | 1.2.4.2 | Client Review & Revisions | Channel & Vendor Evaluation | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.4.2 |  |  | 195 | 195
1229 | DEL-0029 | TSK-01220 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.2.2 | 1.2.4.2 | Client Review & Revisions | Channel & Vendor Evaluation | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.2.4.2.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.3 | 1.2.4 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review |  |  | 0 | 48 | 0 | 1.2.4.2.2 |  |  | 0 | 0
1236 | DEL-0029 | TSK-01227 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.3.1 | 1.2.4.3 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review | Account Manager | Mid | 2 |  |  | 1.2.4.3 |  |  | 195 | 390
1230 | DEL-0029 | TSK-01221 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.3.2 | 1.2.4.3 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review | Designer | Mid | 2 |  |  | 1.2.4.3.1 |  |  | 195 | 390
1233 | DEL-0029 | TSK-01224 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.3.3 | 1.2.4.3 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review | Media Planner | Mid | 7 |  |  | 1.2.4.3.2 |  |  | 195 | 1365
1234 | DEL-0029 | TSK-01225 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.3.4 | 1.2.4.3 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review | Media Strategist | Mid | 3 |  |  | 1.2.4.3.3 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3 | 1 | Reporting |  |  |  |  | 128 | 48 | 7 | 1.2 |  | Advanced/T2_MediumVolume | 195 | 24960
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.1 | 1.3 | Dashboards | Dashboards |  |  |  | 9 | 48 | 7 | 1.3 |  |  | 195 | 1755
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.1.1 | 1.3.1 | QA | Dashboards | QA |  |  | 0 | 48 | 3 | 1.3.1 |  |  | 0 | 0
1116 | DEL-0024 | TSK-01107 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.1.1.1 | 1.3.1.1 | QA | Dashboards | QA | QA Specialist | Mid | 3 |  |  | 1.3.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.1.2 | 1.3.1 | Dashboard Build/Refresh | Dashboards | Dashboard Build/Refresh |  |  | 0 | 51 | 4 | 1.3.1.1.1 |  |  | 0 | 0
1115 | DEL-0024 | TSK-01106 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.1.2.1 | 1.3.1.2 | Dashboard Build/Refresh | Dashboards | Dashboard Build/Refresh | Analyst | Mid | 6 |  |  | 1.3.1.2 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.2 | 1.3 | Engagement Rate | Engagement Rate |  |  |  | 6 | 48 | 3 | 1.3.1 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.2.1 | 1.3.2 | Data Refresh & Calc Check | Engagement Rate | Data Refresh & Calc Check |  |  | 0 | 48 | 3 | 1.3.2 |  |  | 0 | 0
1119 | DEL-0024 | TSK-01110 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.2.1.1 | 1.3.2.1 | Data Refresh & Calc Check | Engagement Rate | Data Refresh & Calc Check | Analyst | Mid | 3 |  |  | 1.3.2.1 |  |  | 195 | 585
1120 | DEL-0024 | TSK-01111 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.2.1.2 | 1.3.2.1 | Data Refresh & Calc Check | Engagement Rate | Data Refresh & Calc Check | QA Specialist | Mid | 3 |  |  | 1.3.2.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.3 | 1.3 | Emplifi Reports | Emplifi Reports |  |  |  | 7 | 51 | 4 | 1.3.2 |  |  | 195 | 1365
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.3.1 | 1.3.3 | Emplifi Extract & Summary | Emplifi Reports | Emplifi Extract & Summary |  |  | 0 | 51 | 4 | 1.3.3 |  |  | 0 | 0
1117 | DEL-0024 | TSK-01108 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.3.1.1 | 1.3.3.1 | Emplifi Extract & Summary | Emplifi Reports | Emplifi Extract & Summary | Account Manager | Mid | 1 |  |  | 1.3.3.1 |  |  | 195 | 195
1118 | DEL-0024 | TSK-01109 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.3.1.2 | 1.3.3.1 | Emplifi Extract & Summary | Emplifi Reports | Emplifi Extract & Summary | Analyst | Mid | 6 |  |  | 1.3.3.1.1 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.4 | 1.3 | Monthly Comprehensive Report | Monthly Comprehensive Report |  |  |  | 11 | 51 | 4 | 1.3.3 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.4.1 | 1.3.4 | Monthly Report | Monthly Comprehensive Report | Monthly Report |  |  | 0 | 51 | 4 | 1.3.4 |  |  | 0 | 0
1127 | DEL-0024 | TSK-01118 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.4.1.1 | 1.3.4.1 | Monthly Report | Monthly Comprehensive Report | Monthly Report | Analyst | Mid | 6 |  |  | 1.3.4.1 |  |  | 195 | 1170
1128 | DEL-0024 | TSK-01119 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.4.1.2 | 1.3.4.1 | Monthly Report | Monthly Comprehensive Report | Monthly Report | Designer | Mid | 2 |  |  | 1.3.4.1.1 |  |  | 195 | 390
1129 | DEL-0024 | TSK-01120 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.4.1.3 | 1.3.4.1 | Monthly Report | Monthly Comprehensive Report | Monthly Report | Social Strategist | Mid | 3 |  |  | 1.3.4.1.2 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.5 | 1.3 | Monthly Organic Social Report | Monthly Organic Social Report |  |  |  | 11 | 51 | 4 | 1.3.4 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.5.1 | 1.3.5 | Monthly Organic Report | Monthly Organic Social Report | Monthly Organic Report |  |  | 0 | 51 | 4 | 1.3.5 |  |  | 0 | 0
1130 | DEL-0024 | TSK-01121 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.5.1.1 | 1.3.5.1 | Monthly Organic Report | Monthly Organic Social Report | Monthly Organic Report | Analyst | Mid | 6 |  |  | 1.3.5.1 |  |  | 195 | 1170
1131 | DEL-0024 | TSK-01122 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.5.1.2 | 1.3.5.1 | Monthly Organic Report | Monthly Organic Social Report | Monthly Organic Report | Designer | Mid | 2 |  |  | 1.3.5.1.1 |  |  | 195 | 390
1132 | DEL-0024 | TSK-01123 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.5.1.3 | 1.3.5.1 | Monthly Organic Report | Monthly Organic Social Report | Monthly Organic Report | Social Strategist | Mid | 3 |  |  | 1.3.5.1.2 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.6 | 1.3 | Optimization Recommendations Report | Optimization Recommendations Report |  |  |  | 10 | 51 | 4 | 1.3.5 |  |  | 195 | 1950
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.6.1 | 1.3.6 | Recs & Next Steps | Optimization Recommendations Report | Recs & Next Steps |  |  | 0 | 51 | 4 | 1.3.6 |  |  | 0 | 0
1133 | DEL-0024 | TSK-01124 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.6.1.1 | 1.3.6.1 | Recs & Next Steps | Optimization Recommendations Report | Recs & Next Steps | Account Manager | Mid | 1 |  |  | 1.3.6.1 |  |  | 195 | 195
1134 | DEL-0024 | TSK-01125 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.6.1.2 | 1.3.6.1 | Recs & Next Steps | Optimization Recommendations Report | Recs & Next Steps | Analyst | Mid | 6 |  |  | 1.3.6.1.1 |  |  | 195 | 1170
1135 | DEL-0024 | TSK-01126 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.6.1.3 | 1.3.6.1 | Recs & Next Steps | Optimization Recommendations Report | Recs & Next Steps | Social Strategist | Mid | 3 |  |  | 1.3.6.1.2 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.7 | 1.3 | Quarterly Ad-Hoc Report | Quarterly Ad-Hoc Report |  |  |  | 9 | 51 | 4 | 1.3.6 |  |  | 195 | 1755
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.7.1 | 1.3.7 | Quarterly Ad-hoc Deep Dive | Quarterly Ad-Hoc Report | Quarterly Ad-hoc Deep Dive |  |  | 0 | 51 | 4 | 1.3.7 |  |  | 0 | 0
1138 | DEL-0024 | TSK-01129 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.7.1.1 | 1.3.7.1 | Quarterly Ad-hoc Deep Dive | Quarterly Ad-Hoc Report | Quarterly Ad-hoc Deep Dive | Analyst | Mid | 6 |  |  | 1.3.7.1 |  |  | 195 | 1170
1139 | DEL-0024 | TSK-01130 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.7.1.2 | 1.3.7.1 | Quarterly Ad-hoc Deep Dive | Quarterly Ad-Hoc Report | Quarterly Ad-hoc Deep Dive | QA Specialist | Mid | 3 |  |  | 1.3.7.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.8 | 1.3 | Quarterly Key Learnings & Insights Report | Quarterly Key Learnings & Insights Report |  |  |  | 11 | 51 | 4 | 1.3.7 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.8.1 | 1.3.8 | Quarterly Learnings & Insights | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights |  |  | 0 | 51 | 4 | 1.3.8 |  |  | 0 | 0
1140 | DEL-0024 | TSK-01131 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.8.1.1 | 1.3.8.1 | Quarterly Learnings & Insights | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights | Analyst | Mid | 6 |  |  | 1.3.8.1 |  |  | 195 | 1170
1141 | DEL-0024 | TSK-01132 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.8.1.2 | 1.3.8.1 | Quarterly Learnings & Insights | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights | Designer | Mid | 2 |  |  | 1.3.8.1.1 |  |  | 195 | 390
1142 | DEL-0024 | TSK-01133 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.8.1.3 | 1.3.8.1 | Quarterly Learnings & Insights | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights | Social Strategist | Mid | 3 |  |  | 1.3.8.1.2 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.9 | 1.3 | Quarterly Report | Quarterly Report |  |  |  | 11 | 51 | 4 | 1.3.8 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.9.1 | 1.3.9 | Quarterly Report | Quarterly Report | Quarterly Report |  |  | 0 | 51 | 4 | 1.3.9 |  |  | 0 | 0
1143 | DEL-0024 | TSK-01134 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.9.1.1 | 1.3.9.1 | Quarterly Report | Quarterly Report | Quarterly Report | Analyst | Mid | 6 |  |  | 1.3.9.1 |  |  | 195 | 1170
1144 | DEL-0024 | TSK-01135 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.9.1.2 | 1.3.9.1 | Quarterly Report | Quarterly Report | Quarterly Report | Designer | Mid | 2 |  |  | 1.3.9.1.1 |  |  | 195 | 390
1145 | DEL-0024 | TSK-01136 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.9.1.3 | 1.3.9.1 | Quarterly Report | Quarterly Report | Quarterly Report | Social Strategist | Mid | 3 |  |  | 1.3.9.1.2 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.10 | 1.3 | Summary overview | Summary overview |  |  |  | 4 | 51 | 4 | 1.3.9 |  |  | 195 | 780
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.10.1 | 1.3.10 | Summary Narrative | Summary overview | Summary Narrative |  |  | 0 | 51 | 4 | 1.3.10 |  |  | 0 | 0
1150 | DEL-0024 | TSK-01141 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.10.1.1 | 1.3.10.1 | Summary Narrative | Summary overview | Summary Narrative | Account Manager | Mid | 1 |  |  | 1.3.10.1 |  |  | 195 | 195
1151 | DEL-0024 | TSK-01142 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.10.1.2 | 1.3.10.1 | Summary Narrative | Summary overview | Summary Narrative | Social Strategist | Mid | 3 |  |  | 1.3.10.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.11 | 1.3 | Weekly Activity Report | Weekly Activity Report |  |  |  | 7 | 51 | 4 | 1.3.10 |  |  | 195 | 1365
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.11.1 | 1.3.11 | Weekly Activity Summary | Weekly Activity Report | Weekly Activity Summary |  |  | 0 | 51 | 4 | 1.3.11 |  |  | 0 | 0
1153 | DEL-0024 | TSK-01144 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.11.1.1 | 1.3.11.1 | Weekly Activity Summary | Weekly Activity Report | Weekly Activity Summary | Account Manager | Mid | 1 |  |  | 1.3.11.1 |  |  | 195 | 195
1154 | DEL-0024 | TSK-01145 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.11.1.2 | 1.3.11.1 | Weekly Activity Summary | Weekly Activity Report | Weekly Activity Summary | Analyst | Mid | 6 |  |  | 1.3.11.1.1 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.12 | 1.3 | Follower Growth | Follower Growth |  |  |  | 6 | 55 | 0 | 1.3.11 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.12.1 | 1.3.12 | Metric Pull & Notes | Follower Growth | Metric Pull & Notes |  |  | 0 | 55 | 0 | 1.3.12 |  |  | 0 | 0
1121 | DEL-0024 | TSK-01112 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.12.1.1 | 1.3.12.1 | Metric Pull & Notes | Follower Growth | Metric Pull & Notes | Analyst | Mid | 3 |  |  | 1.3.12.1 |  |  | 195 | 585
1122 | DEL-0024 | TSK-01113 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.12.1.2 | 1.3.12.1 | Metric Pull & Notes | Follower Growth | Metric Pull & Notes | QA Specialist | Mid | 3 |  |  | 1.3.12.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.13 | 1.3 | Impressions | Impressions |  |  |  | 6 | 55 | 0 | 1.3.12 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.13.1 | 1.3.13 | Metric Pull & Notes | Impressions | Metric Pull & Notes |  |  | 0 | 55 | 0 | 1.3.13 |  |  | 0 | 0
1123 | DEL-0024 | TSK-01114 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.13.1.1 | 1.3.13.1 | Metric Pull & Notes | Impressions | Metric Pull & Notes | Analyst | Mid | 3 |  |  | 1.3.13.1 |  |  | 195 | 585
1124 | DEL-0024 | TSK-01115 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.13.1.2 | 1.3.13.1 | Metric Pull & Notes | Impressions | Metric Pull & Notes | QA Specialist | Mid | 3 |  |  | 1.3.13.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.14 | 1.3 | Interactions | Interactions |  |  |  | 5 | 55 | 0 | 1.3.13 |  |  | 195 | 975
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.14.1 | 1.3.14 | Metric Pull & Notes | Interactions | Metric Pull & Notes |  |  | 0 | 55 | 0 | 1.3.14 |  |  | 0 | 0
1125 | DEL-0024 | TSK-01116 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.14.1.1 | 1.3.14.1 | Metric Pull & Notes | Interactions | Metric Pull & Notes | Analyst | Mid | 2 |  |  | 1.3.14.1 |  |  | 195 | 390
1126 | DEL-0024 | TSK-01117 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.14.1.2 | 1.3.14.1 | Metric Pull & Notes | Interactions | Metric Pull & Notes | QA Specialist | Mid | 3 |  |  | 1.3.14.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.15 | 1.3 | Profile Reach | Profile Reach |  |  |  | 5 | 55 | 0 | 1.3.14 |  |  | 195 | 975
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.15.1 | 1.3.15 | Metric Pull & Notes | Profile Reach | Metric Pull & Notes |  |  | 0 | 55 | 0 | 1.3.15 |  |  | 0 | 0
1136 | DEL-0024 | TSK-01127 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.15.1.1 | 1.3.15.1 | Metric Pull & Notes | Profile Reach | Metric Pull & Notes | Analyst | Mid | 2 |  |  | 1.3.15.1 |  |  | 195 | 390
1137 | DEL-0024 | TSK-01128 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.15.1.2 | 1.3.15.1 | Metric Pull & Notes | Profile Reach | Metric Pull & Notes | QA Specialist | Mid | 3 |  |  | 1.3.15.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.16 | 1.3 | Recap Reports | Recap Reports |  |  |  | 4 | 55 | 0 | 1.3.15 |  |  | 195 | 780
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.16.1 | 1.3.16 | Campaign/Period Recaps | Recap Reports | Campaign/Period Recaps |  |  | 0 | 55 | 0 | 1.3.16 |  |  | 0 | 0
1146 | DEL-0024 | TSK-01137 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.16.1.1 | 1.3.16.1 | Campaign/Period Recaps | Recap Reports | Campaign/Period Recaps | Account Manager | Mid | 2 |  |  | 1.3.16.1 |  |  | 195 | 390
1147 | DEL-0024 | TSK-01138 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.16.1.2 | 1.3.16.1 | Campaign/Period Recaps | Recap Reports | Campaign/Period Recaps | Analyst | Mid | 2 |  |  | 1.3.16.1.1 |  |  | 195 | 390
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.17 | 1.3 | Social Reporting | Social Reporting |  |  |  | 4 | 55 | 0 | 1.3.16 |  |  | 195 | 780
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.17.1 | 1.3.17 | Ongoing Social Reporting | Social Reporting | Ongoing Social Reporting |  |  | 0 | 55 | 0 | 1.3.17 |  |  | 0 | 0
1148 | DEL-0024 | TSK-01139 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.17.1.1 | 1.3.17.1 | Ongoing Social Reporting | Social Reporting | Ongoing Social Reporting | Account Manager | Mid | 2 |  |  | 1.3.17.1 |  |  | 195 | 390
1149 | DEL-0024 | TSK-01140 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.17.1.2 | 1.3.17.1 | Ongoing Social Reporting | Social Reporting | Ongoing Social Reporting | Analyst | Mid | 2 |  |  | 1.3.17.1.1 |  |  | 195 | 390
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.18 | 1.3 | Update/maintain Z/Russia tracker | Update/maintain Z/Russia tracker |  |  |  | 2 | 55 | 0 | 1.3.17 |  |  | 195 | 390
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.18.1 | 1.3.18 | Tracker Update | Update/maintain Z/Russia tracker | Tracker Update |  |  | 0 | 55 | 0 | 1.3.18 |  |  | 0 | 0
1152 | DEL-0024 | TSK-01143 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.18.1.1 | 1.3.18.1 | Tracker Update | Update/maintain Z/Russia tracker | Tracker Update | Analyst | Mid | 2 |  |  | 1.3.18.1 |  |  | 195 | 390