## Sheet1
Row_ID | Deliverable_Code | Task_Code | Service_Department | Deliverable | Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes | Rate_USD | Price_USD
[5 empty] | Casa-Dragones-Digital-MKT-RFP | 1 |  | Casa-Dragones-Digital-MKT-RFP | Project |  |  |  | 0 | 0 |  |  |  |  | 0 | 0
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1 | 1 | Campaign Strategy |  |  |  |  | 109 | 0 | 15 |  |  | Advanced/T2_MediumVolume | 195 | 21255
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1 | 1.1 | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) |  |  |  | 17 | 0 | 11 | 1.1 |  |  | 195 | 3315
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1 | 1.1.1 | Channel Roles & Cadence | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Channel Roles & Cadence |  |  | 0 | 0 | 6 | 1.1.1 |  |  | 0 | 0
714 | DEL-0011 | TSK-00705 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.1 | 1.1.1.1 | Channel Roles & Cadence | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Channel Roles & Cadence | Creative Director | Lead/Director | 2 |  |  | 1.1.1.1 |  |  | 195 | 390
715 | DEL-0011 | TSK-00706 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.2 | 1.1.1.1 | Channel Roles & Cadence | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Channel Roles & Cadence | Designer | Mid | 9 |  |  | 1.1.1.1.1 |  |  | 195 | 1755
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2 | 1.1.1 | Internal Review & Critique | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.1.1.2 |  |  | 0 | 0
720 | DEL-0011 | TSK-00711 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.1 | 1.1.1.2 | Internal Review & Critique | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.1.2 |  |  | 195 | 195
721 | DEL-0011 | TSK-00712 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.2 | 1.1.1.2 | Internal Review & Critique | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.1.2.1 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3 | 1.1.1 | Client Review & Revisions | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.1.2.2 |  |  | 0 | 0
716 | DEL-0011 | TSK-00707 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.1 | 1.1.1.3 | Client Review & Revisions | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.1.3 |  |  | 195 | 390
717 | DEL-0011 | TSK-00708 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.2 | 1.1.1.3 | Client Review & Revisions | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.1.3.1 |  |  | 195 | 195
718 | DEL-0011 | TSK-00709 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.3 | 1.1.1.3 | Client Review & Revisions | Marketing Tactics (Platforms, Formats, Cadence, Organic, Paid) | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.1.3.2 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2 | 1.1 | 10k Ft View | 10k Ft View |  |  |  | 15 | 6 | 9 | 1.1.1 |  |  | 195 | 2925
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.1 | 1.1.2 | Visual Summary | 10k Ft View | Visual Summary |  |  | 0 | 6 | 4 | 1.1.2 |  |  | 0 | 0
705 | DEL-0011 | TSK-00696 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.1.1 | 1.1.2.1 | Visual Summary | 10k Ft View | Visual Summary | Designer | Mid | 2 |  |  | 1.1.2.1 |  |  | 195 | 390
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.2 | 1.1.2 | Internal Review & Critique | 10k Ft View | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.2.1.1 |  |  | 0 | 0
701 | DEL-0011 | TSK-00692 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.2.1 | 1.1.2.2 | Internal Review & Critique | 10k Ft View | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.2.2 |  |  | 195 | 195
702 | DEL-0011 | TSK-00693 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.2.2 | 1.1.2.2 | Internal Review & Critique | 10k Ft View | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.2.2.1 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.3 | 1.1.2 | Client Review & Revisions | 10k Ft View | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.2.2.2 |  |  | 0 | 0
696 | DEL-0011 | TSK-00687 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.3.1 | 1.1.2.3 | Client Review & Revisions | 10k Ft View | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.2.3 |  |  | 195 | 390
697 | DEL-0011 | TSK-00688 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.3.2 | 1.1.2.3 | Client Review & Revisions | 10k Ft View | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.1.2.3.1 |  |  | 195 | 195
698 | DEL-0011 | TSK-00689 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.3.3 | 1.1.2.3 | Client Review & Revisions | 10k Ft View | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.2.3.2 |  |  | 195 | 195
699 | DEL-0011 | TSK-00690 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.3.4 | 1.1.2.3 | Client Review & Revisions | 10k Ft View | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.2.3.3 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.4 | 1.1.2 | Narrative Overview | 10k Ft View | Narrative Overview |  |  | 0 | 15 | 0 | 1.1.2.3.4 |  |  | 0 | 0
703 | DEL-0011 | TSK-00694 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.4.1 | 1.1.2.4 | Narrative Overview | 10k Ft View | Narrative Overview | Copywriter | Mid | 2 |  |  | 1.1.2.4 |  |  | 195 | 390
704 | DEL-0011 | TSK-00695 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.4.2 | 1.1.2.4 | Narrative Overview | 10k Ft View | Narrative Overview | Creative Director | Lead/Director | 2 |  |  | 1.1.2.4.1 |  |  | 195 | 390
700 | DEL-0011 | TSK-00691 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.2.4.3 | 1.1.2.4 | Narrative Overview | 10k Ft View | Narrative Overview | Designer | Mid | 2 |  |  | 1.1.2.4.2 |  |  | 195 | 390
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3 | 1.1 | Image Usage Guidelines | Image Usage Guidelines |  |  |  | 27 | 10 | 5 | 1.1.2 |  |  | 195 | 5265
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.1 | 1.1.3 | Internal Review & Critique | Image Usage Guidelines | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.3 |  |  | 0 | 0
712 | DEL-0011 | TSK-00703 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.1.1 | 1.1.3.1 | Internal Review & Critique | Image Usage Guidelines | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.3.1 |  |  | 195 | 195
713 | DEL-0011 | TSK-00704 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.1.2 | 1.1.3.1 | Internal Review & Critique | Image Usage Guidelines | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.3.1.1 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.2 | 1.1.3 | Client Review & Revisions | Image Usage Guidelines | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.3.1.2 |  |  | 0 | 0
706 | DEL-0011 | TSK-00697 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.2.1 | 1.1.3.2 | Client Review & Revisions | Image Usage Guidelines | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.3.2 |  |  | 195 | 390
707 | DEL-0011 | TSK-00698 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.2.2 | 1.1.3.2 | Client Review & Revisions | Image Usage Guidelines | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.3.2.1 |  |  | 195 | 195
708 | DEL-0011 | TSK-00699 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.2.3 | 1.1.3.2 | Client Review & Revisions | Image Usage Guidelines | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.3.2.2 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.3 | 1.1.3 | Examples | Image Usage Guidelines | Examples |  |  | 0 | 15 | 0 | 1.1.3.2.3 |  |  | 0 | 0
711 | DEL-0011 | TSK-00702 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.3.1 | 1.1.3.3 | Examples | Image Usage Guidelines | Examples | Art Director | Lead/Director | 1 |  |  | 1.1.3.3 |  |  | 195 | 195
709 | DEL-0011 | TSK-00700 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.3.3.2 | 1.1.3.3 | Examples | Image Usage Guidelines | Examples | Designer | Mid | 20 |  |  | 1.1.3.3.1 |  |  | 195 | 3900
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4 | 1.1 | Media Assets | Media Assets |  |  |  | 12 | 10 | 5 | 1.1.3 |  |  | 195 | 2340
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.1 | 1.1.4 | Internal Review & Critique | Media Assets | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.4 |  |  | 0 | 0
729 | DEL-0011 | TSK-00720 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.1.1 | 1.1.4.1 | Internal Review & Critique | Media Assets | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.4.1 |  |  | 195 | 195
730 | DEL-0011 | TSK-00721 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.1.2 | 1.1.4.1 | Internal Review & Critique | Media Assets | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.4.1.1 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.2 | 1.1.4 | Client Review & Revisions | Media Assets | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.4.1.2 |  |  | 0 | 0
725 | DEL-0011 | TSK-00716 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.2.1 | 1.1.4.2 | Client Review & Revisions | Media Assets | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.4.2 |  |  | 195 | 390
726 | DEL-0011 | TSK-00717 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.2.2 | 1.1.4.2 | Client Review & Revisions | Media Assets | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.4.2.1 |  |  | 195 | 195
727 | DEL-0011 | TSK-00718 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.2.3 | 1.1.4.2 | Client Review & Revisions | Media Assets | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.4.2.2 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.3 | 1.1.4 | Asset Matrix | Media Assets | Asset Matrix |  |  | 0 | 15 | 0 | 1.1.4.2.3 |  |  | 0 | 0
723 | DEL-0011 | TSK-00714 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.3.1 | 1.1.4.3 | Asset Matrix | Media Assets | Asset Matrix | Designer | Mid | 5 |  |  | 1.1.4.3 |  |  | 195 | 975
724 | DEL-0011 | TSK-00715 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.4.3.2 | 1.1.4.3 | Asset Matrix | Media Assets | Asset Matrix | Project Manager | Mid | 1 |  |  | 1.1.4.3.1 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5 | 1.1 | Photo / Video Direction | Photo / Video Direction |  |  |  | 14 | 10 | 5 | 1.1.4 |  |  | 195 | 2730
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.1 | 1.1.5 | Internal Review & Critique | Photo / Video Direction | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.5 |  |  | 0 | 0
737 | DEL-0011 | TSK-00728 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.1.1 | 1.1.5.1 | Internal Review & Critique | Photo / Video Direction | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.5.1 |  |  | 195 | 195
738 | DEL-0011 | TSK-00729 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.1.2 | 1.1.5.1 | Internal Review & Critique | Photo / Video Direction | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.5.1.1 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.2 | 1.1.5 | Client Review & Revisions | Photo / Video Direction | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.5.1.2 |  |  | 0 | 0
731 | DEL-0011 | TSK-00722 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.2.1 | 1.1.5.2 | Client Review & Revisions | Photo / Video Direction | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.5.2 |  |  | 195 | 390
732 | DEL-0011 | TSK-00723 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.2.2 | 1.1.5.2 | Client Review & Revisions | Photo / Video Direction | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.5.2.1 |  |  | 195 | 195
733 | DEL-0011 | TSK-00724 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.2.3 | 1.1.5.2 | Client Review & Revisions | Photo / Video Direction | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.5.2.2 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.3 | 1.1.5 | Direction Notes | Photo / Video Direction | Direction Notes |  |  | 0 | 15 | 0 | 1.1.5.2.3 |  |  | 0 | 0
734 | DEL-0011 | TSK-00725 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.3.1 | 1.1.5.3 | Direction Notes | Photo / Video Direction | Direction Notes | Art Director | Lead/Director | 1 |  |  | 1.1.5.3 |  |  | 195 | 195
735 | DEL-0011 | TSK-00726 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.3.2 | 1.1.5.3 | Direction Notes | Photo / Video Direction | Direction Notes | Creative Director | Lead/Director | 2 |  |  | 1.1.5.3.1 |  |  | 195 | 390
736 | DEL-0011 | TSK-00727 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.5.3.3 | 1.1.5.3 | Direction Notes | Photo / Video Direction | Direction Notes | Designer | Mid | 5 |  |  | 1.1.5.3.2 |  |  | 195 | 975
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6 | 1.1 | Rollout | Rollout |  |  |  | 14 | 10 | 5 | 1.1.5 |  |  | 195 | 2730
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.1 | 1.1.6 | Internal Review & Critique | Rollout | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.6 |  |  | 0 | 0
744 | DEL-0011 | TSK-00735 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.1.1 | 1.1.6.1 | Internal Review & Critique | Rollout | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.6.1 |  |  | 195 | 195
745 | DEL-0011 | TSK-00736 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.1.2 | 1.1.6.1 | Internal Review & Critique | Rollout | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.6.1.1 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.2 | 1.1.6 | Client Review & Revisions | Rollout | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.6.1.2 |  |  | 0 | 0
740 | DEL-0011 | TSK-00731 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.2.1 | 1.1.6.2 | Client Review & Revisions | Rollout | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.6.2 |  |  | 195 | 390
741 | DEL-0011 | TSK-00732 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.2.2 | 1.1.6.2 | Client Review & Revisions | Rollout | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.6.2.1 |  |  | 195 | 195
742 | DEL-0011 | TSK-00733 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.2.3 | 1.1.6.2 | Client Review & Revisions | Rollout | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.6.2.2 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.3 | 1.1.6 | Phasing & Milestones | Rollout | Phasing & Milestones |  |  | 0 | 15 | 0 | 1.1.6.2.3 |  |  | 0 | 0
746 | DEL-0011 | TSK-00737 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.3.1 | 1.1.6.3 | Phasing & Milestones | Rollout | Phasing & Milestones | Creative Director | Lead/Director | 2 |  |  | 1.1.6.3 |  |  | 195 | 390
743 | DEL-0011 | TSK-00734 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.3.2 | 1.1.6.3 | Phasing & Milestones | Rollout | Phasing & Milestones | Designer | Mid | 5 |  |  | 1.1.6.3.1 |  |  | 195 | 975
747 | DEL-0011 | TSK-00738 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.6.3.3 | 1.1.6.3 | Phasing & Milestones | Rollout | Phasing & Milestones | Project Manager | Mid | 1 |  |  | 1.1.6.3.2 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7 | 1.1 | Use Cases | Use Cases |  |  |  | 10 | 10 | 5 | 1.1.6 |  |  | 195 | 1950
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.1 | 1.1.7 | Internal Review & Critique | Use Cases | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.7 |  |  | 0 | 0
753 | DEL-0011 | TSK-00744 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.1.1 | 1.1.7.1 | Internal Review & Critique | Use Cases | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.7.1 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.2 | 1.1.7 | Client Review & Revisions | Use Cases | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.7.1.1 |  |  | 0 | 0
749 | DEL-0011 | TSK-00740 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.2.1 | 1.1.7.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.7.2 |  |  | 195 | 390
750 | DEL-0011 | TSK-00741 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.2.2 | 1.1.7.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.7.2.1 |  |  | 195 | 195
751 | DEL-0011 | TSK-00742 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.2.3 | 1.1.7.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.7.2.2 |  |  | 195 | 195
| DEL-0011 |  | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.3 | 1.1.7 | Final Packaging | Use Cases | Final Packaging |  |  | 0 | 15 | 0 | 1.1.7.2.3 |  |  | 0 | 0
752 | DEL-0011 | TSK-00743 | Creative | Campaign Strategy | Casa-Dragones-Digital-MKT-RFP | 1.1.7.3.1 | 1.1.7.3 | Final Packaging | Use Cases | Final Packaging | Designer | Mid | 5 |  |  | 1.1.7.3 |  |  | 195 | 975
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2 | 1 | Paid Media Planning |  |  |  |  | 82 | 15 | 33 | 1.1 |  | Advanced/T2_MediumVolume | 195 | 15990
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1 | 1.2 | Media Planning Deck | Media Planning Deck |  |  |  | 19 | 15 | 16 | 1.2 |  |  | 195 | 3705
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1 | 1.2.1 | Deck Narrative | Media Planning Deck | Deck Narrative |  |  | 0 | 15 | 6 | 1.2.1 |  |  | 0 | 0
1241 | DEL-0029 | TSK-01232 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.1 | 1.2.1.1 | Deck Narrative | Media Planning Deck | Deck Narrative | Designer | Mid | 8 |  |  | 1.2.1.1 |  |  | 195 | 1560
1240 | DEL-0029 | TSK-01231 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.2 | 1.2.1.1 | Deck Narrative | Media Planning Deck | Deck Narrative | Media Strategist | Mid | 4 |  |  | 1.2.1.1.1 |  |  | 195 | 780
1244 | DEL-0029 | TSK-01235 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.3 | 1.2.1.1 | Deck Narrative | Media Planning Deck | Deck Narrative | Project Manager | Mid | 2 |  |  | 1.2.1.1.2 |  |  | 195 | 390
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.2 | 1.2.1 | Deck Build | Media Planning Deck | Deck Build |  |  | 0 | 27 | 5 | 1.2.1.1.3 |  |  | 0 | 0
1239 | DEL-0029 | TSK-01230 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.2.1 | 1.2.1.2 | Deck Build | Media Planning Deck | Deck Build | Designer | Mid | 2 |  |  | 1.2.1.2 |  |  | 195 | 390
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3 | 1.2.1 | Internal Review & Critique | Media Planning Deck | Internal Review & Critique |  |  | 0 | 43 | 2 | 1.2.1.2.1 |  |  | 0 | 0
1242 | DEL-0029 | TSK-01233 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3.1 | 1.2.1.3 | Internal Review & Critique | Media Planning Deck | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.1.3 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.4 | 1.2.1 | Client Review & Revisions | Media Planning Deck | Client Review & Revisions |  |  | 0 | 45 | 3 | 1.2.1.3.1 |  |  | 0 | 0
1237 | DEL-0029 | TSK-01228 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.4.1 | 1.2.1.4 | Client Review & Revisions | Media Planning Deck | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.1.4 |  |  | 195 | 195
1238 | DEL-0029 | TSK-01229 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.4.2 | 1.2.1.4 | Client Review & Revisions | Media Planning Deck | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.2.1.4.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.2 | 1.2 | Paid Media Plan | Paid Media Plan |  |  |  | 29 | 21 | 11 | 1.2.1 |  |  | 195 | 5655
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.2.1 | 1.2.2 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes |  |  | 0 | 21 | 6 | 1.2.2 |  |  | 0 | 0
1248 | DEL-0029 | TSK-01239 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.2.1.1 | 1.2.2.1 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes | Designer | Mid | 3 |  |  | 1.2.2.1 |  |  | 195 | 585
1252 | DEL-0029 | TSK-01243 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.2.1.2 | 1.2.2.1 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes | Media Planner | Mid | 10 |  |  | 1.2.2.1.1 |  |  | 195 | 1950
1245 | DEL-0029 | TSK-01236 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.2.1.3 | 1.2.2.1 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes | Media Strategist | Mid | 10 |  |  | 1.2.2.1.2 |  |  | 195 | 1950
1251 | DEL-0029 | TSK-01242 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.2.1.4 | 1.2.2.1 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes | Project Manager | Mid | 2 |  |  | 1.2.2.1.3 |  |  | 195 | 390
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.2.2 | 1.2.2 | Internal Review & Critique | Paid Media Plan | Internal Review & Critique |  |  | 0 | 43 | 2 | 1.2.2.1.4 |  |  | 0 | 0
1249 | DEL-0029 | TSK-01240 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.2.2.1 | 1.2.2.2 | Internal Review & Critique | Paid Media Plan | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.2.2 |  |  | 195 | 195
1250 | DEL-0029 | TSK-01241 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.2.2.2 | 1.2.2.2 | Internal Review & Critique | Paid Media Plan | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.2.2.2.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.2.3 | 1.2.2 | Client Review & Revisions | Paid Media Plan | Client Review & Revisions |  |  | 0 | 45 | 3 | 1.2.2.2.2 |  |  | 0 | 0
1246 | DEL-0029 | TSK-01237 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.2.3.1 | 1.2.2.3 | Client Review & Revisions | Paid Media Plan | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.2.3 |  |  | 195 | 195
1247 | DEL-0029 | TSK-01238 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.2.3.2 | 1.2.2.3 | Client Review & Revisions | Paid Media Plan | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.2.2.3.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.3 | 1.2 | Ad Unit & Format POV | Ad Unit & Format POV |  |  |  | 16 | 32 | 16 | 1.2.2 |  |  | 195 | 3120
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.3.1 | 1.2.3 | Spec Page Build | Ad Unit & Format POV | Spec Page Build |  |  | 0 | 32 | 11 | 1.2.3 |  |  | 0 | 0
1227 | DEL-0029 | TSK-01218 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.3.1.1 | 1.2.3.1 | Spec Page Build | Ad Unit & Format POV | Spec Page Build | Designer | Mid | 3 |  |  | 1.2.3.1 |  |  | 195 | 585
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.3.2 | 1.2.3 | Internal Review & Critique | Ad Unit & Format POV | Internal Review & Critique |  |  | 0 | 43 | 2 | 1.2.3.1.1 |  |  | 0 | 0
1223 | DEL-0029 | TSK-01214 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.3.2.1 | 1.2.3.2 | Internal Review & Critique | Ad Unit & Format POV | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.3.2 |  |  | 195 | 195
1224 | DEL-0029 | TSK-01215 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.3.2.2 | 1.2.3.2 | Internal Review & Critique | Ad Unit & Format POV | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.2.3.2.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.3.3 | 1.2.3 | Client Review & Revisions | Ad Unit & Format POV | Client Review & Revisions |  |  | 0 | 45 | 3 | 1.2.3.2.2 |  |  | 0 | 0
1220 | DEL-0029 | TSK-01211 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.3.3.1 | 1.2.3.3 | Client Review & Revisions | Ad Unit & Format POV | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.3.3 |  |  | 195 | 195
1221 | DEL-0029 | TSK-01212 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.3.3.2 | 1.2.3.3 | Client Review & Revisions | Ad Unit & Format POV | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.2.3.3.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.3.4 | 1.2.3 | Spec Matrix & POV | Ad Unit & Format POV | Spec Matrix & POV |  |  | 0 | 48 | 0 | 1.2.3.3.2 |  |  | 0 | 0
1222 | DEL-0029 | TSK-01213 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.3.4.1 | 1.2.3.4 | Spec Matrix & POV | Ad Unit & Format POV | Spec Matrix & POV | Designer | Mid | 3 |  |  | 1.2.3.4 |  |  | 195 | 585
1225 | DEL-0029 | TSK-01216 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.3.4.2 | 1.2.3.4 | Spec Matrix & POV | Ad Unit & Format POV | Spec Matrix & POV | Media Planner | Mid | 3 |  |  | 1.2.3.4.1 |  |  | 195 | 585
1226 | DEL-0029 | TSK-01217 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.3.4.3 | 1.2.3.4 | Spec Matrix & POV | Ad Unit & Format POV | Spec Matrix & POV | Media Strategist | Mid | 3 |  |  | 1.2.3.4.2 |  |  | 195 | 585
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.4 | 1.2 | Channel & Vendor Evaluation | Channel & Vendor Evaluation |  |  |  | 18 | 43 | 5 | 1.2.3 |  |  | 195 | 3510
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.4.1 | 1.2.4 | Internal Review & Critique | Channel & Vendor Evaluation | Internal Review & Critique |  |  | 0 | 43 | 2 | 1.2.4 |  |  | 0 | 0
1231 | DEL-0029 | TSK-01222 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.4.1.1 | 1.2.4.1 | Internal Review & Critique | Channel & Vendor Evaluation | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.4.1 |  |  | 195 | 195
1232 | DEL-0029 | TSK-01223 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.4.1.2 | 1.2.4.1 | Internal Review & Critique | Channel & Vendor Evaluation | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.2.4.1.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.4.2 | 1.2.4 | Client Review & Revisions | Channel & Vendor Evaluation | Client Review & Revisions |  |  | 0 | 45 | 3 | 1.2.4.1.2 |  |  | 0 | 0
1228 | DEL-0029 | TSK-01219 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.4.2.1 | 1.2.4.2 | Client Review & Revisions | Channel & Vendor Evaluation | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.4.2 |  |  | 195 | 195
1229 | DEL-0029 | TSK-01220 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.4.2.2 | 1.2.4.2 | Client Review & Revisions | Channel & Vendor Evaluation | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.2.4.2.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.4.3 | 1.2.4 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review |  |  | 0 | 48 | 0 | 1.2.4.2.2 |  |  | 0 | 0
1236 | DEL-0029 | TSK-01227 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.4.3.1 | 1.2.4.3 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review | Account Manager | Mid | 2 |  |  | 1.2.4.3 |  |  | 195 | 390
1230 | DEL-0029 | TSK-01221 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.4.3.2 | 1.2.4.3 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review | Designer | Mid | 2 |  |  | 1.2.4.3.1 |  |  | 195 | 390
1233 | DEL-0029 | TSK-01224 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.4.3.3 | 1.2.4.3 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review | Media Planner | Mid | 7 |  |  | 1.2.4.3.2 |  |  | 195 | 1365
1234 | DEL-0029 | TSK-01225 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.4.3.4 | 1.2.4.3 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review | Media Strategist | Mid | 3 |  |  | 1.2.4.3.3 |  |  | 195 | 585
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3 | 1 | Reporting |  |  |  |  | 69 | 48 | 19 | 1.2 |  | Advanced/T2_MediumVolume | 195 | 13455
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1 | 1.3 | Campaign Reporting (Quarterly) | Campaign Reporting (Quarterly) |  |  |  | 14 | 48 | 4 | 1.3 |  |  | 195 | 2730
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.1 | 1.3.1 | Design Polish | Campaign Reporting (Quarterly) | Design Polish |  |  | 0 | 48 | 4 | 1.3.1 |  |  | 0 | 0
1355 | DEL-0032 | TSK-01346 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.1.1 | 1.3.1.1 | Design Polish | Campaign Reporting (Quarterly) | Design Polish | Designer | Mid | 3 |  |  | 1.3.1.1 |  |  | 195 | 585
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.2 | 1.3.1 | Data Deep Dive | Campaign Reporting (Quarterly) | Data Deep Dive |  |  | 0 | 67 | 0 | 1.3.1.1.1 |  |  | 0 | 0
1353 | DEL-0032 | TSK-01344 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.2.1 | 1.3.1.2 | Data Deep Dive | Campaign Reporting (Quarterly) | Data Deep Dive | Analyst | Mid | 3 |  |  | 1.3.1.2 |  |  | 195 | 585
1356 | DEL-0032 | TSK-01347 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.2.2 | 1.3.1.2 | Data Deep Dive | Campaign Reporting (Quarterly) | Data Deep Dive | Creative Director | Lead/Director | 2 |  |  | 1.3.1.2.1 |  |  | 195 | 390
1357 | DEL-0032 | TSK-01348 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.2.3 | 1.3.1.2 | Data Deep Dive | Campaign Reporting (Quarterly) | Data Deep Dive | Media Strategist | Mid | 3 |  |  | 1.3.1.2.2 |  |  | 195 | 585
1354 | DEL-0032 | TSK-01345 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.2.4 | 1.3.1.2 | Data Deep Dive | Campaign Reporting (Quarterly) | Data Deep Dive | QA Specialist | Mid | 3 |  |  | 1.3.1.2.3 |  |  | 195 | 585
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.2 | 1.3 | Campaign Reporting (Bi-Weekly) | Campaign Reporting (Bi-Weekly) |  |  |  | 10 | 52 | 7 | 1.3.1 |  |  | 195 | 1950
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.2.1 | 1.3.2 | Data Refresh & QA | Campaign Reporting (Bi-Weekly) | Data Refresh & QA |  |  | 0 | 52 | 3 | 1.3.2 |  |  | 0 | 0
1350 | DEL-0032 | TSK-01341 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.2.1.1 | 1.3.2.1 | Data Refresh & QA | Campaign Reporting (Bi-Weekly) | Data Refresh & QA | Analyst | Mid | 3 |  |  | 1.3.2.1 |  |  | 195 | 585
1351 | DEL-0032 | TSK-01342 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.2.1.2 | 1.3.2.1 | Data Refresh & QA | Campaign Reporting (Bi-Weekly) | Data Refresh & QA | QA Specialist | Mid | 3 |  |  | 1.3.2.1.1 |  |  | 195 | 585
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.2.2 | 1.3.2 | Client Summary | Campaign Reporting (Bi-Weekly) | Client Summary |  |  | 0 | 59 | 4 | 1.3.2.1.2 |  |  | 0 | 0
1349 | DEL-0032 | TSK-01340 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.2.2.1 | 1.3.2.2 | Client Summary | Campaign Reporting (Bi-Weekly) | Client Summary | Account Manager | Mid | 1 |  |  | 1.3.2.2 |  |  | 195 | 195
1352 | DEL-0032 | TSK-01343 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.2.2.2 | 1.3.2.2 | Client Summary | Campaign Reporting (Bi-Weekly) | Client Summary | Media Strategist | Mid | 3 |  |  | 1.3.2.2.1 |  |  | 195 | 585
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.3 | 1.3 | Campaign Tracking | Campaign Tracking |  |  |  | 8 | 52 | 7 | 1.3.2 |  |  | 195 | 1560
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.3.1 | 1.3.3 | QA Spot Check | Campaign Tracking | QA Spot Check |  |  | 0 | 52 | 3 | 1.3.3 |  |  | 0 | 0
1358 | DEL-0032 | TSK-01349 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.3.1.1 | 1.3.3.1 | QA Spot Check | Campaign Tracking | QA Spot Check | QA Specialist | Mid | 3 |  |  | 1.3.3.1 |  |  | 195 | 585
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.3.2 | 1.3.3 | Tracker Update | Campaign Tracking | Tracker Update |  |  | 0 | 55 | 4 | 1.3.3.1.1 |  |  | 0 | 0
1359 | DEL-0032 | TSK-01350 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.3.2.1 | 1.3.3.2 | Tracker Update | Campaign Tracking | Tracker Update | Analyst | Mid | 5 |  |  | 1.3.3.2 |  |  | 195 | 975
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.4 | 1.3 | Dashboard Analytics | Dashboard Analytics |  |  |  | 9 | 52 | 7 | 1.3.3 |  |  | 195 | 1755
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.4.1 | 1.3.4 | QA & Calc Checks | Dashboard Analytics | QA & Calc Checks |  |  | 0 | 52 | 3 | 1.3.4 |  |  | 0 | 0
1361 | DEL-0032 | TSK-01352 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.4.1.1 | 1.3.4.1 | QA & Calc Checks | Dashboard Analytics | QA & Calc Checks | QA Specialist | Mid | 3 |  |  | 1.3.4.1 |  |  | 195 | 585
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.4.2 | 1.3.4 | Dashboard Build/Refresh | Dashboard Analytics | Dashboard Build/Refresh |  |  | 0 | 59 | 4 | 1.3.4.1.1 |  |  | 0 | 0
1360 | DEL-0032 | TSK-01351 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.4.2.1 | 1.3.4.2 | Dashboard Build/Refresh | Dashboard Analytics | Dashboard Build/Refresh | Analyst | Mid | 6 |  |  | 1.3.4.2 |  |  | 195 | 1170
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.5 | 1.3 | Reporting & Ad-Tagging Support | Reporting & Ad-Tagging Support |  |  |  | 8 | 52 | 7 | 1.3.4 |  |  | 195 | 1560
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.5.1 | 1.3.5 | QA | Reporting & Ad-Tagging Support | QA |  |  | 0 | 52 | 3 | 1.3.5 |  |  | 0 | 0
1369 | DEL-0032 | TSK-01360 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.5.1.1 | 1.3.5.1 | QA | Reporting & Ad-Tagging Support | QA | QA Specialist | Mid | 3 |  |  | 1.3.5.1 |  |  | 195 | 585
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.5.2 | 1.3.5 | UTM/Tag Guidance | Reporting & Ad-Tagging Support | UTM/Tag Guidance |  |  | 0 | 55 | 4 | 1.3.5.1.1 |  |  | 0 | 0
1371 | DEL-0032 | TSK-01362 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.5.2.1 | 1.3.5.2 | UTM/Tag Guidance | Reporting & Ad-Tagging Support | UTM/Tag Guidance | Media Strategist | Mid | 3 |  |  | 1.3.5.2 |  |  | 195 | 585
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.5.3 | 1.3.5 | Tagging Support | Reporting & Ad-Tagging Support | Tagging Support |  |  | 0 | 67 | 0 | 1.3.5.2.1 |  |  | 0 | 0
1370 | DEL-0032 | TSK-01361 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.5.3.1 | 1.3.5.3 | Tagging Support | Reporting & Ad-Tagging Support | Tagging Support | Ad Ops / Trafficker | Mid | 2 |  |  | 1.3.5.3 |  |  | 195 | 390
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.6 | 1.3 | Dashboard Maintenance | Dashboard Maintenance |  |  |  | 7 | 59 | 4 | 1.3.5 |  |  | 195 | 1365
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.6.1 | 1.3.6 | Connector Checks & Fixes | Dashboard Maintenance | Connector Checks & Fixes |  |  | 0 | 59 | 4 | 1.3.6 |  |  | 0 | 0
1362 | DEL-0032 | TSK-01353 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.6.1.1 | 1.3.6.1 | Connector Checks & Fixes | Dashboard Maintenance | Connector Checks & Fixes | Analyst | Mid | 6 |  |  | 1.3.6.1 |  |  | 195 | 1170
1363 | DEL-0032 | TSK-01354 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.6.1.2 | 1.3.6.1 | Connector Checks & Fixes | Dashboard Maintenance | Connector Checks & Fixes | Project Manager | Mid | 1 |  |  | 1.3.6.1.1 |  |  | 195 | 195
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.7 | 1.3 | Reconcilliation & Media Budget Authorization | Reconcilliation & Media Budget Authorization |  |  |  | 5 | 63 | 2 | 1.3.6 |  |  | 195 | 975
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.7.1 | 1.3.7 | Authorization & Docs | Reconcilliation & Media Budget Authorization | Authorization & Docs |  |  | 0 | 63 | 2 | 1.3.7 |  |  | 0 | 0
1366 | DEL-0032 | TSK-01357 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.7.1.1 | 1.3.7.1 | Authorization & Docs | Reconcilliation & Media Budget Authorization | Authorization & Docs | Account Manager | Mid | 2 |  |  | 1.3.7.1 |  |  | 195 | 390
1368 | DEL-0032 | TSK-01359 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.7.1.2 | 1.3.7.1 | Authorization & Docs | Reconcilliation & Media Budget Authorization | Authorization & Docs | Media Buyer | Mid | 1 |  |  | 1.3.7.1.1 |  |  | 195 | 195
1367 | DEL-0032 | TSK-01358 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.7.1.3 | 1.3.7.1 | Authorization & Docs | Reconcilliation & Media Budget Authorization | Authorization & Docs | Project Manager | Mid | 2 |  |  | 1.3.7.1.2 |  |  | 195 | 390
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.8 | 1.3 | KPI Monitoring | KPI Monitoring |  |  |  | 4 | 65 | 2 | 1.3.7 |  |  | 195 | 780
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.8.1 | 1.3.8 | Weekly KPI Scan | KPI Monitoring | Weekly KPI Scan |  |  | 0 | 65 | 2 | 1.3.8 |  |  | 0 | 0
1365 | DEL-0032 | TSK-01356 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.8.1.1 | 1.3.8.1 | Weekly KPI Scan | KPI Monitoring | Weekly KPI Scan | Analyst | Mid | 1 |  |  | 1.3.8.1 |  |  | 195 | 195
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.8.2 | 1.3.8 | Notes & Flags | KPI Monitoring | Notes & Flags |  |  | 0 | 67 | 0 | 1.3.8.1.1 |  |  | 0 | 0
1364 | DEL-0032 | TSK-01355 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.8.2.1 | 1.3.8.2 | Notes & Flags | KPI Monitoring | Notes & Flags | Media Strategist | Mid | 3 |  |  | 1.3.8.2 |  |  | 195 | 585
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.9 | 1.3 | Ad-Platform Reporting | Ad-Platform Reporting |  |  |  | 4 | 67 | 0 | 1.3.8 |  |  | 195 | 780
| DEL-0032 |  | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.9.1 | 1.3.9 | Distribution | Ad-Platform Reporting | Distribution |  |  | 0 | 67 | 0 | 1.3.9 |  |  | 0 | 0
1348 | DEL-0032 | TSK-01339 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.9.1.1 | 1.3.9.1 | Distribution | Ad-Platform Reporting | Distribution | Analyst | Mid | 3 |  |  | 1.3.9.1 |  |  | 195 | 585
1347 | DEL-0032 | TSK-01338 | Paid Media | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.9.1.2 | 1.3.9.1 | Distribution | Ad-Platform Reporting | Distribution | Project Manager | Mid | 1 |  |  | 1.3.9.1.1 |  |  | 195 | 195
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4 | 1 | Reporting |  |  |  |  | 128 | 67 | 7 | 1.3 |  | Advanced/T2_MediumVolume | 195 | 24960
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.1 | 1.4 | Dashboards | Dashboards |  |  |  | 9 | 67 | 7 | 1.4 |  |  | 195 | 1755
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.1.1 | 1.4.1 | QA | Dashboards | QA |  |  | 0 | 67 | 3 | 1.4.1 |  |  | 0 | 0
1116 | DEL-0024 | TSK-01107 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.1.1.1 | 1.4.1.1 | QA | Dashboards | QA | QA Specialist | Mid | 3 |  |  | 1.4.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.1.2 | 1.4.1 | Dashboard Build/Refresh | Dashboards | Dashboard Build/Refresh |  |  | 0 | 70 | 4 | 1.4.1.1.1 |  |  | 0 | 0
1115 | DEL-0024 | TSK-01106 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.1.2.1 | 1.4.1.2 | Dashboard Build/Refresh | Dashboards | Dashboard Build/Refresh | Analyst | Mid | 6 |  |  | 1.4.1.2 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.2 | 1.4 | Engagement Rate | Engagement Rate |  |  |  | 6 | 67 | 3 | 1.4.1 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.2.1 | 1.4.2 | Data Refresh & Calc Check | Engagement Rate | Data Refresh & Calc Check |  |  | 0 | 67 | 3 | 1.4.2 |  |  | 0 | 0
1119 | DEL-0024 | TSK-01110 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.2.1.1 | 1.4.2.1 | Data Refresh & Calc Check | Engagement Rate | Data Refresh & Calc Check | Analyst | Mid | 3 |  |  | 1.4.2.1 |  |  | 195 | 585
1120 | DEL-0024 | TSK-01111 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.2.1.2 | 1.4.2.1 | Data Refresh & Calc Check | Engagement Rate | Data Refresh & Calc Check | QA Specialist | Mid | 3 |  |  | 1.4.2.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.3 | 1.4 | Emplifi Reports | Emplifi Reports |  |  |  | 7 | 70 | 4 | 1.4.2 |  |  | 195 | 1365
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.3.1 | 1.4.3 | Emplifi Extract & Summary | Emplifi Reports | Emplifi Extract & Summary |  |  | 0 | 70 | 4 | 1.4.3 |  |  | 0 | 0
1117 | DEL-0024 | TSK-01108 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.3.1.1 | 1.4.3.1 | Emplifi Extract & Summary | Emplifi Reports | Emplifi Extract & Summary | Account Manager | Mid | 1 |  |  | 1.4.3.1 |  |  | 195 | 195
1118 | DEL-0024 | TSK-01109 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.3.1.2 | 1.4.3.1 | Emplifi Extract & Summary | Emplifi Reports | Emplifi Extract & Summary | Analyst | Mid | 6 |  |  | 1.4.3.1.1 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.4 | 1.4 | Monthly Comprehensive Report | Monthly Comprehensive Report |  |  |  | 11 | 70 | 4 | 1.4.3 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.4.1 | 1.4.4 | Monthly Report | Monthly Comprehensive Report | Monthly Report |  |  | 0 | 70 | 4 | 1.4.4 |  |  | 0 | 0
1127 | DEL-0024 | TSK-01118 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.4.1.1 | 1.4.4.1 | Monthly Report | Monthly Comprehensive Report | Monthly Report | Analyst | Mid | 6 |  |  | 1.4.4.1 |  |  | 195 | 1170
1128 | DEL-0024 | TSK-01119 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.4.1.2 | 1.4.4.1 | Monthly Report | Monthly Comprehensive Report | Monthly Report | Designer | Mid | 2 |  |  | 1.4.4.1.1 |  |  | 195 | 390
1129 | DEL-0024 | TSK-01120 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.4.1.3 | 1.4.4.1 | Monthly Report | Monthly Comprehensive Report | Monthly Report | Social Strategist | Mid | 3 |  |  | 1.4.4.1.2 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.5 | 1.4 | Monthly Organic Social Report | Monthly Organic Social Report |  |  |  | 11 | 70 | 4 | 1.4.4 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.5.1 | 1.4.5 | Monthly Organic Report | Monthly Organic Social Report | Monthly Organic Report |  |  | 0 | 70 | 4 | 1.4.5 |  |  | 0 | 0
1130 | DEL-0024 | TSK-01121 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.5.1.1 | 1.4.5.1 | Monthly Organic Report | Monthly Organic Social Report | Monthly Organic Report | Analyst | Mid | 6 |  |  | 1.4.5.1 |  |  | 195 | 1170
1131 | DEL-0024 | TSK-01122 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.5.1.2 | 1.4.5.1 | Monthly Organic Report | Monthly Organic Social Report | Monthly Organic Report | Designer | Mid | 2 |  |  | 1.4.5.1.1 |  |  | 195 | 390
1132 | DEL-0024 | TSK-01123 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.5.1.3 | 1.4.5.1 | Monthly Organic Report | Monthly Organic Social Report | Monthly Organic Report | Social Strategist | Mid | 3 |  |  | 1.4.5.1.2 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.6 | 1.4 | Optimization Recommendations Report | Optimization Recommendations Report |  |  |  | 10 | 70 | 4 | 1.4.5 |  |  | 195 | 1950
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.6.1 | 1.4.6 | Recs & Next Steps | Optimization Recommendations Report | Recs & Next Steps |  |  | 0 | 70 | 4 | 1.4.6 |  |  | 0 | 0
1133 | DEL-0024 | TSK-01124 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.6.1.1 | 1.4.6.1 | Recs & Next Steps | Optimization Recommendations Report | Recs & Next Steps | Account Manager | Mid | 1 |  |  | 1.4.6.1 |  |  | 195 | 195
1134 | DEL-0024 | TSK-01125 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.6.1.2 | 1.4.6.1 | Recs & Next Steps | Optimization Recommendations Report | Recs & Next Steps | Analyst | Mid | 6 |  |  | 1.4.6.1.1 |  |  | 195 | 1170
1135 | DEL-0024 | TSK-01126 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.6.1.3 | 1.4.6.1 | Recs & Next Steps | Optimization Recommendations Report | Recs & Next Steps | Social Strategist | Mid | 3 |  |  | 1.4.6.1.2 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.7 | 1.4 | Quarterly Ad-Hoc Report | Quarterly Ad-Hoc Report |  |  |  | 9 | 70 | 4 | 1.4.6 |  |  | 195 | 1755
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.7.1 | 1.4.7 | Quarterly Ad-hoc Deep Dive | Quarterly Ad-Hoc Report | Quarterly Ad-hoc Deep Dive |  |  | 0 | 70 | 4 | 1.4.7 |  |  | 0 | 0
1138 | DEL-0024 | TSK-01129 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.7.1.1 | 1.4.7.1 | Quarterly Ad-hoc Deep Dive | Quarterly Ad-Hoc Report | Quarterly Ad-hoc Deep Dive | Analyst | Mid | 6 |  |  | 1.4.7.1 |  |  | 195 | 1170
1139 | DEL-0024 | TSK-01130 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.7.1.2 | 1.4.7.1 | Quarterly Ad-hoc Deep Dive | Quarterly Ad-Hoc Report | Quarterly Ad-hoc Deep Dive | QA Specialist | Mid | 3 |  |  | 1.4.7.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.8 | 1.4 | Quarterly Key Learnings & Insights Report | Quarterly Key Learnings & Insights Report |  |  |  | 11 | 70 | 4 | 1.4.7 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.8.1 | 1.4.8 | Quarterly Learnings & Insights | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights |  |  | 0 | 70 | 4 | 1.4.8 |  |  | 0 | 0
1140 | DEL-0024 | TSK-01131 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.8.1.1 | 1.4.8.1 | Quarterly Learnings & Insights | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights | Analyst | Mid | 6 |  |  | 1.4.8.1 |  |  | 195 | 1170
1141 | DEL-0024 | TSK-01132 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.8.1.2 | 1.4.8.1 | Quarterly Learnings & Insights | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights | Designer | Mid | 2 |  |  | 1.4.8.1.1 |  |  | 195 | 390
1142 | DEL-0024 | TSK-01133 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.8.1.3 | 1.4.8.1 | Quarterly Learnings & Insights | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights | Social Strategist | Mid | 3 |  |  | 1.4.8.1.2 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.9 | 1.4 | Quarterly Report | Quarterly Report |  |  |  | 11 | 70 | 4 | 1.4.8 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.9.1 | 1.4.9 | Quarterly Report | Quarterly Report | Quarterly Report |  |  | 0 | 70 | 4 | 1.4.9 |  |  | 0 | 0
1143 | DEL-0024 | TSK-01134 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.9.1.1 | 1.4.9.1 | Quarterly Report | Quarterly Report | Quarterly Report | Analyst | Mid | 6 |  |  | 1.4.9.1 |  |  | 195 | 1170
1144 | DEL-0024 | TSK-01135 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.9.1.2 | 1.4.9.1 | Quarterly Report | Quarterly Report | Quarterly Report | Designer | Mid | 2 |  |  | 1.4.9.1.1 |  |  | 195 | 390
1145 | DEL-0024 | TSK-01136 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.9.1.3 | 1.4.9.1 | Quarterly Report | Quarterly Report | Quarterly Report | Social Strategist | Mid | 3 |  |  | 1.4.9.1.2 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.10 | 1.4 | Summary overview | Summary overview |  |  |  | 4 | 70 | 4 | 1.4.9 |  |  | 195 | 780
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.10.1 | 1.4.10 | Summary Narrative | Summary overview | Summary Narrative |  |  | 0 | 70 | 4 | 1.4.10 |  |  | 0 | 0
1150 | DEL-0024 | TSK-01141 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.10.1.1 | 1.4.10.1 | Summary Narrative | Summary overview | Summary Narrative | Account Manager | Mid | 1 |  |  | 1.4.10.1 |  |  | 195 | 195
1151 | DEL-0024 | TSK-01142 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.10.1.2 | 1.4.10.1 | Summary Narrative | Summary overview | Summary Narrative | Social Strategist | Mid | 3 |  |  | 1.4.10.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.11 | 1.4 | Weekly Activity Report | Weekly Activity Report |  |  |  | 7 | 70 | 4 | 1.4.10 |  |  | 195 | 1365
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.11.1 | 1.4.11 | Weekly Activity Summary | Weekly Activity Report | Weekly Activity Summary |  |  | 0 | 70 | 4 | 1.4.11 |  |  | 0 | 0
1153 | DEL-0024 | TSK-01144 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.11.1.1 | 1.4.11.1 | Weekly Activity Summary | Weekly Activity Report | Weekly Activity Summary | Account Manager | Mid | 1 |  |  | 1.4.11.1 |  |  | 195 | 195
1154 | DEL-0024 | TSK-01145 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.11.1.2 | 1.4.11.1 | Weekly Activity Summary | Weekly Activity Report | Weekly Activity Summary | Analyst | Mid | 6 |  |  | 1.4.11.1.1 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.12 | 1.4 | Follower Growth | Follower Growth |  |  |  | 6 | 74 | 0 | 1.4.11 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.12.1 | 1.4.12 | Metric Pull & Notes | Follower Growth | Metric Pull & Notes |  |  | 0 | 74 | 0 | 1.4.12 |  |  | 0 | 0
1121 | DEL-0024 | TSK-01112 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.12.1.1 | 1.4.12.1 | Metric Pull & Notes | Follower Growth | Metric Pull & Notes | Analyst | Mid | 3 |  |  | 1.4.12.1 |  |  | 195 | 585
1122 | DEL-0024 | TSK-01113 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.12.1.2 | 1.4.12.1 | Metric Pull & Notes | Follower Growth | Metric Pull & Notes | QA Specialist | Mid | 3 |  |  | 1.4.12.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.13 | 1.4 | Impressions | Impressions |  |  |  | 6 | 74 | 0 | 1.4.12 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.13.1 | 1.4.13 | Metric Pull & Notes | Impressions | Metric Pull & Notes |  |  | 0 | 74 | 0 | 1.4.13 |  |  | 0 | 0
1123 | DEL-0024 | TSK-01114 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.13.1.1 | 1.4.13.1 | Metric Pull & Notes | Impressions | Metric Pull & Notes | Analyst | Mid | 3 |  |  | 1.4.13.1 |  |  | 195 | 585
1124 | DEL-0024 | TSK-01115 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.13.1.2 | 1.4.13.1 | Metric Pull & Notes | Impressions | Metric Pull & Notes | QA Specialist | Mid | 3 |  |  | 1.4.13.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.14 | 1.4 | Interactions | Interactions |  |  |  | 5 | 74 | 0 | 1.4.13 |  |  | 195 | 975
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.14.1 | 1.4.14 | Metric Pull & Notes | Interactions | Metric Pull & Notes |  |  | 0 | 74 | 0 | 1.4.14 |  |  | 0 | 0
1125 | DEL-0024 | TSK-01116 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.14.1.1 | 1.4.14.1 | Metric Pull & Notes | Interactions | Metric Pull & Notes | Analyst | Mid | 2 |  |  | 1.4.14.1 |  |  | 195 | 390
1126 | DEL-0024 | TSK-01117 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.14.1.2 | 1.4.14.1 | Metric Pull & Notes | Interactions | Metric Pull & Notes | QA Specialist | Mid | 3 |  |  | 1.4.14.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.15 | 1.4 | Profile Reach | Profile Reach |  |  |  | 5 | 74 | 0 | 1.4.14 |  |  | 195 | 975
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.15.1 | 1.4.15 | Metric Pull & Notes | Profile Reach | Metric Pull & Notes |  |  | 0 | 74 | 0 | 1.4.15 |  |  | 0 | 0
1136 | DEL-0024 | TSK-01127 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.15.1.1 | 1.4.15.1 | Metric Pull & Notes | Profile Reach | Metric Pull & Notes | Analyst | Mid | 2 |  |  | 1.4.15.1 |  |  | 195 | 390
1137 | DEL-0024 | TSK-01128 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.15.1.2 | 1.4.15.1 | Metric Pull & Notes | Profile Reach | Metric Pull & Notes | QA Specialist | Mid | 3 |  |  | 1.4.15.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.16 | 1.4 | Recap Reports | Recap Reports |  |  |  | 4 | 74 | 0 | 1.4.15 |  |  | 195 | 780
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.16.1 | 1.4.16 | Campaign/Period Recaps | Recap Reports | Campaign/Period Recaps |  |  | 0 | 74 | 0 | 1.4.16 |  |  | 0 | 0
1146 | DEL-0024 | TSK-01137 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.16.1.1 | 1.4.16.1 | Campaign/Period Recaps | Recap Reports | Campaign/Period Recaps | Account Manager | Mid | 2 |  |  | 1.4.16.1 |  |  | 195 | 390
1147 | DEL-0024 | TSK-01138 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.16.1.2 | 1.4.16.1 | Campaign/Period Recaps | Recap Reports | Campaign/Period Recaps | Analyst | Mid | 2 |  |  | 1.4.16.1.1 |  |  | 195 | 390
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.17 | 1.4 | Social Reporting | Social Reporting |  |  |  | 4 | 74 | 0 | 1.4.16 |  |  | 195 | 780
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.17.1 | 1.4.17 | Ongoing Social Reporting | Social Reporting | Ongoing Social Reporting |  |  | 0 | 74 | 0 | 1.4.17 |  |  | 0 | 0
1148 | DEL-0024 | TSK-01139 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.17.1.1 | 1.4.17.1 | Ongoing Social Reporting | Social Reporting | Ongoing Social Reporting | Account Manager | Mid | 2 |  |  | 1.4.17.1 |  |  | 195 | 390
1149 | DEL-0024 | TSK-01140 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.17.1.2 | 1.4.17.1 | Ongoing Social Reporting | Social Reporting | Ongoing Social Reporting | Analyst | Mid | 2 |  |  | 1.4.17.1.1 |  |  | 195 | 390
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.18 | 1.4 | Update/maintain Z/Russia tracker | Update/maintain Z/Russia tracker |  |  |  | 2 | 74 | 0 | 1.4.17 |  |  | 195 | 390
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.18.1 | 1.4.18 | Tracker Update | Update/maintain Z/Russia tracker | Tracker Update |  |  | 0 | 74 | 0 | 1.4.18 |  |  | 0 | 0
1152 | DEL-0024 | TSK-01143 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.4.18.1.1 | 1.4.18.1 | Tracker Update | Update/maintain Z/Russia tracker | Tracker Update | Analyst | Mid | 2 |  |  | 1.4.18.1 |  |  | 195 | 390
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5 | 1 | Development |  |  |  |  | 268 | 74 | 26 | 1.4 |  | Advanced/T2_MediumVolume | 195 | 52260
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.1 | 1.5 | ADA Compliance | ADA Compliance |  |  |  | 59 | 74 | 18 | 1.5 |  |  | 195 | 11505
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.1.1 | 1.5.1 | Accessibility Audit | ADA Compliance | Accessibility Audit |  |  | 0 | 74 | 4 | 1.5.1 |  |  | 0 | 0
1738 | DEL-0044 | TSK-01729 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.1.1.1 | 1.5.1.1 | Accessibility Audit | ADA Compliance | Accessibility Audit | Accessibility Specialist | Mid | 2 |  |  | 1.5.1.1 |  |  | 195 | 390
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.1.2 | 1.5.1 | Accessibility QA | ADA Compliance | Accessibility QA |  |  | 0 | 86 | 3 | 1.5.1.1.1 |  |  | 0 | 0
1739 | DEL-0044 | TSK-01730 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.1.2.1 | 1.5.1.2 | Accessibility QA | ADA Compliance | Accessibility QA | Accessibility Specialist | Mid | 2 |  |  | 1.5.1.2 |  |  | 195 | 390
1744 | DEL-0044 | TSK-01735 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.1.2.2 | 1.5.1.2 | Accessibility QA | ADA Compliance | Accessibility QA | QA Engineer | Mid | 3 |  |  | 1.5.1.2.1 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.1.3 | 1.5.1 | Code Review | ADA Compliance | Code Review |  |  | 0 | 89 | 11 | 1.5.1.2.2 |  |  | 0 | 0
1740 | DEL-0044 | TSK-01731 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.1.3.1 | 1.5.1.3 | Code Review | ADA Compliance | Code Review | Backend Engineer | Mid | 12 |  |  | 1.5.1.3 |  |  | 195 | 2340
1742 | DEL-0044 | TSK-01733 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.1.3.2 | 1.5.1.3 | Code Review | ADA Compliance | Code Review | DevOps Engineer | Mid | 12 |  |  | 1.5.1.3.1 |  |  | 195 | 2340
1741 | DEL-0044 | TSK-01732 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.1.3.3 | 1.5.1.3 | Code Review | ADA Compliance | Code Review | Frontend Engineer | Mid | 24 |  |  | 1.5.1.3.2 |  |  | 195 | 4680
1743 | DEL-0044 | TSK-01734 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.1.3.4 | 1.5.1.3 | Code Review | ADA Compliance | Code Review | Project Manager | Mid | 4 |  |  | 1.5.1.3.3 |  |  | 195 | 780
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.2 | 1.5 | Audit & Requirement gathering | Audit & Requirement gathering |  |  |  | 20 | 74 | 4 | 1.5.1 |  |  | 195 | 3900
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.2.1 | 1.5.2 | Analytics Audit | Audit & Requirement gathering | Analytics Audit |  |  | 0 | 74 | 4 | 1.5.2 |  |  | 0 | 0
1750 | DEL-0044 | TSK-01741 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.2.1.1 | 1.5.2.1 | Analytics Audit | Audit & Requirement gathering | Analytics Audit | Business Analyst | Mid | 10 |  |  | 1.5.2.1 |  |  | 195 | 1950
1749 | DEL-0044 | TSK-01740 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.2.1.2 | 1.5.2.1 | Analytics Audit | Audit & Requirement gathering | Analytics Audit | Data/Analytics Engineer | Mid | 10 |  |  | 1.5.2.1.1 |  |  | 195 | 1950
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.3 | 1.5 | Audit existing UA Property | Audit existing UA Property |  |  |  | 20 | 74 | 4 | 1.5.2 |  |  | 195 | 3900
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.3.1 | 1.5.3 | Documentation | Audit existing UA Property | Documentation |  |  | 0 | 74 | 4 | 1.5.3 |  |  | 0 | 0
1753 | DEL-0044 | TSK-01744 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.3.1.1 | 1.5.3.1 | Documentation | Audit existing UA Property | Documentation | Business Analyst | Mid | 10 |  |  | 1.5.3.1 |  |  | 195 | 1950
1755 | DEL-0044 | TSK-01746 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.3.1.2 | 1.5.3.1 | Documentation | Audit existing UA Property | Documentation | Data/Analytics Engineer | Mid | 10 |  |  | 1.5.3.1.1 |  |  | 195 | 1950
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.4 | 1.5 | Footer CTA | Footer CTA |  |  |  | 51 | 78 | 22 | 1.5.3 |  |  | 195 | 9945
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.4.1 | 1.5.4 | Design Consult | Footer CTA | Design Consult |  |  | 0 | 78 | 8 | 1.5.4 |  |  | 0 | 0
1765 | DEL-0044 | TSK-01756 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.4.1.1 | 1.5.4.1 | Design Consult | Footer CTA | Design Consult | UI Designer | Mid | 4 |  |  | 1.5.4.1 |  |  | 195 | 780
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.4.2 | 1.5.4 | Accessibility QA | Footer CTA | Accessibility QA |  |  | 0 | 86 | 3 | 1.5.4.1.1 |  |  | 0 | 0
1760 | DEL-0044 | TSK-01751 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.4.2.1 | 1.5.4.2 | Accessibility QA | Footer CTA | Accessibility QA | Accessibility Specialist | Mid | 2 |  |  | 1.5.4.2 |  |  | 195 | 390
1767 | DEL-0044 | TSK-01758 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.4.2.2 | 1.5.4.2 | Accessibility QA | Footer CTA | Accessibility QA | Frontend Engineer | Mid | 2 |  |  | 1.5.4.2.1 |  |  | 195 | 390
1766 | DEL-0044 | TSK-01757 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.4.2.3 | 1.5.4.2 | Accessibility QA | Footer CTA | Accessibility QA | QA Engineer | Mid | 3 |  |  | 1.5.4.2.2 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.4.3 | 1.5.4 | Code Review | Footer CTA | Code Review |  |  | 0 | 89 | 11 | 1.5.4.2.3 |  |  | 0 | 0
1761 | DEL-0044 | TSK-01752 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.4.3.1 | 1.5.4.3 | Code Review | Footer CTA | Code Review | Backend Engineer | Mid | 12 |  |  | 1.5.4.3 |  |  | 195 | 2340
1763 | DEL-0044 | TSK-01754 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.4.3.2 | 1.5.4.3 | Code Review | Footer CTA | Code Review | DevOps Engineer | Mid | 12 |  |  | 1.5.4.3.1 |  |  | 195 | 2340
1762 | DEL-0044 | TSK-01753 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.4.3.3 | 1.5.4.3 | Code Review | Footer CTA | Code Review | Frontend Engineer | Mid | 12 |  |  | 1.5.4.3.2 |  |  | 195 | 2340
1764 | DEL-0044 | TSK-01755 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.4.3.4 | 1.5.4.3 | Code Review | Footer CTA | Code Review | Project Manager | Mid | 4 |  |  | 1.5.4.3.3 |  |  | 195 | 780
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.5 | 1.5 | Header & Footer Navigation | Header & Footer Navigation |  |  |  | 51 | 78 | 22 | 1.5.4 |  |  | 195 | 9945
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.5.1 | 1.5.5 | Design Consult | Header & Footer Navigation | Design Consult |  |  | 0 | 78 | 8 | 1.5.5 |  |  | 0 | 0
1773 | DEL-0044 | TSK-01764 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.5.1.1 | 1.5.5.1 | Design Consult | Header & Footer Navigation | Design Consult | UI Designer | Mid | 4 |  |  | 1.5.5.1 |  |  | 195 | 780
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.5.2 | 1.5.5 | Accessibility QA | Header & Footer Navigation | Accessibility QA |  |  | 0 | 86 | 3 | 1.5.5.1.1 |  |  | 0 | 0
1768 | DEL-0044 | TSK-01759 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.5.2.1 | 1.5.5.2 | Accessibility QA | Header & Footer Navigation | Accessibility QA | Accessibility Specialist | Mid | 2 |  |  | 1.5.5.2 |  |  | 195 | 390
1775 | DEL-0044 | TSK-01766 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.5.2.2 | 1.5.5.2 | Accessibility QA | Header & Footer Navigation | Accessibility QA | Frontend Engineer | Mid | 2 |  |  | 1.5.5.2.1 |  |  | 195 | 390
1774 | DEL-0044 | TSK-01765 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.5.2.3 | 1.5.5.2 | Accessibility QA | Header & Footer Navigation | Accessibility QA | QA Engineer | Mid | 3 |  |  | 1.5.5.2.2 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.5.3 | 1.5.5 | Code Review | Header & Footer Navigation | Code Review |  |  | 0 | 89 | 11 | 1.5.5.2.3 |  |  | 0 | 0
1769 | DEL-0044 | TSK-01760 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.5.3.1 | 1.5.5.3 | Code Review | Header & Footer Navigation | Code Review | Backend Engineer | Mid | 12 |  |  | 1.5.5.3 |  |  | 195 | 2340
1771 | DEL-0044 | TSK-01762 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.5.3.2 | 1.5.5.3 | Code Review | Header & Footer Navigation | Code Review | DevOps Engineer | Mid | 12 |  |  | 1.5.5.3.1 |  |  | 195 | 2340
1770 | DEL-0044 | TSK-01761 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.5.3.3 | 1.5.5.3 | Code Review | Header & Footer Navigation | Code Review | Frontend Engineer | Mid | 12 |  |  | 1.5.5.3.2 |  |  | 195 | 2340
1772 | DEL-0044 | TSK-01763 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.5.3.4 | 1.5.5.3 | Code Review | Header & Footer Navigation | Code Review | Project Manager | Mid | 4 |  |  | 1.5.5.3.3 |  |  | 195 | 780
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.6 | 1.5 | Additional Goals Setup | Additional Goals Setup |  |  |  | 8 | 86 | 14 | 1.5.5 |  |  | 195 | 1560
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.6.1 | 1.5.6 | QA Cycle | Additional Goals Setup | QA Cycle |  |  | 0 | 86 | 3 | 1.5.6 |  |  | 0 | 0
1747 | DEL-0044 | TSK-01738 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.6.1.1 | 1.5.6.1 | QA Cycle | Additional Goals Setup | QA Cycle | QA Engineer | Mid | 3 |  |  | 1.5.6.1 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.6.2 | 1.5.6 | Define & Configure Goals | Additional Goals Setup | Define & Configure Goals |  |  | 0 | 89 | 11 | 1.5.6.1.1 |  |  | 0 | 0
1746 | DEL-0044 | TSK-01737 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.6.2.1 | 1.5.6.2 | Define & Configure Goals | Additional Goals Setup | Define & Configure Goals | Data/Analytics Engineer | Mid | 5 |  |  | 1.5.6.2 |  |  | 195 | 975
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.7 | 1.5 | Custom Event Tracking | Custom Event Tracking |  |  |  | 8 | 86 | 14 | 1.5.6 |  |  | 195 | 1560
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.7.1 | 1.5.7 | QA Cycle | Custom Event Tracking | QA Cycle |  |  | 0 | 86 | 3 | 1.5.7 |  |  | 0 | 0
1758 | DEL-0044 | TSK-01749 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.7.1.1 | 1.5.7.1 | QA Cycle | Custom Event Tracking | QA Cycle | QA Engineer | Mid | 3 |  |  | 1.5.7.1 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.7.2 | 1.5.7 | Event Schema & Tagging | Custom Event Tracking | Event Schema & Tagging |  |  | 0 | 89 | 11 | 1.5.7.1.1 |  |  | 0 | 0
1757 | DEL-0044 | TSK-01748 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.7.2.1 | 1.5.7.2 | Event Schema & Tagging | Custom Event Tracking | Event Schema & Tagging | Data/Analytics Engineer | Mid | 5 |  |  | 1.5.7.2 |  |  | 195 | 975
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.8 | 1.5 | Implement Paid Media Pixel on website w GTM-Google Ads | Implement Paid Media Pixel on website w GTM-Google Ads |  |  |  | 6 | 86 | 14 | 1.5.7 |  |  | 195 | 1170
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.8.1 | 1.5.8 | Spec QA | Implement Paid Media Pixel on website w GTM-Google Ads | Spec QA |  |  | 0 | 86 | 3 | 1.5.8 |  |  | 0 | 0
1777 | DEL-0044 | TSK-01768 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.8.1.1 | 1.5.8.1 | Spec QA | Implement Paid Media Pixel on website w GTM-Google Ads | Spec QA | QA Engineer | Mid | 3 |  |  | 1.5.8.1 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.8.2 | 1.5.8 | Pixel Setup (GTM) | Implement Paid Media Pixel on website w GTM-Google Ads | Pixel Setup (GTM) |  |  | 0 | 89 | 11 | 1.5.8.1.1 |  |  | 0 | 0
1776 | DEL-0044 | TSK-01767 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.8.2.1 | 1.5.8.2 | Pixel Setup (GTM) | Implement Paid Media Pixel on website w GTM-Google Ads | Pixel Setup (GTM) | Data/Analytics Engineer | Mid | 3 |  |  | 1.5.8.2 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.9 | 1.5 | Implement goals listed in UA as Conversions in G4 | Implement goals listed in UA as Conversions in G4 |  |  |  | 8 | 86 | 14 | 1.5.8 |  |  | 195 | 1560
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.9.1 | 1.5.9 | QA Cycle | Implement goals listed in UA as Conversions in G4 | QA Cycle |  |  | 0 | 86 | 3 | 1.5.9 |  |  | 0 | 0
1779 | DEL-0044 | TSK-01770 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.9.1.1 | 1.5.9.1 | QA Cycle | Implement goals listed in UA as Conversions in G4 | QA Cycle | QA Engineer | Mid | 3 |  |  | 1.5.9.1 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.9.2 | 1.5.9 | Migrate UA Goals → GA4 Conversions | Implement goals listed in UA as Conversions in G4 | Migrate UA Goals → GA4 Conversions |  |  | 0 | 89 | 11 | 1.5.9.1.1 |  |  | 0 | 0
1778 | DEL-0044 | TSK-01769 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.9.2.1 | 1.5.9.2 | Migrate UA Goals → GA4 Conversions | Implement goals listed in UA as Conversions in G4 | Migrate UA Goals → GA4 Conversions | Data/Analytics Engineer | Mid | 5 |  |  | 1.5.9.2 |  |  | 195 | 975
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.10 | 1.5 | Implementation | Implementation |  |  |  | 8 | 86 | 14 | 1.5.9 |  |  | 195 | 1560
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.10.1 | 1.5.10 | QA Cycle | Implementation | QA Cycle |  |  | 0 | 86 | 3 | 1.5.10 |  |  | 0 | 0
1782 | DEL-0044 | TSK-01773 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.10.1.1 | 1.5.10.1 | QA Cycle | Implementation | QA Cycle | QA Engineer | Mid | 3 |  |  | 1.5.10.1 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.10.2 | 1.5.10 | Implement Tags/Events | Implementation | Implement Tags/Events |  |  | 0 | 89 | 11 | 1.5.10.1.1 |  |  | 0 | 0
1781 | DEL-0044 | TSK-01772 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.10.2.1 | 1.5.10.2 | Implement Tags/Events | Implementation | Implement Tags/Events | Data/Analytics Engineer | Mid | 5 |  |  | 1.5.10.2 |  |  | 195 | 975
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.11 | 1.5 | Outbound link clicks | Outbound link clicks |  |  |  | 6 | 86 | 14 | 1.5.10 |  |  | 195 | 1170
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.11.1 | 1.5.11 | QA | Outbound link clicks | QA |  |  | 0 | 86 | 3 | 1.5.11 |  |  | 0 | 0
1785 | DEL-0044 | TSK-01776 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.11.1.1 | 1.5.11.1 | QA | Outbound link clicks | QA | QA Engineer | Mid | 3 |  |  | 1.5.11.1 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.11.2 | 1.5.11 | Event Config | Outbound link clicks | Event Config |  |  | 0 | 89 | 11 | 1.5.11.1.1 |  |  | 0 | 0
1784 | DEL-0044 | TSK-01775 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.11.2.1 | 1.5.11.2 | Event Config | Outbound link clicks | Event Config | Data/Analytics Engineer | Mid | 3 |  |  | 1.5.11.2 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.12 | 1.5 | Publishing tags, Testing and Auditing | Publishing tags, Testing and Auditing |  |  |  | 5 | 86 | 3 | 1.5.11 |  |  | 195 | 975
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.12.1 | 1.5.12 | Publish & Smoke Test | Publishing tags, Testing and Auditing | Publish & Smoke Test |  |  | 0 | 86 | 3 | 1.5.12 |  |  | 0 | 0
1786 | DEL-0044 | TSK-01777 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.12.1.1 | 1.5.12.1 | Publish & Smoke Test | Publishing tags, Testing and Auditing | Publish & Smoke Test | Data/Analytics Engineer | Mid | 2 |  |  | 1.5.12.1 |  |  | 195 | 390
1787 | DEL-0044 | TSK-01778 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.12.1.2 | 1.5.12.1 | Publish & Smoke Test | Publishing tags, Testing and Auditing | Publish & Smoke Test | QA Engineer | Mid | 3 |  |  | 1.5.12.1.1 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.13 | 1.5 | Setup cross-domain tracking | Setup cross-domain tracking |  |  |  | 5 | 86 | 14 | 1.5.12 |  |  | 195 | 975
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.13.1 | 1.5.13 | QA | Setup cross-domain tracking | QA |  |  | 0 | 86 | 3 | 1.5.13 |  |  | 0 | 0
1789 | DEL-0044 | TSK-01780 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.13.1.1 | 1.5.13.1 | QA | Setup cross-domain tracking | QA | QA Engineer | Mid | 3 |  |  | 1.5.13.1 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.13.2 | 1.5.13 | Cross-domain Config | Setup cross-domain tracking | Cross-domain Config |  |  | 0 | 89 | 11 | 1.5.13.1.1 |  |  | 0 | 0
1788 | DEL-0044 | TSK-01779 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.13.2.1 | 1.5.13.2 | Cross-domain Config | Setup cross-domain tracking | Cross-domain Config | Data/Analytics Engineer | Mid | 2 |  |  | 1.5.13.2 |  |  | 195 | 390
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.14 | 1.5 | Setup eCommerce tracking | Setup eCommerce tracking |  |  |  | 5 | 86 | 14 | 1.5.13 |  |  | 195 | 975
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.14.1 | 1.5.14 | QA | Setup eCommerce tracking | QA |  |  | 0 | 86 | 3 | 1.5.14 |  |  | 0 | 0
1791 | DEL-0044 | TSK-01782 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.14.1.1 | 1.5.14.1 | QA | Setup eCommerce tracking | QA | QA Engineer | Mid | 3 |  |  | 1.5.14.1 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.14.2 | 1.5.14 | Ecommerce Data Layer | Setup eCommerce tracking | Ecommerce Data Layer |  |  | 0 | 89 | 11 | 1.5.14.1.1 |  |  | 0 | 0
1790 | DEL-0044 | TSK-01781 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.14.2.1 | 1.5.14.2 | Ecommerce Data Layer | Setup eCommerce tracking | Ecommerce Data Layer | Data/Analytics Engineer | Mid | 2 |  |  | 1.5.14.2 |  |  | 195 | 390
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.15 | 1.5 | Setup new GA4 acct for Caledera House | Setup new GA4 acct for Caledera House |  |  |  | 8 | 86 | 14 | 1.5.14 |  |  | 195 | 1560
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.15.1 | 1.5.15 | QA Cycle | Setup new GA4 acct for Caledera House | QA Cycle |  |  | 0 | 86 | 3 | 1.5.15 |  |  | 0 | 0
1793 | DEL-0044 | TSK-01784 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.15.1.1 | 1.5.15.1 | QA Cycle | Setup new GA4 acct for Caledera House | QA Cycle | QA Engineer | Mid | 3 |  |  | 1.5.15.1 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.15.2 | 1.5.15 | GA4 Property Setup | Setup new GA4 acct for Caledera House | GA4 Property Setup |  |  | 0 | 89 | 11 | 1.5.15.1.1 |  |  | 0 | 0
1792 | DEL-0044 | TSK-01783 | Technology | Development | Casa-Dragones-Digital-MKT-RFP | 1.5.15.2.1 | 1.5.15.2 | GA4 Property Setup | Setup new GA4 acct for Caledera House | GA4 Property Setup | Data/Analytics Engineer | Mid | 5 |  |  | 1.5.15.2 |  |  | 195 | 975
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6 | 1 | Post-Production |  |  |  |  | 222 | 100 | 50 | 1.5 |  | Advanced/T2_MediumVolume | 195 | 43290
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.1 | 1.6 | Content Licensing / Art Buying | Content Licensing / Art Buying |  |  |  | 2 | 100 | 4 | 1.6 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.1.1 | 1.6.1 | Rights/License Research | Content Licensing / Art Buying | Rights/License Research |  |  | 0 | 100 | 4 | 1.6.1 |  |  | 0 | 0
65 | DEL-0003 | TSK-00065 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.1.1.1 | 1.6.1.1 | Rights/License Research | Content Licensing / Art Buying | Rights/License Research | Producer | Mid | 1 |  |  | 1.6.1.1 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.1.2 | 1.6.1 | Usage Notes | Content Licensing / Art Buying | Usage Notes |  |  | 0 | 150 | 0 | 1.6.1.1.1 |  |  | 0 | 0
66 | DEL-0003 | TSK-00066 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.1.2.1 | 1.6.1.2 | Usage Notes | Content Licensing / Art Buying | Usage Notes | Account Manager | Mid | 1 |  |  | 1.6.1.2 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.2 | 1.6 | VO Recording Sessions | VO Recording Sessions |  |  |  | 6 | 104 | 5 | 1.6.1 |  |  | 195 | 1170
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.2.1 | 1.6.2 | Script Polish | VO Recording Sessions | Script Polish |  |  | 0 | 104 | 5 | 1.6.2 |  |  | 0 | 0
124 | DEL-0003 | TSK-00124 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.2.1.1 | 1.6.2.1 | Script Polish | VO Recording Sessions | Script Polish | Copywriter | Mid | 2 |  |  | 1.6.2.1 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.2.2 | 1.6.2 | VO Session | VO Recording Sessions | VO Session |  |  | 0 | 150 | 0 | 1.6.2.1.1 |  |  | 0 | 0
125 | DEL-0003 | TSK-00125 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.2.2.1 | 1.6.2.2 | VO Session | VO Recording Sessions | VO Session | Producer | Mid | 2 |  |  | 1.6.2.2 |  |  | 195 | 390
126 | DEL-0003 | TSK-00126 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.2.2.2 | 1.6.2.2 | VO Session | VO Recording Sessions | VO Session | Sound Designer | Mid | 2 |  |  | 1.6.2.2.1 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.3 | 1.6 | Editing | Editing |  |  |  | 20 | 109 | 6 | 1.6.2 |  |  | 195 | 3900
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.3.1 | 1.6.3 | Client Review & Revisions | Editing | Client Review & Revisions |  |  | 0 | 109 | 6 | 1.6.3 |  |  | 0 | 0
74 | DEL-0003 | TSK-00074 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.3.1.1 | 1.6.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.6.3.1 |  |  | 195 | 390
77 | DEL-0003 | TSK-00077 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.3.1.2 | 1.6.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.6.3.1.1 |  |  | 195 | 390
76 | DEL-0003 | TSK-00076 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.3.1.3 | 1.6.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.6.3.1.2 |  |  | 195 | 390
79 | DEL-0003 | TSK-00079 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.3.1.4 | 1.6.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Editor | Mid | 10 |  |  | 1.6.3.1.3 |  |  | 195 | 1950
75 | DEL-0003 | TSK-00075 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.3.1.5 | 1.6.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Producer | Mid | 4 |  |  | 1.6.3.1.4 |  |  | 195 | 780
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.4 | 1.6 | Video Editing | Video Editing |  |  |  | 30 | 109 | 6 | 1.6.3 |  |  | 195 | 5850
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.4.1 | 1.6.4 | Client Review & Revisions | Video Editing | Client Review & Revisions |  |  | 0 | 109 | 6 | 1.6.4 |  |  | 0 | 0
127 | DEL-0003 | TSK-00127 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.4.1.1 | 1.6.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.6.4.1 |  |  | 195 | 390
131 | DEL-0003 | TSK-00131 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.4.1.2 | 1.6.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.6.4.1.1 |  |  | 195 | 390
129 | DEL-0003 | TSK-00129 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.4.1.3 | 1.6.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.6.4.1.2 |  |  | 195 | 390
130 | DEL-0003 | TSK-00130 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.4.1.4 | 1.6.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Editor | Mid | 20 |  |  | 1.6.4.1.3 |  |  | 195 | 3900
128 | DEL-0003 | TSK-00128 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.4.1.5 | 1.6.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Producer | Mid | 4 |  |  | 1.6.4.1.4 |  |  | 195 | 780
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.5 | 1.6 | Voice Over | Voice Over |  |  |  | 20 | 109 | 14 | 1.6.4 |  |  | 195 | 3900
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.5.1 | 1.6.5 | VO Edit | Voice Over | VO Edit |  |  | 0 | 109 | 6 | 1.6.5 |  |  | 0 | 0
140 | DEL-0003 | TSK-00140 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.5.1.1 | 1.6.5.1 | VO Edit | Voice Over | VO Edit | Editor | Mid | 10 |  |  | 1.6.5.1 |  |  | 195 | 1950
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.5.2 | 1.6.5 | Mix | Voice Over | Mix |  |  | 0 | 130 | 3 | 1.6.5.1.1 |  |  | 0 | 0
139 | DEL-0003 | TSK-00139 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.5.2.1 | 1.6.5.2 | Mix | Voice Over | Mix | Sound Designer | Mid | 3 |  |  | 1.6.5.2 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.5.3 | 1.6.5 | Internal Review & Critique | Voice Over | Internal Review & Critique |  |  | 0 | 140 | 2 | 1.6.5.2.1 |  |  | 0 | 0
137 | DEL-0003 | TSK-00137 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.5.3.1 | 1.6.5.3 | Internal Review & Critique | Voice Over | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.6.5.3 |  |  | 195 | 195
138 | DEL-0003 | TSK-00138 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.5.3.2 | 1.6.5.3 | Internal Review & Critique | Voice Over | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.6.5.3.1 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.5.4 | 1.6.5 | Client Review & Revisions | Voice Over | Client Review & Revisions |  |  | 0 | 142 | 3 | 1.6.5.3.2 |  |  | 0 | 0
134 | DEL-0003 | TSK-00134 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.5.4.1 | 1.6.5.4 | Client Review & Revisions | Voice Over | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.6.5.4 |  |  | 195 | 390
135 | DEL-0003 | TSK-00135 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.5.4.2 | 1.6.5.4 | Client Review & Revisions | Voice Over | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.6.5.4.1 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.5.5 | 1.6.5 | Final Packaging | Voice Over | Final Packaging |  |  | 0 | 150 | 0 | 1.6.5.4.2 |  |  | 0 | 0
136 | DEL-0003 | TSK-00136 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.5.5.1 | 1.6.5.5 | Final Packaging | Voice Over | Final Packaging | Designer | Mid | 2 |  |  | 1.6.5.5 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.6 | 1.6 | Motion Design/VFX | Motion Design/VFX |  |  |  | 20 | 115 | 8 | 1.6.5 |  |  | 195 | 3900
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.6.1 | 1.6.6 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions |  |  | 0 | 115 | 8 | 1.6.6 |  |  | 0 | 0
90 | DEL-0003 | TSK-00090 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.6.1.1 | 1.6.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.6.6.1 |  |  | 195 | 390
94 | DEL-0003 | TSK-00094 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.6.1.2 | 1.6.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.6.6.1.1 |  |  | 195 | 390
92 | DEL-0003 | TSK-00092 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.6.1.3 | 1.6.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.6.6.1.2 |  |  | 195 | 585
96 | DEL-0003 | TSK-00096 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.6.1.4 | 1.6.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Editor | Mid | 6 |  |  | 1.6.6.1.3 |  |  | 195 | 1170
93 | DEL-0003 | TSK-00093 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.6.1.5 | 1.6.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Motion Designer | Mid | 3 |  |  | 1.6.6.1.4 |  |  | 195 | 585
91 | DEL-0003 | TSK-00091 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.6.1.6 | 1.6.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Producer | Mid | 4 |  |  | 1.6.6.1.5 |  |  | 195 | 780
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.7 | 1.6 | Color Correction | Color Correction |  |  |  | 14 | 123 | 3 | 1.6.6 |  |  | 195 | 2730
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.7.1 | 1.6.7 | Client Review & Revisions | Color Correction | Client Review & Revisions |  |  | 0 | 123 | 3 | 1.6.7 |  |  | 0 | 0
53 | DEL-0003 | TSK-00053 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.7.1.1 | 1.6.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.6.7.1 |  |  | 195 | 195
55 | DEL-0003 | TSK-00055 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.7.1.2 | 1.6.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Colorist | Mid | 6 |  |  | 1.6.7.1.1 |  |  | 195 | 1170
57 | DEL-0003 | TSK-00057 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.7.1.3 | 1.6.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.6.7.1.2 |  |  | 195 | 390
56 | DEL-0003 | TSK-00056 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.7.1.4 | 1.6.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.6.7.1.3 |  |  | 195 | 585
54 | DEL-0003 | TSK-00054 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.7.1.5 | 1.6.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.6.7.1.4 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.8 | 1.6 | Color Grading | Color Grading |  |  |  | 14 | 123 | 3 | 1.6.7 |  |  | 195 | 2730
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.8.1 | 1.6.8 | Client Review & Revisions | Color Grading | Client Review & Revisions |  |  | 0 | 123 | 3 | 1.6.8 |  |  | 0 | 0
59 | DEL-0003 | TSK-00059 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.8.1.1 | 1.6.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.6.8.1 |  |  | 195 | 195
61 | DEL-0003 | TSK-00061 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.8.1.2 | 1.6.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Colorist | Mid | 6 |  |  | 1.6.8.1.1 |  |  | 195 | 1170
63 | DEL-0003 | TSK-00063 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.8.1.3 | 1.6.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.6.8.1.2 |  |  | 195 | 390
62 | DEL-0003 | TSK-00062 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.8.1.4 | 1.6.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.6.8.1.3 |  |  | 195 | 585
60 | DEL-0003 | TSK-00060 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.8.1.5 | 1.6.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.6.8.1.4 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.9 | 1.6 | Final Retouched Stills Review | Final Retouched Stills Review |  |  |  | 12 | 126 | 9 | 1.6.8 |  |  | 195 | 2340
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.9.1 | 1.6.9 | Retouch | Final Retouched Stills Review | Retouch |  |  | 0 | 126 | 4 | 1.6.9 |  |  | 0 | 0
89 | DEL-0003 | TSK-00089 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.9.1.1 | 1.6.9.1 | Retouch | Final Retouched Stills Review | Retouch | Retoucher | Mid | 5 |  |  | 1.6.9.1 |  |  | 195 | 975
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.9.2 | 1.6.9 | Internal Review & Critique | Final Retouched Stills Review | Internal Review & Critique |  |  | 0 | 140 | 2 | 1.6.9.1.1 |  |  | 0 | 0
87 | DEL-0003 | TSK-00087 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.9.2.1 | 1.6.9.2 | Internal Review & Critique | Final Retouched Stills Review | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.6.9.2 |  |  | 195 | 195
88 | DEL-0003 | TSK-00088 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.9.2.2 | 1.6.9.2 | Internal Review & Critique | Final Retouched Stills Review | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.6.9.2.1 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.9.3 | 1.6.9 | Client Review & Revisions | Final Retouched Stills Review | Client Review & Revisions |  |  | 0 | 142 | 3 | 1.6.9.2.2 |  |  | 0 | 0
84 | DEL-0003 | TSK-00084 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.9.3.1 | 1.6.9.3 | Client Review & Revisions | Final Retouched Stills Review | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.6.9.3 |  |  | 195 | 390
85 | DEL-0003 | TSK-00085 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.9.3.2 | 1.6.9.3 | Client Review & Revisions | Final Retouched Stills Review | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.6.9.3.1 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.9.4 | 1.6.9 | Final Packaging | Final Retouched Stills Review | Final Packaging |  |  | 0 | 150 | 0 | 1.6.9.3.2 |  |  | 0 | 0
86 | DEL-0003 | TSK-00086 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.9.4.1 | 1.6.9.4 | Final Packaging | Final Retouched Stills Review | Final Packaging | Designer | Mid | 2 |  |  | 1.6.9.4 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.10 | 1.6 | Retouching | Retouching |  |  |  | 12 | 126 | 9 | 1.6.9 |  |  | 195 | 2340
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.10.1 | 1.6.10 | Retouch | Retouching | Retouch |  |  | 0 | 126 | 4 | 1.6.10 |  |  | 0 | 0
102 | DEL-0003 | TSK-00102 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.10.1.1 | 1.6.10.1 | Retouch | Retouching | Retouch | Retoucher | Mid | 5 |  |  | 1.6.10.1 |  |  | 195 | 975
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.10.2 | 1.6.10 | Internal Review & Critique | Retouching | Internal Review & Critique |  |  | 0 | 140 | 2 | 1.6.10.1.1 |  |  | 0 | 0
100 | DEL-0003 | TSK-00100 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.10.2.1 | 1.6.10.2 | Internal Review & Critique | Retouching | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.6.10.2 |  |  | 195 | 195
101 | DEL-0003 | TSK-00101 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.10.2.2 | 1.6.10.2 | Internal Review & Critique | Retouching | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.6.10.2.1 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.10.3 | 1.6.10 | Client Review & Revisions | Retouching | Client Review & Revisions |  |  | 0 | 142 | 3 | 1.6.10.2.2 |  |  | 0 | 0
97 | DEL-0003 | TSK-00097 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.10.3.1 | 1.6.10.3 | Client Review & Revisions | Retouching | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.6.10.3 |  |  | 195 | 390
98 | DEL-0003 | TSK-00098 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.10.3.2 | 1.6.10.3 | Client Review & Revisions | Retouching | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.6.10.3.1 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.10.4 | 1.6.10 | Final Packaging | Retouching | Final Packaging |  |  | 0 | 150 | 0 | 1.6.10.3.2 |  |  | 0 | 0
99 | DEL-0003 | TSK-00099 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.10.4.1 | 1.6.10.4 | Final Packaging | Retouching | Final Packaging | Designer | Mid | 2 |  |  | 1.6.10.4 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.11 | 1.6 | Sound Mix | Sound Mix |  |  |  | 10 | 130 | 3 | 1.6.10 |  |  | 195 | 1950
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.11.1 | 1.6.11 | Client Review & Revisions | Sound Mix | Client Review & Revisions |  |  | 0 | 130 | 3 | 1.6.11 |  |  | 0 | 0
107 | DEL-0003 | TSK-00107 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.11.1.1 | 1.6.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.6.11.1 |  |  | 195 | 195
110 | DEL-0003 | TSK-00110 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.11.1.2 | 1.6.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.6.11.1.1 |  |  | 195 | 390
109 | DEL-0003 | TSK-00109 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.11.1.3 | 1.6.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.6.11.1.2 |  |  | 195 | 585
108 | DEL-0003 | TSK-00108 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.11.1.4 | 1.6.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.6.11.1.3 |  |  | 195 | 390
112 | DEL-0003 | TSK-00112 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.11.1.5 | 1.6.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Sound Designer | Mid | 2 |  |  | 1.6.11.1.4 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.12 | 1.6 | Sound Sourcing | Sound Sourcing |  |  |  | 3 | 130 | 3 | 1.6.11 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.12.1 | 1.6.12 | Music Search & License | Sound Sourcing | Music Search & License |  |  | 0 | 130 | 3 | 1.6.12 |  |  | 0 | 0
113 | DEL-0003 | TSK-00113 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.12.1.1 | 1.6.12.1 | Music Search & License | Sound Sourcing | Music Search & License | Producer | Mid | 1 |  |  | 1.6.12.1 |  |  | 195 | 195
114 | DEL-0003 | TSK-00114 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.12.1.2 | 1.6.12.1 | Music Search & License | Sound Sourcing | Music Search & License | Sound Designer | Mid | 2 |  |  | 1.6.12.1.1 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.13 | 1.6 | Final File Delivery | Final File Delivery |  |  |  | 8 | 133 | 3 | 1.6.12 |  |  | 195 | 1560
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.13.1 | 1.6.13 | QA (Tech & Content) | Final File Delivery | QA (Tech & Content) |  |  | 0 | 133 | 3 | 1.6.13 |  |  | 0 | 0
83 | DEL-0003 | TSK-00083 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.13.1.1 | 1.6.13.1 | QA (Tech & Content) | Final File Delivery | QA (Tech & Content) | QA Specialist | Mid | 3 |  |  | 1.6.13.1 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.13.2 | 1.6.13 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload |  |  | 0 | 150 | 0 | 1.6.13.1.1 |  |  | 0 | 0
80 | DEL-0003 | TSK-00080 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.13.2.1 | 1.6.13.2 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload | Media Manager / DIT | Mid | 2 |  |  | 1.6.13.2 |  |  | 195 | 390
81 | DEL-0003 | TSK-00081 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.13.2.2 | 1.6.13.2 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload | Producer | Mid | 2 |  |  | 1.6.13.2.1 |  |  | 195 | 390
82 | DEL-0003 | TSK-00082 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.13.2.3 | 1.6.13.2 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload | Project Manager | Mid | 1 |  |  | 1.6.13.2.2 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.14 | 1.6 | True-ups (for vendor costs) | True-ups (for vendor costs) |  |  |  | 11 | 136 | 9 | 1.6.13 |  |  | 195 | 2145
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.14.1 | 1.6.14 | Change Orders & Tracking | True-ups (for vendor costs) | Change Orders & Tracking |  |  | 0 | 136 | 4 | 1.6.14 |  |  | 0 | 0
116 | DEL-0003 | TSK-00116 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.14.1.1 | 1.6.14.1 | Change Orders & Tracking | True-ups (for vendor costs) | Change Orders & Tracking | Project Manager | Mid | 1 |  |  | 1.6.14.1 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.14.2 | 1.6.14 | Internal Review & Critique | True-ups (for vendor costs) | Internal Review & Critique |  |  | 0 | 140 | 2 | 1.6.14.1.1 |  |  | 0 | 0
120 | DEL-0003 | TSK-00120 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.14.2.1 | 1.6.14.2 | Internal Review & Critique | True-ups (for vendor costs) | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.6.14.2 |  |  | 195 | 195
121 | DEL-0003 | TSK-00121 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.14.2.2 | 1.6.14.2 | Internal Review & Critique | True-ups (for vendor costs) | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.6.14.2.1 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.14.3 | 1.6.14 | Client Review & Revisions | True-ups (for vendor costs) | Client Review & Revisions |  |  | 0 | 142 | 3 | 1.6.14.2.2 |  |  | 0 | 0
117 | DEL-0003 | TSK-00117 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.14.3.1 | 1.6.14.3 | Client Review & Revisions | True-ups (for vendor costs) | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.6.14.3 |  |  | 195 | 390
118 | DEL-0003 | TSK-00118 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.14.3.2 | 1.6.14.3 | Client Review & Revisions | True-ups (for vendor costs) | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.6.14.3.1 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.14.4 | 1.6.14 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation |  |  | 0 | 150 | 0 | 1.6.14.3.2 |  |  | 0 | 0
122 | DEL-0003 | TSK-00122 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.14.4.1 | 1.6.14.4 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation | Account Manager | Mid | 2 |  |  | 1.6.14.4 |  |  | 195 | 390
119 | DEL-0003 | TSK-00119 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.14.4.2 | 1.6.14.4 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation | Designer | Mid | 2 |  |  | 1.6.14.4.1 |  |  | 195 | 390
123 | DEL-0003 | TSK-00123 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.14.4.3 | 1.6.14.4 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation | Producer | Mid | 1 |  |  | 1.6.14.4.2 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.15 | 1.6 | Cutdowns | Cutdowns |  |  |  | 13 | 140 | 5 | 1.6.14 |  |  | 195 | 2535
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.15.1 | 1.6.15 | Internal Review & Critique | Cutdowns | Internal Review & Critique |  |  | 0 | 140 | 2 | 1.6.15 |  |  | 0 | 0
71 | DEL-0003 | TSK-00071 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.15.1.1 | 1.6.15.1 | Internal Review & Critique | Cutdowns | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.6.15.1 |  |  | 195 | 195
72 | DEL-0003 | TSK-00072 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.15.1.2 | 1.6.15.1 | Internal Review & Critique | Cutdowns | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.6.15.1.1 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.15.2 | 1.6.15 | Client Review & Revisions | Cutdowns | Client Review & Revisions |  |  | 0 | 142 | 3 | 1.6.15.1.2 |  |  | 0 | 0
67 | DEL-0003 | TSK-00067 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.15.2.1 | 1.6.15.2 | Client Review & Revisions | Cutdowns | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.6.15.2 |  |  | 195 | 390
68 | DEL-0003 | TSK-00068 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.15.2.2 | 1.6.15.2 | Client Review & Revisions | Cutdowns | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.6.15.2.1 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.15.3 | 1.6.15 | Cutdowns (2-3) | Cutdowns | Cutdowns (2-3) |  |  | 0 | 150 | 0 | 1.6.15.2.2 |  |  | 0 | 0
70 | DEL-0003 | TSK-00070 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.15.3.1 | 1.6.15.3 | Cutdowns (2-3) | Cutdowns | Cutdowns (2-3) | Designer | Mid | 2 |  |  | 1.6.15.3 |  |  | 195 | 390
69 | DEL-0003 | TSK-00069 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.15.3.2 | 1.6.15.3 | Cutdowns (2-3) | Cutdowns | Cutdowns (2-3) | Editor | Mid | 6 |  |  | 1.6.15.3.1 |  |  | 195 | 1170
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.16 | 1.6 | Client Review | Client Review |  |  |  | 5 | 142 | 3 | 1.6.15 |  |  | 195 | 975
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.16.1 | 1.6.16 | Client Review Coordination | Client Review | Client Review Coordination |  |  | 0 | 142 | 3 | 1.6.16 |  |  | 0 | 0
50 | DEL-0003 | TSK-00050 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.16.1.1 | 1.6.16.1 | Client Review Coordination | Client Review | Client Review Coordination | Account Manager | Mid | 2 |  |  | 1.6.16.1 |  |  | 195 | 390
51 | DEL-0003 | TSK-00051 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.16.1.2 | 1.6.16.1 | Client Review Coordination | Client Review | Client Review Coordination | Producer | Mid | 2 |  |  | 1.6.16.1.1 |  |  | 195 | 390
52 | DEL-0003 | TSK-00052 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.16.1.3 | 1.6.16.1 | Client Review Coordination | Client Review | Client Review Coordination | Project Manager | Mid | 1 |  |  | 1.6.16.1.2 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.17 | 1.6 | Review & Sign-Off | Review & Sign-Off |  |  |  | 4 | 142 | 5 | 1.6.16 |  |  | 195 | 780
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.17.1 | 1.6.17 | Client Review Coordination | Review & Sign-Off | Client Review Coordination |  |  | 0 | 142 | 3 | 1.6.17 |  |  | 0 | 0
103 | DEL-0003 | TSK-00103 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.17.1.1 | 1.6.17.1 | Client Review Coordination | Review & Sign-Off | Client Review Coordination | Account Manager | Mid | 2 |  |  | 1.6.17.1 |  |  | 195 | 390
104 | DEL-0003 | TSK-00104 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.17.1.2 | 1.6.17.1 | Client Review Coordination | Review & Sign-Off | Client Review Coordination | Producer | Mid | 1 |  |  | 1.6.17.1.1 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.17.2 | 1.6.17 | Notes Triage | Review & Sign-Off | Notes Triage |  |  | 0 | 148 | 2 | 1.6.17.1.2 |  |  | 0 | 0
105 | DEL-0003 | TSK-00105 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.17.2.1 | 1.6.17.2 | Notes Triage | Review & Sign-Off | Notes Triage | Project Manager | Mid | 1 |  |  | 1.6.17.2 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.18 | 1.6 | Asset Library | Asset Library |  |  |  | 2 | 145 | 3 | 1.6.17 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.18.1 | 1.6.18 | Post Support | Asset Library | Post Support |  |  | 0 | 145 | 3 | 1.6.18 |  |  | 0 | 0
48 | DEL-0003 | TSK-00048 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.18.1.1 | 1.6.18.1 | Post Support | Asset Library | Post Support | Editor | Mid | 2 |  |  | 1.6.18.1 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.19 | 1.6 | Capture Library | Capture Library |  |  |  | 2 | 145 | 3 | 1.6.18 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.19.1 | 1.6.19 | Post Support | Capture Library | Post Support |  |  | 0 | 145 | 3 | 1.6.19 |  |  | 0 | 0
49 | DEL-0003 | TSK-00049 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.19.1.1 | 1.6.19.1 | Post Support | Capture Library | Post Support | Editor | Mid | 2 |  |  | 1.6.19.1 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.20 | 1.6 | Selects Deck | Selects Deck |  |  |  | 2 | 145 | 3 | 1.6.19 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.20.1 | 1.6.20 | Post Support | Selects Deck | Post Support |  |  | 0 | 145 | 3 | 1.6.20 |  |  | 0 | 0
106 | DEL-0003 | TSK-00106 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.20.1.1 | 1.6.20.1 | Post Support | Selects Deck | Post Support | Editor | Mid | 2 |  |  | 1.6.20.1 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.21 | 1.6 | Delivery | Delivery |  |  |  | 6 | 150 | 0 | 1.6.20 |  |  | 195 | 1170
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.21.1 | 1.6.21 | Post Support | Delivery | Post Support |  |  | 0 | 150 | 0 | 1.6.21 |  |  | 0 | 0
73 | DEL-0003 | TSK-00073 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.21.1.1 | 1.6.21.1 | Post Support | Delivery | Post Support | Editor | Mid | 6 |  |  | 1.6.21.1 |  |  | 195 | 1170
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.22 | 1.6 | Stills/Footage Selection | Stills/Footage Selection |  |  |  | 6 | 150 | 0 | 1.6.21 |  |  | 195 | 1170
| DEL-0003 |  | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.22.1 | 1.6.22 | Post Support | Stills/Footage Selection | Post Support |  |  | 0 | 150 | 0 | 1.6.22 |  |  | 0 | 0
115 | DEL-0003 | TSK-00115 | Content | Post-Production | Casa-Dragones-Digital-MKT-RFP | 1.6.22.1.1 | 1.6.22.1 | Post Support | Stills/Footage Selection | Post Support | Editor | Mid | 6 |  |  | 1.6.22.1 |  |  | 195 | 1170