## Scenario A
Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Deliverable | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes
RFP_154542403_Digital_Marketing_Services | 1 |  | RFP_154542403_Digital_Marketing_Services |  | Project |  |  |  |  | 0
RFP_154542403_Digital_Marketing_Services | 1.1 | 1 | Development | Development |  |  |  |  | 227 | 0 | 22 |  |  | Core/T2_MediumVolume
RFP_154542403_Digital_Marketing_Services | 1.1.1 | 1.1 | ADA Compliance | Development | ADA Compliance |  |  |  | 50 | 0 | 15 | 1.1
RFP_154542403_Digital_Marketing_Services | 1.1.1.1 | 1.1.1 | Accessibility Audit | Development | ADA Compliance | Accessibility Audit | Accessibility Specialist | Mid | 2 | 0 | 3 | 1.1.1
RFP_154542403_Digital_Marketing_Services | 1.1.1.2 | 1.1.1 | Accessibility QA | Development | ADA Compliance | Accessibility QA | QA Engineer | Mid | 4 | 10 | 2 | 1.1.1.1
RFP_154542403_Digital_Marketing_Services | 1.1.1.3 | 1.1.1 | Code Review | Development | ADA Compliance | Code Review | Frontend Engineer | Mid | 44 | 12 | 10 | 1.1.1.2
RFP_154542403_Digital_Marketing_Services | 1.1.2 | 1.1 | Audit & Requirement gathering | Development | Audit & Requirement gathering |  |  |  | 17 | 0 | 3 | 1.1.1
RFP_154542403_Digital_Marketing_Services | 1.1.2.1 | 1.1.2 | Analytics Audit | Development | Audit & Requirement gathering | Analytics Audit | Business Analyst | Mid | 17 | 0 | 3 | 1.1.2
RFP_154542403_Digital_Marketing_Services | 1.1.3 | 1.1 | Audit existing UA Property | Development | Audit existing UA Property |  |  |  | 17 | 0 | 3 | 1.1.2
RFP_154542403_Digital_Marketing_Services | 1.1.3.1 | 1.1.3 | Documentation | Development | Audit existing UA Property | Documentation | Business Analyst | Mid | 17 | 0 | 3 | 1.1.3
RFP_154542403_Digital_Marketing_Services | 1.1.4 | 1.1 | Footer CTA | Development | Footer CTA |  |  |  | 43 | 3 | 19 | 1.1.3
RFP_154542403_Digital_Marketing_Services | 1.1.4.1 | 1.1.4 | Design Consult | Development | Footer CTA | Design Consult | UI Designer | Mid | 3 | 3 | 7 | 1.1.4
RFP_154542403_Digital_Marketing_Services | 1.1.4.2 | 1.1.4 | Accessibility QA | Development | Footer CTA | Accessibility QA | QA Engineer | Mid | 6 | 10 | 2 | 1.1.4.1
RFP_154542403_Digital_Marketing_Services | 1.1.4.3 | 1.1.4 | Code Review | Development | Footer CTA | Code Review | Backend Engineer | Mid | 34 | 12 | 10 | 1.1.4.2
RFP_154542403_Digital_Marketing_Services | 1.1.5 | 1.1 | Header & Footer Navigation | Development | Header & Footer Navigation |  |  |  | 43 | 3 | 19 | 1.1.4
RFP_154542403_Digital_Marketing_Services | 1.1.5.1 | 1.1.5 | Design Consult | Development | Header & Footer Navigation | Design Consult | UI Designer | Mid | 3 | 3 | 7 | 1.1.5
RFP_154542403_Digital_Marketing_Services | 1.1.5.2 | 1.1.5 | Accessibility QA | Development | Header & Footer Navigation | Accessibility QA | QA Engineer | Mid | 6 | 10 | 2 | 1.1.5.1
RFP_154542403_Digital_Marketing_Services | 1.1.5.3 | 1.1.5 | Code Review | Development | Header & Footer Navigation | Code Review | Backend Engineer | Mid | 34 | 12 | 10 | 1.1.5.2
RFP_154542403_Digital_Marketing_Services | 1.1.6 | 1.1 | Additional Goals Setup | Development | Additional Goals Setup |  |  |  | 7 | 10 | 12 | 1.1.5
RFP_154542403_Digital_Marketing_Services | 1.1.6.1 | 1.1.6 | QA Cycle | Development | Additional Goals Setup | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.6
RFP_154542403_Digital_Marketing_Services | 1.1.6.2 | 1.1.6 | Define & Configure Goals | Development | Additional Goals Setup | Define & Configure Goals | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.6.1
RFP_154542403_Digital_Marketing_Services | 1.1.7 | 1.1 | Custom Event Tracking | Development | Custom Event Tracking |  |  |  | 7 | 10 | 12 | 1.1.6
RFP_154542403_Digital_Marketing_Services | 1.1.7.1 | 1.1.7 | QA Cycle | Development | Custom Event Tracking | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.7
RFP_154542403_Digital_Marketing_Services | 1.1.7.2 | 1.1.7 | Event Schema & Tagging | Development | Custom Event Tracking | Event Schema & Tagging | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.7.1
RFP_154542403_Digital_Marketing_Services | 1.1.8 | 1.1 | Implement Paid Media Pixel on website w GTM-Google Ads | Development | Implement Paid Media Pixel on website w GTM-Google Ads |  |  |  | 5 | 10 | 12 | 1.1.7
RFP_154542403_Digital_Marketing_Services | 1.1.8.1 | 1.1.8 | Spec QA | Development | Implement Paid Media Pixel on website w GTM-Google Ads | Spec QA | QA Engineer | Mid | 3 | 10 | 2 | 1.1.8
RFP_154542403_Digital_Marketing_Services | 1.1.8.2 | 1.1.8 | Pixel Setup (GTM) | Development | Implement Paid Media Pixel on website w GTM-Google Ads | Pixel Setup (GTM) | Data/Analytics Engineer | Mid | 2 | 12 | 10 | 1.1.8.1
RFP_154542403_Digital_Marketing_Services | 1.1.9 | 1.1 | Implement goals listed in UA as Conversions in G4 | Development | Implement goals listed in UA as Conversions in G4 |  |  |  | 7 | 10 | 12 | 1.1.8
RFP_154542403_Digital_Marketing_Services | 1.1.9.1 | 1.1.9 | QA Cycle | Development | Implement goals listed in UA as Conversions in G4 | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.9
RFP_154542403_Digital_Marketing_Services | 1.1.9.2 | 1.1.9 | Migrate UA Goals → GA4 Conversions | Development | Implement goals listed in UA as Conversions in G4 | Migrate UA Goals → GA4 Conversions | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.9.1
RFP_154542403_Digital_Marketing_Services | 1.1.10 | 1.1 | Implementation | Development | Implementation |  |  |  | 7 | 10 | 12 | 1.1.9
RFP_154542403_Digital_Marketing_Services | 1.1.10.1 | 1.1.10 | QA Cycle | Development | Implementation | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.10
RFP_154542403_Digital_Marketing_Services | 1.1.10.2 | 1.1.10 | Implement Tags/Events | Development | Implementation | Implement Tags/Events | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.10.1
RFP_154542403_Digital_Marketing_Services | 1.1.11 | 1.1 | Outbound link clicks | Development | Outbound link clicks |  |  |  | 5 | 10 | 12 | 1.1.10
RFP_154542403_Digital_Marketing_Services | 1.1.11.1 | 1.1.11 | QA | Development | Outbound link clicks | QA | QA Engineer | Mid | 3 | 10 | 2 | 1.1.11
RFP_154542403_Digital_Marketing_Services | 1.1.11.2 | 1.1.11 | Event Config | Development | Outbound link clicks | Event Config | Data/Analytics Engineer | Mid | 2 | 12 | 10 | 1.1.11.1
RFP_154542403_Digital_Marketing_Services | 1.1.12 | 1.1 | Publishing tags, Testing and Auditing | Development | Publishing tags, Testing and Auditing |  |  |  | 4 | 10 | 2 | 1.1.11
RFP_154542403_Digital_Marketing_Services | 1.1.12.1 | 1.1.12 | Publish & Smoke Test | Development | Publishing tags, Testing and Auditing | Publish & Smoke Test | QA Engineer | Mid | 4 | 10 | 2 | 1.1.12
RFP_154542403_Digital_Marketing_Services | 1.1.13 | 1.1 | Setup cross-domain tracking | Development | Setup cross-domain tracking |  |  |  | 4 | 10 | 12 | 1.1.12
RFP_154542403_Digital_Marketing_Services | 1.1.13.1 | 1.1.13 | QA | Development | Setup cross-domain tracking | QA | QA Engineer | Mid | 2 | 10 | 2 | 1.1.13
RFP_154542403_Digital_Marketing_Services | 1.1.13.2 | 1.1.13 | Cross-domain Config | Development | Setup cross-domain tracking | Cross-domain Config | Data/Analytics Engineer | Mid | 2 | 12 | 10 | 1.1.13.1
RFP_154542403_Digital_Marketing_Services | 1.1.14 | 1.1 | Setup eCommerce tracking | Development | Setup eCommerce tracking |  |  |  | 4 | 10 | 12 | 1.1.13
RFP_154542403_Digital_Marketing_Services | 1.1.14.1 | 1.1.14 | QA | Development | Setup eCommerce tracking | QA | QA Engineer | Mid | 2 | 10 | 2 | 1.1.14
RFP_154542403_Digital_Marketing_Services | 1.1.14.2 | 1.1.14 | Ecommerce Data Layer | Development | Setup eCommerce tracking | Ecommerce Data Layer | Data/Analytics Engineer | Mid | 2 | 12 | 10 | 1.1.14.1
RFP_154542403_Digital_Marketing_Services | 1.1.15 | 1.1 | Setup new GA4 acct for Caledera House | Development | Setup new GA4 acct for Caledera House |  |  |  | 7 | 10 | 12 | 1.1.14
RFP_154542403_Digital_Marketing_Services | 1.1.15.1 | 1.1.15 | QA Cycle | Development | Setup new GA4 acct for Caledera House | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.15
RFP_154542403_Digital_Marketing_Services | 1.1.15.2 | 1.1.15 | GA4 Property Setup | Development | Setup new GA4 acct for Caledera House | GA4 Property Setup | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.15.1
RFP_154542403_Digital_Marketing_Services | 1.2 | 1 | Paid Media Strategy | Paid Media Strategy |  |  |  |  | 138 | 22 | 40 | 1.1 |  | Core/T2_MediumVolume
RFP_154542403_Digital_Marketing_Services | 1.2.1 | 1.2 | Audience Research | Paid Media Strategy | Audience Research |  |  |  | 11 | 22 | 8 | 1.2
RFP_154542403_Digital_Marketing_Services | 1.2.1.1 | 1.2.1 | Audience Build & Rationale | Paid Media Strategy | Audience Research | Audience Build & Rationale | Analyst | Mid | 8 | 22 | 3 | 1.2.1
RFP_154542403_Digital_Marketing_Services | 1.2.1.2 | 1.2.1 | Internal Review & Critique | Paid Media Strategy | Audience Research | Internal Review & Critique | Creative Director | Lead/Director | 1 | 55 | 2 | 1.2.1.1
RFP_154542403_Digital_Marketing_Services | 1.2.1.3 | 1.2.1 | Client Review & Revisions | Paid Media Strategy | Audience Research | Client Review & Revisions | Account Manager | Mid | 2 | 57 | 3 | 1.2.1.2
RFP_154542403_Digital_Marketing_Services | 1.2.2 | 1.2 | Keyword List Development | Paid Media Strategy | Keyword List Development |  |  |  | 14 | 22 | 18 | 1.2.1
RFP_154542403_Digital_Marketing_Services | 1.2.2.1 | 1.2.2 | Keyword Discovery | Paid Media Strategy | Keyword List Development | Keyword Discovery | Analyst | Mid | 5 | 22 | 3 | 1.2.2
RFP_154542403_Digital_Marketing_Services | 1.2.2.2 | 1.2.2 | List Development & Grouping | Paid Media Strategy | Keyword List Development | List Development & Grouping | Media Strategist | Mid | 6 | 45 | 10 | 1.2.2.1
RFP_154542403_Digital_Marketing_Services | 1.2.2.3 | 1.2.2 | Internal Review & Critique | Paid Media Strategy | Keyword List Development | Internal Review & Critique | Creative Director | Lead/Director | 1 | 55 | 2 | 1.2.2.2
RFP_154542403_Digital_Marketing_Services | 1.2.2.4 | 1.2.2 | Client Review & Revisions | Paid Media Strategy | Keyword List Development | Client Review & Revisions | Account Manager | Mid | 2 | 57 | 3 | 1.2.2.3
RFP_154542403_Digital_Marketing_Services | 1.2.3 | 1.2 | Paid Media & Paid Creative Audit | Paid Media Strategy | Paid Media & Paid Creative Audit |  |  |  | 19 | 22 | 13 | 1.2.2
RFP_154542403_Digital_Marketing_Services | 1.2.3.1 | 1.2.3 | Platform/Creative Audit | Paid Media Strategy | Paid Media & Paid Creative Audit | Platform/Creative Audit | Analyst | Mid | 9 | 22 | 3 | 1.2.3
RFP_154542403_Digital_Marketing_Services | 1.2.3.2 | 1.2.3 | Findings Deck | Paid Media Strategy | Paid Media & Paid Creative Audit | Findings Deck | Designer | Mid | 7 | 25 | 5 | 1.2.3.1
RFP_154542403_Digital_Marketing_Services | 1.2.3.3 | 1.2.3 | Internal Review & Critique | Paid Media Strategy | Paid Media & Paid Creative Audit | Internal Review & Critique | Creative Director | Lead/Director | 1 | 55 | 2 | 1.2.3.2
RFP_154542403_Digital_Marketing_Services | 1.2.3.4 | 1.2.3 | Client Review & Revisions | Paid Media Strategy | Paid Media & Paid Creative Audit | Client Review & Revisions | Account Manager | Mid | 2 | 57 | 3 | 1.2.3.3
RFP_154542403_Digital_Marketing_Services | 1.2.4 | 1.2 | Mock Ad Examples | Paid Media Strategy | Mock Ad Examples |  |  |  | 14 | 30 | 15 | 1.2.3
RFP_154542403_Digital_Marketing_Services | 1.2.4.1 | 1.2.4 | Concept & Copy | Paid Media Strategy | Mock Ad Examples | Concept & Copy | Copywriter | Mid | 4 | 30 | 3 | 1.2.4
RFP_154542403_Digital_Marketing_Services | 1.2.4.2 | 1.2.4 | Design (3-4 mocks) | Paid Media Strategy | Mock Ad Examples | Design (3-4 mocks) | Designer | Mid | 4 | 33 | 7 | 1.2.4.1
RFP_154542403_Digital_Marketing_Services | 1.2.4.3 | 1.2.4 | Internal Review & Critique | Paid Media Strategy | Mock Ad Examples | Internal Review & Critique | Creative Director | Lead/Director | 1 | 55 | 2 | 1.2.4.2
RFP_154542403_Digital_Marketing_Services | 1.2.4.4 | 1.2.4 | Client Review & Revisions | Paid Media Strategy | Mock Ad Examples | Client Review & Revisions | Account Manager | Mid | 3 | 57 | 3 | 1.2.4.3
RFP_154542403_Digital_Marketing_Services | 1.2.4.5 | 1.2.4 | Final Packaging | Paid Media Strategy | Mock Ad Examples | Final Packaging | Designer | Mid | 2 | 62 | 0 | 1.2.4.4
RFP_154542403_Digital_Marketing_Services | 1.2.5 | 1.2 | Campaigns | Paid Media Strategy | Campaigns |  |  |  | 20 | 40 | 10 | 1.2.4
RFP_154542403_Digital_Marketing_Services | 1.2.5.1 | 1.2.5 | Campaign Architecture | Paid Media Strategy | Campaigns | Campaign Architecture | Media Planner | Mid | 17 | 40 | 5 | 1.2.5
RFP_154542403_Digital_Marketing_Services | 1.2.5.2 | 1.2.5 | Internal Review & Critique | Paid Media Strategy | Campaigns | Internal Review & Critique | Creative Director | Lead/Director | 1 | 55 | 2 | 1.2.5.1
RFP_154542403_Digital_Marketing_Services | 1.2.5.3 | 1.2.5 | Client Review & Revisions | Paid Media Strategy | Campaigns | Client Review & Revisions | Account Manager | Mid | 2 | 57 | 3 | 1.2.5.2
RFP_154542403_Digital_Marketing_Services | 1.2.6 | 1.2 | Ad Funnel | Paid Media Strategy | Ad Funnel |  |  |  | 14 | 55 | 5 | 1.2.5
RFP_154542403_Digital_Marketing_Services | 1.2.6.1 | 1.2.6 | Internal Review & Critique | Paid Media Strategy | Ad Funnel | Internal Review & Critique | Creative Director | Lead/Director | 1 | 55 | 2 | 1.2.6
RFP_154542403_Digital_Marketing_Services | 1.2.6.2 | 1.2.6 | Client Review & Revisions | Paid Media Strategy | Ad Funnel | Client Review & Revisions | Account Manager | Mid | 2 | 57 | 3 | 1.2.6.1
RFP_154542403_Digital_Marketing_Services | 1.2.6.3 | 1.2.6 | Messaging/Asset Mapping | Paid Media Strategy | Ad Funnel | Messaging/Asset Mapping | Media Strategist | Mid | 11 | 62 | 0 | 1.2.6.2
RFP_154542403_Digital_Marketing_Services | 1.2.7 | 1.2 | Budget Distribution | Paid Media Strategy | Budget Distribution |  |  |  | 5 | 55 | 7 | 1.2.6
RFP_154542403_Digital_Marketing_Services | 1.2.7.1 | 1.2.7 | Internal Review & Critique | Paid Media Strategy | Budget Distribution | Internal Review & Critique | Creative Director | Lead/Director | 1 | 55 | 2 | 1.2.7
RFP_154542403_Digital_Marketing_Services | 1.2.7.2 | 1.2.7 | Client Review & Revisions | Paid Media Strategy | Budget Distribution | Client Review & Revisions | Account Manager | Mid | 2 | 57 | 3 | 1.2.7.1
RFP_154542403_Digital_Marketing_Services | 1.2.7.3 | 1.2.7 | Allocation Modeling | Paid Media Strategy | Budget Distribution | Allocation Modeling | Media Planner | Mid | 2 | 60 | 2 | 1.2.7.2
RFP_154542403_Digital_Marketing_Services | 1.2.8 | 1.2 | Identification of Media Needs | Paid Media Strategy | Identification of Media Needs |  |  |  | 11 | 55 | 5 | 1.2.7
RFP_154542403_Digital_Marketing_Services | 1.2.8.1 | 1.2.8 | Internal Review & Critique | Paid Media Strategy | Identification of Media Needs | Internal Review & Critique | Creative Director | Lead/Director | 1 | 55 | 2 | 1.2.8
RFP_154542403_Digital_Marketing_Services | 1.2.8.2 | 1.2.8 | Client Review & Revisions | Paid Media Strategy | Identification of Media Needs | Client Review & Revisions | Account Manager | Mid | 2 | 57 | 3 | 1.2.8.1
RFP_154542403_Digital_Marketing_Services | 1.2.8.3 | 1.2.8 | Needs Matrix (Assets/Specs/Formats) | Paid Media Strategy | Identification of Media Needs | Needs Matrix (Assets/Specs/Formats) | Designer | Mid | 8 | 62 | 0 | 1.2.8.2
RFP_154542403_Digital_Marketing_Services | 1.2.9 | 1.2 | Paid Media Recommendations | Paid Media Strategy | Paid Media Recommendations |  |  |  | 13 | 55 | 5 | 1.2.8
RFP_154542403_Digital_Marketing_Services | 1.2.9.1 | 1.2.9 | Internal Review & Critique | Paid Media Strategy | Paid Media Recommendations | Internal Review & Critique | Creative Director | Lead/Director | 1 | 55 | 2 | 1.2.9
RFP_154542403_Digital_Marketing_Services | 1.2.9.2 | 1.2.9 | Client Review & Revisions | Paid Media Strategy | Paid Media Recommendations | Client Review & Revisions | Account Manager | Mid | 2 | 57 | 3 | 1.2.9.1
RFP_154542403_Digital_Marketing_Services | 1.2.9.3 | 1.2.9 | Prioritized Recs | Paid Media Strategy | Paid Media Recommendations | Prioritized Recs | Media Planner | Mid | 10 | 62 | 0 | 1.2.9.2
RFP_154542403_Digital_Marketing_Services | 1.2.10 | 1.2 | Platform Identification | Paid Media Strategy | Platform Identification |  |  |  | 9 | 55 | 5 | 1.2.9
RFP_154542403_Digital_Marketing_Services | 1.2.10.1 | 1.2.10 | Internal Review & Critique | Paid Media Strategy | Platform Identification | Internal Review & Critique | Creative Director | Lead/Director | 1 | 55 | 2 | 1.2.10
RFP_154542403_Digital_Marketing_Services | 1.2.10.2 | 1.2.10 | Client Review & Revisions | Paid Media Strategy | Platform Identification | Client Review & Revisions | Account Manager | Mid | 2 | 57 | 3 | 1.2.10.1
RFP_154542403_Digital_Marketing_Services | 1.2.10.3 | 1.2.10 | Platform Fit Assessment | Paid Media Strategy | Platform Identification | Platform Fit Assessment | Media Planner | Mid | 6 | 62 | 0 | 1.2.10.2
RFP_154542403_Digital_Marketing_Services | 1.2.11 | 1.2 | Target Audience & Demographics | Paid Media Strategy | Target Audience & Demographics |  |  |  | 8 | 55 | 5 | 1.2.10
RFP_154542403_Digital_Marketing_Services | 1.2.11.1 | 1.2.11 | Internal Review & Critique | Paid Media Strategy | Target Audience & Demographics | Internal Review & Critique | Creative Director | Lead/Director | 1 | 55 | 2 | 1.2.11
RFP_154542403_Digital_Marketing_Services | 1.2.11.2 | 1.2.11 | Client Review & Revisions | Paid Media Strategy | Target Audience & Demographics | Client Review & Revisions | Account Manager | Mid | 2 | 57 | 3 | 1.2.11.1
RFP_154542403_Digital_Marketing_Services | 1.2.11.3 | 1.2.11 | Audience Definition | Paid Media Strategy | Target Audience & Demographics | Audience Definition | Media Strategist | Mid | 5 | 62 | 0 | 1.2.11.2
RFP_154542403_Digital_Marketing_Services | 1.3 | 1 | Post-Production | Post-Production |  |  |  |  | 188 | 62 | 41 | 1.2 |  | Core/T2_MediumVolume
RFP_154542403_Digital_Marketing_Services | 1.3.1 | 1.3 | Content Licensing / Art Buying | Post-Production | Content Licensing / Art Buying |  |  |  | 2 | 62 | 3 | 1.3
RFP_154542403_Digital_Marketing_Services | 1.3.1.1 | 1.3.1 | Rights/License Research | Post-Production | Content Licensing / Art Buying | Rights/License Research | Producer | Mid | 1 | 62 | 3 | 1.3.1
RFP_154542403_Digital_Marketing_Services | 1.3.1.2 | 1.3.1 | Usage Notes | Post-Production | Content Licensing / Art Buying | Usage Notes | Account Manager | Mid | 1 | 103 | 0 | 1.3.1.1
RFP_154542403_Digital_Marketing_Services | 1.3.2 | 1.3 | VO Recording Sessions | Post-Production | VO Recording Sessions |  |  |  | 5 | 65 | 4 | 1.3.1
RFP_154542403_Digital_Marketing_Services | 1.3.2.1 | 1.3.2 | Script Polish | Post-Production | VO Recording Sessions | Script Polish | Copywriter | Mid | 1 | 65 | 4 | 1.3.2
RFP_154542403_Digital_Marketing_Services | 1.3.2.2 | 1.3.2 | VO Session | Post-Production | VO Recording Sessions | VO Session | Sound Designer | Mid | 4 | 103 | 0 | 1.3.2.1
RFP_154542403_Digital_Marketing_Services | 1.3.3 | 1.3 | Editing | Post-Production | Editing |  |  |  | 17 | 69 | 5 | 1.3.2
RFP_154542403_Digital_Marketing_Services | 1.3.3.1 | 1.3.3 | Client Review & Revisions | Post-Production | Editing | Client Review & Revisions | Editor | Mid | 17 | 69 | 5 | 1.3.3
RFP_154542403_Digital_Marketing_Services | 1.3.4 | 1.3 | Video Editing | Post-Production | Video Editing |  |  |  | 25 | 69 | 5 | 1.3.3
RFP_154542403_Digital_Marketing_Services | 1.3.4.1 | 1.3.4 | Client Review & Revisions | Post-Production | Video Editing | Client Review & Revisions | Editor | Mid | 25 | 69 | 5 | 1.3.4
RFP_154542403_Digital_Marketing_Services | 1.3.5 | 1.3 | Voice Over | Post-Production | Voice Over |  |  |  | 17 | 69 | 12 | 1.3.4
RFP_154542403_Digital_Marketing_Services | 1.3.5.1 | 1.3.5 | VO Edit | Post-Production | Voice Over | VO Edit | Editor | Mid | 9 | 69 | 5 | 1.3.5
RFP_154542403_Digital_Marketing_Services | 1.3.5.2 | 1.3.5 | Mix | Post-Production | Voice Over | Mix | Sound Designer | Mid | 2 | 86 | 2 | 1.3.5.1
RFP_154542403_Digital_Marketing_Services | 1.3.5.3 | 1.3.5 | Internal Review & Critique | Post-Production | Voice Over | Internal Review & Critique | Producer | Mid | 1 | 93 | 2 | 1.3.5.2
RFP_154542403_Digital_Marketing_Services | 1.3.5.4 | 1.3.5 | Client Review & Revisions | Post-Production | Voice Over | Client Review & Revisions | Account Manager | Mid | 3 | 95 | 3 | 1.3.5.3
RFP_154542403_Digital_Marketing_Services | 1.3.5.5 | 1.3.5 | Final Packaging | Post-Production | Voice Over | Final Packaging | Designer | Mid | 2 | 103 | 0 | 1.3.5.4
RFP_154542403_Digital_Marketing_Services | 1.3.6 | 1.3 | Motion Design/VFX | Post-Production | Motion Design/VFX |  |  |  | 17 | 74 | 7 | 1.3.5
RFP_154542403_Digital_Marketing_Services | 1.3.6.1 | 1.3.6 | Client Review & Revisions | Post-Production | Motion Design/VFX | Client Review & Revisions | Editor | Mid | 17 | 74 | 7 | 1.3.6
RFP_154542403_Digital_Marketing_Services | 1.3.7 | 1.3 | Color Correction | Post-Production | Color Correction |  |  |  | 11 | 81 | 2 | 1.3.6
RFP_154542403_Digital_Marketing_Services | 1.3.7.1 | 1.3.7 | Client Review & Revisions | Post-Production | Color Correction | Client Review & Revisions | Colorist | Mid | 11 | 81 | 2 | 1.3.7
RFP_154542403_Digital_Marketing_Services | 1.3.8 | 1.3 | Color Grading | Post-Production | Color Grading |  |  |  | 11 | 81 | 2 | 1.3.7
RFP_154542403_Digital_Marketing_Services | 1.3.8.1 | 1.3.8 | Client Review & Revisions | Post-Production | Color Grading | Client Review & Revisions | Colorist | Mid | 11 | 81 | 2 | 1.3.8
RFP_154542403_Digital_Marketing_Services | 1.3.9 | 1.3 | Final Retouched Stills Review | Post-Production | Final Retouched Stills Review |  |  |  | 10 | 83 | 8 | 1.3.8
RFP_154542403_Digital_Marketing_Services | 1.3.9.1 | 1.3.9 | Retouch | Post-Production | Final Retouched Stills Review | Retouch | Retoucher | Mid | 4 | 83 | 3 | 1.3.9
RFP_154542403_Digital_Marketing_Services | 1.3.9.2 | 1.3.9 | Internal Review & Critique | Post-Production | Final Retouched Stills Review | Internal Review & Critique | Producer | Mid | 1 | 93 | 2 | 1.3.9.1
RFP_154542403_Digital_Marketing_Services | 1.3.9.3 | 1.3.9 | Client Review & Revisions | Post-Production | Final Retouched Stills Review | Client Review & Revisions | Account Manager | Mid | 3 | 95 | 3 | 1.3.9.2
RFP_154542403_Digital_Marketing_Services | 1.3.9.4 | 1.3.9 | Final Packaging | Post-Production | Final Retouched Stills Review | Final Packaging | Designer | Mid | 2 | 103 | 0 | 1.3.9.3
RFP_154542403_Digital_Marketing_Services | 1.3.10 | 1.3 | Retouching | Post-Production | Retouching |  |  |  | 10 | 83 | 8 | 1.3.9
RFP_154542403_Digital_Marketing_Services | 1.3.10.1 | 1.3.10 | Retouch | Post-Production | Retouching | Retouch | Retoucher | Mid | 4 | 83 | 3 | 1.3.10
RFP_154542403_Digital_Marketing_Services | 1.3.10.2 | 1.3.10 | Internal Review & Critique | Post-Production | Retouching | Internal Review & Critique | Producer | Mid | 1 | 93 | 2 | 1.3.10.1
RFP_154542403_Digital_Marketing_Services | 1.3.10.3 | 1.3.10 | Client Review & Revisions | Post-Production | Retouching | Client Review & Revisions | Account Manager | Mid | 3 | 95 | 3 | 1.3.10.2
RFP_154542403_Digital_Marketing_Services | 1.3.10.4 | 1.3.10 | Final Packaging | Post-Production | Retouching | Final Packaging | Designer | Mid | 2 | 103 | 0 | 1.3.10.3
RFP_154542403_Digital_Marketing_Services | 1.3.11 | 1.3 | Sound Mix | Post-Production | Sound Mix |  |  |  | 9 | 86 | 2 | 1.3.10
RFP_154542403_Digital_Marketing_Services | 1.3.11.1 | 1.3.11 | Client Review & Revisions | Post-Production | Sound Mix | Client Review & Revisions | Designer | Mid | 9 | 86 | 2 | 1.3.11
RFP_154542403_Digital_Marketing_Services | 1.3.12 | 1.3 | Sound Sourcing | Post-Production | Sound Sourcing |  |  |  | 3 | 86 | 2 | 1.3.11
RFP_154542403_Digital_Marketing_Services | 1.3.12.1 | 1.3.12 | Music Search & License | Post-Production | Sound Sourcing | Music Search & License | Sound Designer | Mid | 3 | 86 | 2 | 1.3.12
RFP_154542403_Digital_Marketing_Services | 1.3.13 | 1.3 | Final File Delivery | Post-Production | Final File Delivery |  |  |  | 7 | 88 | 2 | 1.3.12
RFP_154542403_Digital_Marketing_Services | 1.3.13.1 | 1.3.13 | QA (Tech & Content) | Post-Production | Final File Delivery | QA (Tech & Content) | QA Specialist | Mid | 3 | 88 | 2 | 1.3.13
RFP_154542403_Digital_Marketing_Services | 1.3.13.2 | 1.3.13 | Final Checklist & Upload | Post-Production | Final File Delivery | Final Checklist & Upload | Media Manager / DIT | Mid | 4 | 103 | 0 | 1.3.13.1
RFP_154542403_Digital_Marketing_Services | 1.3.14 | 1.3 | True-ups (for vendor costs) | Post-Production | True-ups (for vendor costs) |  |  |  | 10 | 90 | 8 | 1.3.13
RFP_154542403_Digital_Marketing_Services | 1.3.14.1 | 1.3.14 | Change Orders & Tracking | Post-Production | True-ups (for vendor costs) | Change Orders & Tracking | Project Manager | Mid | 1 | 90 | 3 | 1.3.14
RFP_154542403_Digital_Marketing_Services | 1.3.14.2 | 1.3.14 | Internal Review & Critique | Post-Production | True-ups (for vendor costs) | Internal Review & Critique | Producer | Mid | 1 | 93 | 2 | 1.3.14.1
RFP_154542403_Digital_Marketing_Services | 1.3.14.3 | 1.3.14 | Client Review & Revisions | Post-Production | True-ups (for vendor costs) | Client Review & Revisions | Account Manager | Mid | 3 | 95 | 3 | 1.3.14.2
RFP_154542403_Digital_Marketing_Services | 1.3.14.4 | 1.3.14 | Invoice Reconciliation | Post-Production | True-ups (for vendor costs) | Invoice Reconciliation | Designer | Mid | 5 | 103 | 0 | 1.3.14.3
RFP_154542403_Digital_Marketing_Services | 1.3.15 | 1.3 | Cutdowns | Post-Production | Cutdowns |  |  |  | 11 | 93 | 5 | 1.3.14
RFP_154542403_Digital_Marketing_Services | 1.3.15.1 | 1.3.15 | Internal Review & Critique | Post-Production | Cutdowns | Internal Review & Critique | Producer | Mid | 1 | 93 | 2 | 1.3.15
RFP_154542403_Digital_Marketing_Services | 1.3.15.2 | 1.3.15 | Client Review & Revisions | Post-Production | Cutdowns | Client Review & Revisions | Account Manager | Mid | 3 | 95 | 3 | 1.3.15.1
RFP_154542403_Digital_Marketing_Services | 1.3.15.3 | 1.3.15 | Cutdowns (2-3) | Post-Production | Cutdowns | Cutdowns (2-3) | Editor | Mid | 7 | 103 | 0 | 1.3.15.2
RFP_154542403_Digital_Marketing_Services | 1.3.16 | 1.3 | Client Review | Post-Production | Client Review |  |  |  | 4 | 95 | 3 | 1.3.15
RFP_154542403_Digital_Marketing_Services | 1.3.16.1 | 1.3.16 | Client Review Coordination | Post-Production | Client Review | Client Review Coordination | Account Manager | Mid | 4 | 95 | 3 | 1.3.16
RFP_154542403_Digital_Marketing_Services | 1.3.17 | 1.3 | Review & Sign-Off | Post-Production | Review & Sign-Off |  |  |  | 3 | 95 | 5 | 1.3.16
RFP_154542403_Digital_Marketing_Services | 1.3.17.1 | 1.3.17 | Client Review Coordination | Post-Production | Review & Sign-Off | Client Review Coordination | Account Manager | Mid | 2 | 95 | 3 | 1.3.17
RFP_154542403_Digital_Marketing_Services | 1.3.17.2 | 1.3.17 | Notes Triage | Post-Production | Review & Sign-Off | Notes Triage | Project Manager | Mid | 1 | 101 | 2 | 1.3.17.1
RFP_154542403_Digital_Marketing_Services | 1.3.18 | 1.3 | Asset Library | Post-Production | Asset Library |  |  |  | 2 | 98 | 3 | 1.3.17
RFP_154542403_Digital_Marketing_Services | 1.3.18.1 | 1.3.18 | Post Support | Post-Production | Asset Library | Post Support | Editor | Mid | 2 | 98 | 3 | 1.3.18
RFP_154542403_Digital_Marketing_Services | 1.3.19 | 1.3 | Capture Library | Post-Production | Capture Library |  |  |  | 2 | 98 | 3 | 1.3.18
RFP_154542403_Digital_Marketing_Services | 1.3.19.1 | 1.3.19 | Post Support | Post-Production | Capture Library | Post Support | Editor | Mid | 2 | 98 | 3 | 1.3.19
RFP_154542403_Digital_Marketing_Services | 1.3.20 | 1.3 | Selects Deck | Post-Production | Selects Deck |  |  |  | 2 | 98 | 3 | 1.3.19
RFP_154542403_Digital_Marketing_Services | 1.3.20.1 | 1.3.20 | Post Support | Post-Production | Selects Deck | Post Support | Editor | Mid | 2 | 98 | 3 | 1.3.20
RFP_154542403_Digital_Marketing_Services | 1.3.21 | 1.3 | Delivery | Post-Production | Delivery |  |  |  | 5 | 103 | 0 | 1.3.20
RFP_154542403_Digital_Marketing_Services | 1.3.21.1 | 1.3.21 | Post Support | Post-Production | Delivery | Post Support | Editor | Mid | 5 | 103 | 0 | 1.3.21
RFP_154542403_Digital_Marketing_Services | 1.3.22 | 1.3 | Stills/Footage Selection | Post-Production | Stills/Footage Selection |  |  |  | 5 | 103 | 0 | 1.3.21
RFP_154542403_Digital_Marketing_Services | 1.3.22.1 | 1.3.22 | Post Support | Post-Production | Stills/Footage Selection | Post Support | Editor | Mid | 5 | 103 | 0 | 1.3.22
RFP_154542403_Digital_Marketing_Services | 1.4 | 1 | Paid Media Assets | Paid Media Assets |  |  |  |  | 126 | 103 | 19 | 1.3 |  | Core/T2_MediumVolume
RFP_154542403_Digital_Marketing_Services | 1.4.1 | 1.4 | Awareness Assets (Paid) | Paid Media Assets | Awareness Assets (Paid) |  |  |  | 20 | 103 | 17 | 1.4
RFP_154542403_Digital_Marketing_Services | 1.4.1.1 | 1.4.1 | Concept & Copy | Paid Media Assets | Awareness Assets (Paid) | Concept & Copy | Copywriter | Mid | 4 | 103 | 3 | 1.4.1
RFP_154542403_Digital_Marketing_Services | 1.4.1.2 | 1.4.1 | Design Explorations (3-4) | Paid Media Assets | Awareness Assets (Paid) | Design Explorations (3-4) | Designer | Mid | 4 | 106 | 7 | 1.4.1.1
RFP_154542403_Digital_Marketing_Services | 1.4.1.3 | 1.4.1 | Quality Check (Specs/Accessibility) | Paid Media Assets | Awareness Assets (Paid) | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 | 115 | 2 | 1.4.1.2
RFP_154542403_Digital_Marketing_Services | 1.4.1.4 | 1.4.1 | Internal Review & Critique | Paid Media Assets | Awareness Assets (Paid) | Internal Review & Critique | Art Director | Lead/Director | 1 | 117 | 2 | 1.4.1.3
RFP_154542403_Digital_Marketing_Services | 1.4.1.5 | 1.4.1 | Client Review & Revisions | Paid Media Assets | Awareness Assets (Paid) | Client Review & Revisions | Account Manager | Mid | 4 | 119 | 3 | 1.4.1.4
RFP_154542403_Digital_Marketing_Services | 1.4.1.6 | 1.4.1 | Final Packaging | Paid Media Assets | Awareness Assets (Paid) | Final Packaging | Designer | Mid | 4 | 122 | 0 | 1.4.1.5
RFP_154542403_Digital_Marketing_Services | 1.4.2 | 1.4 | Unique Assets | Paid Media Assets | Unique Assets |  |  |  | 15 | 103 | 10 | 1.4.1
RFP_154542403_Digital_Marketing_Services | 1.4.2.1 | 1.4.2 | Build & Polish | Paid Media Assets | Unique Assets | Build & Polish | Designer | Mid | 2 | 103 | 3 | 1.4.2
RFP_154542403_Digital_Marketing_Services | 1.4.2.2 | 1.4.2 | Quality Check (Specs/Accessibility) | Paid Media Assets | Unique Assets | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 | 115 | 2 | 1.4.2.1
RFP_154542403_Digital_Marketing_Services | 1.4.2.3 | 1.4.2 | Internal Review & Critique | Paid Media Assets | Unique Assets | Internal Review & Critique | Art Director | Lead/Director | 1 | 117 | 2 | 1.4.2.2
RFP_154542403_Digital_Marketing_Services | 1.4.2.4 | 1.4.2 | Client Review & Revisions | Paid Media Assets | Unique Assets | Client Review & Revisions | Account Manager | Mid | 3 | 119 | 3 | 1.4.2.3
RFP_154542403_Digital_Marketing_Services | 1.4.2.5 | 1.4.2 | Custom Concept | Paid Media Assets | Unique Assets | Custom Concept | Designer | Mid | 6 | 122 | 0 | 1.4.2.4
RFP_154542403_Digital_Marketing_Services | 1.4.3 | 1.4 | Conversion Assets (Paid) | Paid Media Assets | Conversion Assets (Paid) |  |  |  | 17 | 106 | 14 | 1.4.2
RFP_154542403_Digital_Marketing_Services | 1.4.3.1 | 1.4.3 | Design Variants (3-4) | Paid Media Assets | Conversion Assets (Paid) | Design Variants (3-4) | Designer | Mid | 3 | 106 | 7 | 1.4.3
RFP_154542403_Digital_Marketing_Services | 1.4.3.2 | 1.4.3 | Quality Check (Specs/Accessibility) | Paid Media Assets | Conversion Assets (Paid) | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 | 115 | 2 | 1.4.3.1
RFP_154542403_Digital_Marketing_Services | 1.4.3.3 | 1.4.3 | Internal Review & Critique | Paid Media Assets | Conversion Assets (Paid) | Internal Review & Critique | Art Director | Lead/Director | 1 | 117 | 2 | 1.4.3.2
RFP_154542403_Digital_Marketing_Services | 1.4.3.4 | 1.4.3 | Client Review & Revisions | Paid Media Assets | Conversion Assets (Paid) | Client Review & Revisions | Account Manager | Mid | 4 | 119 | 3 | 1.4.3.3
RFP_154542403_Digital_Marketing_Services | 1.4.3.5 | 1.4.3 | Final Packaging | Paid Media Assets | Conversion Assets (Paid) | Final Packaging | Designer | Mid | 6 | 122 | 0 | 1.4.3.4
RFP_154542403_Digital_Marketing_Services | 1.4.4 | 1.4 | National Spotify Audio (Paid) | Paid Media Assets | National Spotify Audio (Paid) |  |  |  | 16 | 113 | 2 | 1.4.3
RFP_154542403_Digital_Marketing_Services | 1.4.4.1 | 1.4.4 | Client Review & Revisions | Paid Media Assets | National Spotify Audio (Paid) | Client Review & Revisions | Sound Designer | Mid | 16 | 113 | 2 | 1.4.4
RFP_154542403_Digital_Marketing_Services | 1.4.5 | 1.4 | Regional Spotify Audio (Paid) | Paid Media Assets | Regional Spotify Audio (Paid) |  |  |  | 16 | 113 | 2 | 1.4.4
RFP_154542403_Digital_Marketing_Services | 1.4.5.1 | 1.4.5 | Client Review & Revisions | Paid Media Assets | Regional Spotify Audio (Paid) | Client Review & Revisions | Sound Designer | Mid | 16 | 113 | 2 | 1.4.5
RFP_154542403_Digital_Marketing_Services | 1.4.6 | 1.4 | National Pinterest assets (Paid) | Paid Media Assets | National Pinterest assets (Paid) |  |  |  | 14 | 115 | 7 | 1.4.5
RFP_154542403_Digital_Marketing_Services | 1.4.6.1 | 1.4.6 | Quality Check (Specs/Accessibility) | Paid Media Assets | National Pinterest assets (Paid) | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 | 115 | 2 | 1.4.6
RFP_154542403_Digital_Marketing_Services | 1.4.6.2 | 1.4.6 | Internal Review & Critique | Paid Media Assets | National Pinterest assets (Paid) | Internal Review & Critique | Art Director | Lead/Director | 1 | 117 | 2 | 1.4.6.1
RFP_154542403_Digital_Marketing_Services | 1.4.6.3 | 1.4.6 | Client Review & Revisions | Paid Media Assets | National Pinterest assets (Paid) | Client Review & Revisions | Account Manager | Mid | 3 | 119 | 3 | 1.4.6.2
RFP_154542403_Digital_Marketing_Services | 1.4.6.4 | 1.4.6 | Concept & Layouts (2-3) | Paid Media Assets | National Pinterest assets (Paid) | Concept & Layouts (2-3) | Designer | Mid | 7 | 122 | 0 | 1.4.6.3
RFP_154542403_Digital_Marketing_Services | 1.4.7 | 1.4 | Regional Pinterest assets (Paid) | Paid Media Assets | Regional Pinterest assets (Paid) |  |  |  | 14 | 115 | 7 | 1.4.6
RFP_154542403_Digital_Marketing_Services | 1.4.7.1 | 1.4.7 | Quality Check (Specs/Accessibility) | Paid Media Assets | Regional Pinterest assets (Paid) | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 | 115 | 2 | 1.4.7
RFP_154542403_Digital_Marketing_Services | 1.4.7.2 | 1.4.7 | Internal Review & Critique | Paid Media Assets | Regional Pinterest assets (Paid) | Internal Review & Critique | Art Director | Lead/Director | 1 | 117 | 2 | 1.4.7.1
RFP_154542403_Digital_Marketing_Services | 1.4.7.3 | 1.4.7 | Client Review & Revisions | Paid Media Assets | Regional Pinterest assets (Paid) | Client Review & Revisions | Account Manager | Mid | 3 | 119 | 3 | 1.4.7.2
RFP_154542403_Digital_Marketing_Services | 1.4.7.4 | 1.4.7 | Concept & Layouts (2-3) | Paid Media Assets | Regional Pinterest assets (Paid) | Concept & Layouts (2-3) | Designer | Mid | 7 | 122 | 0 | 1.4.7.3
RFP_154542403_Digital_Marketing_Services | 1.4.8 | 1.4 | Resize Assets | Paid Media Assets | Resize Assets |  |  |  | 14 | 115 | 7 | 1.4.7
RFP_154542403_Digital_Marketing_Services | 1.4.8.1 | 1.4.8 | Quality Check (Specs/Accessibility) | Paid Media Assets | Resize Assets | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 5 | 115 | 2 | 1.4.8
RFP_154542403_Digital_Marketing_Services | 1.4.8.2 | 1.4.8 | Internal Review & Critique | Paid Media Assets | Resize Assets | Internal Review & Critique | Art Director | Lead/Director | 1 | 117 | 2 | 1.4.8.1
RFP_154542403_Digital_Marketing_Services | 1.4.8.3 | 1.4.8 | Client Review & Revisions | Paid Media Assets | Resize Assets | Client Review & Revisions | Account Manager | Mid | 4 | 119 | 3 | 1.4.8.2
RFP_154542403_Digital_Marketing_Services | 1.4.8.4 | 1.4.8 | Final Packaging | Paid Media Assets | Resize Assets | Final Packaging | Designer | Mid | 4 | 122 | 0 | 1.4.8.3
RFP_154542403_Digital_Marketing_Services | 1.5 | 1 | Reporting | Reporting |  |  |  |  | 58 | 122 | 15 | 1.4 |  | Core/T2_MediumVolume
RFP_154542403_Digital_Marketing_Services | 1.5.1 | 1.5 | Campaign Reporting (Quarterly) | Reporting | Campaign Reporting (Quarterly) |  |  |  | 11 | 122 | 3 | 1.5
RFP_154542403_Digital_Marketing_Services | 1.5.1.1 | 1.5.1 | Design Polish | Reporting | Campaign Reporting (Quarterly) | Design Polish | Designer | Mid | 2 | 122 | 3 | 1.5.1
RFP_154542403_Digital_Marketing_Services | 1.5.1.2 | 1.5.1 | Data Deep Dive | Reporting | Campaign Reporting (Quarterly) | Data Deep Dive | Media Strategist | Mid | 9 | 137 | 0 | 1.5.1.1
RFP_154542403_Digital_Marketing_Services | 1.5.2 | 1.5 | Campaign Reporting (Bi-Weekly) | Reporting | Campaign Reporting (Bi-Weekly) |  |  |  | 8 | 125 | 5 | 1.5.1
RFP_154542403_Digital_Marketing_Services | 1.5.2.1 | 1.5.2 | Data Refresh & QA | Reporting | Campaign Reporting (Bi-Weekly) | Data Refresh & QA | QA Specialist | Mid | 5 | 125 | 2 | 1.5.2
RFP_154542403_Digital_Marketing_Services | 1.5.2.2 | 1.5.2 | Client Summary | Reporting | Campaign Reporting (Bi-Weekly) | Client Summary | Media Strategist | Mid | 3 | 130 | 3 | 1.5.2.1
RFP_154542403_Digital_Marketing_Services | 1.5.3 | 1.5 | Campaign Tracking | Reporting | Campaign Tracking |  |  |  | 7 | 125 | 5 | 1.5.2
RFP_154542403_Digital_Marketing_Services | 1.5.3.1 | 1.5.3 | QA Spot Check | Reporting | Campaign Tracking | QA Spot Check | QA Specialist | Mid | 3 | 125 | 2 | 1.5.3
RFP_154542403_Digital_Marketing_Services | 1.5.3.2 | 1.5.3 | Tracker Update | Reporting | Campaign Tracking | Tracker Update | Analyst | Mid | 4 | 127 | 3 | 1.5.3.1
RFP_154542403_Digital_Marketing_Services | 1.5.4 | 1.5 | Dashboard Analytics | Reporting | Dashboard Analytics |  |  |  | 8 | 125 | 5 | 1.5.3
RFP_154542403_Digital_Marketing_Services | 1.5.4.1 | 1.5.4 | QA & Calc Checks | Reporting | Dashboard Analytics | QA & Calc Checks | QA Specialist | Mid | 3 | 125 | 2 | 1.5.4
RFP_154542403_Digital_Marketing_Services | 1.5.4.2 | 1.5.4 | Dashboard Build/Refresh | Reporting | Dashboard Analytics | Dashboard Build/Refresh | Analyst | Mid | 5 | 130 | 3 | 1.5.4.1
RFP_154542403_Digital_Marketing_Services | 1.5.5 | 1.5 | Reporting & Ad-Tagging Support | Reporting | Reporting & Ad-Tagging Support |  |  |  | 7 | 125 | 5 | 1.5.4
RFP_154542403_Digital_Marketing_Services | 1.5.5.1 | 1.5.5 | QA | Reporting | Reporting & Ad-Tagging Support | QA | QA Specialist | Mid | 2 | 125 | 2 | 1.5.5
RFP_154542403_Digital_Marketing_Services | 1.5.5.2 | 1.5.5 | UTM/Tag Guidance | Reporting | Reporting & Ad-Tagging Support | UTM/Tag Guidance | Media Strategist | Mid | 3 | 127 | 3 | 1.5.5.1
RFP_154542403_Digital_Marketing_Services | 1.5.5.3 | 1.5.5 | Tagging Support | Reporting | Reporting & Ad-Tagging Support | Tagging Support | Ad Ops / Trafficker | Mid | 2 | 137 | 0 | 1.5.5.2
RFP_154542403_Digital_Marketing_Services | 1.5.6 | 1.5 | Dashboard Maintenance | Reporting | Dashboard Maintenance |  |  |  | 6 | 130 | 3 | 1.5.5
RFP_154542403_Digital_Marketing_Services | 1.5.6.1 | 1.5.6 | Connector Checks & Fixes | Reporting | Dashboard Maintenance | Connector Checks & Fixes | Analyst | Mid | 6 | 130 | 3 | 1.5.6
RFP_154542403_Digital_Marketing_Services | 1.5.7 | 1.5 | Reconcilliation & Media Budget Authorization | Reporting | Reconcilliation & Media Budget Authorization |  |  |  | 4 | 133 | 2 | 1.5.6
RFP_154542403_Digital_Marketing_Services | 1.5.7.1 | 1.5.7 | Authorization & Docs | Reporting | Reconcilliation & Media Budget Authorization | Authorization & Docs | Account Manager | Mid | 4 | 133 | 2 | 1.5.7
RFP_154542403_Digital_Marketing_Services | 1.5.8 | 1.5 | KPI Monitoring | Reporting | KPI Monitoring |  |  |  | 4 | 135 | 2 | 1.5.7
RFP_154542403_Digital_Marketing_Services | 1.5.8.1 | 1.5.8 | Weekly KPI Scan | Reporting | KPI Monitoring | Weekly KPI Scan | Analyst | Mid | 1 | 135 | 2 | 1.5.8
RFP_154542403_Digital_Marketing_Services | 1.5.8.2 | 1.5.8 | Notes & Flags | Reporting | KPI Monitoring | Notes & Flags | Media Strategist | Mid | 3 | 137 | 0 | 1.5.8.1
RFP_154542403_Digital_Marketing_Services | 1.5.9 | 1.5 | Ad-Platform Reporting | Reporting | Ad-Platform Reporting |  |  |  | 3 | 137 | 0 | 1.5.8
RFP_154542403_Digital_Marketing_Services | 1.5.9.1 | 1.5.9 | Distribution | Reporting | Ad-Platform Reporting | Distribution | Analyst | Mid | 3 | 137 | 0 | 1.5.9
RFP_154542403_Digital_Marketing_Services | 1.6 | 1 | Brand Identity Development | Brand Identity Development |  |  |  |  | 255 | 137 | 12 | 1.5 |  | Core/T2_MediumVolume
RFP_154542403_Digital_Marketing_Services | 1.6.1 | 1.6 | Color Palette | Brand Identity Development | Color Palette |  |  |  | 15 | 137 | 2 | 1.6
RFP_154542403_Digital_Marketing_Services | 1.6.1.1 | 1.6.1 | Client Review & Revisions | Brand Identity Development | Color Palette | Client Review & Revisions | Designer | Mid | 15 | 137 | 2 | 1.6.1
RFP_154542403_Digital_Marketing_Services | 1.6.2 | 1.6 | Graphic Mock-Ups | Brand Identity Development | Graphic Mock-Ups |  |  |  | 25 | 139 | 8 | 1.6.1
RFP_154542403_Digital_Marketing_Services | 1.6.2.1 | 1.6.2 | Compositing/Retouch | Brand Identity Development | Graphic Mock-Ups | Compositing/Retouch | Retoucher | Mid | 4 | 139 | 3 | 1.6.2
RFP_154542403_Digital_Marketing_Services | 1.6.2.2 | 1.6.2 | Internal Review & Critique | Brand Identity Development | Graphic Mock-Ups | Internal Review & Critique | Art Director | Lead/Director | 1 | 144 | 2 | 1.6.2.1
RFP_154542403_Digital_Marketing_Services | 1.6.2.3 | 1.6.2 | Client Review & Revisions | Brand Identity Development | Graphic Mock-Ups | Client Review & Revisions | Account Manager | Mid | 4 | 146 | 3 | 1.6.2.2
RFP_154542403_Digital_Marketing_Services | 1.6.2.4 | 1.6.2 | Mockup Scenarios (3-4) | Brand Identity Development | Graphic Mock-Ups | Mockup Scenarios (3-4) | Designer | Mid | 16 | 149 | 0 | 1.6.2.3
RFP_154542403_Digital_Marketing_Services | 1.6.3 | 1.6 | Logo | Brand Identity Development | Logo |  |  |  | 37 | 142 | 7 | 1.6.2
RFP_154542403_Digital_Marketing_Services | 1.6.3.1 | 1.6.3 | Quality Check (Specs/Accessibility) | Brand Identity Development | Logo | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 | 142 | 2 | 1.6.3
RFP_154542403_Digital_Marketing_Services | 1.6.3.2 | 1.6.3 | Internal Review & Critique | Brand Identity Development | Logo | Internal Review & Critique | Art Director | Lead/Director | 1 | 144 | 2 | 1.6.3.1
RFP_154542403_Digital_Marketing_Services | 1.6.3.3 | 1.6.3 | Client Review & Revisions | Brand Identity Development | Logo | Client Review & Revisions | Account Manager | Mid | 3 | 146 | 3 | 1.6.3.2
RFP_154542403_Digital_Marketing_Services | 1.6.3.4 | 1.6.3 | Logo Exploration (6-8 dirs) | Brand Identity Development | Logo | Logo Exploration (6-8 dirs) | Designer | Mid | 30 | 149 | 0 | 1.6.3.3
RFP_154542403_Digital_Marketing_Services | 1.6.4 | 1.6 | Typography | Brand Identity Development | Typography |  |  |  | 34 | 142 | 7 | 1.6.3
RFP_154542403_Digital_Marketing_Services | 1.6.4.1 | 1.6.4 | Quality Check (Specs/Accessibility) | Brand Identity Development | Typography | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 | 142 | 2 | 1.6.4
RFP_154542403_Digital_Marketing_Services | 1.6.4.2 | 1.6.4 | Internal Review & Critique | Brand Identity Development | Typography | Internal Review & Critique | Art Director | Lead/Director | 1 | 144 | 2 | 1.6.4.1
RFP_154542403_Digital_Marketing_Services | 1.6.4.3 | 1.6.4 | Client Review & Revisions | Brand Identity Development | Typography | Client Review & Revisions | Account Manager | Mid | 3 | 146 | 3 | 1.6.4.2
RFP_154542403_Digital_Marketing_Services | 1.6.4.4 | 1.6.4 | Final Packaging | Brand Identity Development | Typography | Final Packaging | Designer | Mid | 27 | 149 | 0 | 1.6.4.3
RFP_154542403_Digital_Marketing_Services | 1.6.5 | 1.6 | Graphic & Copy Messaging Cornerstones | Brand Identity Development | Graphic & Copy Messaging Cornerstones |  |  |  | 23 | 144 | 5 | 1.6.4
RFP_154542403_Digital_Marketing_Services | 1.6.5.1 | 1.6.5 | Internal Review & Critique | Brand Identity Development | Graphic & Copy Messaging Cornerstones | Internal Review & Critique | Art Director | Lead/Director | 1 | 144 | 2 | 1.6.5
RFP_154542403_Digital_Marketing_Services | 1.6.5.2 | 1.6.5 | Client Review & Revisions | Brand Identity Development | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Account Manager | Mid | 4 | 146 | 3 | 1.6.5.1
RFP_154542403_Digital_Marketing_Services | 1.6.5.3 | 1.6.5 | Messaging Cornerstones Draft | Brand Identity Development | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft | Designer | Mid | 18 | 149 | 0 | 1.6.5.2
RFP_154542403_Digital_Marketing_Services | 1.6.6 | 1.6 | Iconography | Brand Identity Development | Iconography |  |  |  | 27 | 144 | 5 | 1.6.5
RFP_154542403_Digital_Marketing_Services | 1.6.6.1 | 1.6.6 | Internal Review & Critique | Brand Identity Development | Iconography | Internal Review & Critique | Art Director | Lead/Director | 1 | 144 | 2 | 1.6.6
RFP_154542403_Digital_Marketing_Services | 1.6.6.2 | 1.6.6 | Client Review & Revisions | Brand Identity Development | Iconography | Client Review & Revisions | Account Manager | Mid | 4 | 146 | 3 | 1.6.6.1
RFP_154542403_Digital_Marketing_Services | 1.6.6.3 | 1.6.6 | Export & Spec | Brand Identity Development | Iconography | Export & Spec | Designer | Mid | 22 | 149 | 0 | 1.6.6.2
RFP_154542403_Digital_Marketing_Services | 1.6.7 | 1.6 | Overarching Moodboard | Brand Identity Development | Overarching Moodboard |  |  |  | 23 | 144 | 5 | 1.6.6
RFP_154542403_Digital_Marketing_Services | 1.6.7.1 | 1.6.7 | Internal Review & Critique | Brand Identity Development | Overarching Moodboard | Internal Review & Critique | Art Director | Lead/Director | 1 | 144 | 2 | 1.6.7
RFP_154542403_Digital_Marketing_Services | 1.6.7.2 | 1.6.7 | Client Review & Revisions | Brand Identity Development | Overarching Moodboard | Client Review & Revisions | Account Manager | Mid | 4 | 146 | 3 | 1.6.7.1
RFP_154542403_Digital_Marketing_Services | 1.6.7.3 | 1.6.7 | Curate Moodboard | Brand Identity Development | Overarching Moodboard | Curate Moodboard | Designer | Mid | 18 | 149 | 0 | 1.6.7.2
RFP_154542403_Digital_Marketing_Services | 1.6.8 | 1.6 | Tagline Copy Bank | Brand Identity Development | Tagline Copy Bank |  |  |  | 18 | 144 | 5 | 1.6.7
RFP_154542403_Digital_Marketing_Services | 1.6.8.1 | 1.6.8 | Internal Review & Critique | Brand Identity Development | Tagline Copy Bank | Internal Review & Critique | Art Director | Lead/Director | 1 | 144 | 2 | 1.6.8
RFP_154542403_Digital_Marketing_Services | 1.6.8.2 | 1.6.8 | Client Review & Revisions | Brand Identity Development | Tagline Copy Bank | Client Review & Revisions | Account Manager | Mid | 4 | 146 | 3 | 1.6.8.1
RFP_154542403_Digital_Marketing_Services | 1.6.8.3 | 1.6.8 | Shortlist & Rationale | Brand Identity Development | Tagline Copy Bank | Shortlist & Rationale | Designer | Mid | 13 | 149 | 0 | 1.6.8.2
RFP_154542403_Digital_Marketing_Services | 1.6.9 | 1.6 | Textures/Patterns/Materials | Brand Identity Development | Textures/Patterns/Materials |  |  |  | 25 | 144 | 5 | 1.6.8
RFP_154542403_Digital_Marketing_Services | 1.6.9.1 | 1.6.9 | Internal Review & Critique | Brand Identity Development | Textures/Patterns/Materials | Internal Review & Critique | Art Director | Lead/Director | 1 | 144 | 2 | 1.6.9
RFP_154542403_Digital_Marketing_Services | 1.6.9.2 | 1.6.9 | Client Review & Revisions | Brand Identity Development | Textures/Patterns/Materials | Client Review & Revisions | Account Manager | Mid | 4 | 146 | 3 | 1.6.9.1
RFP_154542403_Digital_Marketing_Services | 1.6.9.3 | 1.6.9 | Build Repeating Tiles | Brand Identity Development | Textures/Patterns/Materials | Build Repeating Tiles | Designer | Mid | 20 | 149 | 0 | 1.6.9.2
RFP_154542403_Digital_Marketing_Services | 1.6.10 | 1.6 | Visual Elements/Comps | Brand Identity Development | Visual Elements/Comps |  |  |  | 28 | 144 | 5 | 1.6.9
RFP_154542403_Digital_Marketing_Services | 1.6.10.1 | 1.6.10 | Internal Review & Critique | Brand Identity Development | Visual Elements/Comps | Internal Review & Critique | Art Director | Lead/Director | 1 | 144 | 2 | 1.6.10
RFP_154542403_Digital_Marketing_Services | 1.6.10.2 | 1.6.10 | Client Review & Revisions | Brand Identity Development | Visual Elements/Comps | Client Review & Revisions | Account Manager | Mid | 4 | 146 | 3 | 1.6.10.1
RFP_154542403_Digital_Marketing_Services | 1.6.10.3 | 1.6.10 | Compositions (2-3) | Brand Identity Development | Visual Elements/Comps | Compositions (2-3) | Designer | Mid | 23 | 149 | 0 | 1.6.10.2
RFP_154542403_Digital_Marketing_Services | 1.7 | 1 | Brand Style & Usage Guidelines | Brand Style & Usage Guidelines |  |  |  |  | 250 | 149 | 9 | 1.6 |  | Core/T2_MediumVolume
RFP_154542403_Digital_Marketing_Services | 1.7.1 | 1.7 | Color Palettes | Brand Style & Usage Guidelines | Color Palettes |  |  |  | 13 | 149 | 2 | 1.7
RFP_154542403_Digital_Marketing_Services | 1.7.1.1 | 1.7.1 | Client Review & Revisions | Brand Style & Usage Guidelines | Color Palettes | Client Review & Revisions | Designer | Mid | 13 | 149 | 2 | 1.7.1
RFP_154542403_Digital_Marketing_Services | 1.7.2 | 1.7 | Logo Lock-Ups | Brand Style & Usage Guidelines | Logo Lock-Ups |  |  |  | 28 | 151 | 7 | 1.7.1
RFP_154542403_Digital_Marketing_Services | 1.7.2.1 | 1.7.2 | Quality Check (Specs/Accessibility) | Brand Style & Usage Guidelines | Logo Lock-Ups | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 | 151 | 2 | 1.7.2
RFP_154542403_Digital_Marketing_Services | 1.7.2.2 | 1.7.2 | Internal Review & Critique | Brand Style & Usage Guidelines | Logo Lock-Ups | Internal Review & Critique | Art Director | Lead/Director | 1 | 153 | 2 | 1.7.2.1
RFP_154542403_Digital_Marketing_Services | 1.7.2.3 | 1.7.2 | Client Review & Revisions | Brand Style & Usage Guidelines | Logo Lock-Ups | Client Review & Revisions | Account Manager | Mid | 3 | 155 | 3 | 1.7.2.2
RFP_154542403_Digital_Marketing_Services | 1.7.2.4 | 1.7.2 | Final Packaging | Brand Style & Usage Guidelines | Logo Lock-Ups | Final Packaging | Designer | Mid | 21 | 158 | 0 | 1.7.2.3
RFP_154542403_Digital_Marketing_Services | 1.7.3 | 1.7 | Logo Placement | Brand Style & Usage Guidelines | Logo Placement |  |  |  | 27 | 151 | 7 | 1.7.2
RFP_154542403_Digital_Marketing_Services | 1.7.3.1 | 1.7.3 | Quality Check (Specs/Accessibility) | Brand Style & Usage Guidelines | Logo Placement | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 | 151 | 2 | 1.7.3
RFP_154542403_Digital_Marketing_Services | 1.7.3.2 | 1.7.3 | Internal Review & Critique | Brand Style & Usage Guidelines | Logo Placement | Internal Review & Critique | Art Director | Lead/Director | 1 | 153 | 2 | 1.7.3.1
RFP_154542403_Digital_Marketing_Services | 1.7.3.3 | 1.7.3 | Client Review & Revisions | Brand Style & Usage Guidelines | Logo Placement | Client Review & Revisions | Account Manager | Mid | 3 | 155 | 3 | 1.7.3.2
RFP_154542403_Digital_Marketing_Services | 1.7.3.4 | 1.7.3 | Final Packaging | Brand Style & Usage Guidelines | Logo Placement | Final Packaging | Designer | Mid | 20 | 158 | 0 | 1.7.3.3
RFP_154542403_Digital_Marketing_Services | 1.7.4 | 1.7 | Brand Do's & Dont's | Brand Style & Usage Guidelines | Brand Do's & Dont's |  |  |  | 33 | 153 | 5 | 1.7.3
RFP_154542403_Digital_Marketing_Services | 1.7.4.1 | 1.7.4 | Internal Review & Critique | Brand Style & Usage Guidelines | Brand Do's & Dont's | Internal Review & Critique | Art Director | Lead/Director | 1 | 153 | 2 | 1.7.4
RFP_154542403_Digital_Marketing_Services | 1.7.4.2 | 1.7.4 | Client Review & Revisions | Brand Style & Usage Guidelines | Brand Do's & Dont's | Client Review & Revisions | Account Manager | Mid | 4 | 155 | 3 | 1.7.4.1
RFP_154542403_Digital_Marketing_Services | 1.7.4.3 | 1.7.4 | Outline & Examples | Brand Style & Usage Guidelines | Brand Do's & Dont's | Outline & Examples | Designer | Mid | 28 | 158 | 0 | 1.7.4.2
RFP_154542403_Digital_Marketing_Services | 1.7.5 | 1.7 | Design Style Tile | Brand Style & Usage Guidelines | Design Style Tile |  |  |  | 23 | 153 | 5 | 1.7.4
RFP_154542403_Digital_Marketing_Services | 1.7.5.1 | 1.7.5 | Internal Review & Critique | Brand Style & Usage Guidelines | Design Style Tile | Internal Review & Critique | Art Director | Lead/Director | 1 | 153 | 2 | 1.7.5
RFP_154542403_Digital_Marketing_Services | 1.7.5.2 | 1.7.5 | Client Review & Revisions | Brand Style & Usage Guidelines | Design Style Tile | Client Review & Revisions | Account Manager | Mid | 4 | 155 | 3 | 1.7.5.1
RFP_154542403_Digital_Marketing_Services | 1.7.5.3 | 1.7.5 | Style Tile Build | Brand Style & Usage Guidelines | Design Style Tile | Style Tile Build | Designer | Mid | 18 | 158 | 0 | 1.7.5.2
RFP_154542403_Digital_Marketing_Services | 1.7.6 | 1.7 | Image Use Guidance | Brand Style & Usage Guidelines | Image Use Guidance |  |  |  | 23 | 153 | 5 | 1.7.5
RFP_154542403_Digital_Marketing_Services | 1.7.6.1 | 1.7.6 | Internal Review & Critique | Brand Style & Usage Guidelines | Image Use Guidance | Internal Review & Critique | Art Director | Lead/Director | 1 | 153 | 2 | 1.7.6
RFP_154542403_Digital_Marketing_Services | 1.7.6.2 | 1.7.6 | Client Review & Revisions | Brand Style & Usage Guidelines | Image Use Guidance | Client Review & Revisions | Account Manager | Mid | 4 | 155 | 3 | 1.7.6.1
RFP_154542403_Digital_Marketing_Services | 1.7.6.3 | 1.7.6 | Examples & Callouts | Brand Style & Usage Guidelines | Image Use Guidance | Examples & Callouts | Designer | Mid | 18 | 158 | 0 | 1.7.6.2
RFP_154542403_Digital_Marketing_Services | 1.7.7 | 1.7 | Imagery Style | Brand Style & Usage Guidelines | Imagery Style |  |  |  | 23 | 153 | 5 | 1.7.6
RFP_154542403_Digital_Marketing_Services | 1.7.7.1 | 1.7.7 | Internal Review & Critique | Brand Style & Usage Guidelines | Imagery Style | Internal Review & Critique | Art Director | Lead/Director | 1 | 153 | 2 | 1.7.7
RFP_154542403_Digital_Marketing_Services | 1.7.7.2 | 1.7.7 | Client Review & Revisions | Brand Style & Usage Guidelines | Imagery Style | Client Review & Revisions | Account Manager | Mid | 4 | 155 | 3 | 1.7.7.1
RFP_154542403_Digital_Marketing_Services | 1.7.7.3 | 1.7.7 | Examples & Callouts | Brand Style & Usage Guidelines | Imagery Style | Examples & Callouts | Designer | Mid | 18 | 158 | 0 | 1.7.7.2
RFP_154542403_Digital_Marketing_Services | 1.7.8 | 1.7 | Photo & Video Direction | Brand Style & Usage Guidelines | Photo & Video Direction |  |  |  | 25 | 153 | 5 | 1.7.7
RFP_154542403_Digital_Marketing_Services | 1.7.8.1 | 1.7.8 | Internal Review & Critique | Brand Style & Usage Guidelines | Photo & Video Direction | Internal Review & Critique | Art Director | Lead/Director | 1 | 153 | 2 | 1.7.8
RFP_154542403_Digital_Marketing_Services | 1.7.8.2 | 1.7.8 | Client Review & Revisions | Brand Style & Usage Guidelines | Photo & Video Direction | Client Review & Revisions | Account Manager | Mid | 4 | 155 | 3 | 1.7.8.1
RFP_154542403_Digital_Marketing_Services | 1.7.8.3 | 1.7.8 | Direction Pages | Brand Style & Usage Guidelines | Photo & Video Direction | Direction Pages | Designer | Mid | 20 | 158 | 0 | 1.7.8.2
RFP_154542403_Digital_Marketing_Services | 1.7.9 | 1.7 | Typography | Brand Style & Usage Guidelines | Typography |  |  |  | 18 | 153 | 5 | 1.7.8
RFP_154542403_Digital_Marketing_Services | 1.7.9.1 | 1.7.9 | Internal Review & Critique | Brand Style & Usage Guidelines | Typography | Internal Review & Critique | Art Director | Lead/Director | 1 | 153 | 2 | 1.7.9
RFP_154542403_Digital_Marketing_Services | 1.7.9.2 | 1.7.9 | Client Review & Revisions | Brand Style & Usage Guidelines | Typography | Client Review & Revisions | Account Manager | Mid | 3 | 155 | 3 | 1.7.9.1
RFP_154542403_Digital_Marketing_Services | 1.7.9.3 | 1.7.9 | Final Packaging | Brand Style & Usage Guidelines | Typography | Final Packaging | Designer | Mid | 14 | 158 | 0 | 1.7.9.2
RFP_154542403_Digital_Marketing_Services | 1.7.10 | 1.7 | Use Cases | Brand Style & Usage Guidelines | Use Cases |  |  |  | 22 | 153 | 5 | 1.7.9
RFP_154542403_Digital_Marketing_Services | 1.7.10.1 | 1.7.10 | Internal Review & Critique | Brand Style & Usage Guidelines | Use Cases | Internal Review & Critique | Art Director | Lead/Director | 1 | 153 | 2 | 1.7.10
RFP_154542403_Digital_Marketing_Services | 1.7.10.2 | 1.7.10 | Client Review & Revisions | Brand Style & Usage Guidelines | Use Cases | Client Review & Revisions | Account Manager | Mid | 4 | 155 | 3 | 1.7.10.1
RFP_154542403_Digital_Marketing_Services | 1.7.10.3 | 1.7.10 | Final Packaging | Brand Style & Usage Guidelines | Use Cases | Final Packaging | Designer | Mid | 17 | 158 | 0 | 1.7.10.2
RFP_154542403_Digital_Marketing_Services | 1.7.11 | 1.7 | Graphic Treatment Direction | Brand Style & Usage Guidelines | Graphic Treatment Direction |  |  |  | 15 | 158 | 0 | 1.7.10
RFP_154542403_Digital_Marketing_Services | 1.7.11.1 | 1.7.11 | Client Review & Revisions | Brand Style & Usage Guidelines | Graphic Treatment Direction | Client Review & Revisions | Creative Director | Lead/Director | 15 | 158 | 0 | 1.7.11
RFP_154542403_Digital_Marketing_Services | 1.8 | 1 | Reporting | Reporting |  |  |  |  | 109 | 158 | 5 | 1.7 |  | Core/T2_MediumVolume
RFP_154542403_Digital_Marketing_Services | 1.8.1 | 1.8 | Dashboards | Reporting | Dashboards |  |  |  | 8 | 158 | 5 | 1.8
RFP_154542403_Digital_Marketing_Services | 1.8.1.1 | 1.8.1 | QA | Reporting | Dashboards | QA | QA Specialist | Mid | 3 | 158 | 2 | 1.8.1
RFP_154542403_Digital_Marketing_Services | 1.8.1.2 | 1.8.1 | Dashboard Build/Refresh | Reporting | Dashboards | Dashboard Build/Refresh | Analyst | Mid | 5 | 160 | 3 | 1.8.1.1
RFP_154542403_Digital_Marketing_Services | 1.8.2 | 1.8 | Engagement Rate | Reporting | Engagement Rate |  |  |  | 5 | 158 | 2 | 1.8.1
RFP_154542403_Digital_Marketing_Services | 1.8.2.1 | 1.8.2 | Data Refresh & Calc Check | Reporting | Engagement Rate | Data Refresh & Calc Check | QA Specialist | Mid | 5 | 158 | 2 | 1.8.2
RFP_154542403_Digital_Marketing_Services | 1.8.3 | 1.8 | Emplifi Reports | Reporting | Emplifi Reports |  |  |  | 6 | 160 | 3 | 1.8.2
RFP_154542403_Digital_Marketing_Services | 1.8.3.1 | 1.8.3 | Emplifi Extract & Summary | Reporting | Emplifi Reports | Emplifi Extract & Summary | Analyst | Mid | 6 | 160 | 3 | 1.8.3
RFP_154542403_Digital_Marketing_Services | 1.8.4 | 1.8 | Monthly Comprehensive Report | Reporting | Monthly Comprehensive Report |  |  |  | 9 | 160 | 3 | 1.8.3
RFP_154542403_Digital_Marketing_Services | 1.8.4.1 | 1.8.4 | Monthly Report | Reporting | Monthly Comprehensive Report | Monthly Report | Analyst | Mid | 9 | 160 | 3 | 1.8.4
RFP_154542403_Digital_Marketing_Services | 1.8.5 | 1.8 | Monthly Organic Social Report | Reporting | Monthly Organic Social Report |  |  |  | 9 | 160 | 3 | 1.8.4
RFP_154542403_Digital_Marketing_Services | 1.8.5.1 | 1.8.5 | Monthly Organic Report | Reporting | Monthly Organic Social Report | Monthly Organic Report | Analyst | Mid | 9 | 160 | 3 | 1.8.5
RFP_154542403_Digital_Marketing_Services | 1.8.6 | 1.8 | Optimization Recommendations Report | Reporting | Optimization Recommendations Report |  |  |  | 9 | 160 | 3 | 1.8.5
RFP_154542403_Digital_Marketing_Services | 1.8.6.1 | 1.8.6 | Recs & Next Steps | Reporting | Optimization Recommendations Report | Recs & Next Steps | Analyst | Mid | 9 | 160 | 3 | 1.8.6
RFP_154542403_Digital_Marketing_Services | 1.8.7 | 1.8 | Quarterly Ad-Hoc Report | Reporting | Quarterly Ad-Hoc Report |  |  |  | 8 | 160 | 3 | 1.8.6
RFP_154542403_Digital_Marketing_Services | 1.8.7.1 | 1.8.7 | Quarterly Ad-hoc Deep Dive | Reporting | Quarterly Ad-Hoc Report | Quarterly Ad-hoc Deep Dive | Analyst | Mid | 8 | 160 | 3 | 1.8.7
RFP_154542403_Digital_Marketing_Services | 1.8.8 | 1.8 | Quarterly Key Learnings & Insights Report | Reporting | Quarterly Key Learnings & Insights Report |  |  |  | 9 | 160 | 3 | 1.8.7
RFP_154542403_Digital_Marketing_Services | 1.8.8.1 | 1.8.8 | Quarterly Learnings & Insights | Reporting | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights | Analyst | Mid | 9 | 160 | 3 | 1.8.8
RFP_154542403_Digital_Marketing_Services | 1.8.9 | 1.8 | Quarterly Report | Reporting | Quarterly Report |  |  |  | 9 | 160 | 3 | 1.8.8
RFP_154542403_Digital_Marketing_Services | 1.8.9.1 | 1.8.9 | Quarterly Report | Reporting | Quarterly Report | Quarterly Report | Analyst | Mid | 9 | 160 | 3 | 1.8.9
RFP_154542403_Digital_Marketing_Services | 1.8.10 | 1.8 | Summary overview | Reporting | Summary overview |  |  |  | 3 | 160 | 3 | 1.8.9
RFP_154542403_Digital_Marketing_Services | 1.8.10.1 | 1.8.10 | Summary Narrative | Reporting | Summary overview | Summary Narrative | Social Strategist | Mid | 3 | 160 | 3 | 1.8.10
RFP_154542403_Digital_Marketing_Services | 1.8.11 | 1.8 | Weekly Activity Report | Reporting | Weekly Activity Report |  |  |  | 6 | 160 | 3 | 1.8.10
RFP_154542403_Digital_Marketing_Services | 1.8.11.1 | 1.8.11 | Weekly Activity Summary | Reporting | Weekly Activity Report | Weekly Activity Summary | Analyst | Mid | 6 | 160 | 3 | 1.8.11
RFP_154542403_Digital_Marketing_Services | 1.8.12 | 1.8 | Follower Growth | Reporting | Follower Growth |  |  |  | 5 | 163 | 0 | 1.8.11
RFP_154542403_Digital_Marketing_Services | 1.8.12.1 | 1.8.12 | Metric Pull & Notes | Reporting | Follower Growth | Metric Pull & Notes | QA Specialist | Mid | 5 | 163 | 0 | 1.8.12
RFP_154542403_Digital_Marketing_Services | 1.8.13 | 1.8 | Impressions | Reporting | Impressions |  |  |  | 5 | 163 | 0 | 1.8.12
RFP_154542403_Digital_Marketing_Services | 1.8.13.1 | 1.8.13 | Metric Pull & Notes | Reporting | Impressions | Metric Pull & Notes | QA Specialist | Mid | 5 | 163 | 0 | 1.8.13
RFP_154542403_Digital_Marketing_Services | 1.8.14 | 1.8 | Interactions | Reporting | Interactions |  |  |  | 5 | 163 | 0 | 1.8.13
RFP_154542403_Digital_Marketing_Services | 1.8.14.1 | 1.8.14 | Metric Pull & Notes | Reporting | Interactions | Metric Pull & Notes | QA Specialist | Mid | 5 | 163 | 0 | 1.8.14
RFP_154542403_Digital_Marketing_Services | 1.8.15 | 1.8 | Profile Reach | Reporting | Profile Reach |  |  |  | 5 | 163 | 0 | 1.8.14
RFP_154542403_Digital_Marketing_Services | 1.8.15.1 | 1.8.15 | Metric Pull & Notes | Reporting | Profile Reach | Metric Pull & Notes | QA Specialist | Mid | 5 | 163 | 0 | 1.8.15
RFP_154542403_Digital_Marketing_Services | 1.8.16 | 1.8 | Recap Reports | Reporting | Recap Reports |  |  |  | 3 | 163 | 0 | 1.8.15
RFP_154542403_Digital_Marketing_Services | 1.8.16.1 | 1.8.16 | Campaign/Period Recaps | Reporting | Recap Reports | Campaign/Period Recaps | Analyst | Mid | 3 | 163 | 0 | 1.8.16
RFP_154542403_Digital_Marketing_Services | 1.8.17 | 1.8 | Social Reporting | Reporting | Social Reporting |  |  |  | 3 | 163 | 0 | 1.8.16
RFP_154542403_Digital_Marketing_Services | 1.8.17.1 | 1.8.17 | Ongoing Social Reporting | Reporting | Social Reporting | Ongoing Social Reporting | Analyst | Mid | 3 | 163 | 0 | 1.8.17
RFP_154542403_Digital_Marketing_Services | 1.8.18 | 1.8 | Update/maintain Z/Russia tracker | Reporting | Update/maintain Z/Russia tracker |  |  |  | 2 | 163 | 0 | 1.8.17
RFP_154542403_Digital_Marketing_Services | 1.8.18.1 | 1.8.18 | Tracker Update | Reporting | Update/maintain Z/Russia tracker | Tracker Update | Analyst | Mid | 2 | 163 | 0 | 1.8.18

## Scenario B
Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Deliverable | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes
RFP_154542403_Digital_Marketing_Services | 1 |  | RFP_154542403_Digital_Marketing_Services |  | Project |  |  |  |  | 0
RFP_154542403_Digital_Marketing_Services | 1.1 | 1 | Development | Development |  |  |  |  | 348 | 0 | 28 |  |  | Advanced/T1_LargeVolume
RFP_154542403_Digital_Marketing_Services | 1.1.1 | 1.1 | ADA Compliance | Development | ADA Compliance |  |  |  | 77 | 0 | 19 | 1.1
RFP_154542403_Digital_Marketing_Services | 1.1.1.1 | 1.1.1 | Accessibility Audit | Development | ADA Compliance | Accessibility Audit | Accessibility Specialist | Mid | 3 | 0 | 4 | 1.1.1
RFP_154542403_Digital_Marketing_Services | 1.1.1.2 | 1.1.1 | Accessibility QA | Development | ADA Compliance | Accessibility QA | QA Engineer | Mid | 6 | 13 | 3 | 1.1.1.1
RFP_154542403_Digital_Marketing_Services | 1.1.1.3 | 1.1.1 | Code Review | Development | ADA Compliance | Code Review | Frontend Engineer | Mid | 68 | 16 | 12 | 1.1.1.2
RFP_154542403_Digital_Marketing_Services | 1.1.2 | 1.1 | Audit & Requirement gathering | Development | Audit & Requirement gathering |  |  |  | 26 | 0 | 4 | 1.1.1
RFP_154542403_Digital_Marketing_Services | 1.1.2.1 | 1.1.2 | Analytics Audit | Development | Audit & Requirement gathering | Analytics Audit | Business Analyst | Mid | 26 | 0 | 4 | 1.1.2
RFP_154542403_Digital_Marketing_Services | 1.1.3 | 1.1 | Audit existing UA Property | Development | Audit existing UA Property |  |  |  | 26 | 0 | 4 | 1.1.2
RFP_154542403_Digital_Marketing_Services | 1.1.3.1 | 1.1.3 | Documentation | Development | Audit existing UA Property | Documentation | Business Analyst | Mid | 26 | 0 | 4 | 1.1.3
RFP_154542403_Digital_Marketing_Services | 1.1.4 | 1.1 | Footer CTA | Development | Footer CTA |  |  |  | 66 | 4 | 24 | 1.1.3
RFP_154542403_Digital_Marketing_Services | 1.1.4.1 | 1.1.4 | Design Consult | Development | Footer CTA | Design Consult | UI Designer | Mid | 5 | 4 | 9 | 1.1.4
RFP_154542403_Digital_Marketing_Services | 1.1.4.2 | 1.1.4 | Accessibility QA | Development | Footer CTA | Accessibility QA | QA Engineer | Mid | 9 | 13 | 3 | 1.1.4.1
RFP_154542403_Digital_Marketing_Services | 1.1.4.3 | 1.1.4 | Code Review | Development | Footer CTA | Code Review | Backend Engineer | Mid | 52 | 16 | 12 | 1.1.4.2
RFP_154542403_Digital_Marketing_Services | 1.1.5 | 1.1 | Header & Footer Navigation | Development | Header & Footer Navigation |  |  |  | 66 | 4 | 24 | 1.1.4
RFP_154542403_Digital_Marketing_Services | 1.1.5.1 | 1.1.5 | Design Consult | Development | Header & Footer Navigation | Design Consult | UI Designer | Mid | 5 | 4 | 9 | 1.1.5
RFP_154542403_Digital_Marketing_Services | 1.1.5.2 | 1.1.5 | Accessibility QA | Development | Header & Footer Navigation | Accessibility QA | QA Engineer | Mid | 9 | 13 | 3 | 1.1.5.1
RFP_154542403_Digital_Marketing_Services | 1.1.5.3 | 1.1.5 | Code Review | Development | Header & Footer Navigation | Code Review | Backend Engineer | Mid | 52 | 16 | 12 | 1.1.5.2
RFP_154542403_Digital_Marketing_Services | 1.1.6 | 1.1 | Additional Goals Setup | Development | Additional Goals Setup |  |  |  | 11 | 13 | 15 | 1.1.5
RFP_154542403_Digital_Marketing_Services | 1.1.6.1 | 1.1.6 | QA Cycle | Development | Additional Goals Setup | QA Cycle | QA Engineer | Mid | 4 | 13 | 3 | 1.1.6
RFP_154542403_Digital_Marketing_Services | 1.1.6.2 | 1.1.6 | Define & Configure Goals | Development | Additional Goals Setup | Define & Configure Goals | Data/Analytics Engineer | Mid | 7 | 16 | 12 | 1.1.6.1
RFP_154542403_Digital_Marketing_Services | 1.1.7 | 1.1 | Custom Event Tracking | Development | Custom Event Tracking |  |  |  | 11 | 13 | 15 | 1.1.6
RFP_154542403_Digital_Marketing_Services | 1.1.7.1 | 1.1.7 | QA Cycle | Development | Custom Event Tracking | QA Cycle | QA Engineer | Mid | 4 | 13 | 3 | 1.1.7
RFP_154542403_Digital_Marketing_Services | 1.1.7.2 | 1.1.7 | Event Schema & Tagging | Development | Custom Event Tracking | Event Schema & Tagging | Data/Analytics Engineer | Mid | 7 | 16 | 12 | 1.1.7.1
RFP_154542403_Digital_Marketing_Services | 1.1.8 | 1.1 | Implement Paid Media Pixel on website w GTM-Google Ads | Development | Implement Paid Media Pixel on website w GTM-Google Ads |  |  |  | 7 | 13 | 15 | 1.1.7
RFP_154542403_Digital_Marketing_Services | 1.1.8.1 | 1.1.8 | Spec QA | Development | Implement Paid Media Pixel on website w GTM-Google Ads | Spec QA | QA Engineer | Mid | 4 | 13 | 3 | 1.1.8
RFP_154542403_Digital_Marketing_Services | 1.1.8.2 | 1.1.8 | Pixel Setup (GTM) | Development | Implement Paid Media Pixel on website w GTM-Google Ads | Pixel Setup (GTM) | Data/Analytics Engineer | Mid | 3 | 16 | 12 | 1.1.8.1
RFP_154542403_Digital_Marketing_Services | 1.1.9 | 1.1 | Implement goals listed in UA as Conversions in G4 | Development | Implement goals listed in UA as Conversions in G4 |  |  |  | 10 | 13 | 15 | 1.1.8
RFP_154542403_Digital_Marketing_Services | 1.1.9.1 | 1.1.9 | QA Cycle | Development | Implement goals listed in UA as Conversions in G4 | QA Cycle | QA Engineer | Mid | 4 | 13 | 3 | 1.1.9
RFP_154542403_Digital_Marketing_Services | 1.1.9.2 | 1.1.9 | Migrate UA Goals → GA4 Conversions | Development | Implement goals listed in UA as Conversions in G4 | Migrate UA Goals → GA4 Conversions | Data/Analytics Engineer | Mid | 6 | 16 | 12 | 1.1.9.1
RFP_154542403_Digital_Marketing_Services | 1.1.10 | 1.1 | Implementation | Development | Implementation |  |  |  | 10 | 13 | 15 | 1.1.9
RFP_154542403_Digital_Marketing_Services | 1.1.10.1 | 1.1.10 | QA Cycle | Development | Implementation | QA Cycle | QA Engineer | Mid | 4 | 13 | 3 | 1.1.10
RFP_154542403_Digital_Marketing_Services | 1.1.10.2 | 1.1.10 | Implement Tags/Events | Development | Implementation | Implement Tags/Events | Data/Analytics Engineer | Mid | 6 | 16 | 12 | 1.1.10.1
RFP_154542403_Digital_Marketing_Services | 1.1.11 | 1.1 | Outbound link clicks | Development | Outbound link clicks |  |  |  | 7 | 13 | 15 | 1.1.10
RFP_154542403_Digital_Marketing_Services | 1.1.11.1 | 1.1.11 | QA | Development | Outbound link clicks | QA | QA Engineer | Mid | 4 | 13 | 3 | 1.1.11
RFP_154542403_Digital_Marketing_Services | 1.1.11.2 | 1.1.11 | Event Config | Development | Outbound link clicks | Event Config | Data/Analytics Engineer | Mid | 3 | 16 | 12 | 1.1.11.1
RFP_154542403_Digital_Marketing_Services | 1.1.12 | 1.1 | Publishing tags, Testing and Auditing | Development | Publishing tags, Testing and Auditing |  |  |  | 7 | 13 | 3 | 1.1.11
RFP_154542403_Digital_Marketing_Services | 1.1.12.1 | 1.1.12 | Publish & Smoke Test | Development | Publishing tags, Testing and Auditing | Publish & Smoke Test | QA Engineer | Mid | 7 | 13 | 3 | 1.1.12
RFP_154542403_Digital_Marketing_Services | 1.1.13 | 1.1 | Setup cross-domain tracking | Development | Setup cross-domain tracking |  |  |  | 7 | 13 | 15 | 1.1.12
RFP_154542403_Digital_Marketing_Services | 1.1.13.1 | 1.1.13 | QA | Development | Setup cross-domain tracking | QA | QA Engineer | Mid | 4 | 13 | 3 | 1.1.13
RFP_154542403_Digital_Marketing_Services | 1.1.13.2 | 1.1.13 | Cross-domain Config | Development | Setup cross-domain tracking | Cross-domain Config | Data/Analytics Engineer | Mid | 3 | 16 | 12 | 1.1.13.1
RFP_154542403_Digital_Marketing_Services | 1.1.14 | 1.1 | Setup eCommerce tracking | Development | Setup eCommerce tracking |  |  |  | 7 | 13 | 15 | 1.1.13
RFP_154542403_Digital_Marketing_Services | 1.1.14.1 | 1.1.14 | QA | Development | Setup eCommerce tracking | QA | QA Engineer | Mid | 4 | 13 | 3 | 1.1.14
RFP_154542403_Digital_Marketing_Services | 1.1.14.2 | 1.1.14 | Ecommerce Data Layer | Development | Setup eCommerce tracking | Ecommerce Data Layer | Data/Analytics Engineer | Mid | 3 | 16 | 12 | 1.1.14.1
RFP_154542403_Digital_Marketing_Services | 1.1.15 | 1.1 | Setup new GA4 acct for Caledera House | Development | Setup new GA4 acct for Caledera House |  |  |  | 10 | 13 | 15 | 1.1.14
RFP_154542403_Digital_Marketing_Services | 1.1.15.1 | 1.1.15 | QA Cycle | Development | Setup new GA4 acct for Caledera House | QA Cycle | QA Engineer | Mid | 4 | 13 | 3 | 1.1.15
RFP_154542403_Digital_Marketing_Services | 1.1.15.2 | 1.1.15 | GA4 Property Setup | Development | Setup new GA4 acct for Caledera House | GA4 Property Setup | Data/Analytics Engineer | Mid | 6 | 16 | 12 | 1.1.15.1
RFP_154542403_Digital_Marketing_Services | 1.2 | 1 | Paid Media Strategy | Paid Media Strategy |  |  |  |  | 211 | 28 | 48 | 1.1 |  | Advanced/T1_LargeVolume
RFP_154542403_Digital_Marketing_Services | 1.2.1 | 1.2 | Audience Research | Paid Media Strategy | Audience Research |  |  |  | 16 | 28 | 9 | 1.2
RFP_154542403_Digital_Marketing_Services | 1.2.1.1 | 1.2.1 | Audience Build & Rationale | Paid Media Strategy | Audience Research | Audience Build & Rationale | Analyst | Mid | 11 | 28 | 4 | 1.2.1
RFP_154542403_Digital_Marketing_Services | 1.2.1.2 | 1.2.1 | Internal Review & Critique | Paid Media Strategy | Audience Research | Internal Review & Critique | Creative Director | Lead/Director | 2 | 69 | 2 | 1.2.1.1
RFP_154542403_Digital_Marketing_Services | 1.2.1.3 | 1.2.1 | Client Review & Revisions | Paid Media Strategy | Audience Research | Client Review & Revisions | Account Manager | Mid | 3 | 71 | 3 | 1.2.1.2
RFP_154542403_Digital_Marketing_Services | 1.2.2 | 1.2 | Keyword List Development | Paid Media Strategy | Keyword List Development |  |  |  | 21 | 28 | 21 | 1.2.1
RFP_154542403_Digital_Marketing_Services | 1.2.2.1 | 1.2.2 | Keyword Discovery | Paid Media Strategy | Keyword List Development | Keyword Discovery | Analyst | Mid | 7 | 28 | 4 | 1.2.2
RFP_154542403_Digital_Marketing_Services | 1.2.2.2 | 1.2.2 | List Development & Grouping | Paid Media Strategy | Keyword List Development | List Development & Grouping | Media Strategist | Mid | 9 | 57 | 12 | 1.2.2.1
RFP_154542403_Digital_Marketing_Services | 1.2.2.3 | 1.2.2 | Internal Review & Critique | Paid Media Strategy | Keyword List Development | Internal Review & Critique | Creative Director | Lead/Director | 2 | 69 | 2 | 1.2.2.2
RFP_154542403_Digital_Marketing_Services | 1.2.2.4 | 1.2.2 | Client Review & Revisions | Paid Media Strategy | Keyword List Development | Client Review & Revisions | Account Manager | Mid | 3 | 71 | 3 | 1.2.2.3
RFP_154542403_Digital_Marketing_Services | 1.2.3 | 1.2 | Paid Media & Paid Creative Audit | Paid Media Strategy | Paid Media & Paid Creative Audit |  |  |  | 30 | 28 | 15 | 1.2.2
RFP_154542403_Digital_Marketing_Services | 1.2.3.1 | 1.2.3 | Platform/Creative Audit | Paid Media Strategy | Paid Media & Paid Creative Audit | Platform/Creative Audit | Analyst | Mid | 14 | 28 | 4 | 1.2.3
RFP_154542403_Digital_Marketing_Services | 1.2.3.2 | 1.2.3 | Findings Deck | Paid Media Strategy | Paid Media & Paid Creative Audit | Findings Deck | Designer | Mid | 11 | 32 | 6 | 1.2.3.1
RFP_154542403_Digital_Marketing_Services | 1.2.3.3 | 1.2.3 | Internal Review & Critique | Paid Media Strategy | Paid Media & Paid Creative Audit | Internal Review & Critique | Creative Director | Lead/Director | 2 | 69 | 2 | 1.2.3.2
RFP_154542403_Digital_Marketing_Services | 1.2.3.4 | 1.2.3 | Client Review & Revisions | Paid Media Strategy | Paid Media & Paid Creative Audit | Client Review & Revisions | Account Manager | Mid | 3 | 71 | 3 | 1.2.3.3
RFP_154542403_Digital_Marketing_Services | 1.2.4 | 1.2 | Mock Ad Examples | Paid Media Strategy | Mock Ad Examples |  |  |  | 21 | 38 | 18 | 1.2.3
RFP_154542403_Digital_Marketing_Services | 1.2.4.1 | 1.2.4 | Concept & Copy | Paid Media Strategy | Mock Ad Examples | Concept & Copy | Copywriter | Mid | 6 | 38 | 4 | 1.2.4
RFP_154542403_Digital_Marketing_Services | 1.2.4.2 | 1.2.4 | Design (3-4 mocks) | Paid Media Strategy | Mock Ad Examples | Design (3-4 mocks) | Designer | Mid | 5 | 42 | 9 | 1.2.4.1
RFP_154542403_Digital_Marketing_Services | 1.2.4.3 | 1.2.4 | Internal Review & Critique | Paid Media Strategy | Mock Ad Examples | Internal Review & Critique | Creative Director | Lead/Director | 2 | 69 | 2 | 1.2.4.2
RFP_154542403_Digital_Marketing_Services | 1.2.4.4 | 1.2.4 | Client Review & Revisions | Paid Media Strategy | Mock Ad Examples | Client Review & Revisions | Account Manager | Mid | 5 | 71 | 3 | 1.2.4.3
RFP_154542403_Digital_Marketing_Services | 1.2.4.5 | 1.2.4 | Final Packaging | Paid Media Strategy | Mock Ad Examples | Final Packaging | Designer | Mid | 3 | 76 | 0 | 1.2.4.4
RFP_154542403_Digital_Marketing_Services | 1.2.5 | 1.2 | Campaigns | Paid Media Strategy | Campaigns |  |  |  | 31 | 51 | 11 | 1.2.4
RFP_154542403_Digital_Marketing_Services | 1.2.5.1 | 1.2.5 | Campaign Architecture | Paid Media Strategy | Campaigns | Campaign Architecture | Media Planner | Mid | 26 | 51 | 6 | 1.2.5
RFP_154542403_Digital_Marketing_Services | 1.2.5.2 | 1.2.5 | Internal Review & Critique | Paid Media Strategy | Campaigns | Internal Review & Critique | Creative Director | Lead/Director | 2 | 69 | 2 | 1.2.5.1
RFP_154542403_Digital_Marketing_Services | 1.2.5.3 | 1.2.5 | Client Review & Revisions | Paid Media Strategy | Campaigns | Client Review & Revisions | Account Manager | Mid | 3 | 71 | 3 | 1.2.5.2
RFP_154542403_Digital_Marketing_Services | 1.2.6 | 1.2 | Ad Funnel | Paid Media Strategy | Ad Funnel |  |  |  | 21 | 69 | 5 | 1.2.5
RFP_154542403_Digital_Marketing_Services | 1.2.6.1 | 1.2.6 | Internal Review & Critique | Paid Media Strategy | Ad Funnel | Internal Review & Critique | Creative Director | Lead/Director | 2 | 69 | 2 | 1.2.6
RFP_154542403_Digital_Marketing_Services | 1.2.6.2 | 1.2.6 | Client Review & Revisions | Paid Media Strategy | Ad Funnel | Client Review & Revisions | Account Manager | Mid | 3 | 71 | 3 | 1.2.6.1
RFP_154542403_Digital_Marketing_Services | 1.2.6.3 | 1.2.6 | Messaging/Asset Mapping | Paid Media Strategy | Ad Funnel | Messaging/Asset Mapping | Media Strategist | Mid | 16 | 76 | 0 | 1.2.6.2
RFP_154542403_Digital_Marketing_Services | 1.2.7 | 1.2 | Budget Distribution | Paid Media Strategy | Budget Distribution |  |  |  | 8 | 69 | 7 | 1.2.6
RFP_154542403_Digital_Marketing_Services | 1.2.7.1 | 1.2.7 | Internal Review & Critique | Paid Media Strategy | Budget Distribution | Internal Review & Critique | Creative Director | Lead/Director | 2 | 69 | 2 | 1.2.7
RFP_154542403_Digital_Marketing_Services | 1.2.7.2 | 1.2.7 | Client Review & Revisions | Paid Media Strategy | Budget Distribution | Client Review & Revisions | Account Manager | Mid | 3 | 71 | 3 | 1.2.7.1
RFP_154542403_Digital_Marketing_Services | 1.2.7.3 | 1.2.7 | Allocation Modeling | Paid Media Strategy | Budget Distribution | Allocation Modeling | Media Planner | Mid | 3 | 74 | 2 | 1.2.7.2
RFP_154542403_Digital_Marketing_Services | 1.2.8 | 1.2 | Identification of Media Needs | Paid Media Strategy | Identification of Media Needs |  |  |  | 16 | 69 | 5 | 1.2.7
RFP_154542403_Digital_Marketing_Services | 1.2.8.1 | 1.2.8 | Internal Review & Critique | Paid Media Strategy | Identification of Media Needs | Internal Review & Critique | Creative Director | Lead/Director | 2 | 69 | 2 | 1.2.8
RFP_154542403_Digital_Marketing_Services | 1.2.8.2 | 1.2.8 | Client Review & Revisions | Paid Media Strategy | Identification of Media Needs | Client Review & Revisions | Account Manager | Mid | 3 | 71 | 3 | 1.2.8.1
RFP_154542403_Digital_Marketing_Services | 1.2.8.3 | 1.2.8 | Needs Matrix (Assets/Specs/Formats) | Paid Media Strategy | Identification of Media Needs | Needs Matrix (Assets/Specs/Formats) | Designer | Mid | 11 | 76 | 0 | 1.2.8.2
RFP_154542403_Digital_Marketing_Services | 1.2.9 | 1.2 | Paid Media Recommendations | Paid Media Strategy | Paid Media Recommendations |  |  |  | 20 | 69 | 5 | 1.2.8
RFP_154542403_Digital_Marketing_Services | 1.2.9.1 | 1.2.9 | Internal Review & Critique | Paid Media Strategy | Paid Media Recommendations | Internal Review & Critique | Creative Director | Lead/Director | 2 | 69 | 2 | 1.2.9
RFP_154542403_Digital_Marketing_Services | 1.2.9.2 | 1.2.9 | Client Review & Revisions | Paid Media Strategy | Paid Media Recommendations | Client Review & Revisions | Account Manager | Mid | 3 | 71 | 3 | 1.2.9.1
RFP_154542403_Digital_Marketing_Services | 1.2.9.3 | 1.2.9 | Prioritized Recs | Paid Media Strategy | Paid Media Recommendations | Prioritized Recs | Media Planner | Mid | 15 | 76 | 0 | 1.2.9.2
RFP_154542403_Digital_Marketing_Services | 1.2.10 | 1.2 | Platform Identification | Paid Media Strategy | Platform Identification |  |  |  | 14 | 69 | 5 | 1.2.9
RFP_154542403_Digital_Marketing_Services | 1.2.10.1 | 1.2.10 | Internal Review & Critique | Paid Media Strategy | Platform Identification | Internal Review & Critique | Creative Director | Lead/Director | 2 | 69 | 2 | 1.2.10
RFP_154542403_Digital_Marketing_Services | 1.2.10.2 | 1.2.10 | Client Review & Revisions | Paid Media Strategy | Platform Identification | Client Review & Revisions | Account Manager | Mid | 3 | 71 | 3 | 1.2.10.1
RFP_154542403_Digital_Marketing_Services | 1.2.10.3 | 1.2.10 | Platform Fit Assessment | Paid Media Strategy | Platform Identification | Platform Fit Assessment | Media Planner | Mid | 9 | 76 | 0 | 1.2.10.2
RFP_154542403_Digital_Marketing_Services | 1.2.11 | 1.2 | Target Audience & Demographics | Paid Media Strategy | Target Audience & Demographics |  |  |  | 13 | 69 | 5 | 1.2.10
RFP_154542403_Digital_Marketing_Services | 1.2.11.1 | 1.2.11 | Internal Review & Critique | Paid Media Strategy | Target Audience & Demographics | Internal Review & Critique | Creative Director | Lead/Director | 2 | 69 | 2 | 1.2.11
RFP_154542403_Digital_Marketing_Services | 1.2.11.2 | 1.2.11 | Client Review & Revisions | Paid Media Strategy | Target Audience & Demographics | Client Review & Revisions | Account Manager | Mid | 3 | 71 | 3 | 1.2.11.1
RFP_154542403_Digital_Marketing_Services | 1.2.11.3 | 1.2.11 | Audience Definition | Paid Media Strategy | Target Audience & Demographics | Audience Definition | Media Strategist | Mid | 8 | 76 | 0 | 1.2.11.2
RFP_154542403_Digital_Marketing_Services | 1.3 | 1 | Post-Production | Post-Production |  |  |  |  | 288 | 76 | 51 | 1.2 |  | Advanced/T1_LargeVolume
RFP_154542403_Digital_Marketing_Services | 1.3.1 | 1.3 | Content Licensing / Art Buying | Post-Production | Content Licensing / Art Buying |  |  |  | 3 | 76 | 4 | 1.3
RFP_154542403_Digital_Marketing_Services | 1.3.1.1 | 1.3.1 | Rights/License Research | Post-Production | Content Licensing / Art Buying | Rights/License Research | Producer | Mid | 1 | 76 | 4 | 1.3.1
RFP_154542403_Digital_Marketing_Services | 1.3.1.2 | 1.3.1 | Usage Notes | Post-Production | Content Licensing / Art Buying | Usage Notes | Account Manager | Mid | 2 | 127 | 0 | 1.3.1.1
RFP_154542403_Digital_Marketing_Services | 1.3.2 | 1.3 | VO Recording Sessions | Post-Production | VO Recording Sessions |  |  |  | 7 | 80 | 5 | 1.3.1
RFP_154542403_Digital_Marketing_Services | 1.3.2.1 | 1.3.2 | Script Polish | Post-Production | VO Recording Sessions | Script Polish | Copywriter | Mid | 2 | 80 | 5 | 1.3.2
RFP_154542403_Digital_Marketing_Services | 1.3.2.2 | 1.3.2 | VO Session | Post-Production | VO Recording Sessions | VO Session | Sound Designer | Mid | 5 | 127 | 0 | 1.3.2.1
RFP_154542403_Digital_Marketing_Services | 1.3.3 | 1.3 | Editing | Post-Production | Editing |  |  |  | 26 | 85 | 6 | 1.3.2
RFP_154542403_Digital_Marketing_Services | 1.3.3.1 | 1.3.3 | Client Review & Revisions | Post-Production | Editing | Client Review & Revisions | Editor | Mid | 26 | 85 | 6 | 1.3.3
RFP_154542403_Digital_Marketing_Services | 1.3.4 | 1.3 | Video Editing | Post-Production | Video Editing |  |  |  | 39 | 85 | 6 | 1.3.3
RFP_154542403_Digital_Marketing_Services | 1.3.4.1 | 1.3.4 | Client Review & Revisions | Post-Production | Video Editing | Client Review & Revisions | Editor | Mid | 39 | 85 | 6 | 1.3.4
RFP_154542403_Digital_Marketing_Services | 1.3.5 | 1.3 | Voice Over | Post-Production | Voice Over |  |  |  | 26 | 85 | 14 | 1.3.4
RFP_154542403_Digital_Marketing_Services | 1.3.5.1 | 1.3.5 | VO Edit | Post-Production | Voice Over | VO Edit | Editor | Mid | 13 | 85 | 6 | 1.3.5
RFP_154542403_Digital_Marketing_Services | 1.3.5.2 | 1.3.5 | Mix | Post-Production | Voice Over | Mix | Sound Designer | Mid | 3 | 107 | 3 | 1.3.5.1
RFP_154542403_Digital_Marketing_Services | 1.3.5.3 | 1.3.5 | Internal Review & Critique | Post-Production | Voice Over | Internal Review & Critique | Producer | Mid | 3 | 117 | 2 | 1.3.5.2
RFP_154542403_Digital_Marketing_Services | 1.3.5.4 | 1.3.5 | Client Review & Revisions | Post-Production | Voice Over | Client Review & Revisions | Account Manager | Mid | 4 | 119 | 3 | 1.3.5.3
RFP_154542403_Digital_Marketing_Services | 1.3.5.5 | 1.3.5 | Final Packaging | Post-Production | Voice Over | Final Packaging | Designer | Mid | 3 | 127 | 0 | 1.3.5.4
RFP_154542403_Digital_Marketing_Services | 1.3.6 | 1.3 | Motion Design/VFX | Post-Production | Motion Design/VFX |  |  |  | 26 | 91 | 9 | 1.3.5
RFP_154542403_Digital_Marketing_Services | 1.3.6.1 | 1.3.6 | Client Review & Revisions | Post-Production | Motion Design/VFX | Client Review & Revisions | Editor | Mid | 26 | 91 | 9 | 1.3.6
RFP_154542403_Digital_Marketing_Services | 1.3.7 | 1.3 | Color Correction | Post-Production | Color Correction |  |  |  | 17 | 100 | 3 | 1.3.6
RFP_154542403_Digital_Marketing_Services | 1.3.7.1 | 1.3.7 | Client Review & Revisions | Post-Production | Color Correction | Client Review & Revisions | Colorist | Mid | 17 | 100 | 3 | 1.3.7
RFP_154542403_Digital_Marketing_Services | 1.3.8 | 1.3 | Color Grading | Post-Production | Color Grading |  |  |  | 17 | 100 | 3 | 1.3.7
RFP_154542403_Digital_Marketing_Services | 1.3.8.1 | 1.3.8 | Client Review & Revisions | Post-Production | Color Grading | Client Review & Revisions | Colorist | Mid | 17 | 100 | 3 | 1.3.8
RFP_154542403_Digital_Marketing_Services | 1.3.9 | 1.3 | Final Retouched Stills Review | Post-Production | Final Retouched Stills Review |  |  |  | 16 | 103 | 9 | 1.3.8
RFP_154542403_Digital_Marketing_Services | 1.3.9.1 | 1.3.9 | Retouch | Post-Production | Final Retouched Stills Review | Retouch | Retoucher | Mid | 7 | 103 | 4 | 1.3.9
RFP_154542403_Digital_Marketing_Services | 1.3.9.2 | 1.3.9 | Internal Review & Critique | Post-Production | Final Retouched Stills Review | Internal Review & Critique | Producer | Mid | 2 | 117 | 2 | 1.3.9.1
RFP_154542403_Digital_Marketing_Services | 1.3.9.3 | 1.3.9 | Client Review & Revisions | Post-Production | Final Retouched Stills Review | Client Review & Revisions | Account Manager | Mid | 4 | 119 | 3 | 1.3.9.2
RFP_154542403_Digital_Marketing_Services | 1.3.9.4 | 1.3.9 | Final Packaging | Post-Production | Final Retouched Stills Review | Final Packaging | Designer | Mid | 3 | 127 | 0 | 1.3.9.3
RFP_154542403_Digital_Marketing_Services | 1.3.10 | 1.3 | Retouching | Post-Production | Retouching |  |  |  | 16 | 103 | 9 | 1.3.9
RFP_154542403_Digital_Marketing_Services | 1.3.10.1 | 1.3.10 | Retouch | Post-Production | Retouching | Retouch | Retoucher | Mid | 7 | 103 | 4 | 1.3.10
RFP_154542403_Digital_Marketing_Services | 1.3.10.2 | 1.3.10 | Internal Review & Critique | Post-Production | Retouching | Internal Review & Critique | Producer | Mid | 2 | 117 | 2 | 1.3.10.1
RFP_154542403_Digital_Marketing_Services | 1.3.10.3 | 1.3.10 | Client Review & Revisions | Post-Production | Retouching | Client Review & Revisions | Account Manager | Mid | 4 | 119 | 3 | 1.3.10.2
RFP_154542403_Digital_Marketing_Services | 1.3.10.4 | 1.3.10 | Final Packaging | Post-Production | Retouching | Final Packaging | Designer | Mid | 3 | 127 | 0 | 1.3.10.3
RFP_154542403_Digital_Marketing_Services | 1.3.11 | 1.3 | Sound Mix | Post-Production | Sound Mix |  |  |  | 13 | 107 | 3 | 1.3.10
RFP_154542403_Digital_Marketing_Services | 1.3.11.1 | 1.3.11 | Client Review & Revisions | Post-Production | Sound Mix | Client Review & Revisions | Designer | Mid | 13 | 107 | 3 | 1.3.11
RFP_154542403_Digital_Marketing_Services | 1.3.12 | 1.3 | Sound Sourcing | Post-Production | Sound Sourcing |  |  |  | 4 | 107 | 3 | 1.3.11
RFP_154542403_Digital_Marketing_Services | 1.3.12.1 | 1.3.12 | Music Search & License | Post-Production | Sound Sourcing | Music Search & License | Sound Designer | Mid | 4 | 107 | 3 | 1.3.12
RFP_154542403_Digital_Marketing_Services | 1.3.13 | 1.3 | Final File Delivery | Post-Production | Final File Delivery |  |  |  | 10 | 110 | 3 | 1.3.12
RFP_154542403_Digital_Marketing_Services | 1.3.13.1 | 1.3.13 | QA (Tech & Content) | Post-Production | Final File Delivery | QA (Tech & Content) | QA Specialist | Mid | 4 | 110 | 3 | 1.3.13
RFP_154542403_Digital_Marketing_Services | 1.3.13.2 | 1.3.13 | Final Checklist & Upload | Post-Production | Final File Delivery | Final Checklist & Upload | Media Manager / DIT | Mid | 6 | 127 | 0 | 1.3.13.1
RFP_154542403_Digital_Marketing_Services | 1.3.14 | 1.3 | True-ups (for vendor costs) | Post-Production | True-ups (for vendor costs) |  |  |  | 15 | 113 | 9 | 1.3.13
RFP_154542403_Digital_Marketing_Services | 1.3.14.1 | 1.3.14 | Change Orders & Tracking | Post-Production | True-ups (for vendor costs) | Change Orders & Tracking | Project Manager | Mid | 1 | 113 | 4 | 1.3.14
RFP_154542403_Digital_Marketing_Services | 1.3.14.2 | 1.3.14 | Internal Review & Critique | Post-Production | True-ups (for vendor costs) | Internal Review & Critique | Producer | Mid | 3 | 117 | 2 | 1.3.14.1
RFP_154542403_Digital_Marketing_Services | 1.3.14.3 | 1.3.14 | Client Review & Revisions | Post-Production | True-ups (for vendor costs) | Client Review & Revisions | Account Manager | Mid | 4 | 119 | 3 | 1.3.14.2
RFP_154542403_Digital_Marketing_Services | 1.3.14.4 | 1.3.14 | Invoice Reconciliation | Post-Production | True-ups (for vendor costs) | Invoice Reconciliation | Designer | Mid | 7 | 127 | 0 | 1.3.14.3
RFP_154542403_Digital_Marketing_Services | 1.3.15 | 1.3 | Cutdowns | Post-Production | Cutdowns |  |  |  | 17 | 117 | 5 | 1.3.14
RFP_154542403_Digital_Marketing_Services | 1.3.15.1 | 1.3.15 | Internal Review & Critique | Post-Production | Cutdowns | Internal Review & Critique | Producer | Mid | 2 | 117 | 2 | 1.3.15
RFP_154542403_Digital_Marketing_Services | 1.3.15.2 | 1.3.15 | Client Review & Revisions | Post-Production | Cutdowns | Client Review & Revisions | Account Manager | Mid | 4 | 119 | 3 | 1.3.15.1
RFP_154542403_Digital_Marketing_Services | 1.3.15.3 | 1.3.15 | Cutdowns (2-3) | Post-Production | Cutdowns | Cutdowns (2-3) | Editor | Mid | 11 | 127 | 0 | 1.3.15.2
RFP_154542403_Digital_Marketing_Services | 1.3.16 | 1.3 | Client Review | Post-Production | Client Review |  |  |  | 6 | 119 | 3 | 1.3.15
RFP_154542403_Digital_Marketing_Services | 1.3.16.1 | 1.3.16 | Client Review Coordination | Post-Production | Client Review | Client Review Coordination | Account Manager | Mid | 6 | 119 | 3 | 1.3.16
RFP_154542403_Digital_Marketing_Services | 1.3.17 | 1.3 | Review & Sign-Off | Post-Production | Review & Sign-Off |  |  |  | 5 | 119 | 5 | 1.3.16
RFP_154542403_Digital_Marketing_Services | 1.3.17.1 | 1.3.17 | Client Review Coordination | Post-Production | Review & Sign-Off | Client Review Coordination | Account Manager | Mid | 4 | 119 | 3 | 1.3.17
RFP_154542403_Digital_Marketing_Services | 1.3.17.2 | 1.3.17 | Notes Triage | Post-Production | Review & Sign-Off | Notes Triage | Project Manager | Mid | 1 | 125 | 2 | 1.3.17.1
RFP_154542403_Digital_Marketing_Services | 1.3.18 | 1.3 | Asset Library | Post-Production | Asset Library |  |  |  | 3 | 122 | 3 | 1.3.17
RFP_154542403_Digital_Marketing_Services | 1.3.18.1 | 1.3.18 | Post Support | Post-Production | Asset Library | Post Support | Editor | Mid | 3 | 122 | 3 | 1.3.18
RFP_154542403_Digital_Marketing_Services | 1.3.19 | 1.3 | Capture Library | Post-Production | Capture Library |  |  |  | 3 | 122 | 3 | 1.3.18
RFP_154542403_Digital_Marketing_Services | 1.3.19.1 | 1.3.19 | Post Support | Post-Production | Capture Library | Post Support | Editor | Mid | 3 | 122 | 3 | 1.3.19
RFP_154542403_Digital_Marketing_Services | 1.3.20 | 1.3 | Selects Deck | Post-Production | Selects Deck |  |  |  | 3 | 122 | 3 | 1.3.19
RFP_154542403_Digital_Marketing_Services | 1.3.20.1 | 1.3.20 | Post Support | Post-Production | Selects Deck | Post Support | Editor | Mid | 3 | 122 | 3 | 1.3.20
RFP_154542403_Digital_Marketing_Services | 1.3.21 | 1.3 | Delivery | Post-Production | Delivery |  |  |  | 8 | 127 | 0 | 1.3.20
RFP_154542403_Digital_Marketing_Services | 1.3.21.1 | 1.3.21 | Post Support | Post-Production | Delivery | Post Support | Editor | Mid | 8 | 127 | 0 | 1.3.21
RFP_154542403_Digital_Marketing_Services | 1.3.22 | 1.3 | Stills/Footage Selection | Post-Production | Stills/Footage Selection |  |  |  | 8 | 127 | 0 | 1.3.21
RFP_154542403_Digital_Marketing_Services | 1.3.22.1 | 1.3.22 | Post Support | Post-Production | Stills/Footage Selection | Post Support | Editor | Mid | 8 | 127 | 0 | 1.3.22
RFP_154542403_Digital_Marketing_Services | 1.4 | 1 | Paid Media Assets | Paid Media Assets |  |  |  |  | 193 | 127 | 24 | 1.3 |  | Advanced/T1_LargeVolume
RFP_154542403_Digital_Marketing_Services | 1.4.1 | 1.4 | Awareness Assets (Paid) | Paid Media Assets | Awareness Assets (Paid) |  |  |  | 30 | 127 | 21 | 1.4
RFP_154542403_Digital_Marketing_Services | 1.4.1.1 | 1.4.1 | Concept & Copy | Paid Media Assets | Awareness Assets (Paid) | Concept & Copy | Copywriter | Mid | 6 | 127 | 4 | 1.4.1
RFP_154542403_Digital_Marketing_Services | 1.4.1.2 | 1.4.1 | Design Explorations (3-4) | Paid Media Assets | Awareness Assets (Paid) | Design Explorations (3-4) | Designer | Mid | 5 | 131 | 9 | 1.4.1.1
RFP_154542403_Digital_Marketing_Services | 1.4.1.3 | 1.4.1 | Quality Check (Specs/Accessibility) | Paid Media Assets | Awareness Assets (Paid) | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 4 | 143 | 3 | 1.4.1.2
RFP_154542403_Digital_Marketing_Services | 1.4.1.4 | 1.4.1 | Internal Review & Critique | Paid Media Assets | Awareness Assets (Paid) | Internal Review & Critique | Art Director | Lead/Director | 2 | 146 | 2 | 1.4.1.3
RFP_154542403_Digital_Marketing_Services | 1.4.1.5 | 1.4.1 | Client Review & Revisions | Paid Media Assets | Awareness Assets (Paid) | Client Review & Revisions | Account Manager | Mid | 7 | 148 | 3 | 1.4.1.4
RFP_154542403_Digital_Marketing_Services | 1.4.1.6 | 1.4.1 | Final Packaging | Paid Media Assets | Awareness Assets (Paid) | Final Packaging | Designer | Mid | 6 | 151 | 0 | 1.4.1.5
RFP_154542403_Digital_Marketing_Services | 1.4.2 | 1.4 | Unique Assets | Paid Media Assets | Unique Assets |  |  |  | 23 | 127 | 12 | 1.4.1
RFP_154542403_Digital_Marketing_Services | 1.4.2.1 | 1.4.2 | Build & Polish | Paid Media Assets | Unique Assets | Build & Polish | Designer | Mid | 3 | 127 | 4 | 1.4.2
RFP_154542403_Digital_Marketing_Services | 1.4.2.2 | 1.4.2 | Quality Check (Specs/Accessibility) | Paid Media Assets | Unique Assets | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 4 | 143 | 3 | 1.4.2.1
RFP_154542403_Digital_Marketing_Services | 1.4.2.3 | 1.4.2 | Internal Review & Critique | Paid Media Assets | Unique Assets | Internal Review & Critique | Art Director | Lead/Director | 2 | 146 | 2 | 1.4.2.2
RFP_154542403_Digital_Marketing_Services | 1.4.2.4 | 1.4.2 | Client Review & Revisions | Paid Media Assets | Unique Assets | Client Review & Revisions | Account Manager | Mid | 5 | 148 | 3 | 1.4.2.3
RFP_154542403_Digital_Marketing_Services | 1.4.2.5 | 1.4.2 | Custom Concept | Paid Media Assets | Unique Assets | Custom Concept | Designer | Mid | 9 | 151 | 0 | 1.4.2.4
RFP_154542403_Digital_Marketing_Services | 1.4.3 | 1.4 | Conversion Assets (Paid) | Paid Media Assets | Conversion Assets (Paid) |  |  |  | 27 | 131 | 17 | 1.4.2
RFP_154542403_Digital_Marketing_Services | 1.4.3.1 | 1.4.3 | Design Variants (3-4) | Paid Media Assets | Conversion Assets (Paid) | Design Variants (3-4) | Designer | Mid | 5 | 131 | 9 | 1.4.3
RFP_154542403_Digital_Marketing_Services | 1.4.3.2 | 1.4.3 | Quality Check (Specs/Accessibility) | Paid Media Assets | Conversion Assets (Paid) | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 4 | 143 | 3 | 1.4.3.1
RFP_154542403_Digital_Marketing_Services | 1.4.3.3 | 1.4.3 | Internal Review & Critique | Paid Media Assets | Conversion Assets (Paid) | Internal Review & Critique | Art Director | Lead/Director | 2 | 146 | 2 | 1.4.3.2
RFP_154542403_Digital_Marketing_Services | 1.4.3.4 | 1.4.3 | Client Review & Revisions | Paid Media Assets | Conversion Assets (Paid) | Client Review & Revisions | Account Manager | Mid | 7 | 148 | 3 | 1.4.3.3
RFP_154542403_Digital_Marketing_Services | 1.4.3.5 | 1.4.3 | Final Packaging | Paid Media Assets | Conversion Assets (Paid) | Final Packaging | Designer | Mid | 9 | 151 | 0 | 1.4.3.4
RFP_154542403_Digital_Marketing_Services | 1.4.4 | 1.4 | National Spotify Audio (Paid) | Paid Media Assets | National Spotify Audio (Paid) |  |  |  | 25 | 140 | 3 | 1.4.3
RFP_154542403_Digital_Marketing_Services | 1.4.4.1 | 1.4.4 | Client Review & Revisions | Paid Media Assets | National Spotify Audio (Paid) | Client Review & Revisions | Sound Designer | Mid | 25 | 140 | 3 | 1.4.4
RFP_154542403_Digital_Marketing_Services | 1.4.5 | 1.4 | Regional Spotify Audio (Paid) | Paid Media Assets | Regional Spotify Audio (Paid) |  |  |  | 25 | 140 | 3 | 1.4.4
RFP_154542403_Digital_Marketing_Services | 1.4.5.1 | 1.4.5 | Client Review & Revisions | Paid Media Assets | Regional Spotify Audio (Paid) | Client Review & Revisions | Sound Designer | Mid | 25 | 140 | 3 | 1.4.5
RFP_154542403_Digital_Marketing_Services | 1.4.6 | 1.4 | National Pinterest assets (Paid) | Paid Media Assets | National Pinterest assets (Paid) |  |  |  | 21 | 143 | 8 | 1.4.5
RFP_154542403_Digital_Marketing_Services | 1.4.6.1 | 1.4.6 | Quality Check (Specs/Accessibility) | Paid Media Assets | National Pinterest assets (Paid) | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 4 | 143 | 3 | 1.4.6
RFP_154542403_Digital_Marketing_Services | 1.4.6.2 | 1.4.6 | Internal Review & Critique | Paid Media Assets | National Pinterest assets (Paid) | Internal Review & Critique | Art Director | Lead/Director | 2 | 146 | 2 | 1.4.6.1
RFP_154542403_Digital_Marketing_Services | 1.4.6.3 | 1.4.6 | Client Review & Revisions | Paid Media Assets | National Pinterest assets (Paid) | Client Review & Revisions | Account Manager | Mid | 5 | 148 | 3 | 1.4.6.2
RFP_154542403_Digital_Marketing_Services | 1.4.6.4 | 1.4.6 | Concept & Layouts (2-3) | Paid Media Assets | National Pinterest assets (Paid) | Concept & Layouts (2-3) | Designer | Mid | 10 | 151 | 0 | 1.4.6.3
RFP_154542403_Digital_Marketing_Services | 1.4.7 | 1.4 | Regional Pinterest assets (Paid) | Paid Media Assets | Regional Pinterest assets (Paid) |  |  |  | 21 | 143 | 8 | 1.4.6
RFP_154542403_Digital_Marketing_Services | 1.4.7.1 | 1.4.7 | Quality Check (Specs/Accessibility) | Paid Media Assets | Regional Pinterest assets (Paid) | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 4 | 143 | 3 | 1.4.7
RFP_154542403_Digital_Marketing_Services | 1.4.7.2 | 1.4.7 | Internal Review & Critique | Paid Media Assets | Regional Pinterest assets (Paid) | Internal Review & Critique | Art Director | Lead/Director | 2 | 146 | 2 | 1.4.7.1
RFP_154542403_Digital_Marketing_Services | 1.4.7.3 | 1.4.7 | Client Review & Revisions | Paid Media Assets | Regional Pinterest assets (Paid) | Client Review & Revisions | Account Manager | Mid | 5 | 148 | 3 | 1.4.7.2
RFP_154542403_Digital_Marketing_Services | 1.4.7.4 | 1.4.7 | Concept & Layouts (2-3) | Paid Media Assets | Regional Pinterest assets (Paid) | Concept & Layouts (2-3) | Designer | Mid | 10 | 151 | 0 | 1.4.7.3
RFP_154542403_Digital_Marketing_Services | 1.4.8 | 1.4 | Resize Assets | Paid Media Assets | Resize Assets |  |  |  | 21 | 143 | 8 | 1.4.7
RFP_154542403_Digital_Marketing_Services | 1.4.8.1 | 1.4.8 | Quality Check (Specs/Accessibility) | Paid Media Assets | Resize Assets | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 8 | 143 | 3 | 1.4.8
RFP_154542403_Digital_Marketing_Services | 1.4.8.2 | 1.4.8 | Internal Review & Critique | Paid Media Assets | Resize Assets | Internal Review & Critique | Art Director | Lead/Director | 2 | 146 | 2 | 1.4.8.1
RFP_154542403_Digital_Marketing_Services | 1.4.8.3 | 1.4.8 | Client Review & Revisions | Paid Media Assets | Resize Assets | Client Review & Revisions | Account Manager | Mid | 5 | 148 | 3 | 1.4.8.2
RFP_154542403_Digital_Marketing_Services | 1.4.8.4 | 1.4.8 | Final Packaging | Paid Media Assets | Resize Assets | Final Packaging | Designer | Mid | 6 | 151 | 0 | 1.4.8.3
RFP_154542403_Digital_Marketing_Services | 1.5 | 1 | Reporting | Reporting |  |  |  |  | 89 | 151 | 19 | 1.4 |  | Advanced/T1_LargeVolume
RFP_154542403_Digital_Marketing_Services | 1.5.1 | 1.5 | Campaign Reporting (Quarterly) | Reporting | Campaign Reporting (Quarterly) |  |  |  | 18 | 151 | 4 | 1.5
RFP_154542403_Digital_Marketing_Services | 1.5.1.1 | 1.5.1 | Design Polish | Reporting | Campaign Reporting (Quarterly) | Design Polish | Designer | Mid | 3 | 151 | 4 | 1.5.1
RFP_154542403_Digital_Marketing_Services | 1.5.1.2 | 1.5.1 | Data Deep Dive | Reporting | Campaign Reporting (Quarterly) | Data Deep Dive | Media Strategist | Mid | 15 | 170 | 0 | 1.5.1.1
RFP_154542403_Digital_Marketing_Services | 1.5.2 | 1.5 | Campaign Reporting (Bi-Weekly) | Reporting | Campaign Reporting (Bi-Weekly) |  |  |  | 12 | 155 | 7 | 1.5.1
RFP_154542403_Digital_Marketing_Services | 1.5.2.1 | 1.5.2 | Data Refresh & QA | Reporting | Campaign Reporting (Bi-Weekly) | Data Refresh & QA | QA Specialist | Mid | 7 | 155 | 3 | 1.5.2
RFP_154542403_Digital_Marketing_Services | 1.5.2.2 | 1.5.2 | Client Summary | Reporting | Campaign Reporting (Bi-Weekly) | Client Summary | Media Strategist | Mid | 5 | 162 | 4 | 1.5.2.1
RFP_154542403_Digital_Marketing_Services | 1.5.3 | 1.5 | Campaign Tracking | Reporting | Campaign Tracking |  |  |  | 10 | 155 | 7 | 1.5.2
RFP_154542403_Digital_Marketing_Services | 1.5.3.1 | 1.5.3 | QA Spot Check | Reporting | Campaign Tracking | QA Spot Check | QA Specialist | Mid | 4 | 155 | 3 | 1.5.3
RFP_154542403_Digital_Marketing_Services | 1.5.3.2 | 1.5.3 | Tracker Update | Reporting | Campaign Tracking | Tracker Update | Analyst | Mid | 6 | 158 | 4 | 1.5.3.1
RFP_154542403_Digital_Marketing_Services | 1.5.4 | 1.5 | Dashboard Analytics | Reporting | Dashboard Analytics |  |  |  | 12 | 155 | 7 | 1.5.3
RFP_154542403_Digital_Marketing_Services | 1.5.4.1 | 1.5.4 | QA & Calc Checks | Reporting | Dashboard Analytics | QA & Calc Checks | QA Specialist | Mid | 4 | 155 | 3 | 1.5.4
RFP_154542403_Digital_Marketing_Services | 1.5.4.2 | 1.5.4 | Dashboard Build/Refresh | Reporting | Dashboard Analytics | Dashboard Build/Refresh | Analyst | Mid | 8 | 162 | 4 | 1.5.4.1
RFP_154542403_Digital_Marketing_Services | 1.5.5 | 1.5 | Reporting & Ad-Tagging Support | Reporting | Reporting & Ad-Tagging Support |  |  |  | 11 | 155 | 7 | 1.5.4
RFP_154542403_Digital_Marketing_Services | 1.5.5.1 | 1.5.5 | QA | Reporting | Reporting & Ad-Tagging Support | QA | QA Specialist | Mid | 4 | 155 | 3 | 1.5.5
RFP_154542403_Digital_Marketing_Services | 1.5.5.2 | 1.5.5 | UTM/Tag Guidance | Reporting | Reporting & Ad-Tagging Support | UTM/Tag Guidance | Media Strategist | Mid | 4 | 158 | 4 | 1.5.5.1
RFP_154542403_Digital_Marketing_Services | 1.5.5.3 | 1.5.5 | Tagging Support | Reporting | Reporting & Ad-Tagging Support | Tagging Support | Ad Ops / Trafficker | Mid | 3 | 170 | 0 | 1.5.5.2
RFP_154542403_Digital_Marketing_Services | 1.5.6 | 1.5 | Dashboard Maintenance | Reporting | Dashboard Maintenance |  |  |  | 9 | 162 | 4 | 1.5.5
RFP_154542403_Digital_Marketing_Services | 1.5.6.1 | 1.5.6 | Connector Checks & Fixes | Reporting | Dashboard Maintenance | Connector Checks & Fixes | Analyst | Mid | 9 | 162 | 4 | 1.5.6
RFP_154542403_Digital_Marketing_Services | 1.5.7 | 1.5 | Reconcilliation & Media Budget Authorization | Reporting | Reconcilliation & Media Budget Authorization |  |  |  | 6 | 166 | 2 | 1.5.6
RFP_154542403_Digital_Marketing_Services | 1.5.7.1 | 1.5.7 | Authorization & Docs | Reporting | Reconcilliation & Media Budget Authorization | Authorization & Docs | Account Manager | Mid | 6 | 166 | 2 | 1.5.7
RFP_154542403_Digital_Marketing_Services | 1.5.8 | 1.5 | KPI Monitoring | Reporting | KPI Monitoring |  |  |  | 6 | 168 | 2 | 1.5.7
RFP_154542403_Digital_Marketing_Services | 1.5.8.1 | 1.5.8 | Weekly KPI Scan | Reporting | KPI Monitoring | Weekly KPI Scan | Analyst | Mid | 1 | 168 | 2 | 1.5.8
RFP_154542403_Digital_Marketing_Services | 1.5.8.2 | 1.5.8 | Notes & Flags | Reporting | KPI Monitoring | Notes & Flags | Media Strategist | Mid | 5 | 170 | 0 | 1.5.8.1
RFP_154542403_Digital_Marketing_Services | 1.5.9 | 1.5 | Ad-Platform Reporting | Reporting | Ad-Platform Reporting |  |  |  | 5 | 170 | 0 | 1.5.8
RFP_154542403_Digital_Marketing_Services | 1.5.9.1 | 1.5.9 | Distribution | Reporting | Ad-Platform Reporting | Distribution | Analyst | Mid | 5 | 170 | 0 | 1.5.9
RFP_154542403_Digital_Marketing_Services | 1.6 | 1 | Brand Identity Development | Brand Identity Development |  |  |  |  | 391 | 170 | 15 | 1.5 |  | Advanced/T1_LargeVolume
RFP_154542403_Digital_Marketing_Services | 1.6.1 | 1.6 | Color Palette | Brand Identity Development | Color Palette |  |  |  | 23 | 170 | 3 | 1.6
RFP_154542403_Digital_Marketing_Services | 1.6.1.1 | 1.6.1 | Client Review & Revisions | Brand Identity Development | Color Palette | Client Review & Revisions | Designer | Mid | 23 | 170 | 3 | 1.6.1
RFP_154542403_Digital_Marketing_Services | 1.6.2 | 1.6 | Graphic Mock-Ups | Brand Identity Development | Graphic Mock-Ups |  |  |  | 38 | 173 | 9 | 1.6.1
RFP_154542403_Digital_Marketing_Services | 1.6.2.1 | 1.6.2 | Compositing/Retouch | Brand Identity Development | Graphic Mock-Ups | Compositing/Retouch | Retoucher | Mid | 6 | 173 | 4 | 1.6.2
RFP_154542403_Digital_Marketing_Services | 1.6.2.2 | 1.6.2 | Internal Review & Critique | Brand Identity Development | Graphic Mock-Ups | Internal Review & Critique | Art Director | Lead/Director | 2 | 180 | 2 | 1.6.2.1
RFP_154542403_Digital_Marketing_Services | 1.6.2.3 | 1.6.2 | Client Review & Revisions | Brand Identity Development | Graphic Mock-Ups | Client Review & Revisions | Account Manager | Mid | 5 | 182 | 3 | 1.6.2.2
RFP_154542403_Digital_Marketing_Services | 1.6.2.4 | 1.6.2 | Mockup Scenarios (3-4) | Brand Identity Development | Graphic Mock-Ups | Mockup Scenarios (3-4) | Designer | Mid | 25 | 185 | 0 | 1.6.2.3
RFP_154542403_Digital_Marketing_Services | 1.6.3 | 1.6 | Logo | Brand Identity Development | Logo |  |  |  | 57 | 177 | 8 | 1.6.2
RFP_154542403_Digital_Marketing_Services | 1.6.3.1 | 1.6.3 | Quality Check (Specs/Accessibility) | Brand Identity Development | Logo | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 4 | 177 | 3 | 1.6.3
RFP_154542403_Digital_Marketing_Services | 1.6.3.2 | 1.6.3 | Internal Review & Critique | Brand Identity Development | Logo | Internal Review & Critique | Art Director | Lead/Director | 2 | 180 | 2 | 1.6.3.1
RFP_154542403_Digital_Marketing_Services | 1.6.3.3 | 1.6.3 | Client Review & Revisions | Brand Identity Development | Logo | Client Review & Revisions | Account Manager | Mid | 5 | 182 | 3 | 1.6.3.2
RFP_154542403_Digital_Marketing_Services | 1.6.3.4 | 1.6.3 | Logo Exploration (6-8 dirs) | Brand Identity Development | Logo | Logo Exploration (6-8 dirs) | Designer | Mid | 46 | 185 | 0 | 1.6.3.3
RFP_154542403_Digital_Marketing_Services | 1.6.4 | 1.6 | Typography | Brand Identity Development | Typography |  |  |  | 53 | 177 | 8 | 1.6.3
RFP_154542403_Digital_Marketing_Services | 1.6.4.1 | 1.6.4 | Quality Check (Specs/Accessibility) | Brand Identity Development | Typography | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 4 | 177 | 3 | 1.6.4
RFP_154542403_Digital_Marketing_Services | 1.6.4.2 | 1.6.4 | Internal Review & Critique | Brand Identity Development | Typography | Internal Review & Critique | Art Director | Lead/Director | 2 | 180 | 2 | 1.6.4.1
RFP_154542403_Digital_Marketing_Services | 1.6.4.3 | 1.6.4 | Client Review & Revisions | Brand Identity Development | Typography | Client Review & Revisions | Account Manager | Mid | 5 | 182 | 3 | 1.6.4.2
RFP_154542403_Digital_Marketing_Services | 1.6.4.4 | 1.6.4 | Final Packaging | Brand Identity Development | Typography | Final Packaging | Designer | Mid | 42 | 185 | 0 | 1.6.4.3
RFP_154542403_Digital_Marketing_Services | 1.6.5 | 1.6 | Graphic & Copy Messaging Cornerstones | Brand Identity Development | Graphic & Copy Messaging Cornerstones |  |  |  | 36 | 180 | 5 | 1.6.4
RFP_154542403_Digital_Marketing_Services | 1.6.5.1 | 1.6.5 | Internal Review & Critique | Brand Identity Development | Graphic & Copy Messaging Cornerstones | Internal Review & Critique | Art Director | Lead/Director | 2 | 180 | 2 | 1.6.5
RFP_154542403_Digital_Marketing_Services | 1.6.5.2 | 1.6.5 | Client Review & Revisions | Brand Identity Development | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Account Manager | Mid | 7 | 182 | 3 | 1.6.5.1
RFP_154542403_Digital_Marketing_Services | 1.6.5.3 | 1.6.5 | Messaging Cornerstones Draft | Brand Identity Development | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft | Designer | Mid | 27 | 185 | 0 | 1.6.5.2
RFP_154542403_Digital_Marketing_Services | 1.6.6 | 1.6 | Iconography | Brand Identity Development | Iconography |  |  |  | 41 | 180 | 5 | 1.6.5
RFP_154542403_Digital_Marketing_Services | 1.6.6.1 | 1.6.6 | Internal Review & Critique | Brand Identity Development | Iconography | Internal Review & Critique | Art Director | Lead/Director | 2 | 180 | 2 | 1.6.6
RFP_154542403_Digital_Marketing_Services | 1.6.6.2 | 1.6.6 | Client Review & Revisions | Brand Identity Development | Iconography | Client Review & Revisions | Account Manager | Mid | 5 | 182 | 3 | 1.6.6.1
RFP_154542403_Digital_Marketing_Services | 1.6.6.3 | 1.6.6 | Export & Spec | Brand Identity Development | Iconography | Export & Spec | Designer | Mid | 34 | 185 | 0 | 1.6.6.2
RFP_154542403_Digital_Marketing_Services | 1.6.7 | 1.6 | Overarching Moodboard | Brand Identity Development | Overarching Moodboard |  |  |  | 35 | 180 | 5 | 1.6.6
RFP_154542403_Digital_Marketing_Services | 1.6.7.1 | 1.6.7 | Internal Review & Critique | Brand Identity Development | Overarching Moodboard | Internal Review & Critique | Art Director | Lead/Director | 2 | 180 | 2 | 1.6.7
RFP_154542403_Digital_Marketing_Services | 1.6.7.2 | 1.6.7 | Client Review & Revisions | Brand Identity Development | Overarching Moodboard | Client Review & Revisions | Account Manager | Mid | 5 | 182 | 3 | 1.6.7.1
RFP_154542403_Digital_Marketing_Services | 1.6.7.3 | 1.6.7 | Curate Moodboard | Brand Identity Development | Overarching Moodboard | Curate Moodboard | Designer | Mid | 28 | 185 | 0 | 1.6.7.2
RFP_154542403_Digital_Marketing_Services | 1.6.8 | 1.6 | Tagline Copy Bank | Brand Identity Development | Tagline Copy Bank |  |  |  | 28 | 180 | 5 | 1.6.7
RFP_154542403_Digital_Marketing_Services | 1.6.8.1 | 1.6.8 | Internal Review & Critique | Brand Identity Development | Tagline Copy Bank | Internal Review & Critique | Art Director | Lead/Director | 2 | 180 | 2 | 1.6.8
RFP_154542403_Digital_Marketing_Services | 1.6.8.2 | 1.6.8 | Client Review & Revisions | Brand Identity Development | Tagline Copy Bank | Client Review & Revisions | Account Manager | Mid | 6 | 182 | 3 | 1.6.8.1
RFP_154542403_Digital_Marketing_Services | 1.6.8.3 | 1.6.8 | Shortlist & Rationale | Brand Identity Development | Tagline Copy Bank | Shortlist & Rationale | Designer | Mid | 20 | 185 | 0 | 1.6.8.2
RFP_154542403_Digital_Marketing_Services | 1.6.9 | 1.6 | Textures/Patterns/Materials | Brand Identity Development | Textures/Patterns/Materials |  |  |  | 38 | 180 | 5 | 1.6.8
RFP_154542403_Digital_Marketing_Services | 1.6.9.1 | 1.6.9 | Internal Review & Critique | Brand Identity Development | Textures/Patterns/Materials | Internal Review & Critique | Art Director | Lead/Director | 2 | 180 | 2 | 1.6.9
RFP_154542403_Digital_Marketing_Services | 1.6.9.2 | 1.6.9 | Client Review & Revisions | Brand Identity Development | Textures/Patterns/Materials | Client Review & Revisions | Account Manager | Mid | 5 | 182 | 3 | 1.6.9.1
RFP_154542403_Digital_Marketing_Services | 1.6.9.3 | 1.6.9 | Build Repeating Tiles | Brand Identity Development | Textures/Patterns/Materials | Build Repeating Tiles | Designer | Mid | 31 | 185 | 0 | 1.6.9.2
RFP_154542403_Digital_Marketing_Services | 1.6.10 | 1.6 | Visual Elements/Comps | Brand Identity Development | Visual Elements/Comps |  |  |  | 42 | 180 | 5 | 1.6.9
RFP_154542403_Digital_Marketing_Services | 1.6.10.1 | 1.6.10 | Internal Review & Critique | Brand Identity Development | Visual Elements/Comps | Internal Review & Critique | Art Director | Lead/Director | 2 | 180 | 2 | 1.6.10
RFP_154542403_Digital_Marketing_Services | 1.6.10.2 | 1.6.10 | Client Review & Revisions | Brand Identity Development | Visual Elements/Comps | Client Review & Revisions | Account Manager | Mid | 5 | 182 | 3 | 1.6.10.1
RFP_154542403_Digital_Marketing_Services | 1.6.10.3 | 1.6.10 | Compositions (2-3) | Brand Identity Development | Visual Elements/Comps | Compositions (2-3) | Designer | Mid | 35 | 185 | 0 | 1.6.10.2
RFP_154542403_Digital_Marketing_Services | 1.7 | 1 | Brand Style & Usage Guidelines | Brand Style & Usage Guidelines |  |  |  |  | 382 | 185 | 11 | 1.6 |  | Advanced/T1_LargeVolume
RFP_154542403_Digital_Marketing_Services | 1.7.1 | 1.7 | Color Palettes | Brand Style & Usage Guidelines | Color Palettes |  |  |  | 20 | 185 | 3 | 1.7
RFP_154542403_Digital_Marketing_Services | 1.7.1.1 | 1.7.1 | Client Review & Revisions | Brand Style & Usage Guidelines | Color Palettes | Client Review & Revisions | Designer | Mid | 20 | 185 | 3 | 1.7.1
RFP_154542403_Digital_Marketing_Services | 1.7.2 | 1.7 | Logo Lock-Ups | Brand Style & Usage Guidelines | Logo Lock-Ups |  |  |  | 42 | 188 | 8 | 1.7.1
RFP_154542403_Digital_Marketing_Services | 1.7.2.1 | 1.7.2 | Quality Check (Specs/Accessibility) | Brand Style & Usage Guidelines | Logo Lock-Ups | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 4 | 188 | 3 | 1.7.2
RFP_154542403_Digital_Marketing_Services | 1.7.2.2 | 1.7.2 | Internal Review & Critique | Brand Style & Usage Guidelines | Logo Lock-Ups | Internal Review & Critique | Art Director | Lead/Director | 2 | 191 | 2 | 1.7.2.1
RFP_154542403_Digital_Marketing_Services | 1.7.2.3 | 1.7.2 | Client Review & Revisions | Brand Style & Usage Guidelines | Logo Lock-Ups | Client Review & Revisions | Account Manager | Mid | 5 | 193 | 3 | 1.7.2.2
RFP_154542403_Digital_Marketing_Services | 1.7.2.4 | 1.7.2 | Final Packaging | Brand Style & Usage Guidelines | Logo Lock-Ups | Final Packaging | Designer | Mid | 31 | 196 | 0 | 1.7.2.3
RFP_154542403_Digital_Marketing_Services | 1.7.3 | 1.7 | Logo Placement | Brand Style & Usage Guidelines | Logo Placement |  |  |  | 42 | 188 | 8 | 1.7.2
RFP_154542403_Digital_Marketing_Services | 1.7.3.1 | 1.7.3 | Quality Check (Specs/Accessibility) | Brand Style & Usage Guidelines | Logo Placement | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 4 | 188 | 3 | 1.7.3
RFP_154542403_Digital_Marketing_Services | 1.7.3.2 | 1.7.3 | Internal Review & Critique | Brand Style & Usage Guidelines | Logo Placement | Internal Review & Critique | Art Director | Lead/Director | 2 | 191 | 2 | 1.7.3.1
RFP_154542403_Digital_Marketing_Services | 1.7.3.3 | 1.7.3 | Client Review & Revisions | Brand Style & Usage Guidelines | Logo Placement | Client Review & Revisions | Account Manager | Mid | 5 | 193 | 3 | 1.7.3.2
RFP_154542403_Digital_Marketing_Services | 1.7.3.4 | 1.7.3 | Final Packaging | Brand Style & Usage Guidelines | Logo Placement | Final Packaging | Designer | Mid | 31 | 196 | 0 | 1.7.3.3
RFP_154542403_Digital_Marketing_Services | 1.7.4 | 1.7 | Brand Do's & Dont's | Brand Style & Usage Guidelines | Brand Do's & Dont's |  |  |  | 50 | 191 | 5 | 1.7.3
RFP_154542403_Digital_Marketing_Services | 1.7.4.1 | 1.7.4 | Internal Review & Critique | Brand Style & Usage Guidelines | Brand Do's & Dont's | Internal Review & Critique | Art Director | Lead/Director | 2 | 191 | 2 | 1.7.4
RFP_154542403_Digital_Marketing_Services | 1.7.4.2 | 1.7.4 | Client Review & Revisions | Brand Style & Usage Guidelines | Brand Do's & Dont's | Client Review & Revisions | Account Manager | Mid | 6 | 193 | 3 | 1.7.4.1
RFP_154542403_Digital_Marketing_Services | 1.7.4.3 | 1.7.4 | Outline & Examples | Brand Style & Usage Guidelines | Brand Do's & Dont's | Outline & Examples | Designer | Mid | 42 | 196 | 0 | 1.7.4.2
RFP_154542403_Digital_Marketing_Services | 1.7.5 | 1.7 | Design Style Tile | Brand Style & Usage Guidelines | Design Style Tile |  |  |  | 35 | 191 | 5 | 1.7.4
RFP_154542403_Digital_Marketing_Services | 1.7.5.1 | 1.7.5 | Internal Review & Critique | Brand Style & Usage Guidelines | Design Style Tile | Internal Review & Critique | Art Director | Lead/Director | 2 | 191 | 2 | 1.7.5
RFP_154542403_Digital_Marketing_Services | 1.7.5.2 | 1.7.5 | Client Review & Revisions | Brand Style & Usage Guidelines | Design Style Tile | Client Review & Revisions | Account Manager | Mid | 5 | 193 | 3 | 1.7.5.1
RFP_154542403_Digital_Marketing_Services | 1.7.5.3 | 1.7.5 | Style Tile Build | Brand Style & Usage Guidelines | Design Style Tile | Style Tile Build | Designer | Mid | 28 | 196 | 0 | 1.7.5.2
RFP_154542403_Digital_Marketing_Services | 1.7.6 | 1.7 | Image Use Guidance | Brand Style & Usage Guidelines | Image Use Guidance |  |  |  | 35 | 191 | 5 | 1.7.5
RFP_154542403_Digital_Marketing_Services | 1.7.6.1 | 1.7.6 | Internal Review & Critique | Brand Style & Usage Guidelines | Image Use Guidance | Internal Review & Critique | Art Director | Lead/Director | 2 | 191 | 2 | 1.7.6
RFP_154542403_Digital_Marketing_Services | 1.7.6.2 | 1.7.6 | Client Review & Revisions | Brand Style & Usage Guidelines | Image Use Guidance | Client Review & Revisions | Account Manager | Mid | 5 | 193 | 3 | 1.7.6.1
RFP_154542403_Digital_Marketing_Services | 1.7.6.3 | 1.7.6 | Examples & Callouts | Brand Style & Usage Guidelines | Image Use Guidance | Examples & Callouts | Designer | Mid | 28 | 196 | 0 | 1.7.6.2
RFP_154542403_Digital_Marketing_Services | 1.7.7 | 1.7 | Imagery Style | Brand Style & Usage Guidelines | Imagery Style |  |  |  | 35 | 191 | 5 | 1.7.6
RFP_154542403_Digital_Marketing_Services | 1.7.7.1 | 1.7.7 | Internal Review & Critique | Brand Style & Usage Guidelines | Imagery Style | Internal Review & Critique | Art Director | Lead/Director | 2 | 191 | 2 | 1.7.7
RFP_154542403_Digital_Marketing_Services | 1.7.7.2 | 1.7.7 | Client Review & Revisions | Brand Style & Usage Guidelines | Imagery Style | Client Review & Revisions | Account Manager | Mid | 5 | 193 | 3 | 1.7.7.1
RFP_154542403_Digital_Marketing_Services | 1.7.7.3 | 1.7.7 | Examples & Callouts | Brand Style & Usage Guidelines | Imagery Style | Examples & Callouts | Designer | Mid | 28 | 196 | 0 | 1.7.7.2
RFP_154542403_Digital_Marketing_Services | 1.7.8 | 1.7 | Photo & Video Direction | Brand Style & Usage Guidelines | Photo & Video Direction |  |  |  | 38 | 191 | 5 | 1.7.7
RFP_154542403_Digital_Marketing_Services | 1.7.8.1 | 1.7.8 | Internal Review & Critique | Brand Style & Usage Guidelines | Photo & Video Direction | Internal Review & Critique | Art Director | Lead/Director | 2 | 191 | 2 | 1.7.8
RFP_154542403_Digital_Marketing_Services | 1.7.8.2 | 1.7.8 | Client Review & Revisions | Brand Style & Usage Guidelines | Photo & Video Direction | Client Review & Revisions | Account Manager | Mid | 5 | 193 | 3 | 1.7.8.1
RFP_154542403_Digital_Marketing_Services | 1.7.8.3 | 1.7.8 | Direction Pages | Brand Style & Usage Guidelines | Photo & Video Direction | Direction Pages | Designer | Mid | 31 | 196 | 0 | 1.7.8.2
RFP_154542403_Digital_Marketing_Services | 1.7.9 | 1.7 | Typography | Brand Style & Usage Guidelines | Typography |  |  |  | 28 | 191 | 5 | 1.7.8
RFP_154542403_Digital_Marketing_Services | 1.7.9.1 | 1.7.9 | Internal Review & Critique | Brand Style & Usage Guidelines | Typography | Internal Review & Critique | Art Director | Lead/Director | 2 | 191 | 2 | 1.7.9
RFP_154542403_Digital_Marketing_Services | 1.7.9.2 | 1.7.9 | Client Review & Revisions | Brand Style & Usage Guidelines | Typography | Client Review & Revisions | Account Manager | Mid | 5 | 193 | 3 | 1.7.9.1
RFP_154542403_Digital_Marketing_Services | 1.7.9.3 | 1.7.9 | Final Packaging | Brand Style & Usage Guidelines | Typography | Final Packaging | Designer | Mid | 21 | 196 | 0 | 1.7.9.2
RFP_154542403_Digital_Marketing_Services | 1.7.10 | 1.7 | Use Cases | Brand Style & Usage Guidelines | Use Cases |  |  |  | 33 | 191 | 5 | 1.7.9
RFP_154542403_Digital_Marketing_Services | 1.7.10.1 | 1.7.10 | Internal Review & Critique | Brand Style & Usage Guidelines | Use Cases | Internal Review & Critique | Art Director | Lead/Director | 2 | 191 | 2 | 1.7.10
RFP_154542403_Digital_Marketing_Services | 1.7.10.2 | 1.7.10 | Client Review & Revisions | Brand Style & Usage Guidelines | Use Cases | Client Review & Revisions | Account Manager | Mid | 5 | 193 | 3 | 1.7.10.1
RFP_154542403_Digital_Marketing_Services | 1.7.10.3 | 1.7.10 | Final Packaging | Brand Style & Usage Guidelines | Use Cases | Final Packaging | Designer | Mid | 26 | 196 | 0 | 1.7.10.2
RFP_154542403_Digital_Marketing_Services | 1.7.11 | 1.7 | Graphic Treatment Direction | Brand Style & Usage Guidelines | Graphic Treatment Direction |  |  |  | 24 | 196 | 0 | 1.7.10
RFP_154542403_Digital_Marketing_Services | 1.7.11.1 | 1.7.11 | Client Review & Revisions | Brand Style & Usage Guidelines | Graphic Treatment Direction | Client Review & Revisions | Creative Director | Lead/Director | 24 | 196 | 0 | 1.7.11
RFP_154542403_Digital_Marketing_Services | 1.8 | 1 | Reporting | Reporting |  |  |  |  | 166 | 196 | 7 | 1.7 |  | Advanced/T1_LargeVolume
RFP_154542403_Digital_Marketing_Services | 1.8.1 | 1.8 | Dashboards | Reporting | Dashboards |  |  |  | 12 | 196 | 7 | 1.8
RFP_154542403_Digital_Marketing_Services | 1.8.1.1 | 1.8.1 | QA | Reporting | Dashboards | QA | QA Specialist | Mid | 4 | 196 | 3 | 1.8.1
RFP_154542403_Digital_Marketing_Services | 1.8.1.2 | 1.8.1 | Dashboard Build/Refresh | Reporting | Dashboards | Dashboard Build/Refresh | Analyst | Mid | 8 | 199 | 4 | 1.8.1.1
RFP_154542403_Digital_Marketing_Services | 1.8.2 | 1.8 | Engagement Rate | Reporting | Engagement Rate |  |  |  | 7 | 196 | 3 | 1.8.1
RFP_154542403_Digital_Marketing_Services | 1.8.2.1 | 1.8.2 | Data Refresh & Calc Check | Reporting | Engagement Rate | Data Refresh & Calc Check | QA Specialist | Mid | 7 | 196 | 3 | 1.8.2
RFP_154542403_Digital_Marketing_Services | 1.8.3 | 1.8 | Emplifi Reports | Reporting | Emplifi Reports |  |  |  | 9 | 199 | 4 | 1.8.2
RFP_154542403_Digital_Marketing_Services | 1.8.3.1 | 1.8.3 | Emplifi Extract & Summary | Reporting | Emplifi Reports | Emplifi Extract & Summary | Analyst | Mid | 9 | 199 | 4 | 1.8.3
RFP_154542403_Digital_Marketing_Services | 1.8.4 | 1.8 | Monthly Comprehensive Report | Reporting | Monthly Comprehensive Report |  |  |  | 15 | 199 | 4 | 1.8.3
RFP_154542403_Digital_Marketing_Services | 1.8.4.1 | 1.8.4 | Monthly Report | Reporting | Monthly Comprehensive Report | Monthly Report | Analyst | Mid | 15 | 199 | 4 | 1.8.4
RFP_154542403_Digital_Marketing_Services | 1.8.5 | 1.8 | Monthly Organic Social Report | Reporting | Monthly Organic Social Report |  |  |  | 15 | 199 | 4 | 1.8.4
RFP_154542403_Digital_Marketing_Services | 1.8.5.1 | 1.8.5 | Monthly Organic Report | Reporting | Monthly Organic Social Report | Monthly Organic Report | Analyst | Mid | 15 | 199 | 4 | 1.8.5
RFP_154542403_Digital_Marketing_Services | 1.8.6 | 1.8 | Optimization Recommendations Report | Reporting | Optimization Recommendations Report |  |  |  | 13 | 199 | 4 | 1.8.5
RFP_154542403_Digital_Marketing_Services | 1.8.6.1 | 1.8.6 | Recs & Next Steps | Reporting | Optimization Recommendations Report | Recs & Next Steps | Analyst | Mid | 13 | 199 | 4 | 1.8.6
RFP_154542403_Digital_Marketing_Services | 1.8.7 | 1.8 | Quarterly Ad-Hoc Report | Reporting | Quarterly Ad-Hoc Report |  |  |  | 12 | 199 | 4 | 1.8.6
RFP_154542403_Digital_Marketing_Services | 1.8.7.1 | 1.8.7 | Quarterly Ad-hoc Deep Dive | Reporting | Quarterly Ad-Hoc Report | Quarterly Ad-hoc Deep Dive | Analyst | Mid | 12 | 199 | 4 | 1.8.7
RFP_154542403_Digital_Marketing_Services | 1.8.8 | 1.8 | Quarterly Key Learnings & Insights Report | Reporting | Quarterly Key Learnings & Insights Report |  |  |  | 14 | 199 | 4 | 1.8.7
RFP_154542403_Digital_Marketing_Services | 1.8.8.1 | 1.8.8 | Quarterly Learnings & Insights | Reporting | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights | Analyst | Mid | 14 | 199 | 4 | 1.8.8
RFP_154542403_Digital_Marketing_Services | 1.8.9 | 1.8 | Quarterly Report | Reporting | Quarterly Report |  |  |  | 14 | 199 | 4 | 1.8.8
RFP_154542403_Digital_Marketing_Services | 1.8.9.1 | 1.8.9 | Quarterly Report | Reporting | Quarterly Report | Quarterly Report | Analyst | Mid | 14 | 199 | 4 | 1.8.9
RFP_154542403_Digital_Marketing_Services | 1.8.10 | 1.8 | Summary overview | Reporting | Summary overview |  |  |  | 5 | 199 | 4 | 1.8.9
RFP_154542403_Digital_Marketing_Services | 1.8.10.1 | 1.8.10 | Summary Narrative | Reporting | Summary overview | Summary Narrative | Social Strategist | Mid | 5 | 199 | 4 | 1.8.10
RFP_154542403_Digital_Marketing_Services | 1.8.11 | 1.8 | Weekly Activity Report | Reporting | Weekly Activity Report |  |  |  | 9 | 199 | 4 | 1.8.10
RFP_154542403_Digital_Marketing_Services | 1.8.11.1 | 1.8.11 | Weekly Activity Summary | Reporting | Weekly Activity Report | Weekly Activity Summary | Analyst | Mid | 9 | 199 | 4 | 1.8.11
RFP_154542403_Digital_Marketing_Services | 1.8.12 | 1.8 | Follower Growth | Reporting | Follower Growth |  |  |  | 7 | 203 | 0 | 1.8.11
RFP_154542403_Digital_Marketing_Services | 1.8.12.1 | 1.8.12 | Metric Pull & Notes | Reporting | Follower Growth | Metric Pull & Notes | QA Specialist | Mid | 7 | 203 | 0 | 1.8.12
RFP_154542403_Digital_Marketing_Services | 1.8.13 | 1.8 | Impressions | Reporting | Impressions |  |  |  | 7 | 203 | 0 | 1.8.12
RFP_154542403_Digital_Marketing_Services | 1.8.13.1 | 1.8.13 | Metric Pull & Notes | Reporting | Impressions | Metric Pull & Notes | QA Specialist | Mid | 7 | 203 | 0 | 1.8.13
RFP_154542403_Digital_Marketing_Services | 1.8.14 | 1.8 | Interactions | Reporting | Interactions |  |  |  | 7 | 203 | 0 | 1.8.13
RFP_154542403_Digital_Marketing_Services | 1.8.14.1 | 1.8.14 | Metric Pull & Notes | Reporting | Interactions | Metric Pull & Notes | QA Specialist | Mid | 7 | 203 | 0 | 1.8.14
RFP_154542403_Digital_Marketing_Services | 1.8.15 | 1.8 | Profile Reach | Reporting | Profile Reach |  |  |  | 7 | 203 | 0 | 1.8.14
RFP_154542403_Digital_Marketing_Services | 1.8.15.1 | 1.8.15 | Metric Pull & Notes | Reporting | Profile Reach | Metric Pull & Notes | QA Specialist | Mid | 7 | 203 | 0 | 1.8.15
RFP_154542403_Digital_Marketing_Services | 1.8.16 | 1.8 | Recap Reports | Reporting | Recap Reports |  |  |  | 5 | 203 | 0 | 1.8.15
RFP_154542403_Digital_Marketing_Services | 1.8.16.1 | 1.8.16 | Campaign/Period Recaps | Reporting | Recap Reports | Campaign/Period Recaps | Analyst | Mid | 5 | 203 | 0 | 1.8.16
RFP_154542403_Digital_Marketing_Services | 1.8.17 | 1.8 | Social Reporting | Reporting | Social Reporting |  |  |  | 5 | 203 | 0 | 1.8.16
RFP_154542403_Digital_Marketing_Services | 1.8.17.1 | 1.8.17 | Ongoing Social Reporting | Reporting | Social Reporting | Ongoing Social Reporting | Analyst | Mid | 5 | 203 | 0 | 1.8.17
RFP_154542403_Digital_Marketing_Services | 1.8.18 | 1.8 | Update/maintain Z/Russia tracker | Reporting | Update/maintain Z/Russia tracker |  |  |  | 3 | 203 | 0 | 1.8.17
RFP_154542403_Digital_Marketing_Services | 1.8.18.1 | 1.8.18 | Tracker Update | Reporting | Update/maintain Z/Russia tracker | Tracker Update | Analyst | Mid | 3 | 203 | 0 | 1.8.18