## Scenario A
Row_ID | Deliverable_Code | Task_Code | Service_Department | Deliverable | Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes | Rate_USD | Price_USD
[5 empty] | RFP_Brief_ First on SoundCloud 2021 Campaign | 1 |  | RFP_Brief_ First on SoundCloud 2021 Campaign | Project |  |  |  | 0 | 0 |  |  |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1 | 1 | Development |  |  |  |  | 227 | 0 | 22 |  |  | Core/T2_MediumVolume | 195 | 44265
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1 | 1.1 | ADA Compliance | ADA Compliance |  |  |  | 50 | 0 | 15 | 1.1 |  |  | 195 | 9750
1738 | DEL-0044 | TSK-01729 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.1 | 1.1.1 | Accessibility Audit | ADA Compliance | Accessibility Audit | Accessibility Specialist | Mid | 2 | 0 | 3 | 1.1.1 |  |  | 195 | 390
1739 | DEL-0044 | TSK-01730 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.2 | 1.1.1 | Accessibility QA | ADA Compliance | Accessibility QA | QA Engineer | Mid | 4 | 10 | 2 | 1.1.1.1 |  |  | 195 | 780
1740 | DEL-0044 | TSK-01731 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.3 | 1.1.1 | Code Review | ADA Compliance | Code Review | Frontend Engineer | Mid | 44 | 12 | 10 | 1.1.1.2 |  |  | 195 | 8580
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2 | 1.1 | Audit & Requirement gathering | Audit & Requirement gathering |  |  |  | 17 | 0 | 3 | 1.1.1 |  |  | 195 | 3315
1749 | DEL-0044 | TSK-01740 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.1 | 1.1.2 | Analytics Audit | Audit & Requirement gathering | Analytics Audit | Business Analyst | Mid | 17 | 0 | 3 | 1.1.2 |  |  | 195 | 3315
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3 | 1.1 | Audit existing UA Property | Audit existing UA Property |  |  |  | 17 | 0 | 3 | 1.1.2 |  |  | 195 | 3315
1753 | DEL-0044 | TSK-01744 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.1 | 1.1.3 | Documentation | Audit existing UA Property | Documentation | Business Analyst | Mid | 17 | 0 | 3 | 1.1.3 |  |  | 195 | 3315
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4 | 1.1 | Footer CTA | Footer CTA |  |  |  | 43 | 3 | 19 | 1.1.3 |  |  | 195 | 8385
1765 | DEL-0044 | TSK-01756 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.1 | 1.1.4 | Design Consult | Footer CTA | Design Consult | UI Designer | Mid | 3 | 3 | 7 | 1.1.4 |  |  | 195 | 585
1760 | DEL-0044 | TSK-01751 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.2 | 1.1.4 | Accessibility QA | Footer CTA | Accessibility QA | QA Engineer | Mid | 6 | 10 | 2 | 1.1.4.1 |  |  | 195 | 1170
1761 | DEL-0044 | TSK-01752 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.3 | 1.1.4 | Code Review | Footer CTA | Code Review | Backend Engineer | Mid | 34 | 12 | 10 | 1.1.4.2 |  |  | 195 | 6630
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5 | 1.1 | Header & Footer Navigation | Header & Footer Navigation |  |  |  | 43 | 3 | 19 | 1.1.4 |  |  | 195 | 8385
1773 | DEL-0044 | TSK-01764 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.1 | 1.1.5 | Design Consult | Header & Footer Navigation | Design Consult | UI Designer | Mid | 3 | 3 | 7 | 1.1.5 |  |  | 195 | 585
1768 | DEL-0044 | TSK-01759 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.2 | 1.1.5 | Accessibility QA | Header & Footer Navigation | Accessibility QA | QA Engineer | Mid | 6 | 10 | 2 | 1.1.5.1 |  |  | 195 | 1170
1769 | DEL-0044 | TSK-01760 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.3 | 1.1.5 | Code Review | Header & Footer Navigation | Code Review | Backend Engineer | Mid | 34 | 12 | 10 | 1.1.5.2 |  |  | 195 | 6630
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6 | 1.1 | Additional Goals Setup | Additional Goals Setup |  |  |  | 7 | 10 | 12 | 1.1.5 |  |  | 195 | 1365
1747 | DEL-0044 | TSK-01738 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.1 | 1.1.6 | QA Cycle | Additional Goals Setup | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.6 |  |  | 195 | 585
1746 | DEL-0044 | TSK-01737 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.2 | 1.1.6 | Define & Configure Goals | Additional Goals Setup | Define & Configure Goals | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.6.1 |  |  | 195 | 780
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.7 | 1.1 | Custom Event Tracking | Custom Event Tracking |  |  |  | 7 | 10 | 12 | 1.1.6 |  |  | 195 | 1365
1758 | DEL-0044 | TSK-01749 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.7.1 | 1.1.7 | QA Cycle | Custom Event Tracking | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.7 |  |  | 195 | 585
1757 | DEL-0044 | TSK-01748 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.7.2 | 1.1.7 | Event Schema & Tagging | Custom Event Tracking | Event Schema & Tagging | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.7.1 |  |  | 195 | 780
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.8 | 1.1 | Implement Paid Media Pixel on website w GTM-Google Ads | Implement Paid Media Pixel on website w GTM-Google Ads |  |  |  | 5 | 10 | 12 | 1.1.7 |  |  | 195 | 975
1777 | DEL-0044 | TSK-01768 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.8.1 | 1.1.8 | Spec QA | Implement Paid Media Pixel on website w GTM-Google Ads | Spec QA | QA Engineer | Mid | 3 | 10 | 2 | 1.1.8 |  |  | 195 | 585
1776 | DEL-0044 | TSK-01767 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.8.2 | 1.1.8 | Pixel Setup (GTM) | Implement Paid Media Pixel on website w GTM-Google Ads | Pixel Setup (GTM) | Data/Analytics Engineer | Mid | 2 | 12 | 10 | 1.1.8.1 |  |  | 195 | 390
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.9 | 1.1 | Implement goals listed in UA as Conversions in G4 | Implement goals listed in UA as Conversions in G4 |  |  |  | 7 | 10 | 12 | 1.1.8 |  |  | 195 | 1365
1779 | DEL-0044 | TSK-01770 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.9.1 | 1.1.9 | QA Cycle | Implement goals listed in UA as Conversions in G4 | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.9 |  |  | 195 | 585
1778 | DEL-0044 | TSK-01769 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.9.2 | 1.1.9 | Migrate UA Goals → GA4 Conversions | Implement goals listed in UA as Conversions in G4 | Migrate UA Goals → GA4 Conversions | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.9.1 |  |  | 195 | 780
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.10 | 1.1 | Implementation | Implementation |  |  |  | 7 | 10 | 12 | 1.1.9 |  |  | 195 | 1365
1782 | DEL-0044 | TSK-01773 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.10.1 | 1.1.10 | QA Cycle | Implementation | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.10 |  |  | 195 | 585
1781 | DEL-0044 | TSK-01772 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.10.2 | 1.1.10 | Implement Tags/Events | Implementation | Implement Tags/Events | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.10.1 |  |  | 195 | 780
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.11 | 1.1 | Outbound link clicks | Outbound link clicks |  |  |  | 5 | 10 | 12 | 1.1.10 |  |  | 195 | 975
1785 | DEL-0044 | TSK-01776 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.11.1 | 1.1.11 | QA | Outbound link clicks | QA | QA Engineer | Mid | 3 | 10 | 2 | 1.1.11 |  |  | 195 | 585
1784 | DEL-0044 | TSK-01775 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.11.2 | 1.1.11 | Event Config | Outbound link clicks | Event Config | Data/Analytics Engineer | Mid | 2 | 12 | 10 | 1.1.11.1 |  |  | 195 | 390
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.12 | 1.1 | Publishing tags, Testing and Auditing | Publishing tags, Testing and Auditing |  |  |  | 4 | 10 | 2 | 1.1.11 |  |  | 195 | 780
1786 | DEL-0044 | TSK-01777 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.12.1 | 1.1.12 | Publish & Smoke Test | Publishing tags, Testing and Auditing | Publish & Smoke Test | QA Engineer | Mid | 4 | 10 | 2 | 1.1.12 |  |  | 195 | 780
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.13 | 1.1 | Setup cross-domain tracking | Setup cross-domain tracking |  |  |  | 4 | 10 | 12 | 1.1.12 |  |  | 195 | 780
1789 | DEL-0044 | TSK-01780 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.13.1 | 1.1.13 | QA | Setup cross-domain tracking | QA | QA Engineer | Mid | 2 | 10 | 2 | 1.1.13 |  |  | 195 | 390
1788 | DEL-0044 | TSK-01779 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.13.2 | 1.1.13 | Cross-domain Config | Setup cross-domain tracking | Cross-domain Config | Data/Analytics Engineer | Mid | 2 | 12 | 10 | 1.1.13.1 |  |  | 195 | 390
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.14 | 1.1 | Setup eCommerce tracking | Setup eCommerce tracking |  |  |  | 4 | 10 | 12 | 1.1.13 |  |  | 195 | 780
1791 | DEL-0044 | TSK-01782 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.14.1 | 1.1.14 | QA | Setup eCommerce tracking | QA | QA Engineer | Mid | 2 | 10 | 2 | 1.1.14 |  |  | 195 | 390
1790 | DEL-0044 | TSK-01781 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.14.2 | 1.1.14 | Ecommerce Data Layer | Setup eCommerce tracking | Ecommerce Data Layer | Data/Analytics Engineer | Mid | 2 | 12 | 10 | 1.1.14.1 |  |  | 195 | 390
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.15 | 1.1 | Setup new GA4 acct for Caledera House | Setup new GA4 acct for Caledera House |  |  |  | 7 | 10 | 12 | 1.1.14 |  |  | 195 | 1365
1793 | DEL-0044 | TSK-01784 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.15.1 | 1.1.15 | QA Cycle | Setup new GA4 acct for Caledera House | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.15 |  |  | 195 | 585
1792 | DEL-0044 | TSK-01783 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.15.2 | 1.1.15 | GA4 Property Setup | Setup new GA4 acct for Caledera House | GA4 Property Setup | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.15.1 |  |  | 195 | 780
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2 | 1 | Post-Production |  |  |  |  | 188 | 22 | 41 | 1.1 |  | Core/T2_MediumVolume | 195 | 36660
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1 | 1.2 | Content Licensing / Art Buying | Content Licensing / Art Buying |  |  |  | 2 | 22 | 3 | 1.2 |  |  | 195 | 390
65 | DEL-0003 | TSK-00065 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.1 | 1.2.1 | Rights/License Research | Content Licensing / Art Buying | Rights/License Research | Producer | Mid | 1 | 22 | 3 | 1.2.1 |  |  | 195 | 195
66 | DEL-0003 | TSK-00066 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.2 | 1.2.1 | Usage Notes | Content Licensing / Art Buying | Usage Notes | Account Manager | Mid | 1 | 63 | 0 | 1.2.1.1 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2 | 1.2 | VO Recording Sessions | VO Recording Sessions |  |  |  | 5 | 25 | 4 | 1.2.1 |  |  | 195 | 975
124 | DEL-0003 | TSK-00124 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.1 | 1.2.2 | Script Polish | VO Recording Sessions | Script Polish | Copywriter | Mid | 1 | 25 | 4 | 1.2.2 |  |  | 195 | 195
125 | DEL-0003 | TSK-00125 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.2 | 1.2.2 | VO Session | VO Recording Sessions | VO Session | Sound Designer | Mid | 4 | 63 | 0 | 1.2.2.1 |  |  | 195 | 780
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3 | 1.2 | Editing | Editing |  |  |  | 17 | 29 | 5 | 1.2.2 |  |  | 195 | 3315
74 | DEL-0003 | TSK-00074 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.1 | 1.2.3 | Client Review & Revisions | Editing | Client Review & Revisions | Editor | Mid | 17 | 29 | 5 | 1.2.3 |  |  | 195 | 3315
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4 | 1.2 | Video Editing | Video Editing |  |  |  | 25 | 29 | 5 | 1.2.3 |  |  | 195 | 4875
127 | DEL-0003 | TSK-00127 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.1 | 1.2.4 | Client Review & Revisions | Video Editing | Client Review & Revisions | Editor | Mid | 25 | 29 | 5 | 1.2.4 |  |  | 195 | 4875
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5 | 1.2 | Voice Over | Voice Over |  |  |  | 17 | 29 | 12 | 1.2.4 |  |  | 195 | 3315
140 | DEL-0003 | TSK-00140 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.1 | 1.2.5 | VO Edit | Voice Over | VO Edit | Editor | Mid | 9 | 29 | 5 | 1.2.5 |  |  | 195 | 1755
139 | DEL-0003 | TSK-00139 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.2 | 1.2.5 | Mix | Voice Over | Mix | Sound Designer | Mid | 2 | 46 | 2 | 1.2.5.1 |  |  | 195 | 390
137 | DEL-0003 | TSK-00137 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.3 | 1.2.5 | Internal Review & Critique | Voice Over | Internal Review & Critique | Producer | Mid | 1 | 53 | 2 | 1.2.5.2 |  |  | 195 | 195
134 | DEL-0003 | TSK-00134 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.4 | 1.2.5 | Client Review & Revisions | Voice Over | Client Review & Revisions | Account Manager | Mid | 3 | 55 | 3 | 1.2.5.3 |  |  | 195 | 585
136 | DEL-0003 | TSK-00136 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.5 | 1.2.5 | Final Packaging | Voice Over | Final Packaging | Designer | Mid | 2 | 63 | 0 | 1.2.5.4 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.6 | 1.2 | Motion Design/VFX | Motion Design/VFX |  |  |  | 17 | 34 | 7 | 1.2.5 |  |  | 195 | 3315
90 | DEL-0003 | TSK-00090 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.6.1 | 1.2.6 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Editor | Mid | 17 | 34 | 7 | 1.2.6 |  |  | 195 | 3315
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.7 | 1.2 | Color Correction | Color Correction |  |  |  | 11 | 41 | 2 | 1.2.6 |  |  | 195 | 2145
53 | DEL-0003 | TSK-00053 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.7.1 | 1.2.7 | Client Review & Revisions | Color Correction | Client Review & Revisions | Colorist | Mid | 11 | 41 | 2 | 1.2.7 |  |  | 195 | 2145
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.8 | 1.2 | Color Grading | Color Grading |  |  |  | 11 | 41 | 2 | 1.2.7 |  |  | 195 | 2145
59 | DEL-0003 | TSK-00059 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.8.1 | 1.2.8 | Client Review & Revisions | Color Grading | Client Review & Revisions | Colorist | Mid | 11 | 41 | 2 | 1.2.8 |  |  | 195 | 2145
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9 | 1.2 | Final Retouched Stills Review | Final Retouched Stills Review |  |  |  | 10 | 43 | 8 | 1.2.8 |  |  | 195 | 1950
89 | DEL-0003 | TSK-00089 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.1 | 1.2.9 | Retouch | Final Retouched Stills Review | Retouch | Retoucher | Mid | 4 | 43 | 3 | 1.2.9 |  |  | 195 | 780
87 | DEL-0003 | TSK-00087 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.2 | 1.2.9 | Internal Review & Critique | Final Retouched Stills Review | Internal Review & Critique | Producer | Mid | 1 | 53 | 2 | 1.2.9.1 |  |  | 195 | 195
84 | DEL-0003 | TSK-00084 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.3 | 1.2.9 | Client Review & Revisions | Final Retouched Stills Review | Client Review & Revisions | Account Manager | Mid | 3 | 55 | 3 | 1.2.9.2 |  |  | 195 | 585
86 | DEL-0003 | TSK-00086 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.4 | 1.2.9 | Final Packaging | Final Retouched Stills Review | Final Packaging | Designer | Mid | 2 | 63 | 0 | 1.2.9.3 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10 | 1.2 | Retouching | Retouching |  |  |  | 10 | 43 | 8 | 1.2.9 |  |  | 195 | 1950
102 | DEL-0003 | TSK-00102 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.1 | 1.2.10 | Retouch | Retouching | Retouch | Retoucher | Mid | 4 | 43 | 3 | 1.2.10 |  |  | 195 | 780
100 | DEL-0003 | TSK-00100 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.2 | 1.2.10 | Internal Review & Critique | Retouching | Internal Review & Critique | Producer | Mid | 1 | 53 | 2 | 1.2.10.1 |  |  | 195 | 195
97 | DEL-0003 | TSK-00097 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.3 | 1.2.10 | Client Review & Revisions | Retouching | Client Review & Revisions | Account Manager | Mid | 3 | 55 | 3 | 1.2.10.2 |  |  | 195 | 585
99 | DEL-0003 | TSK-00099 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.4 | 1.2.10 | Final Packaging | Retouching | Final Packaging | Designer | Mid | 2 | 63 | 0 | 1.2.10.3 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.11 | 1.2 | Sound Mix | Sound Mix |  |  |  | 9 | 46 | 2 | 1.2.10 |  |  | 195 | 1755
107 | DEL-0003 | TSK-00107 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.11.1 | 1.2.11 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Designer | Mid | 9 | 46 | 2 | 1.2.11 |  |  | 195 | 1755
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.12 | 1.2 | Sound Sourcing | Sound Sourcing |  |  |  | 3 | 46 | 2 | 1.2.11 |  |  | 195 | 585
113 | DEL-0003 | TSK-00113 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.12.1 | 1.2.12 | Music Search & License | Sound Sourcing | Music Search & License | Sound Designer | Mid | 3 | 46 | 2 | 1.2.12 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13 | 1.2 | Final File Delivery | Final File Delivery |  |  |  | 7 | 48 | 2 | 1.2.12 |  |  | 195 | 1365
83 | DEL-0003 | TSK-00083 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13.1 | 1.2.13 | QA (Tech & Content) | Final File Delivery | QA (Tech & Content) | QA Specialist | Mid | 3 | 48 | 2 | 1.2.13 |  |  | 195 | 585
80 | DEL-0003 | TSK-00080 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13.2 | 1.2.13 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload | Media Manager / DIT | Mid | 4 | 63 | 0 | 1.2.13.1 |  |  | 195 | 780
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14 | 1.2 | True-ups (for vendor costs) | True-ups (for vendor costs) |  |  |  | 10 | 50 | 8 | 1.2.13 |  |  | 195 | 1950
116 | DEL-0003 | TSK-00116 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.1 | 1.2.14 | Change Orders & Tracking | True-ups (for vendor costs) | Change Orders & Tracking | Project Manager | Mid | 1 | 50 | 3 | 1.2.14 |  |  | 195 | 195
120 | DEL-0003 | TSK-00120 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.2 | 1.2.14 | Internal Review & Critique | True-ups (for vendor costs) | Internal Review & Critique | Producer | Mid | 1 | 53 | 2 | 1.2.14.1 |  |  | 195 | 195
117 | DEL-0003 | TSK-00117 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.3 | 1.2.14 | Client Review & Revisions | True-ups (for vendor costs) | Client Review & Revisions | Account Manager | Mid | 3 | 55 | 3 | 1.2.14.2 |  |  | 195 | 585
119 | DEL-0003 | TSK-00119 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.4 | 1.2.14 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation | Designer | Mid | 5 | 63 | 0 | 1.2.14.3 |  |  | 195 | 975
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15 | 1.2 | Cutdowns | Cutdowns |  |  |  | 11 | 53 | 5 | 1.2.14 |  |  | 195 | 2145
71 | DEL-0003 | TSK-00071 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15.1 | 1.2.15 | Internal Review & Critique | Cutdowns | Internal Review & Critique | Producer | Mid | 1 | 53 | 2 | 1.2.15 |  |  | 195 | 195
67 | DEL-0003 | TSK-00067 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15.2 | 1.2.15 | Client Review & Revisions | Cutdowns | Client Review & Revisions | Account Manager | Mid | 3 | 55 | 3 | 1.2.15.1 |  |  | 195 | 585
69 | DEL-0003 | TSK-00069 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15.3 | 1.2.15 | Cutdowns (2-3) | Cutdowns | Cutdowns (2-3) | Editor | Mid | 7 | 63 | 0 | 1.2.15.2 |  |  | 195 | 1365
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.16 | 1.2 | Client Review | Client Review |  |  |  | 4 | 55 | 3 | 1.2.15 |  |  | 195 | 780
50 | DEL-0003 | TSK-00050 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.16.1 | 1.2.16 | Client Review Coordination | Client Review | Client Review Coordination | Account Manager | Mid | 4 | 55 | 3 | 1.2.16 |  |  | 195 | 780
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.17 | 1.2 | Review & Sign-Off | Review & Sign-Off |  |  |  | 3 | 55 | 5 | 1.2.16 |  |  | 195 | 585
103 | DEL-0003 | TSK-00103 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.17.1 | 1.2.17 | Client Review Coordination | Review & Sign-Off | Client Review Coordination | Account Manager | Mid | 2 | 55 | 3 | 1.2.17 |  |  | 195 | 390
105 | DEL-0003 | TSK-00105 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.17.2 | 1.2.17 | Notes Triage | Review & Sign-Off | Notes Triage | Project Manager | Mid | 1 | 61 | 2 | 1.2.17.1 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.18 | 1.2 | Asset Library | Asset Library |  |  |  | 2 | 58 | 3 | 1.2.17 |  |  | 195 | 390
48 | DEL-0003 | TSK-00048 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.18.1 | 1.2.18 | Post Support | Asset Library | Post Support | Editor | Mid | 2 | 58 | 3 | 1.2.18 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.19 | 1.2 | Capture Library | Capture Library |  |  |  | 2 | 58 | 3 | 1.2.18 |  |  | 195 | 390
49 | DEL-0003 | TSK-00049 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.19.1 | 1.2.19 | Post Support | Capture Library | Post Support | Editor | Mid | 2 | 58 | 3 | 1.2.19 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.20 | 1.2 | Selects Deck | Selects Deck |  |  |  | 2 | 58 | 3 | 1.2.19 |  |  | 195 | 390
106 | DEL-0003 | TSK-00106 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.20.1 | 1.2.20 | Post Support | Selects Deck | Post Support | Editor | Mid | 2 | 58 | 3 | 1.2.20 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.21 | 1.2 | Delivery | Delivery |  |  |  | 5 | 63 | 0 | 1.2.20 |  |  | 195 | 975
73 | DEL-0003 | TSK-00073 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.21.1 | 1.2.21 | Post Support | Delivery | Post Support | Editor | Mid | 5 | 63 | 0 | 1.2.21 |  |  | 195 | 975
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.22 | 1.2 | Stills/Footage Selection | Stills/Footage Selection |  |  |  | 5 | 63 | 0 | 1.2.21 |  |  | 195 | 975
115 | DEL-0003 | TSK-00115 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.22.1 | 1.2.22 | Post Support | Stills/Footage Selection | Post Support | Editor | Mid | 5 | 63 | 0 | 1.2.22 |  |  | 195 | 975

## Scenario B
Row_ID | Deliverable_Code | Task_Code | Service_Department | Deliverable | Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes | Rate_USD | Price_USD
[5 empty] | RFP_Brief_ First on SoundCloud 2021 Campaign | 1 |  | RFP_Brief_ First on SoundCloud 2021 Campaign | Project |  |  |  | 0 | 0 |  |  |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1 | 1 | Development |  |  |  |  | 348 | 0 | 28 |  |  | Advanced/T1_LargeVolume | 195 | 67860
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1 | 1.1 | ADA Compliance | ADA Compliance |  |  |  | 77 | 0 | 19 | 1.1 |  |  | 195 | 15015
1738 | DEL-0044 | TSK-01729 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.1 | 1.1.1 | Accessibility Audit | ADA Compliance | Accessibility Audit | Accessibility Specialist | Mid | 3 | 0 | 4 | 1.1.1 |  |  | 195 | 585
1739 | DEL-0044 | TSK-01730 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.2 | 1.1.1 | Accessibility QA | ADA Compliance | Accessibility QA | QA Engineer | Mid | 6 | 13 | 3 | 1.1.1.1 |  |  | 195 | 1170
1740 | DEL-0044 | TSK-01731 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.3 | 1.1.1 | Code Review | ADA Compliance | Code Review | Frontend Engineer | Mid | 68 | 16 | 12 | 1.1.1.2 |  |  | 195 | 13260
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2 | 1.1 | Audit & Requirement gathering | Audit & Requirement gathering |  |  |  | 26 | 0 | 4 | 1.1.1 |  |  | 195 | 5070
1749 | DEL-0044 | TSK-01740 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.1 | 1.1.2 | Analytics Audit | Audit & Requirement gathering | Analytics Audit | Business Analyst | Mid | 26 | 0 | 4 | 1.1.2 |  |  | 195 | 5070
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3 | 1.1 | Audit existing UA Property | Audit existing UA Property |  |  |  | 26 | 0 | 4 | 1.1.2 |  |  | 195 | 5070
1753 | DEL-0044 | TSK-01744 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.1 | 1.1.3 | Documentation | Audit existing UA Property | Documentation | Business Analyst | Mid | 26 | 0 | 4 | 1.1.3 |  |  | 195 | 5070
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4 | 1.1 | Footer CTA | Footer CTA |  |  |  | 66 | 4 | 24 | 1.1.3 |  |  | 195 | 12870
1765 | DEL-0044 | TSK-01756 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.1 | 1.1.4 | Design Consult | Footer CTA | Design Consult | UI Designer | Mid | 5 | 4 | 9 | 1.1.4 |  |  | 195 | 975
1760 | DEL-0044 | TSK-01751 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.2 | 1.1.4 | Accessibility QA | Footer CTA | Accessibility QA | QA Engineer | Mid | 9 | 13 | 3 | 1.1.4.1 |  |  | 195 | 1755
1761 | DEL-0044 | TSK-01752 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.3 | 1.1.4 | Code Review | Footer CTA | Code Review | Backend Engineer | Mid | 52 | 16 | 12 | 1.1.4.2 |  |  | 195 | 10140
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5 | 1.1 | Header & Footer Navigation | Header & Footer Navigation |  |  |  | 66 | 4 | 24 | 1.1.4 |  |  | 195 | 12870
1773 | DEL-0044 | TSK-01764 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.1 | 1.1.5 | Design Consult | Header & Footer Navigation | Design Consult | UI Designer | Mid | 5 | 4 | 9 | 1.1.5 |  |  | 195 | 975
1768 | DEL-0044 | TSK-01759 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.2 | 1.1.5 | Accessibility QA | Header & Footer Navigation | Accessibility QA | QA Engineer | Mid | 9 | 13 | 3 | 1.1.5.1 |  |  | 195 | 1755
1769 | DEL-0044 | TSK-01760 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.3 | 1.1.5 | Code Review | Header & Footer Navigation | Code Review | Backend Engineer | Mid | 52 | 16 | 12 | 1.1.5.2 |  |  | 195 | 10140
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6 | 1.1 | Additional Goals Setup | Additional Goals Setup |  |  |  | 11 | 13 | 15 | 1.1.5 |  |  | 195 | 2145
1747 | DEL-0044 | TSK-01738 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.1 | 1.1.6 | QA Cycle | Additional Goals Setup | QA Cycle | QA Engineer | Mid | 4 | 13 | 3 | 1.1.6 |  |  | 195 | 780
1746 | DEL-0044 | TSK-01737 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.2 | 1.1.6 | Define & Configure Goals | Additional Goals Setup | Define & Configure Goals | Data/Analytics Engineer | Mid | 7 | 16 | 12 | 1.1.6.1 |  |  | 195 | 1365
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.7 | 1.1 | Custom Event Tracking | Custom Event Tracking |  |  |  | 11 | 13 | 15 | 1.1.6 |  |  | 195 | 2145
1758 | DEL-0044 | TSK-01749 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.7.1 | 1.1.7 | QA Cycle | Custom Event Tracking | QA Cycle | QA Engineer | Mid | 4 | 13 | 3 | 1.1.7 |  |  | 195 | 780
1757 | DEL-0044 | TSK-01748 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.7.2 | 1.1.7 | Event Schema & Tagging | Custom Event Tracking | Event Schema & Tagging | Data/Analytics Engineer | Mid | 7 | 16 | 12 | 1.1.7.1 |  |  | 195 | 1365
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.8 | 1.1 | Implement Paid Media Pixel on website w GTM-Google Ads | Implement Paid Media Pixel on website w GTM-Google Ads |  |  |  | 7 | 13 | 15 | 1.1.7 |  |  | 195 | 1365
1777 | DEL-0044 | TSK-01768 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.8.1 | 1.1.8 | Spec QA | Implement Paid Media Pixel on website w GTM-Google Ads | Spec QA | QA Engineer | Mid | 4 | 13 | 3 | 1.1.8 |  |  | 195 | 780
1776 | DEL-0044 | TSK-01767 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.8.2 | 1.1.8 | Pixel Setup (GTM) | Implement Paid Media Pixel on website w GTM-Google Ads | Pixel Setup (GTM) | Data/Analytics Engineer | Mid | 3 | 16 | 12 | 1.1.8.1 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.9 | 1.1 | Implement goals listed in UA as Conversions in G4 | Implement goals listed in UA as Conversions in G4 |  |  |  | 10 | 13 | 15 | 1.1.8 |  |  | 195 | 1950
1779 | DEL-0044 | TSK-01770 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.9.1 | 1.1.9 | QA Cycle | Implement goals listed in UA as Conversions in G4 | QA Cycle | QA Engineer | Mid | 4 | 13 | 3 | 1.1.9 |  |  | 195 | 780
1778 | DEL-0044 | TSK-01769 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.9.2 | 1.1.9 | Migrate UA Goals → GA4 Conversions | Implement goals listed in UA as Conversions in G4 | Migrate UA Goals → GA4 Conversions | Data/Analytics Engineer | Mid | 6 | 16 | 12 | 1.1.9.1 |  |  | 195 | 1170
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.10 | 1.1 | Implementation | Implementation |  |  |  | 10 | 13 | 15 | 1.1.9 |  |  | 195 | 1950
1782 | DEL-0044 | TSK-01773 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.10.1 | 1.1.10 | QA Cycle | Implementation | QA Cycle | QA Engineer | Mid | 4 | 13 | 3 | 1.1.10 |  |  | 195 | 780
1781 | DEL-0044 | TSK-01772 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.10.2 | 1.1.10 | Implement Tags/Events | Implementation | Implement Tags/Events | Data/Analytics Engineer | Mid | 6 | 16 | 12 | 1.1.10.1 |  |  | 195 | 1170
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.11 | 1.1 | Outbound link clicks | Outbound link clicks |  |  |  | 7 | 13 | 15 | 1.1.10 |  |  | 195 | 1365
1785 | DEL-0044 | TSK-01776 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.11.1 | 1.1.11 | QA | Outbound link clicks | QA | QA Engineer | Mid | 4 | 13 | 3 | 1.1.11 |  |  | 195 | 780
1784 | DEL-0044 | TSK-01775 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.11.2 | 1.1.11 | Event Config | Outbound link clicks | Event Config | Data/Analytics Engineer | Mid | 3 | 16 | 12 | 1.1.11.1 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.12 | 1.1 | Publishing tags, Testing and Auditing | Publishing tags, Testing and Auditing |  |  |  | 7 | 13 | 3 | 1.1.11 |  |  | 195 | 1365
1786 | DEL-0044 | TSK-01777 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.12.1 | 1.1.12 | Publish & Smoke Test | Publishing tags, Testing and Auditing | Publish & Smoke Test | QA Engineer | Mid | 7 | 13 | 3 | 1.1.12 |  |  | 195 | 1365
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.13 | 1.1 | Setup cross-domain tracking | Setup cross-domain tracking |  |  |  | 7 | 13 | 15 | 1.1.12 |  |  | 195 | 1365
1789 | DEL-0044 | TSK-01780 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.13.1 | 1.1.13 | QA | Setup cross-domain tracking | QA | QA Engineer | Mid | 4 | 13 | 3 | 1.1.13 |  |  | 195 | 780
1788 | DEL-0044 | TSK-01779 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.13.2 | 1.1.13 | Cross-domain Config | Setup cross-domain tracking | Cross-domain Config | Data/Analytics Engineer | Mid | 3 | 16 | 12 | 1.1.13.1 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.14 | 1.1 | Setup eCommerce tracking | Setup eCommerce tracking |  |  |  | 7 | 13 | 15 | 1.1.13 |  |  | 195 | 1365
1791 | DEL-0044 | TSK-01782 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.14.1 | 1.1.14 | QA | Setup eCommerce tracking | QA | QA Engineer | Mid | 4 | 13 | 3 | 1.1.14 |  |  | 195 | 780
1790 | DEL-0044 | TSK-01781 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.14.2 | 1.1.14 | Ecommerce Data Layer | Setup eCommerce tracking | Ecommerce Data Layer | Data/Analytics Engineer | Mid | 3 | 16 | 12 | 1.1.14.1 |  |  | 195 | 585
| DEL-0044 |  | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.15 | 1.1 | Setup new GA4 acct for Caledera House | Setup new GA4 acct for Caledera House |  |  |  | 10 | 13 | 15 | 1.1.14 |  |  | 195 | 1950
1793 | DEL-0044 | TSK-01784 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.15.1 | 1.1.15 | QA Cycle | Setup new GA4 acct for Caledera House | QA Cycle | QA Engineer | Mid | 4 | 13 | 3 | 1.1.15 |  |  | 195 | 780
1792 | DEL-0044 | TSK-01783 | Technology | Development | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.15.2 | 1.1.15 | GA4 Property Setup | Setup new GA4 acct for Caledera House | GA4 Property Setup | Data/Analytics Engineer | Mid | 6 | 16 | 12 | 1.1.15.1 |  |  | 195 | 1170
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2 | 1 | Post-Production |  |  |  |  | 288 | 28 | 51 | 1.1 |  | Advanced/T1_LargeVolume | 195 | 56160
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1 | 1.2 | Content Licensing / Art Buying | Content Licensing / Art Buying |  |  |  | 3 | 28 | 4 | 1.2 |  |  | 195 | 585
65 | DEL-0003 | TSK-00065 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.1 | 1.2.1 | Rights/License Research | Content Licensing / Art Buying | Rights/License Research | Producer | Mid | 1 | 28 | 4 | 1.2.1 |  |  | 195 | 195
66 | DEL-0003 | TSK-00066 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.2 | 1.2.1 | Usage Notes | Content Licensing / Art Buying | Usage Notes | Account Manager | Mid | 2 | 79 | 0 | 1.2.1.1 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2 | 1.2 | VO Recording Sessions | VO Recording Sessions |  |  |  | 7 | 32 | 5 | 1.2.1 |  |  | 195 | 1365
124 | DEL-0003 | TSK-00124 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.1 | 1.2.2 | Script Polish | VO Recording Sessions | Script Polish | Copywriter | Mid | 2 | 32 | 5 | 1.2.2 |  |  | 195 | 390
125 | DEL-0003 | TSK-00125 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.2 | 1.2.2 | VO Session | VO Recording Sessions | VO Session | Sound Designer | Mid | 5 | 79 | 0 | 1.2.2.1 |  |  | 195 | 975
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3 | 1.2 | Editing | Editing |  |  |  | 26 | 37 | 6 | 1.2.2 |  |  | 195 | 5070
74 | DEL-0003 | TSK-00074 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.1 | 1.2.3 | Client Review & Revisions | Editing | Client Review & Revisions | Editor | Mid | 26 | 37 | 6 | 1.2.3 |  |  | 195 | 5070
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4 | 1.2 | Video Editing | Video Editing |  |  |  | 39 | 37 | 6 | 1.2.3 |  |  | 195 | 7605
127 | DEL-0003 | TSK-00127 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.1 | 1.2.4 | Client Review & Revisions | Video Editing | Client Review & Revisions | Editor | Mid | 39 | 37 | 6 | 1.2.4 |  |  | 195 | 7605
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5 | 1.2 | Voice Over | Voice Over |  |  |  | 26 | 37 | 14 | 1.2.4 |  |  | 195 | 5070
140 | DEL-0003 | TSK-00140 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.1 | 1.2.5 | VO Edit | Voice Over | VO Edit | Editor | Mid | 13 | 37 | 6 | 1.2.5 |  |  | 195 | 2535
139 | DEL-0003 | TSK-00139 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.2 | 1.2.5 | Mix | Voice Over | Mix | Sound Designer | Mid | 3 | 59 | 3 | 1.2.5.1 |  |  | 195 | 585
137 | DEL-0003 | TSK-00137 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.3 | 1.2.5 | Internal Review & Critique | Voice Over | Internal Review & Critique | Producer | Mid | 3 | 69 | 2 | 1.2.5.2 |  |  | 195 | 585
134 | DEL-0003 | TSK-00134 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.4 | 1.2.5 | Client Review & Revisions | Voice Over | Client Review & Revisions | Account Manager | Mid | 4 | 71 | 3 | 1.2.5.3 |  |  | 195 | 780
136 | DEL-0003 | TSK-00136 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.5 | 1.2.5 | Final Packaging | Voice Over | Final Packaging | Designer | Mid | 3 | 79 | 0 | 1.2.5.4 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.6 | 1.2 | Motion Design/VFX | Motion Design/VFX |  |  |  | 26 | 43 | 9 | 1.2.5 |  |  | 195 | 5070
90 | DEL-0003 | TSK-00090 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.6.1 | 1.2.6 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Editor | Mid | 26 | 43 | 9 | 1.2.6 |  |  | 195 | 5070
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.7 | 1.2 | Color Correction | Color Correction |  |  |  | 17 | 52 | 3 | 1.2.6 |  |  | 195 | 3315
53 | DEL-0003 | TSK-00053 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.7.1 | 1.2.7 | Client Review & Revisions | Color Correction | Client Review & Revisions | Colorist | Mid | 17 | 52 | 3 | 1.2.7 |  |  | 195 | 3315
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.8 | 1.2 | Color Grading | Color Grading |  |  |  | 17 | 52 | 3 | 1.2.7 |  |  | 195 | 3315
59 | DEL-0003 | TSK-00059 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.8.1 | 1.2.8 | Client Review & Revisions | Color Grading | Client Review & Revisions | Colorist | Mid | 17 | 52 | 3 | 1.2.8 |  |  | 195 | 3315
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9 | 1.2 | Final Retouched Stills Review | Final Retouched Stills Review |  |  |  | 16 | 55 | 9 | 1.2.8 |  |  | 195 | 3120
89 | DEL-0003 | TSK-00089 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.1 | 1.2.9 | Retouch | Final Retouched Stills Review | Retouch | Retoucher | Mid | 7 | 55 | 4 | 1.2.9 |  |  | 195 | 1365
87 | DEL-0003 | TSK-00087 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.2 | 1.2.9 | Internal Review & Critique | Final Retouched Stills Review | Internal Review & Critique | Producer | Mid | 2 | 69 | 2 | 1.2.9.1 |  |  | 195 | 390
84 | DEL-0003 | TSK-00084 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.3 | 1.2.9 | Client Review & Revisions | Final Retouched Stills Review | Client Review & Revisions | Account Manager | Mid | 4 | 71 | 3 | 1.2.9.2 |  |  | 195 | 780
86 | DEL-0003 | TSK-00086 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.4 | 1.2.9 | Final Packaging | Final Retouched Stills Review | Final Packaging | Designer | Mid | 3 | 79 | 0 | 1.2.9.3 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10 | 1.2 | Retouching | Retouching |  |  |  | 16 | 55 | 9 | 1.2.9 |  |  | 195 | 3120
102 | DEL-0003 | TSK-00102 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.1 | 1.2.10 | Retouch | Retouching | Retouch | Retoucher | Mid | 7 | 55 | 4 | 1.2.10 |  |  | 195 | 1365
100 | DEL-0003 | TSK-00100 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.2 | 1.2.10 | Internal Review & Critique | Retouching | Internal Review & Critique | Producer | Mid | 2 | 69 | 2 | 1.2.10.1 |  |  | 195 | 390
97 | DEL-0003 | TSK-00097 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.3 | 1.2.10 | Client Review & Revisions | Retouching | Client Review & Revisions | Account Manager | Mid | 4 | 71 | 3 | 1.2.10.2 |  |  | 195 | 780
99 | DEL-0003 | TSK-00099 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.4 | 1.2.10 | Final Packaging | Retouching | Final Packaging | Designer | Mid | 3 | 79 | 0 | 1.2.10.3 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.11 | 1.2 | Sound Mix | Sound Mix |  |  |  | 13 | 59 | 3 | 1.2.10 |  |  | 195 | 2535
107 | DEL-0003 | TSK-00107 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.11.1 | 1.2.11 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Designer | Mid | 13 | 59 | 3 | 1.2.11 |  |  | 195 | 2535
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.12 | 1.2 | Sound Sourcing | Sound Sourcing |  |  |  | 4 | 59 | 3 | 1.2.11 |  |  | 195 | 780
113 | DEL-0003 | TSK-00113 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.12.1 | 1.2.12 | Music Search & License | Sound Sourcing | Music Search & License | Sound Designer | Mid | 4 | 59 | 3 | 1.2.12 |  |  | 195 | 780
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13 | 1.2 | Final File Delivery | Final File Delivery |  |  |  | 10 | 62 | 3 | 1.2.12 |  |  | 195 | 1950
83 | DEL-0003 | TSK-00083 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13.1 | 1.2.13 | QA (Tech & Content) | Final File Delivery | QA (Tech & Content) | QA Specialist | Mid | 4 | 62 | 3 | 1.2.13 |  |  | 195 | 780
80 | DEL-0003 | TSK-00080 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13.2 | 1.2.13 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload | Media Manager / DIT | Mid | 6 | 79 | 0 | 1.2.13.1 |  |  | 195 | 1170
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14 | 1.2 | True-ups (for vendor costs) | True-ups (for vendor costs) |  |  |  | 15 | 65 | 9 | 1.2.13 |  |  | 195 | 2925
116 | DEL-0003 | TSK-00116 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.1 | 1.2.14 | Change Orders & Tracking | True-ups (for vendor costs) | Change Orders & Tracking | Project Manager | Mid | 1 | 65 | 4 | 1.2.14 |  |  | 195 | 195
120 | DEL-0003 | TSK-00120 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.2 | 1.2.14 | Internal Review & Critique | True-ups (for vendor costs) | Internal Review & Critique | Producer | Mid | 3 | 69 | 2 | 1.2.14.1 |  |  | 195 | 585
117 | DEL-0003 | TSK-00117 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.3 | 1.2.14 | Client Review & Revisions | True-ups (for vendor costs) | Client Review & Revisions | Account Manager | Mid | 4 | 71 | 3 | 1.2.14.2 |  |  | 195 | 780
119 | DEL-0003 | TSK-00119 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.4 | 1.2.14 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation | Designer | Mid | 7 | 79 | 0 | 1.2.14.3 |  |  | 195 | 1365
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15 | 1.2 | Cutdowns | Cutdowns |  |  |  | 17 | 69 | 5 | 1.2.14 |  |  | 195 | 3315
71 | DEL-0003 | TSK-00071 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15.1 | 1.2.15 | Internal Review & Critique | Cutdowns | Internal Review & Critique | Producer | Mid | 2 | 69 | 2 | 1.2.15 |  |  | 195 | 390
67 | DEL-0003 | TSK-00067 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15.2 | 1.2.15 | Client Review & Revisions | Cutdowns | Client Review & Revisions | Account Manager | Mid | 4 | 71 | 3 | 1.2.15.1 |  |  | 195 | 780
69 | DEL-0003 | TSK-00069 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15.3 | 1.2.15 | Cutdowns (2-3) | Cutdowns | Cutdowns (2-3) | Editor | Mid | 11 | 79 | 0 | 1.2.15.2 |  |  | 195 | 2145
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.16 | 1.2 | Client Review | Client Review |  |  |  | 6 | 71 | 3 | 1.2.15 |  |  | 195 | 1170
50 | DEL-0003 | TSK-00050 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.16.1 | 1.2.16 | Client Review Coordination | Client Review | Client Review Coordination | Account Manager | Mid | 6 | 71 | 3 | 1.2.16 |  |  | 195 | 1170
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.17 | 1.2 | Review & Sign-Off | Review & Sign-Off |  |  |  | 5 | 71 | 5 | 1.2.16 |  |  | 195 | 975
103 | DEL-0003 | TSK-00103 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.17.1 | 1.2.17 | Client Review Coordination | Review & Sign-Off | Client Review Coordination | Account Manager | Mid | 4 | 71 | 3 | 1.2.17 |  |  | 195 | 780
105 | DEL-0003 | TSK-00105 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.17.2 | 1.2.17 | Notes Triage | Review & Sign-Off | Notes Triage | Project Manager | Mid | 1 | 77 | 2 | 1.2.17.1 |  |  | 195 | 195
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.18 | 1.2 | Asset Library | Asset Library |  |  |  | 3 | 74 | 3 | 1.2.17 |  |  | 195 | 585
48 | DEL-0003 | TSK-00048 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.18.1 | 1.2.18 | Post Support | Asset Library | Post Support | Editor | Mid | 3 | 74 | 3 | 1.2.18 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.19 | 1.2 | Capture Library | Capture Library |  |  |  | 3 | 74 | 3 | 1.2.18 |  |  | 195 | 585
49 | DEL-0003 | TSK-00049 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.19.1 | 1.2.19 | Post Support | Capture Library | Post Support | Editor | Mid | 3 | 74 | 3 | 1.2.19 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.20 | 1.2 | Selects Deck | Selects Deck |  |  |  | 3 | 74 | 3 | 1.2.19 |  |  | 195 | 585
106 | DEL-0003 | TSK-00106 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.20.1 | 1.2.20 | Post Support | Selects Deck | Post Support | Editor | Mid | 3 | 74 | 3 | 1.2.20 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.21 | 1.2 | Delivery | Delivery |  |  |  | 8 | 79 | 0 | 1.2.20 |  |  | 195 | 1560
73 | DEL-0003 | TSK-00073 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.21.1 | 1.2.21 | Post Support | Delivery | Post Support | Editor | Mid | 8 | 79 | 0 | 1.2.21 |  |  | 195 | 1560
| DEL-0003 |  | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.22 | 1.2 | Stills/Footage Selection | Stills/Footage Selection |  |  |  | 8 | 79 | 0 | 1.2.21 |  |  | 195 | 1560
115 | DEL-0003 | TSK-00115 | Content | Post-Production | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.22.1 | 1.2.22 | Post Support | Stills/Footage Selection | Post Support | Editor | Mid | 8 | 79 | 0 | 1.2.22 |  |  | 195 | 1560