## Sheet1
Row_ID | Deliverable_Code | Task_Code | Service_Department | Deliverable | Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes | Rate_USD | Price_USD
[5 empty] | RFP_Brief_ First on SoundCloud 2021 Campaign | 1 |  | RFP_Brief_ First on SoundCloud 2021 Campaign | Project |  |  |  | 0 | 0 |  |  |  |  | 0 | 0
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1 | 1 | Brand Positioning Strategy |  |  |  |  | 98 | 0 | 8 |  |  | Advanced/T2_MediumVolume | 195 | 19110
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1 | 1.1 | Key Pillars | Key Pillars |  |  |  | 17 | 0 | 8 | 1.1 |  |  | 195 | 3315
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.1 | 1.1.1 | Draft Pillars & Proof Points | Key Pillars | Draft Pillars & Proof Points |  |  | 0 | 0 | 3 | 1.1.1 |  |  | 0 | 0
1420 | DEL-0034 | TSK-01411 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.1.1 | 1.1.1.1 | Draft Pillars & Proof Points | Key Pillars | Draft Pillars & Proof Points | Copywriter | Mid | 2 |  |  | 1.1.1.1 |  |  | 195 | 390
1421 | DEL-0034 | TSK-01412 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.1.2 | 1.1.1.1 | Draft Pillars & Proof Points | Key Pillars | Draft Pillars & Proof Points | Strategist | Mid | 4 |  |  | 1.1.1.1.1 |  |  | 195 | 780
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.2 | 1.1.1 | Internal Review & Critique | Key Pillars | Internal Review & Critique |  |  | 0 | 3 | 2 | 1.1.1.1.2 |  |  | 0 | 0
1423 | DEL-0034 | TSK-01414 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.2.1 | 1.1.1.2 | Internal Review & Critique | Key Pillars | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.1.2 |  |  | 195 | 195
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.3 | 1.1.1 | Client Review & Revisions | Key Pillars | Client Review & Revisions |  |  | 0 | 5 | 3 | 1.1.1.2.1 |  |  | 0 | 0
1416 | DEL-0034 | TSK-01407 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.3.1 | 1.1.1.3 | Client Review & Revisions | Key Pillars | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.1.3 |  |  | 195 | 390
1417 | DEL-0034 | TSK-01408 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.3.2 | 1.1.1.3 | Client Review & Revisions | Key Pillars | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.1.1.3.1 |  |  | 195 | 195
1418 | DEL-0034 | TSK-01409 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.3.3 | 1.1.1.3 | Client Review & Revisions | Key Pillars | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.1.1.3.2 |  |  | 195 | 195
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.4 | 1.1.1 | Define Pillar Architecture | Key Pillars | Define Pillar Architecture |  |  | 0 | 8 | 0 | 1.1.1.3.3 |  |  | 0 | 0
1422 | DEL-0034 | TSK-01413 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.4.1 | 1.1.1.4 | Define Pillar Architecture | Key Pillars | Define Pillar Architecture | Designer | Mid | 3 |  |  | 1.1.1.4 |  |  | 195 | 585
1419 | DEL-0034 | TSK-01410 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.4.2 | 1.1.1.4 | Define Pillar Architecture | Key Pillars | Define Pillar Architecture | Strategist | Mid | 3 |  |  | 1.1.1.4.1 |  |  | 195 | 585
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2 | 1.1 | Brand Narrative | Brand Narrative |  |  |  | 17 | 3 | 5 | 1.1.1 |  |  | 195 | 3315
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.1 | 1.1.2 | Internal Review & Critique | Brand Narrative | Internal Review & Critique |  |  | 0 | 3 | 2 | 1.1.2 |  |  | 0 | 0
1396 | DEL-0034 | TSK-01387 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.1.1 | 1.1.2.1 | Internal Review & Critique | Brand Narrative | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.2.1 |  |  | 195 | 195
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.2 | 1.1.2 | Client Review & Revisions | Brand Narrative | Client Review & Revisions |  |  | 0 | 5 | 3 | 1.1.2.1.1 |  |  | 0 | 0
1389 | DEL-0034 | TSK-01380 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.2.1 | 1.1.2.2 | Client Review & Revisions | Brand Narrative | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.2.2 |  |  | 195 | 390
1390 | DEL-0034 | TSK-01381 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.2.2 | 1.1.2.2 | Client Review & Revisions | Brand Narrative | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.1.2.2.1 |  |  | 195 | 195
1391 | DEL-0034 | TSK-01382 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.2.3 | 1.1.2.2 | Client Review & Revisions | Brand Narrative | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.1.2.2.2 |  |  | 195 | 195
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.3 | 1.1.2 | Draft Narrative | Brand Narrative | Draft Narrative |  |  | 0 | 8 | 0 | 1.1.2.2.3 |  |  | 0 | 0
1392 | DEL-0034 | TSK-01383 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.3.1 | 1.1.2.3 | Draft Narrative | Brand Narrative | Draft Narrative | Copywriter | Mid | 2 |  |  | 1.1.2.3 |  |  | 195 | 390
1394 | DEL-0034 | TSK-01385 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.3.2 | 1.1.2.3 | Draft Narrative | Brand Narrative | Draft Narrative | Designer | Mid | 3 |  |  | 1.1.2.3.1 |  |  | 195 | 585
1393 | DEL-0034 | TSK-01384 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.3.3 | 1.1.2.3 | Draft Narrative | Brand Narrative | Draft Narrative | Strategist | Mid | 7 |  |  | 1.1.2.3.2 |  |  | 195 | 1365
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3 | 1.1 | Brand Values Statement and or Proposition | Brand Values Statement and or Proposition |  |  |  | 15 | 3 | 5 | 1.1.2 |  |  | 195 | 2925
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.1 | 1.1.3 | Internal Review & Critique | Brand Values Statement and or Proposition | Internal Review & Critique |  |  | 0 | 3 | 2 | 1.1.3 |  |  | 0 | 0
1405 | DEL-0034 | TSK-01396 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.1.1 | 1.1.3.1 | Internal Review & Critique | Brand Values Statement and or Proposition | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.3.1 |  |  | 195 | 195
1406 | DEL-0034 | TSK-01397 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.1.2 | 1.1.3.1 | Internal Review & Critique | Brand Values Statement and or Proposition | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.1.3.1.1 |  |  | 195 | 195
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.2 | 1.1.3 | Client Review & Revisions | Brand Values Statement and or Proposition | Client Review & Revisions |  |  | 0 | 5 | 3 | 1.1.3.1.2 |  |  | 0 | 0
1398 | DEL-0034 | TSK-01389 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.2.1 | 1.1.3.2 | Client Review & Revisions | Brand Values Statement and or Proposition | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.1.3.2 |  |  | 195 | 195
1399 | DEL-0034 | TSK-01390 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.2.2 | 1.1.3.2 | Client Review & Revisions | Brand Values Statement and or Proposition | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.1.3.2.1 |  |  | 195 | 195
1400 | DEL-0034 | TSK-01391 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.2.3 | 1.1.3.2 | Client Review & Revisions | Brand Values Statement and or Proposition | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.1.3.2.2 |  |  | 195 | 195
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.3 | 1.1.3 | Draft Values/Proposition | Brand Values Statement and or Proposition | Draft Values/Proposition |  |  | 0 | 8 | 0 | 1.1.3.2.3 |  |  | 0 | 0
1401 | DEL-0034 | TSK-01392 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.3.1 | 1.1.3.3 | Draft Values/Proposition | Brand Values Statement and or Proposition | Draft Values/Proposition | Copywriter | Mid | 4 |  |  | 1.1.3.3 |  |  | 195 | 780
1404 | DEL-0034 | TSK-01395 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.3.2 | 1.1.3.3 | Draft Values/Proposition | Brand Values Statement and or Proposition | Draft Values/Proposition | Designer | Mid | 3 |  |  | 1.1.3.3.1 |  |  | 195 | 585
1402 | DEL-0034 | TSK-01393 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.3.3 | 1.1.3.3 | Draft Values/Proposition | Brand Values Statement and or Proposition | Draft Values/Proposition | Strategist | Mid | 3 |  |  | 1.1.3.3.2 |  |  | 195 | 585
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4 | 1.1 | Brand Vision Statement | Brand Vision Statement |  |  |  | 17 | 3 | 5 | 1.1.3 |  |  | 195 | 3315
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.1 | 1.1.4 | Internal Review & Critique | Brand Vision Statement | Internal Review & Critique |  |  | 0 | 3 | 2 | 1.1.4 |  |  | 0 | 0
1413 | DEL-0034 | TSK-01404 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.1.1 | 1.1.4.1 | Internal Review & Critique | Brand Vision Statement | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.4.1 |  |  | 195 | 195
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.2 | 1.1.4 | Client Review & Revisions | Brand Vision Statement | Client Review & Revisions |  |  | 0 | 5 | 3 | 1.1.4.1.1 |  |  | 0 | 0
1407 | DEL-0034 | TSK-01398 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.2.1 | 1.1.4.2 | Client Review & Revisions | Brand Vision Statement | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.4.2 |  |  | 195 | 390
1408 | DEL-0034 | TSK-01399 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.2.2 | 1.1.4.2 | Client Review & Revisions | Brand Vision Statement | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.1.4.2.1 |  |  | 195 | 195
1409 | DEL-0034 | TSK-01400 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.2.3 | 1.1.4.2 | Client Review & Revisions | Brand Vision Statement | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.1.4.2.2 |  |  | 195 | 195
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.3 | 1.1.4 | Draft Statements (Purpose/Mission/Vision) | Brand Vision Statement | Draft Statements (Purpose/Mission/Vision) |  |  | 0 | 8 | 0 | 1.1.4.2.3 |  |  | 0 | 0
1410 | DEL-0034 | TSK-01401 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.3.1 | 1.1.4.3 | Draft Statements (Purpose/Mission/Vision) | Brand Vision Statement | Draft Statements (Purpose/Mission/Vision) | Copywriter | Mid | 2 |  |  | 1.1.4.3 |  |  | 195 | 390
1412 | DEL-0034 | TSK-01403 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.3.2 | 1.1.4.3 | Draft Statements (Purpose/Mission/Vision) | Brand Vision Statement | Draft Statements (Purpose/Mission/Vision) | Designer | Mid | 3 |  |  | 1.1.4.3.1 |  |  | 195 | 585
1411 | DEL-0034 | TSK-01402 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.3.3 | 1.1.4.3 | Draft Statements (Purpose/Mission/Vision) | Brand Vision Statement | Draft Statements (Purpose/Mission/Vision) | Strategist | Mid | 7 |  |  | 1.1.4.3.2 |  |  | 195 | 1365
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5 | 1.1 | Mission Statement | Mission Statement |  |  |  | 16 | 3 | 5 | 1.1.4 |  |  | 195 | 3120
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.1 | 1.1.5 | Internal Review & Critique | Mission Statement | Internal Review & Critique |  |  | 0 | 3 | 2 | 1.1.5 |  |  | 0 | 0
1431 | DEL-0034 | TSK-01422 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.1.1 | 1.1.5.1 | Internal Review & Critique | Mission Statement | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.5.1 |  |  | 195 | 195
1432 | DEL-0034 | TSK-01423 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.1.2 | 1.1.5.1 | Internal Review & Critique | Mission Statement | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.1.5.1.1 |  |  | 195 | 195
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.2 | 1.1.5 | Client Review & Revisions | Mission Statement | Client Review & Revisions |  |  | 0 | 5 | 3 | 1.1.5.1.2 |  |  | 0 | 0
1425 | DEL-0034 | TSK-01416 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.2.1 | 1.1.5.2 | Client Review & Revisions | Mission Statement | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.1.5.2 |  |  | 195 | 195
1426 | DEL-0034 | TSK-01417 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.2.2 | 1.1.5.2 | Client Review & Revisions | Mission Statement | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.1.5.2.1 |  |  | 195 | 195
1427 | DEL-0034 | TSK-01418 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.2.3 | 1.1.5.2 | Client Review & Revisions | Mission Statement | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.1.5.2.2 |  |  | 195 | 195
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.3 | 1.1.5 | Draft Statements (Purpose/Mission/Vision) | Mission Statement | Draft Statements (Purpose/Mission/Vision) |  |  | 0 | 8 | 0 | 1.1.5.2.3 |  |  | 0 | 0
1428 | DEL-0034 | TSK-01419 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.3.1 | 1.1.5.3 | Draft Statements (Purpose/Mission/Vision) | Mission Statement | Draft Statements (Purpose/Mission/Vision) | Copywriter | Mid | 2 |  |  | 1.1.5.3 |  |  | 195 | 390
1430 | DEL-0034 | TSK-01421 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.3.2 | 1.1.5.3 | Draft Statements (Purpose/Mission/Vision) | Mission Statement | Draft Statements (Purpose/Mission/Vision) | Designer | Mid | 2 |  |  | 1.1.5.3.1 |  |  | 195 | 390
1429 | DEL-0034 | TSK-01420 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.3.3 | 1.1.5.3 | Draft Statements (Purpose/Mission/Vision) | Mission Statement | Draft Statements (Purpose/Mission/Vision) | Strategist | Mid | 7 |  |  | 1.1.5.3.2 |  |  | 195 | 1365
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6 | 1.1 | Purpose Statement | Purpose Statement |  |  |  | 16 | 3 | 5 | 1.1.5 |  |  | 195 | 3120
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.1 | 1.1.6 | Internal Review & Critique | Purpose Statement | Internal Review & Critique |  |  | 0 | 3 | 2 | 1.1.6 |  |  | 0 | 0
1440 | DEL-0034 | TSK-01431 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.1.1 | 1.1.6.1 | Internal Review & Critique | Purpose Statement | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.6.1 |  |  | 195 | 195
1441 | DEL-0034 | TSK-01432 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.1.2 | 1.1.6.1 | Internal Review & Critique | Purpose Statement | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.1.6.1.1 |  |  | 195 | 195
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.2 | 1.1.6 | Client Review & Revisions | Purpose Statement | Client Review & Revisions |  |  | 0 | 5 | 3 | 1.1.6.1.2 |  |  | 0 | 0
1434 | DEL-0034 | TSK-01425 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.2.1 | 1.1.6.2 | Client Review & Revisions | Purpose Statement | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.1.6.2 |  |  | 195 | 195
1435 | DEL-0034 | TSK-01426 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.2.2 | 1.1.6.2 | Client Review & Revisions | Purpose Statement | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.1.6.2.1 |  |  | 195 | 195
1436 | DEL-0034 | TSK-01427 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.2.3 | 1.1.6.2 | Client Review & Revisions | Purpose Statement | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.1.6.2.2 |  |  | 195 | 195
| DEL-0034 |  | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.3 | 1.1.6 | Draft Statements (Purpose/Mission/Vision) | Purpose Statement | Draft Statements (Purpose/Mission/Vision) |  |  | 0 | 8 | 0 | 1.1.6.2.3 |  |  | 0 | 0
1437 | DEL-0034 | TSK-01428 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.3.1 | 1.1.6.3 | Draft Statements (Purpose/Mission/Vision) | Purpose Statement | Draft Statements (Purpose/Mission/Vision) | Copywriter | Mid | 2 |  |  | 1.1.6.3 |  |  | 195 | 390
1439 | DEL-0034 | TSK-01430 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.3.2 | 1.1.6.3 | Draft Statements (Purpose/Mission/Vision) | Purpose Statement | Draft Statements (Purpose/Mission/Vision) | Designer | Mid | 2 |  |  | 1.1.6.3.1 |  |  | 195 | 390
1438 | DEL-0034 | TSK-01429 | Strategy | Brand Positioning Strategy | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.3.3 | 1.1.6.3 | Draft Statements (Purpose/Mission/Vision) | Purpose Statement | Draft Statements (Purpose/Mission/Vision) | Strategist | Mid | 7 |  |  | 1.1.6.3.2 |  |  | 195 | 1365
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2 | 1 | Creative Strategy / Campaign Plan Deck |  |  |  |  | 582 | 8 | 28 | 1.1 |  | Advanced/T2_MediumVolume | 195 | 113490
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1 | 1.2 | Activation Ideas | Activation Ideas |  |  |  | 40 | 8 | 11 | 1.2 |  |  | 195 | 7800
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.1 | 1.2.1 | Idea Write-Ups | Activation Ideas | Idea Write-Ups |  |  | 0 | 8 | 6 | 1.2.1 |  |  | 0 | 0
1475 | DEL-0036 | TSK-01466 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.1.1 | 1.2.1.1 | Idea Write-Ups | Activation Ideas | Idea Write-Ups | Copywriter | Mid | 4 |  |  | 1.2.1.1 |  |  | 195 | 780
1477 | DEL-0036 | TSK-01468 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.1.2 | 1.2.1.1 | Idea Write-Ups | Activation Ideas | Idea Write-Ups | Creative Director | Lead/Director | 3 |  |  | 1.2.1.1.1 |  |  | 195 | 585
1474 | DEL-0036 | TSK-01465 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.1.3 | 1.2.1.1 | Idea Write-Ups | Activation Ideas | Idea Write-Ups | Designer | Mid | 16 |  |  | 1.2.1.1.2 |  |  | 195 | 3120
1476 | DEL-0036 | TSK-01467 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.1.4 | 1.2.1.1 | Idea Write-Ups | Activation Ideas | Idea Write-Ups | Strategist | Mid | 12 |  |  | 1.2.1.1.3 |  |  | 195 | 2340
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.2 | 1.2.1 | Internal Review & Critique | Activation Ideas | Internal Review & Critique |  |  | 0 | 31 | 2 | 1.2.1.1.4 |  |  | 0 | 0
1479 | DEL-0036 | TSK-01470 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.2.1 | 1.2.1.2 | Internal Review & Critique | Activation Ideas | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.1.2 |  |  | 195 | 195
1480 | DEL-0036 | TSK-01471 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.2.2 | 1.2.1.2 | Internal Review & Critique | Activation Ideas | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.1.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.3 | 1.2.1 | Client Review & Revisions | Activation Ideas | Client Review & Revisions |  |  | 0 | 33 | 3 | 1.2.1.2.2 |  |  | 0 | 0
1471 | DEL-0036 | TSK-01462 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.3.1 | 1.2.1.3 | Client Review & Revisions | Activation Ideas | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.1.3 |  |  | 195 | 195
1472 | DEL-0036 | TSK-01463 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.3.2 | 1.2.1.3 | Client Review & Revisions | Activation Ideas | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.1.3.1 |  |  | 195 | 195
1473 | DEL-0036 | TSK-01464 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.3.3 | 1.2.1.3 | Client Review & Revisions | Activation Ideas | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.1.3.2 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2 | 1.2 | Art Direction | Art Direction |  |  |  | 29 | 8 | 11 | 1.2.1 |  |  | 195 | 5655
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.1 | 1.2.2 | Moodboards & References | Art Direction | Moodboards & References |  |  | 0 | 8 | 6 | 1.2.2 |  |  | 0 | 0
1487 | DEL-0036 | TSK-01478 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.1.1 | 1.2.2.1 | Moodboards & References | Art Direction | Moodboards & References | Creative Director | Lead/Director | 3 |  |  | 1.2.2.1 |  |  | 195 | 585
1484 | DEL-0036 | TSK-01475 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.1.2 | 1.2.2.1 | Moodboards & References | Art Direction | Moodboards & References | Designer | Mid | 16 |  |  | 1.2.2.1.1 |  |  | 195 | 3120
1489 | DEL-0036 | TSK-01480 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.1.3 | 1.2.2.1 | Moodboards & References | Art Direction | Moodboards & References | Strategist | Mid | 6 |  |  | 1.2.2.1.2 |  |  | 195 | 1170
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.2 | 1.2.2 | Internal Review & Critique | Art Direction | Internal Review & Critique |  |  | 0 | 31 | 2 | 1.2.2.1.3 |  |  | 0 | 0
1485 | DEL-0036 | TSK-01476 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.2.1 | 1.2.2.2 | Internal Review & Critique | Art Direction | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.2.2 |  |  | 195 | 195
1486 | DEL-0036 | TSK-01477 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.2.2 | 1.2.2.2 | Internal Review & Critique | Art Direction | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.2.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.3 | 1.2.2 | Client Review & Revisions | Art Direction | Client Review & Revisions |  |  | 0 | 33 | 3 | 1.2.2.2.2 |  |  | 0 | 0
1482 | DEL-0036 | TSK-01473 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.3.1 | 1.2.2.3 | Client Review & Revisions | Art Direction | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.2.3 |  |  | 195 | 195
1483 | DEL-0036 | TSK-01474 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.3.2 | 1.2.2.3 | Client Review & Revisions | Art Direction | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.2.3.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3 | 1.2 | Brand Approach for Campaign Period | Brand Approach for Campaign Period |  |  |  | 32 | 8 | 11 | 1.2.2 |  |  | 195 | 6240
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.1 | 1.2.3 | Approach Outline | Brand Approach for Campaign Period | Approach Outline |  |  | 0 | 8 | 6 | 1.2.3 |  |  | 0 | 0
1494 | DEL-0036 | TSK-01485 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.1.1 | 1.2.3.1 | Approach Outline | Brand Approach for Campaign Period | Approach Outline | Designer | Mid | 16 |  |  | 1.2.3.1 |  |  | 195 | 3120
1490 | DEL-0036 | TSK-01481 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.1.2 | 1.2.3.1 | Approach Outline | Brand Approach for Campaign Period | Approach Outline | Strategist | Mid | 12 |  |  | 1.2.3.1.1 |  |  | 195 | 2340
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.2 | 1.2.3 | Internal Review & Critique | Brand Approach for Campaign Period | Internal Review & Critique |  |  | 0 | 31 | 2 | 1.2.3.1.2 |  |  | 0 | 0
1495 | DEL-0036 | TSK-01486 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.2.1 | 1.2.3.2 | Internal Review & Critique | Brand Approach for Campaign Period | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.3.2 |  |  | 195 | 195
1496 | DEL-0036 | TSK-01487 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.2.2 | 1.2.3.2 | Internal Review & Critique | Brand Approach for Campaign Period | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.3.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.3 | 1.2.3 | Client Review & Revisions | Brand Approach for Campaign Period | Client Review & Revisions |  |  | 0 | 33 | 3 | 1.2.3.2.2 |  |  | 0 | 0
1491 | DEL-0036 | TSK-01482 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.3.1 | 1.2.3.3 | Client Review & Revisions | Brand Approach for Campaign Period | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.3.3 |  |  | 195 | 195
1492 | DEL-0036 | TSK-01483 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.3.2 | 1.2.3.3 | Client Review & Revisions | Brand Approach for Campaign Period | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.3.3.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4 | 1.2 | Campaign Roll-Out/Launch Road Map | Campaign Roll-Out/Launch Road Map |  |  |  | 30 | 8 | 11 | 1.2.3 |  |  | 195 | 5850
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.1 | 1.2.4 | Phasing & Milestones | Campaign Roll-Out/Launch Road Map | Phasing & Milestones |  |  | 0 | 8 | 6 | 1.2.4 |  |  | 0 | 0
1501 | DEL-0036 | TSK-01492 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.1.1 | 1.2.4.1 | Phasing & Milestones | Campaign Roll-Out/Launch Road Map | Phasing & Milestones | Designer | Mid | 16 |  |  | 1.2.4.1 |  |  | 195 | 3120
1500 | DEL-0036 | TSK-01491 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.1.2 | 1.2.4.1 | Phasing & Milestones | Campaign Roll-Out/Launch Road Map | Phasing & Milestones | Project Manager | Mid | 4 |  |  | 1.2.4.1.1 |  |  | 195 | 780
1505 | DEL-0036 | TSK-01496 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.1.3 | 1.2.4.1 | Phasing & Milestones | Campaign Roll-Out/Launch Road Map | Phasing & Milestones | Strategist | Mid | 6 |  |  | 1.2.4.1.2 |  |  | 195 | 1170
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.2 | 1.2.4 | Internal Review & Critique | Campaign Roll-Out/Launch Road Map | Internal Review & Critique |  |  | 0 | 31 | 2 | 1.2.4.1.3 |  |  | 0 | 0
1502 | DEL-0036 | TSK-01493 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.2.1 | 1.2.4.2 | Internal Review & Critique | Campaign Roll-Out/Launch Road Map | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.4.2 |  |  | 195 | 195
1503 | DEL-0036 | TSK-01494 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.2.2 | 1.2.4.2 | Internal Review & Critique | Campaign Roll-Out/Launch Road Map | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.4.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.3 | 1.2.4 | Client Review & Revisions | Campaign Roll-Out/Launch Road Map | Client Review & Revisions |  |  | 0 | 33 | 3 | 1.2.4.2.2 |  |  | 0 | 0
1498 | DEL-0036 | TSK-01489 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.3.1 | 1.2.4.3 | Client Review & Revisions | Campaign Roll-Out/Launch Road Map | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.4.3 |  |  | 195 | 195
1499 | DEL-0036 | TSK-01490 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.3.2 | 1.2.4.3 | Client Review & Revisions | Campaign Roll-Out/Launch Road Map | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.4.3.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5 | 1.2 | Content Plan | Content Plan |  |  |  | 37 | 8 | 11 | 1.2.4 |  |  | 195 | 7215
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.1 | 1.2.5 | Calendar Draft | Content Plan | Calendar Draft |  |  | 0 | 8 | 6 | 1.2.5 |  |  | 0 | 0
1507 | DEL-0036 | TSK-01498 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.1.1 | 1.2.5.1 | Calendar Draft | Content Plan | Calendar Draft | Copywriter | Mid | 8 |  |  | 1.2.5.1 |  |  | 195 | 1560
1513 | DEL-0036 | TSK-01504 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.1.2 | 1.2.5.1 | Calendar Draft | Content Plan | Calendar Draft | Designer | Mid | 16 |  |  | 1.2.5.1.1 |  |  | 195 | 3120
1508 | DEL-0036 | TSK-01499 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.1.3 | 1.2.5.1 | Calendar Draft | Content Plan | Calendar Draft | Project Manager | Mid | 2 |  |  | 1.2.5.1.2 |  |  | 195 | 390
1517 | DEL-0036 | TSK-01508 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.1.4 | 1.2.5.1 | Calendar Draft | Content Plan | Calendar Draft | Strategist | Mid | 6 |  |  | 1.2.5.1.3 |  |  | 195 | 1170
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.2 | 1.2.5 | Internal Review & Critique | Content Plan | Internal Review & Critique |  |  | 0 | 31 | 2 | 1.2.5.1.4 |  |  | 0 | 0
1515 | DEL-0036 | TSK-01506 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.2.1 | 1.2.5.2 | Internal Review & Critique | Content Plan | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.5.2 |  |  | 195 | 195
1516 | DEL-0036 | TSK-01507 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.2.2 | 1.2.5.2 | Internal Review & Critique | Content Plan | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.5.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.3 | 1.2.5 | Client Review & Revisions | Content Plan | Client Review & Revisions |  |  | 0 | 33 | 3 | 1.2.5.2.2 |  |  | 0 | 0
1509 | DEL-0036 | TSK-01500 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.3.1 | 1.2.5.3 | Client Review & Revisions | Content Plan | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.5.3 |  |  | 195 | 195
1510 | DEL-0036 | TSK-01501 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.3.2 | 1.2.5.3 | Client Review & Revisions | Content Plan | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.5.3.1 |  |  | 195 | 195
1511 | DEL-0036 | TSK-01502 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.3.3 | 1.2.5.3 | Client Review & Revisions | Content Plan | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.5.3.2 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.6 | 1.2 | Content Production Shoot Approach | Content Production Shoot Approach |  |  |  | 26 | 8 | 19 | 1.2.5 |  |  | 195 | 5070
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.6.1 | 1.2.6 | Final Packaging | Content Production Shoot Approach | Final Packaging |  |  | 0 | 8 | 6 | 1.2.6 |  |  | 0 | 0
1520 | DEL-0036 | TSK-01511 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.6.1.1 | 1.2.6.1 | Final Packaging | Content Production Shoot Approach | Final Packaging | Designer | Mid | 16 |  |  | 1.2.6.1 |  |  | 195 | 3120
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.6.2 | 1.2.6 | Shoot Approach & Logistics | Content Production Shoot Approach | Shoot Approach & Logistics |  |  | 0 | 19 | 8 | 1.2.6.1.1 |  |  | 0 | 0
1523 | DEL-0036 | TSK-01514 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.6.2.1 | 1.2.6.2 | Shoot Approach & Logistics | Content Production Shoot Approach | Shoot Approach & Logistics | Creative Director | Lead/Director | 1 |  |  | 1.2.6.2 |  |  | 195 | 195
1524 | DEL-0036 | TSK-01515 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.6.2.2 | 1.2.6.2 | Shoot Approach & Logistics | Content Production Shoot Approach | Shoot Approach & Logistics | Project Manager | Mid | 4 |  |  | 1.2.6.2.1 |  |  | 195 | 780
1525 | DEL-0036 | TSK-01516 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.6.2.3 | 1.2.6.2 | Shoot Approach & Logistics | Content Production Shoot Approach | Shoot Approach & Logistics | Strategist | Mid | 1 |  |  | 1.2.6.2.2 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.6.3 | 1.2.6 | Internal Review & Critique | Content Production Shoot Approach | Internal Review & Critique |  |  | 0 | 31 | 2 | 1.2.6.2.3 |  |  | 0 | 0
1521 | DEL-0036 | TSK-01512 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.6.3.1 | 1.2.6.3 | Internal Review & Critique | Content Production Shoot Approach | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.6.3 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.6.4 | 1.2.6 | Client Review & Revisions | Content Production Shoot Approach | Client Review & Revisions |  |  | 0 | 33 | 3 | 1.2.6.3.1 |  |  | 0 | 0
1518 | DEL-0036 | TSK-01509 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.6.4.1 | 1.2.6.4 | Client Review & Revisions | Content Production Shoot Approach | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.2.6.4 |  |  | 195 | 390
1519 | DEL-0036 | TSK-01510 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.6.4.2 | 1.2.6.4 | Client Review & Revisions | Content Production Shoot Approach | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.6.4.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.7 | 1.2 | Content Types across Full Funnel | Content Types across Full Funnel |  |  |  | 37 | 8 | 11 | 1.2.6 |  |  | 195 | 7215
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.7.1 | 1.2.7 | Content Type Matrix | Content Types across Full Funnel | Content Type Matrix |  |  | 0 | 8 | 6 | 1.2.7 |  |  | 0 | 0
1537 | DEL-0036 | TSK-01528 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.7.1.1 | 1.2.7.1 | Content Type Matrix | Content Types across Full Funnel | Content Type Matrix | Copywriter | Mid | 4 |  |  | 1.2.7.1 |  |  | 195 | 780
1538 | DEL-0036 | TSK-01529 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.7.1.2 | 1.2.7.1 | Content Type Matrix | Content Types across Full Funnel | Content Type Matrix | Designer | Mid | 16 |  |  | 1.2.7.1.1 |  |  | 195 | 3120
1539 | DEL-0036 | TSK-01530 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.7.1.3 | 1.2.7.1 | Content Type Matrix | Content Types across Full Funnel | Content Type Matrix | Strategist | Mid | 12 |  |  | 1.2.7.1.2 |  |  | 195 | 2340
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.7.2 | 1.2.7 | Internal Review & Critique | Content Types across Full Funnel | Internal Review & Critique |  |  | 0 | 31 | 2 | 1.2.7.1.3 |  |  | 0 | 0
1542 | DEL-0036 | TSK-01533 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.7.2.1 | 1.2.7.2 | Internal Review & Critique | Content Types across Full Funnel | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.7.2 |  |  | 195 | 195
1543 | DEL-0036 | TSK-01534 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.7.2.2 | 1.2.7.2 | Internal Review & Critique | Content Types across Full Funnel | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.7.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.7.3 | 1.2.7 | Client Review & Revisions | Content Types across Full Funnel | Client Review & Revisions |  |  | 0 | 33 | 3 | 1.2.7.2.2 |  |  | 0 | 0
1534 | DEL-0036 | TSK-01525 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.7.3.1 | 1.2.7.3 | Client Review & Revisions | Content Types across Full Funnel | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.7.3 |  |  | 195 | 195
1535 | DEL-0036 | TSK-01526 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.7.3.2 | 1.2.7.3 | Client Review & Revisions | Content Types across Full Funnel | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.7.3.1 |  |  | 195 | 195
1536 | DEL-0036 | TSK-01527 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.7.3.3 | 1.2.7.3 | Client Review & Revisions | Content Types across Full Funnel | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.7.3.2 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.8 | 1.2 | Copy Bank | Copy Bank |  |  |  | 17 | 8 | 11 | 1.2.7 |  |  | 195 | 3315
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.8.1 | 1.2.8 | Copy Examples (Headlines/Captions/CTAs) | Copy Bank | Copy Examples (Headlines/Captions/CTAs) |  |  | 0 | 8 | 6 | 1.2.8 |  |  | 0 | 0
1547 | DEL-0036 | TSK-01538 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.8.1.1 | 1.2.8.1 | Copy Examples (Headlines/Captions/CTAs) | Copy Bank | Copy Examples (Headlines/Captions/CTAs) | Copywriter | Mid | 4 |  |  | 1.2.8.1 |  |  | 195 | 780
1548 | DEL-0036 | TSK-01539 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.8.1.2 | 1.2.8.1 | Copy Examples (Headlines/Captions/CTAs) | Copy Bank | Copy Examples (Headlines/Captions/CTAs) | Designer | Mid | 8 |  |  | 1.2.8.1.1 |  |  | 195 | 1560
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.8.2 | 1.2.8 | Internal Review & Critique | Copy Bank | Internal Review & Critique |  |  | 0 | 31 | 2 | 1.2.8.1.2 |  |  | 0 | 0
1549 | DEL-0036 | TSK-01540 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.8.2.1 | 1.2.8.2 | Internal Review & Critique | Copy Bank | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.8.2 |  |  | 195 | 195
1550 | DEL-0036 | TSK-01541 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.8.2.2 | 1.2.8.2 | Internal Review & Critique | Copy Bank | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.8.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.8.3 | 1.2.8 | Client Review & Revisions | Copy Bank | Client Review & Revisions |  |  | 0 | 33 | 3 | 1.2.8.2.2 |  |  | 0 | 0
1544 | DEL-0036 | TSK-01535 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.8.3.1 | 1.2.8.3 | Client Review & Revisions | Copy Bank | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.8.3 |  |  | 195 | 195
1545 | DEL-0036 | TSK-01536 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.8.3.2 | 1.2.8.3 | Client Review & Revisions | Copy Bank | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.8.3.1 |  |  | 195 | 195
1546 | DEL-0036 | TSK-01537 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.8.3.3 | 1.2.8.3 | Client Review & Revisions | Copy Bank | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.8.3.2 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9 | 1.2 | Customer Journey | Customer Journey |  |  |  | 26 | 8 | 11 | 1.2.8 |  |  | 195 | 5070
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.1 | 1.2.9 | Journey Mapping | Customer Journey | Journey Mapping |  |  | 0 | 8 | 6 | 1.2.9 |  |  | 0 | 0
1553 | DEL-0036 | TSK-01544 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.1.1 | 1.2.9.1 | Journey Mapping | Customer Journey | Journey Mapping | Designer | Mid | 16 |  |  | 1.2.9.1 |  |  | 195 | 3120
1557 | DEL-0036 | TSK-01548 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.1.2 | 1.2.9.1 | Journey Mapping | Customer Journey | Journey Mapping | Strategist | Mid | 6 |  |  | 1.2.9.1.1 |  |  | 195 | 1170
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.2 | 1.2.9 | Internal Review & Critique | Customer Journey | Internal Review & Critique |  |  | 0 | 31 | 2 | 1.2.9.1.2 |  |  | 0 | 0
1554 | DEL-0036 | TSK-01545 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.2.1 | 1.2.9.2 | Internal Review & Critique | Customer Journey | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.9.2 |  |  | 195 | 195
1555 | DEL-0036 | TSK-01546 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.2.2 | 1.2.9.2 | Internal Review & Critique | Customer Journey | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.9.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.3 | 1.2.9 | Client Review & Revisions | Customer Journey | Client Review & Revisions |  |  | 0 | 33 | 3 | 1.2.9.2.2 |  |  | 0 | 0
1551 | DEL-0036 | TSK-01542 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.3.1 | 1.2.9.3 | Client Review & Revisions | Customer Journey | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.9.3 |  |  | 195 | 195
1552 | DEL-0036 | TSK-01543 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.3.2 | 1.2.9.3 | Client Review & Revisions | Customer Journey | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.9.3.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10 | 1.2 | High-Fidelity Organic Social Mock-Ups | High-Fidelity Organic Social Mock-Ups |  |  |  | 28 | 8 | 11 | 1.2.9 |  |  | 195 | 5460
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.1 | 1.2.10 | Concept & Layouts (3-4 ex.) | High-Fidelity Organic Social Mock-Ups | Concept & Layouts (3-4 ex.) |  |  | 0 | 8 | 6 | 1.2.10 |  |  | 0 | 0
1561 | DEL-0036 | TSK-01552 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.1.1 | 1.2.10.1 | Concept & Layouts (3-4 ex.) | High-Fidelity Organic Social Mock-Ups | Concept & Layouts (3-4 ex.) | Copywriter | Mid | 4 |  |  | 1.2.10.1 |  |  | 195 | 780
1562 | DEL-0036 | TSK-01553 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.1.2 | 1.2.10.1 | Concept & Layouts (3-4 ex.) | High-Fidelity Organic Social Mock-Ups | Concept & Layouts (3-4 ex.) | Creative Director | Lead/Director | 3 |  |  | 1.2.10.1.1 |  |  | 195 | 585
1563 | DEL-0036 | TSK-01554 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.1.3 | 1.2.10.1 | Concept & Layouts (3-4 ex.) | High-Fidelity Organic Social Mock-Ups | Concept & Layouts (3-4 ex.) | Designer | Mid | 16 |  |  | 1.2.10.1.2 |  |  | 195 | 3120
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.2 | 1.2.10 | Internal Review & Critique | High-Fidelity Organic Social Mock-Ups | Internal Review & Critique |  |  | 0 | 31 | 2 | 1.2.10.1.3 |  |  | 0 | 0
1565 | DEL-0036 | TSK-01556 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.2.1 | 1.2.10.2 | Internal Review & Critique | High-Fidelity Organic Social Mock-Ups | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.10.2 |  |  | 195 | 195
1566 | DEL-0036 | TSK-01557 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.2.2 | 1.2.10.2 | Internal Review & Critique | High-Fidelity Organic Social Mock-Ups | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.10.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.3 | 1.2.10 | Client Review & Revisions | High-Fidelity Organic Social Mock-Ups | Client Review & Revisions |  |  | 0 | 33 | 3 | 1.2.10.2.2 |  |  | 0 | 0
1558 | DEL-0036 | TSK-01549 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.3.1 | 1.2.10.3 | Client Review & Revisions | High-Fidelity Organic Social Mock-Ups | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.10.3 |  |  | 195 | 195
1559 | DEL-0036 | TSK-01550 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.3.2 | 1.2.10.3 | Client Review & Revisions | High-Fidelity Organic Social Mock-Ups | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.10.3.1 |  |  | 195 | 195
1560 | DEL-0036 | TSK-01551 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.3.3 | 1.2.10.3 | Client Review & Revisions | High-Fidelity Organic Social Mock-Ups | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.10.3.2 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.11 | 1.2 | High-Fidelity Paid Media Mock-Ups | High-Fidelity Paid Media Mock-Ups |  |  |  | 28 | 8 | 11 | 1.2.10 |  |  | 195 | 5460
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.11.1 | 1.2.11 | Concept & Layouts (3-4 ex.) | High-Fidelity Paid Media Mock-Ups | Concept & Layouts (3-4 ex.) |  |  | 0 | 8 | 6 | 1.2.11 |  |  | 0 | 0
1570 | DEL-0036 | TSK-01561 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.11.1.1 | 1.2.11.1 | Concept & Layouts (3-4 ex.) | High-Fidelity Paid Media Mock-Ups | Concept & Layouts (3-4 ex.) | Copywriter | Mid | 4 |  |  | 1.2.11.1 |  |  | 195 | 780
1571 | DEL-0036 | TSK-01562 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.11.1.2 | 1.2.11.1 | Concept & Layouts (3-4 ex.) | High-Fidelity Paid Media Mock-Ups | Concept & Layouts (3-4 ex.) | Creative Director | Lead/Director | 3 |  |  | 1.2.11.1.1 |  |  | 195 | 585
1572 | DEL-0036 | TSK-01563 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.11.1.3 | 1.2.11.1 | Concept & Layouts (3-4 ex.) | High-Fidelity Paid Media Mock-Ups | Concept & Layouts (3-4 ex.) | Designer | Mid | 16 |  |  | 1.2.11.1.2 |  |  | 195 | 3120
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.11.2 | 1.2.11 | Internal Review & Critique | High-Fidelity Paid Media Mock-Ups | Internal Review & Critique |  |  | 0 | 31 | 2 | 1.2.11.1.3 |  |  | 0 | 0
1574 | DEL-0036 | TSK-01565 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.11.2.1 | 1.2.11.2 | Internal Review & Critique | High-Fidelity Paid Media Mock-Ups | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.11.2 |  |  | 195 | 195
1575 | DEL-0036 | TSK-01566 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.11.2.2 | 1.2.11.2 | Internal Review & Critique | High-Fidelity Paid Media Mock-Ups | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.11.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.11.3 | 1.2.11 | Client Review & Revisions | High-Fidelity Paid Media Mock-Ups | Client Review & Revisions |  |  | 0 | 33 | 3 | 1.2.11.2.2 |  |  | 0 | 0
1567 | DEL-0036 | TSK-01558 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.11.3.1 | 1.2.11.3 | Client Review & Revisions | High-Fidelity Paid Media Mock-Ups | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.11.3 |  |  | 195 | 195
1568 | DEL-0036 | TSK-01559 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.11.3.2 | 1.2.11.3 | Client Review & Revisions | High-Fidelity Paid Media Mock-Ups | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.11.3.1 |  |  | 195 | 195
1569 | DEL-0036 | TSK-01560 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.11.3.3 | 1.2.11.3 | Client Review & Revisions | High-Fidelity Paid Media Mock-Ups | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.11.3.2 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.12 | 1.2 | Influencer Partnership Approach | Influencer Partnership Approach |  |  |  | 31 | 8 | 11 | 1.2.11 |  |  | 195 | 6045
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.12.1 | 1.2.12 | Outreach & Compensation Framework | Influencer Partnership Approach | Outreach & Compensation Framework |  |  | 0 | 8 | 6 | 1.2.12 |  |  | 0 | 0
1583 | DEL-0036 | TSK-01574 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.12.1.1 | 1.2.12.1 | Outreach & Compensation Framework | Influencer Partnership Approach | Outreach & Compensation Framework | Account Manager | Mid | 2 |  |  | 1.2.12.1 |  |  | 195 | 390
1579 | DEL-0036 | TSK-01570 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.12.1.2 | 1.2.12.1 | Outreach & Compensation Framework | Influencer Partnership Approach | Outreach & Compensation Framework | Copywriter | Mid | 4 |  |  | 1.2.12.1.1 |  |  | 195 | 780
1580 | DEL-0036 | TSK-01571 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.12.1.3 | 1.2.12.1 | Outreach & Compensation Framework | Influencer Partnership Approach | Outreach & Compensation Framework | Designer | Mid | 8 |  |  | 1.2.12.1.2 |  |  | 195 | 1560
1584 | DEL-0036 | TSK-01575 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.12.1.4 | 1.2.12.1 | Outreach & Compensation Framework | Influencer Partnership Approach | Outreach & Compensation Framework | Strategist | Mid | 12 |  |  | 1.2.12.1.3 |  |  | 195 | 2340
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.12.2 | 1.2.12 | Internal Review & Critique | Influencer Partnership Approach | Internal Review & Critique |  |  | 0 | 31 | 2 | 1.2.12.1.4 |  |  | 0 | 0
1581 | DEL-0036 | TSK-01572 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.12.2.1 | 1.2.12.2 | Internal Review & Critique | Influencer Partnership Approach | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.12.2 |  |  | 195 | 195
1582 | DEL-0036 | TSK-01573 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.12.2.2 | 1.2.12.2 | Internal Review & Critique | Influencer Partnership Approach | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.12.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.12.3 | 1.2.12 | Client Review & Revisions | Influencer Partnership Approach | Client Review & Revisions |  |  | 0 | 33 | 3 | 1.2.12.2.2 |  |  | 0 | 0
1576 | DEL-0036 | TSK-01567 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.12.3.1 | 1.2.12.3 | Client Review & Revisions | Influencer Partnership Approach | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.12.3 |  |  | 195 | 195
1577 | DEL-0036 | TSK-01568 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.12.3.2 | 1.2.12.3 | Client Review & Revisions | Influencer Partnership Approach | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.12.3.1 |  |  | 195 | 195
1578 | DEL-0036 | TSK-01569 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.12.3.3 | 1.2.12.3 | Client Review & Revisions | Influencer Partnership Approach | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.12.3.2 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13 | 1.2 | Kick-Off Session | Kick-Off Session |  |  |  | 55 | 8 | 11 | 1.2.12 |  |  | 195 | 10725
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13.1 | 1.2.13 | Agenda & Materials Prep | Kick-Off Session | Agenda & Materials Prep |  |  | 0 | 8 | 6 | 1.2.13 |  |  | 0 | 0
1586 | DEL-0036 | TSK-01577 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13.1.1 | 1.2.13.1 | Agenda & Materials Prep | Kick-Off Session | Agenda & Materials Prep | Account Manager | Mid | 6 |  |  | 1.2.13.1 |  |  | 195 | 1170
1593 | DEL-0036 | TSK-01584 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13.1.2 | 1.2.13.1 | Agenda & Materials Prep | Kick-Off Session | Agenda & Materials Prep | Creative Director | Lead/Director | 3 |  |  | 1.2.13.1.1 |  |  | 195 | 585
1587 | DEL-0036 | TSK-01578 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13.1.3 | 1.2.13.1 | Agenda & Materials Prep | Kick-Off Session | Agenda & Materials Prep | Designer | Mid | 16 |  |  | 1.2.13.1.2 |  |  | 195 | 3120
1588 | DEL-0036 | TSK-01579 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13.1.4 | 1.2.13.1 | Agenda & Materials Prep | Kick-Off Session | Agenda & Materials Prep | Project Manager | Mid | 2 |  |  | 1.2.13.1.3 |  |  | 195 | 390
1589 | DEL-0036 | TSK-01580 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13.1.5 | 1.2.13.1 | Agenda & Materials Prep | Kick-Off Session | Agenda & Materials Prep | Strategist | Mid | 24 |  |  | 1.2.13.1.4 |  |  | 195 | 4680
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13.2 | 1.2.13 | Internal Review & Critique | Kick-Off Session | Internal Review & Critique |  |  | 0 | 31 | 2 | 1.2.13.1.5 |  |  | 0 | 0
1596 | DEL-0036 | TSK-01587 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13.2.1 | 1.2.13.2 | Internal Review & Critique | Kick-Off Session | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.13.2 |  |  | 195 | 195
1597 | DEL-0036 | TSK-01588 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13.2.2 | 1.2.13.2 | Internal Review & Critique | Kick-Off Session | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.13.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13.3 | 1.2.13 | Client Review & Revisions | Kick-Off Session | Client Review & Revisions |  |  | 0 | 33 | 3 | 1.2.13.2.2 |  |  | 0 | 0
1590 | DEL-0036 | TSK-01581 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13.3.1 | 1.2.13.3 | Client Review & Revisions | Kick-Off Session | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.13.3 |  |  | 195 | 195
1591 | DEL-0036 | TSK-01582 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13.3.2 | 1.2.13.3 | Client Review & Revisions | Kick-Off Session | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.13.3.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14 | 1.2 | Messaging Framework (by Audience) | Messaging Framework (by Audience) |  |  |  | 37 | 8 | 11 | 1.2.13 |  |  | 195 | 7215
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.1 | 1.2.14 | Draft Messaging | Messaging Framework (by Audience) | Draft Messaging |  |  | 0 | 8 | 6 | 1.2.14 |  |  | 0 | 0
1605 | DEL-0036 | TSK-01596 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.1.1 | 1.2.14.1 | Draft Messaging | Messaging Framework (by Audience) | Draft Messaging | Copywriter | Mid | 4 |  |  | 1.2.14.1 |  |  | 195 | 780
1604 | DEL-0036 | TSK-01595 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.1.2 | 1.2.14.1 | Draft Messaging | Messaging Framework (by Audience) | Draft Messaging | Designer | Mid | 16 |  |  | 1.2.14.1.1 |  |  | 195 | 3120
1606 | DEL-0036 | TSK-01597 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.1.3 | 1.2.14.1 | Draft Messaging | Messaging Framework (by Audience) | Draft Messaging | Strategist | Mid | 12 |  |  | 1.2.14.1.2 |  |  | 195 | 2340
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.2 | 1.2.14 | Internal Review & Critique | Messaging Framework (by Audience) | Internal Review & Critique |  |  | 0 | 31 | 2 | 1.2.14.1.3 |  |  | 0 | 0
1608 | DEL-0036 | TSK-01599 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.2.1 | 1.2.14.2 | Internal Review & Critique | Messaging Framework (by Audience) | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.14.2 |  |  | 195 | 195
1609 | DEL-0036 | TSK-01600 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.2.2 | 1.2.14.2 | Internal Review & Critique | Messaging Framework (by Audience) | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.14.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.3 | 1.2.14 | Client Review & Revisions | Messaging Framework (by Audience) | Client Review & Revisions |  |  | 0 | 33 | 3 | 1.2.14.2.2 |  |  | 0 | 0
1601 | DEL-0036 | TSK-01592 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.3.1 | 1.2.14.3 | Client Review & Revisions | Messaging Framework (by Audience) | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.14.3 |  |  | 195 | 195
1602 | DEL-0036 | TSK-01593 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.3.2 | 1.2.14.3 | Client Review & Revisions | Messaging Framework (by Audience) | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.14.3.1 |  |  | 195 | 195
1603 | DEL-0036 | TSK-01594 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.3.3 | 1.2.14.3 | Client Review & Revisions | Messaging Framework (by Audience) | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.14.3.2 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15 | 1.2 | Platform/Channel Approach | Platform/Channel Approach |  |  |  | 29 | 8 | 15 | 1.2.14 |  |  | 195 | 5655
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15.1 | 1.2.15 | Baseline KPIs | Platform/Channel Approach | Baseline KPIs |  |  | 0 | 8 | 6 | 1.2.15 |  |  | 0 | 0
1611 | DEL-0036 | TSK-01602 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15.1.1 | 1.2.15.1 | Baseline KPIs | Platform/Channel Approach | Baseline KPIs | Analyst | Mid | 3 |  |  | 1.2.15.1 |  |  | 195 | 585
1616 | DEL-0036 | TSK-01607 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15.1.2 | 1.2.15.1 | Baseline KPIs | Platform/Channel Approach | Baseline KPIs | Designer | Mid | 8 |  |  | 1.2.15.1.1 |  |  | 195 | 1560
1612 | DEL-0036 | TSK-01603 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15.1.3 | 1.2.15.1 | Baseline KPIs | Platform/Channel Approach | Baseline KPIs | Strategist | Mid | 12 |  |  | 1.2.15.1.2 |  |  | 195 | 2340
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15.2 | 1.2.15 | Summary Slides | Platform/Channel Approach | Summary Slides |  |  | 0 | 27 | 4 | 1.2.15.1.3 |  |  | 0 | 0
1619 | DEL-0036 | TSK-01610 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15.2.1 | 1.2.15.2 | Summary Slides | Platform/Channel Approach | Summary Slides | Designer | Mid | 2 |  |  | 1.2.15.2 |  |  | 195 | 390
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15.3 | 1.2.15 | Internal Review & Critique | Platform/Channel Approach | Internal Review & Critique |  |  | 0 | 31 | 2 | 1.2.15.2.1 |  |  | 0 | 0
1617 | DEL-0036 | TSK-01608 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15.3.1 | 1.2.15.3 | Internal Review & Critique | Platform/Channel Approach | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.15.3 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15.4 | 1.2.15 | Client Review & Revisions | Platform/Channel Approach | Client Review & Revisions |  |  | 0 | 33 | 3 | 1.2.15.3.1 |  |  | 0 | 0
1614 | DEL-0036 | TSK-01605 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15.4.1 | 1.2.15.4 | Client Review & Revisions | Platform/Channel Approach | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.2.15.4 |  |  | 195 | 390
1615 | DEL-0036 | TSK-01606 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15.4.2 | 1.2.15.4 | Client Review & Revisions | Platform/Channel Approach | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.15.4.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.16 | 1.2 | Social Templates | Social Templates |  |  |  | 31 | 8 | 11 | 1.2.15 |  |  | 195 | 6045
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.16.1 | 1.2.16 | Template Exploration | Social Templates | Template Exploration |  |  | 0 | 8 | 6 | 1.2.16 |  |  | 0 | 0
1626 | DEL-0036 | TSK-01617 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.16.1.1 | 1.2.16.1 | Template Exploration | Social Templates | Template Exploration | Creative Director | Lead/Director | 3 |  |  | 1.2.16.1 |  |  | 195 | 585
1622 | DEL-0036 | TSK-01613 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.16.1.2 | 1.2.16.1 | Template Exploration | Social Templates | Template Exploration | Designer | Mid | 24 |  |  | 1.2.16.1.1 |  |  | 195 | 4680
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.16.2 | 1.2.16 | Internal Review & Critique | Social Templates | Internal Review & Critique |  |  | 0 | 31 | 2 | 1.2.16.1.2 |  |  | 0 | 0
1623 | DEL-0036 | TSK-01614 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.16.2.1 | 1.2.16.2 | Internal Review & Critique | Social Templates | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.16.2 |  |  | 195 | 195
1624 | DEL-0036 | TSK-01615 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.16.2.2 | 1.2.16.2 | Internal Review & Critique | Social Templates | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.16.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.16.3 | 1.2.16 | Client Review & Revisions | Social Templates | Client Review & Revisions |  |  | 0 | 33 | 3 | 1.2.16.2.2 |  |  | 0 | 0
1620 | DEL-0036 | TSK-01611 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.16.3.1 | 1.2.16.3 | Client Review & Revisions | Social Templates | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.16.3 |  |  | 195 | 195
1621 | DEL-0036 | TSK-01612 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.16.3.2 | 1.2.16.3 | Client Review & Revisions | Social Templates | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.16.3.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.17 | 1.2 | Visual Approach | Visual Approach |  |  |  | 29 | 8 | 11 | 1.2.16 |  |  | 195 | 5655
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.17.1 | 1.2.17 | Moodboards & References | Visual Approach | Moodboards & References |  |  | 0 | 8 | 6 | 1.2.17 |  |  | 0 | 0
1633 | DEL-0036 | TSK-01624 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.17.1.1 | 1.2.17.1 | Moodboards & References | Visual Approach | Moodboards & References | Creative Director | Lead/Director | 3 |  |  | 1.2.17.1 |  |  | 195 | 585
1630 | DEL-0036 | TSK-01621 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.17.1.2 | 1.2.17.1 | Moodboards & References | Visual Approach | Moodboards & References | Designer | Mid | 16 |  |  | 1.2.17.1.1 |  |  | 195 | 3120
1635 | DEL-0036 | TSK-01626 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.17.1.3 | 1.2.17.1 | Moodboards & References | Visual Approach | Moodboards & References | Strategist | Mid | 6 |  |  | 1.2.17.1.2 |  |  | 195 | 1170
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.17.2 | 1.2.17 | Internal Review & Critique | Visual Approach | Internal Review & Critique |  |  | 0 | 31 | 2 | 1.2.17.1.3 |  |  | 0 | 0
1631 | DEL-0036 | TSK-01622 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.17.2.1 | 1.2.17.2 | Internal Review & Critique | Visual Approach | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.17.2 |  |  | 195 | 195
1632 | DEL-0036 | TSK-01623 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.17.2.2 | 1.2.17.2 | Internal Review & Critique | Visual Approach | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.17.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.17.3 | 1.2.17 | Client Review & Revisions | Visual Approach | Client Review & Revisions |  |  | 0 | 33 | 3 | 1.2.17.2.2 |  |  | 0 | 0
1628 | DEL-0036 | TSK-01619 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.17.3.1 | 1.2.17.3 | Client Review & Revisions | Visual Approach | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.17.3 |  |  | 195 | 195
1629 | DEL-0036 | TSK-01620 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.17.3.2 | 1.2.17.3 | Client Review & Revisions | Visual Approach | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.17.3.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.18 | 1.2 | Voice & Tone | Voice & Tone |  |  |  | 27 | 8 | 11 | 1.2.17 |  |  | 195 | 5265
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.18.1 | 1.2.18 | Principles Outline | Voice & Tone | Principles Outline |  |  | 0 | 8 | 6 | 1.2.18 |  |  | 0 | 0
1639 | DEL-0036 | TSK-01630 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.18.1.1 | 1.2.18.1 | Principles Outline | Voice & Tone | Principles Outline | Copywriter | Mid | 8 |  |  | 1.2.18.1 |  |  | 195 | 1560
1640 | DEL-0036 | TSK-01631 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.18.1.2 | 1.2.18.1 | Principles Outline | Voice & Tone | Principles Outline | Designer | Mid | 8 |  |  | 1.2.18.1.1 |  |  | 195 | 1560
1644 | DEL-0036 | TSK-01635 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.18.1.3 | 1.2.18.1 | Principles Outline | Voice & Tone | Principles Outline | Strategist | Mid | 6 |  |  | 1.2.18.1.2 |  |  | 195 | 1170
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.18.2 | 1.2.18 | Internal Review & Critique | Voice & Tone | Internal Review & Critique |  |  | 0 | 31 | 2 | 1.2.18.1.3 |  |  | 0 | 0
1641 | DEL-0036 | TSK-01632 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.18.2.1 | 1.2.18.2 | Internal Review & Critique | Voice & Tone | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.18.2 |  |  | 195 | 195
1642 | DEL-0036 | TSK-01633 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.18.2.2 | 1.2.18.2 | Internal Review & Critique | Voice & Tone | Internal Review & Critique | Strategist | Mid | 1 |  |  | 1.2.18.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.18.3 | 1.2.18 | Client Review & Revisions | Voice & Tone | Client Review & Revisions |  |  | 0 | 33 | 3 | 1.2.18.2.2 |  |  | 0 | 0
1636 | DEL-0036 | TSK-01627 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.18.3.1 | 1.2.18.3 | Client Review & Revisions | Voice & Tone | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.18.3 |  |  | 195 | 195
1637 | DEL-0036 | TSK-01628 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.18.3.2 | 1.2.18.3 | Client Review & Revisions | Voice & Tone | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.18.3.1 |  |  | 195 | 195
1638 | DEL-0036 | TSK-01629 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.18.3.3 | 1.2.18.3 | Client Review & Revisions | Voice & Tone | Client Review & Revisions | Strategist | Mid | 1 |  |  | 1.2.18.3.2 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.19 | 1.2 | Content Production Shot List Review & Guidance | Content Production Shot List Review & Guidance |  |  |  | 13 | 14 | 5 | 1.2.18 |  |  | 195 | 2535
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.19.1 | 1.2.19 | Client Review & Revisions | Content Production Shot List Review & Guidance | Client Review & Revisions |  |  | 0 | 14 | 5 | 1.2.19 |  |  | 0 | 0
1527 | DEL-0036 | TSK-01518 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.19.1.1 | 1.2.19.1 | Client Review & Revisions | Content Production Shot List Review & Guidance | Client Review & Revisions | Account Manager | Mid | 3 |  |  | 1.2.19.1 |  |  | 195 | 585
1530 | DEL-0036 | TSK-01521 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.19.1.2 | 1.2.19.1 | Client Review & Revisions | Content Production Shot List Review & Guidance | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.19.1.1 |  |  | 195 | 195
1529 | DEL-0036 | TSK-01520 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.19.1.3 | 1.2.19.1 | Client Review & Revisions | Content Production Shot List Review & Guidance | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.2.19.1.2 |  |  | 195 | 585
1528 | DEL-0036 | TSK-01519 | Strategy | Creative Strategy / Campaign Plan Deck | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.19.1.4 | 1.2.19.1 | Client Review & Revisions | Content Production Shot List Review & Guidance | Client Review & Revisions | Strategist | Mid | 6 |  |  | 1.2.19.1.3 |  |  | 195 | 1170
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3 | 1 | Paid Media Planning |  |  |  |  | 82 | 36 | 33 | 1.2 |  | Advanced/T2_MediumVolume | 195 | 15990
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.1 | 1.3 | Media Planning Deck | Media Planning Deck |  |  |  | 19 | 36 | 16 | 1.3 |  |  | 195 | 3705
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.1.1 | 1.3.1 | Deck Narrative | Media Planning Deck | Deck Narrative |  |  | 0 | 36 | 6 | 1.3.1 |  |  | 0 | 0
1241 | DEL-0029 | TSK-01232 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.1.1.1 | 1.3.1.1 | Deck Narrative | Media Planning Deck | Deck Narrative | Designer | Mid | 8 |  |  | 1.3.1.1 |  |  | 195 | 1560
1240 | DEL-0029 | TSK-01231 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.1.1.2 | 1.3.1.1 | Deck Narrative | Media Planning Deck | Deck Narrative | Media Strategist | Mid | 4 |  |  | 1.3.1.1.1 |  |  | 195 | 780
1244 | DEL-0029 | TSK-01235 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.1.1.3 | 1.3.1.1 | Deck Narrative | Media Planning Deck | Deck Narrative | Project Manager | Mid | 2 |  |  | 1.3.1.1.2 |  |  | 195 | 390
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.1.2 | 1.3.1 | Deck Build | Media Planning Deck | Deck Build |  |  | 0 | 48 | 5 | 1.3.1.1.3 |  |  | 0 | 0
1239 | DEL-0029 | TSK-01230 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.1.2.1 | 1.3.1.2 | Deck Build | Media Planning Deck | Deck Build | Designer | Mid | 2 |  |  | 1.3.1.2 |  |  | 195 | 390
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.1.3 | 1.3.1 | Internal Review & Critique | Media Planning Deck | Internal Review & Critique |  |  | 0 | 64 | 2 | 1.3.1.2.1 |  |  | 0 | 0
1242 | DEL-0029 | TSK-01233 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.1.3.1 | 1.3.1.3 | Internal Review & Critique | Media Planning Deck | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.1.3 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.1.4 | 1.3.1 | Client Review & Revisions | Media Planning Deck | Client Review & Revisions |  |  | 0 | 66 | 3 | 1.3.1.3.1 |  |  | 0 | 0
1237 | DEL-0029 | TSK-01228 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.1.4.1 | 1.3.1.4 | Client Review & Revisions | Media Planning Deck | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.1.4 |  |  | 195 | 195
1238 | DEL-0029 | TSK-01229 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.1.4.2 | 1.3.1.4 | Client Review & Revisions | Media Planning Deck | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.1.4.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.2 | 1.3 | Paid Media Plan | Paid Media Plan |  |  |  | 29 | 42 | 11 | 1.3.1 |  |  | 195 | 5655
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.2.1 | 1.3.2 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes |  |  | 0 | 42 | 6 | 1.3.2 |  |  | 0 | 0
1248 | DEL-0029 | TSK-01239 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.2.1.1 | 1.3.2.1 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes | Designer | Mid | 3 |  |  | 1.3.2.1 |  |  | 195 | 585
1252 | DEL-0029 | TSK-01243 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.2.1.2 | 1.3.2.1 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes | Media Planner | Mid | 10 |  |  | 1.3.2.1.1 |  |  | 195 | 1950
1245 | DEL-0029 | TSK-01236 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.2.1.3 | 1.3.2.1 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes | Media Strategist | Mid | 10 |  |  | 1.3.2.1.2 |  |  | 195 | 1950
1251 | DEL-0029 | TSK-01242 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.2.1.4 | 1.3.2.1 | Assumptions & Notes | Paid Media Plan | Assumptions & Notes | Project Manager | Mid | 2 |  |  | 1.3.2.1.3 |  |  | 195 | 390
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.2.2 | 1.3.2 | Internal Review & Critique | Paid Media Plan | Internal Review & Critique |  |  | 0 | 64 | 2 | 1.3.2.1.4 |  |  | 0 | 0
1249 | DEL-0029 | TSK-01240 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.2.2.1 | 1.3.2.2 | Internal Review & Critique | Paid Media Plan | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.2.2 |  |  | 195 | 195
1250 | DEL-0029 | TSK-01241 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.2.2.2 | 1.3.2.2 | Internal Review & Critique | Paid Media Plan | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.2.2.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.2.3 | 1.3.2 | Client Review & Revisions | Paid Media Plan | Client Review & Revisions |  |  | 0 | 66 | 3 | 1.3.2.2.2 |  |  | 0 | 0
1246 | DEL-0029 | TSK-01237 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.2.3.1 | 1.3.2.3 | Client Review & Revisions | Paid Media Plan | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.2.3 |  |  | 195 | 195
1247 | DEL-0029 | TSK-01238 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.2.3.2 | 1.3.2.3 | Client Review & Revisions | Paid Media Plan | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.2.3.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.3 | 1.3 | Ad Unit & Format POV | Ad Unit & Format POV |  |  |  | 16 | 53 | 16 | 1.3.2 |  |  | 195 | 3120
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.3.1 | 1.3.3 | Spec Page Build | Ad Unit & Format POV | Spec Page Build |  |  | 0 | 53 | 11 | 1.3.3 |  |  | 0 | 0
1227 | DEL-0029 | TSK-01218 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.3.1.1 | 1.3.3.1 | Spec Page Build | Ad Unit & Format POV | Spec Page Build | Designer | Mid | 3 |  |  | 1.3.3.1 |  |  | 195 | 585
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.3.2 | 1.3.3 | Internal Review & Critique | Ad Unit & Format POV | Internal Review & Critique |  |  | 0 | 64 | 2 | 1.3.3.1.1 |  |  | 0 | 0
1223 | DEL-0029 | TSK-01214 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.3.2.1 | 1.3.3.2 | Internal Review & Critique | Ad Unit & Format POV | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.3.2 |  |  | 195 | 195
1224 | DEL-0029 | TSK-01215 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.3.2.2 | 1.3.3.2 | Internal Review & Critique | Ad Unit & Format POV | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.3.2.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.3.3 | 1.3.3 | Client Review & Revisions | Ad Unit & Format POV | Client Review & Revisions |  |  | 0 | 66 | 3 | 1.3.3.2.2 |  |  | 0 | 0
1220 | DEL-0029 | TSK-01211 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.3.3.1 | 1.3.3.3 | Client Review & Revisions | Ad Unit & Format POV | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.3.3 |  |  | 195 | 195
1221 | DEL-0029 | TSK-01212 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.3.3.2 | 1.3.3.3 | Client Review & Revisions | Ad Unit & Format POV | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.3.3.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.3.4 | 1.3.3 | Spec Matrix & POV | Ad Unit & Format POV | Spec Matrix & POV |  |  | 0 | 69 | 0 | 1.3.3.3.2 |  |  | 0 | 0
1222 | DEL-0029 | TSK-01213 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.3.4.1 | 1.3.3.4 | Spec Matrix & POV | Ad Unit & Format POV | Spec Matrix & POV | Designer | Mid | 3 |  |  | 1.3.3.4 |  |  | 195 | 585
1225 | DEL-0029 | TSK-01216 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.3.4.2 | 1.3.3.4 | Spec Matrix & POV | Ad Unit & Format POV | Spec Matrix & POV | Media Planner | Mid | 3 |  |  | 1.3.3.4.1 |  |  | 195 | 585
1226 | DEL-0029 | TSK-01217 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.3.4.3 | 1.3.3.4 | Spec Matrix & POV | Ad Unit & Format POV | Spec Matrix & POV | Media Strategist | Mid | 3 |  |  | 1.3.3.4.2 |  |  | 195 | 585
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.4 | 1.3 | Channel & Vendor Evaluation | Channel & Vendor Evaluation |  |  |  | 18 | 64 | 5 | 1.3.3 |  |  | 195 | 3510
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.4.1 | 1.3.4 | Internal Review & Critique | Channel & Vendor Evaluation | Internal Review & Critique |  |  | 0 | 64 | 2 | 1.3.4 |  |  | 0 | 0
1231 | DEL-0029 | TSK-01222 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.4.1.1 | 1.3.4.1 | Internal Review & Critique | Channel & Vendor Evaluation | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.3.4.1 |  |  | 195 | 195
1232 | DEL-0029 | TSK-01223 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.4.1.2 | 1.3.4.1 | Internal Review & Critique | Channel & Vendor Evaluation | Internal Review & Critique | Media Strategist | Mid | 1 |  |  | 1.3.4.1.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.4.2 | 1.3.4 | Client Review & Revisions | Channel & Vendor Evaluation | Client Review & Revisions |  |  | 0 | 66 | 3 | 1.3.4.1.2 |  |  | 0 | 0
1228 | DEL-0029 | TSK-01219 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.4.2.1 | 1.3.4.2 | Client Review & Revisions | Channel & Vendor Evaluation | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.3.4.2 |  |  | 195 | 195
1229 | DEL-0029 | TSK-01220 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.4.2.2 | 1.3.4.2 | Client Review & Revisions | Channel & Vendor Evaluation | Client Review & Revisions | Media Strategist | Mid | 1 |  |  | 1.3.4.2.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.4.3 | 1.3.4 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review |  |  | 0 | 69 | 0 | 1.3.4.2.2 |  |  | 0 | 0
1236 | DEL-0029 | TSK-01227 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.4.3.1 | 1.3.4.3 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review | Account Manager | Mid | 2 |  |  | 1.3.4.3 |  |  | 195 | 390
1230 | DEL-0029 | TSK-01221 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.4.3.2 | 1.3.4.3 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review | Designer | Mid | 2 |  |  | 1.3.4.3.1 |  |  | 195 | 390
1233 | DEL-0029 | TSK-01224 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.4.3.3 | 1.3.4.3 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review | Media Planner | Mid | 7 |  |  | 1.3.4.3.2 |  |  | 195 | 1365
1234 | DEL-0029 | TSK-01225 | Paid Media | Paid Media Planning | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.3.4.3.4 | 1.3.4.3 | RFI/Options Review | Channel & Vendor Evaluation | RFI/Options Review | Media Strategist | Mid | 3 |  |  | 1.3.4.3.3 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4 | 1 | Reporting |  |  |  |  | 128 | 69 | 7 | 1.3 |  | Advanced/T2_MediumVolume | 195 | 24960
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.1 | 1.4 | Dashboards | Dashboards |  |  |  | 9 | 69 | 7 | 1.4 |  |  | 195 | 1755
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.1.1 | 1.4.1 | QA | Dashboards | QA |  |  | 0 | 69 | 3 | 1.4.1 |  |  | 0 | 0
1116 | DEL-0024 | TSK-01107 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.1.1.1 | 1.4.1.1 | QA | Dashboards | QA | QA Specialist | Mid | 3 |  |  | 1.4.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.1.2 | 1.4.1 | Dashboard Build/Refresh | Dashboards | Dashboard Build/Refresh |  |  | 0 | 72 | 4 | 1.4.1.1.1 |  |  | 0 | 0
1115 | DEL-0024 | TSK-01106 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.1.2.1 | 1.4.1.2 | Dashboard Build/Refresh | Dashboards | Dashboard Build/Refresh | Analyst | Mid | 6 |  |  | 1.4.1.2 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.2 | 1.4 | Engagement Rate | Engagement Rate |  |  |  | 6 | 69 | 3 | 1.4.1 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.2.1 | 1.4.2 | Data Refresh & Calc Check | Engagement Rate | Data Refresh & Calc Check |  |  | 0 | 69 | 3 | 1.4.2 |  |  | 0 | 0
1119 | DEL-0024 | TSK-01110 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.2.1.1 | 1.4.2.1 | Data Refresh & Calc Check | Engagement Rate | Data Refresh & Calc Check | Analyst | Mid | 3 |  |  | 1.4.2.1 |  |  | 195 | 585
1120 | DEL-0024 | TSK-01111 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.2.1.2 | 1.4.2.1 | Data Refresh & Calc Check | Engagement Rate | Data Refresh & Calc Check | QA Specialist | Mid | 3 |  |  | 1.4.2.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.3 | 1.4 | Emplifi Reports | Emplifi Reports |  |  |  | 7 | 72 | 4 | 1.4.2 |  |  | 195 | 1365
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.3.1 | 1.4.3 | Emplifi Extract & Summary | Emplifi Reports | Emplifi Extract & Summary |  |  | 0 | 72 | 4 | 1.4.3 |  |  | 0 | 0
1117 | DEL-0024 | TSK-01108 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.3.1.1 | 1.4.3.1 | Emplifi Extract & Summary | Emplifi Reports | Emplifi Extract & Summary | Account Manager | Mid | 1 |  |  | 1.4.3.1 |  |  | 195 | 195
1118 | DEL-0024 | TSK-01109 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.3.1.2 | 1.4.3.1 | Emplifi Extract & Summary | Emplifi Reports | Emplifi Extract & Summary | Analyst | Mid | 6 |  |  | 1.4.3.1.1 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.4 | 1.4 | Monthly Comprehensive Report | Monthly Comprehensive Report |  |  |  | 11 | 72 | 4 | 1.4.3 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.4.1 | 1.4.4 | Monthly Report | Monthly Comprehensive Report | Monthly Report |  |  | 0 | 72 | 4 | 1.4.4 |  |  | 0 | 0
1127 | DEL-0024 | TSK-01118 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.4.1.1 | 1.4.4.1 | Monthly Report | Monthly Comprehensive Report | Monthly Report | Analyst | Mid | 6 |  |  | 1.4.4.1 |  |  | 195 | 1170
1128 | DEL-0024 | TSK-01119 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.4.1.2 | 1.4.4.1 | Monthly Report | Monthly Comprehensive Report | Monthly Report | Designer | Mid | 2 |  |  | 1.4.4.1.1 |  |  | 195 | 390
1129 | DEL-0024 | TSK-01120 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.4.1.3 | 1.4.4.1 | Monthly Report | Monthly Comprehensive Report | Monthly Report | Social Strategist | Mid | 3 |  |  | 1.4.4.1.2 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.5 | 1.4 | Monthly Organic Social Report | Monthly Organic Social Report |  |  |  | 11 | 72 | 4 | 1.4.4 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.5.1 | 1.4.5 | Monthly Organic Report | Monthly Organic Social Report | Monthly Organic Report |  |  | 0 | 72 | 4 | 1.4.5 |  |  | 0 | 0
1130 | DEL-0024 | TSK-01121 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.5.1.1 | 1.4.5.1 | Monthly Organic Report | Monthly Organic Social Report | Monthly Organic Report | Analyst | Mid | 6 |  |  | 1.4.5.1 |  |  | 195 | 1170
1131 | DEL-0024 | TSK-01122 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.5.1.2 | 1.4.5.1 | Monthly Organic Report | Monthly Organic Social Report | Monthly Organic Report | Designer | Mid | 2 |  |  | 1.4.5.1.1 |  |  | 195 | 390
1132 | DEL-0024 | TSK-01123 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.5.1.3 | 1.4.5.1 | Monthly Organic Report | Monthly Organic Social Report | Monthly Organic Report | Social Strategist | Mid | 3 |  |  | 1.4.5.1.2 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.6 | 1.4 | Optimization Recommendations Report | Optimization Recommendations Report |  |  |  | 10 | 72 | 4 | 1.4.5 |  |  | 195 | 1950
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.6.1 | 1.4.6 | Recs & Next Steps | Optimization Recommendations Report | Recs & Next Steps |  |  | 0 | 72 | 4 | 1.4.6 |  |  | 0 | 0
1133 | DEL-0024 | TSK-01124 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.6.1.1 | 1.4.6.1 | Recs & Next Steps | Optimization Recommendations Report | Recs & Next Steps | Account Manager | Mid | 1 |  |  | 1.4.6.1 |  |  | 195 | 195
1134 | DEL-0024 | TSK-01125 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.6.1.2 | 1.4.6.1 | Recs & Next Steps | Optimization Recommendations Report | Recs & Next Steps | Analyst | Mid | 6 |  |  | 1.4.6.1.1 |  |  | 195 | 1170
1135 | DEL-0024 | TSK-01126 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.6.1.3 | 1.4.6.1 | Recs & Next Steps | Optimization Recommendations Report | Recs & Next Steps | Social Strategist | Mid | 3 |  |  | 1.4.6.1.2 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.7 | 1.4 | Quarterly Ad-Hoc Report | Quarterly Ad-Hoc Report |  |  |  | 9 | 72 | 4 | 1.4.6 |  |  | 195 | 1755
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.7.1 | 1.4.7 | Quarterly Ad-hoc Deep Dive | Quarterly Ad-Hoc Report | Quarterly Ad-hoc Deep Dive |  |  | 0 | 72 | 4 | 1.4.7 |  |  | 0 | 0
1138 | DEL-0024 | TSK-01129 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.7.1.1 | 1.4.7.1 | Quarterly Ad-hoc Deep Dive | Quarterly Ad-Hoc Report | Quarterly Ad-hoc Deep Dive | Analyst | Mid | 6 |  |  | 1.4.7.1 |  |  | 195 | 1170
1139 | DEL-0024 | TSK-01130 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.7.1.2 | 1.4.7.1 | Quarterly Ad-hoc Deep Dive | Quarterly Ad-Hoc Report | Quarterly Ad-hoc Deep Dive | QA Specialist | Mid | 3 |  |  | 1.4.7.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.8 | 1.4 | Quarterly Key Learnings & Insights Report | Quarterly Key Learnings & Insights Report |  |  |  | 11 | 72 | 4 | 1.4.7 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.8.1 | 1.4.8 | Quarterly Learnings & Insights | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights |  |  | 0 | 72 | 4 | 1.4.8 |  |  | 0 | 0
1140 | DEL-0024 | TSK-01131 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.8.1.1 | 1.4.8.1 | Quarterly Learnings & Insights | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights | Analyst | Mid | 6 |  |  | 1.4.8.1 |  |  | 195 | 1170
1141 | DEL-0024 | TSK-01132 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.8.1.2 | 1.4.8.1 | Quarterly Learnings & Insights | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights | Designer | Mid | 2 |  |  | 1.4.8.1.1 |  |  | 195 | 390
1142 | DEL-0024 | TSK-01133 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.8.1.3 | 1.4.8.1 | Quarterly Learnings & Insights | Quarterly Key Learnings & Insights Report | Quarterly Learnings & Insights | Social Strategist | Mid | 3 |  |  | 1.4.8.1.2 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.9 | 1.4 | Quarterly Report | Quarterly Report |  |  |  | 11 | 72 | 4 | 1.4.8 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.9.1 | 1.4.9 | Quarterly Report | Quarterly Report | Quarterly Report |  |  | 0 | 72 | 4 | 1.4.9 |  |  | 0 | 0
1143 | DEL-0024 | TSK-01134 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.9.1.1 | 1.4.9.1 | Quarterly Report | Quarterly Report | Quarterly Report | Analyst | Mid | 6 |  |  | 1.4.9.1 |  |  | 195 | 1170
1144 | DEL-0024 | TSK-01135 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.9.1.2 | 1.4.9.1 | Quarterly Report | Quarterly Report | Quarterly Report | Designer | Mid | 2 |  |  | 1.4.9.1.1 |  |  | 195 | 390
1145 | DEL-0024 | TSK-01136 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.9.1.3 | 1.4.9.1 | Quarterly Report | Quarterly Report | Quarterly Report | Social Strategist | Mid | 3 |  |  | 1.4.9.1.2 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.10 | 1.4 | Summary overview | Summary overview |  |  |  | 4 | 72 | 4 | 1.4.9 |  |  | 195 | 780
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.10.1 | 1.4.10 | Summary Narrative | Summary overview | Summary Narrative |  |  | 0 | 72 | 4 | 1.4.10 |  |  | 0 | 0
1150 | DEL-0024 | TSK-01141 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.10.1.1 | 1.4.10.1 | Summary Narrative | Summary overview | Summary Narrative | Account Manager | Mid | 1 |  |  | 1.4.10.1 |  |  | 195 | 195
1151 | DEL-0024 | TSK-01142 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.10.1.2 | 1.4.10.1 | Summary Narrative | Summary overview | Summary Narrative | Social Strategist | Mid | 3 |  |  | 1.4.10.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.11 | 1.4 | Weekly Activity Report | Weekly Activity Report |  |  |  | 7 | 72 | 4 | 1.4.10 |  |  | 195 | 1365
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.11.1 | 1.4.11 | Weekly Activity Summary | Weekly Activity Report | Weekly Activity Summary |  |  | 0 | 72 | 4 | 1.4.11 |  |  | 0 | 0
1153 | DEL-0024 | TSK-01144 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.11.1.1 | 1.4.11.1 | Weekly Activity Summary | Weekly Activity Report | Weekly Activity Summary | Account Manager | Mid | 1 |  |  | 1.4.11.1 |  |  | 195 | 195
1154 | DEL-0024 | TSK-01145 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.11.1.2 | 1.4.11.1 | Weekly Activity Summary | Weekly Activity Report | Weekly Activity Summary | Analyst | Mid | 6 |  |  | 1.4.11.1.1 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.12 | 1.4 | Follower Growth | Follower Growth |  |  |  | 6 | 76 | 0 | 1.4.11 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.12.1 | 1.4.12 | Metric Pull & Notes | Follower Growth | Metric Pull & Notes |  |  | 0 | 76 | 0 | 1.4.12 |  |  | 0 | 0
1121 | DEL-0024 | TSK-01112 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.12.1.1 | 1.4.12.1 | Metric Pull & Notes | Follower Growth | Metric Pull & Notes | Analyst | Mid | 3 |  |  | 1.4.12.1 |  |  | 195 | 585
1122 | DEL-0024 | TSK-01113 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.12.1.2 | 1.4.12.1 | Metric Pull & Notes | Follower Growth | Metric Pull & Notes | QA Specialist | Mid | 3 |  |  | 1.4.12.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.13 | 1.4 | Impressions | Impressions |  |  |  | 6 | 76 | 0 | 1.4.12 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.13.1 | 1.4.13 | Metric Pull & Notes | Impressions | Metric Pull & Notes |  |  | 0 | 76 | 0 | 1.4.13 |  |  | 0 | 0
1123 | DEL-0024 | TSK-01114 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.13.1.1 | 1.4.13.1 | Metric Pull & Notes | Impressions | Metric Pull & Notes | Analyst | Mid | 3 |  |  | 1.4.13.1 |  |  | 195 | 585
1124 | DEL-0024 | TSK-01115 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.13.1.2 | 1.4.13.1 | Metric Pull & Notes | Impressions | Metric Pull & Notes | QA Specialist | Mid | 3 |  |  | 1.4.13.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.14 | 1.4 | Interactions | Interactions |  |  |  | 5 | 76 | 0 | 1.4.13 |  |  | 195 | 975
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.14.1 | 1.4.14 | Metric Pull & Notes | Interactions | Metric Pull & Notes |  |  | 0 | 76 | 0 | 1.4.14 |  |  | 0 | 0
1125 | DEL-0024 | TSK-01116 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.14.1.1 | 1.4.14.1 | Metric Pull & Notes | Interactions | Metric Pull & Notes | Analyst | Mid | 2 |  |  | 1.4.14.1 |  |  | 195 | 390
1126 | DEL-0024 | TSK-01117 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.14.1.2 | 1.4.14.1 | Metric Pull & Notes | Interactions | Metric Pull & Notes | QA Specialist | Mid | 3 |  |  | 1.4.14.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.15 | 1.4 | Profile Reach | Profile Reach |  |  |  | 5 | 76 | 0 | 1.4.14 |  |  | 195 | 975
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.15.1 | 1.4.15 | Metric Pull & Notes | Profile Reach | Metric Pull & Notes |  |  | 0 | 76 | 0 | 1.4.15 |  |  | 0 | 0
1136 | DEL-0024 | TSK-01127 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.15.1.1 | 1.4.15.1 | Metric Pull & Notes | Profile Reach | Metric Pull & Notes | Analyst | Mid | 2 |  |  | 1.4.15.1 |  |  | 195 | 390
1137 | DEL-0024 | TSK-01128 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.15.1.2 | 1.4.15.1 | Metric Pull & Notes | Profile Reach | Metric Pull & Notes | QA Specialist | Mid | 3 |  |  | 1.4.15.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.16 | 1.4 | Recap Reports | Recap Reports |  |  |  | 4 | 76 | 0 | 1.4.15 |  |  | 195 | 780
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.16.1 | 1.4.16 | Campaign/Period Recaps | Recap Reports | Campaign/Period Recaps |  |  | 0 | 76 | 0 | 1.4.16 |  |  | 0 | 0
1146 | DEL-0024 | TSK-01137 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.16.1.1 | 1.4.16.1 | Campaign/Period Recaps | Recap Reports | Campaign/Period Recaps | Account Manager | Mid | 2 |  |  | 1.4.16.1 |  |  | 195 | 390
1147 | DEL-0024 | TSK-01138 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.16.1.2 | 1.4.16.1 | Campaign/Period Recaps | Recap Reports | Campaign/Period Recaps | Analyst | Mid | 2 |  |  | 1.4.16.1.1 |  |  | 195 | 390
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.17 | 1.4 | Social Reporting | Social Reporting |  |  |  | 4 | 76 | 0 | 1.4.16 |  |  | 195 | 780
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.17.1 | 1.4.17 | Ongoing Social Reporting | Social Reporting | Ongoing Social Reporting |  |  | 0 | 76 | 0 | 1.4.17 |  |  | 0 | 0
1148 | DEL-0024 | TSK-01139 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.17.1.1 | 1.4.17.1 | Ongoing Social Reporting | Social Reporting | Ongoing Social Reporting | Account Manager | Mid | 2 |  |  | 1.4.17.1 |  |  | 195 | 390
1149 | DEL-0024 | TSK-01140 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.17.1.2 | 1.4.17.1 | Ongoing Social Reporting | Social Reporting | Ongoing Social Reporting | Analyst | Mid | 2 |  |  | 1.4.17.1.1 |  |  | 195 | 390
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.18 | 1.4 | Update/maintain Z/Russia tracker | Update/maintain Z/Russia tracker |  |  |  | 2 | 76 | 0 | 1.4.17 |  |  | 195 | 390
| DEL-0024 |  | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.18.1 | 1.4.18 | Tracker Update | Update/maintain Z/Russia tracker | Tracker Update |  |  | 0 | 76 | 0 | 1.4.18 |  |  | 0 | 0
1152 | DEL-0024 | TSK-01143 | Integrated Marketing Management | Reporting | RFP_Brief_ First on SoundCloud 2021 Campaign | 1.4.18.1.1 | 1.4.18.1 | Tracker Update | Update/maintain Z/Russia tracker | Tracker Update | Analyst | Mid | 2 |  |  | 1.4.18.1 |  |  | 195 | 390