## Sheet1
Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Deliverable | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes | Rate_USD | Price_USD
Vascano Tequila - RFP Creative Services 2022 (8) | 1 |  | Vascano Tequila - RFP Creative Services 2022 (8) |  | Project |  |  |  | 0 | 0 |  |  |  |  | 0 | 0
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1 | 1 | Development | Development |  |  |  |  | 227 | 0 | 22 |  |  | Core/T2_MediumVolume | 185 | 41995
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1 | 1.1 | ADA Compliance | Development | ADA Compliance |  |  |  | 50 | 0 | 15 | 1.1 |  |  | 185 | 9250
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.1 | 1.1.1 | Accessibility Audit | Development | ADA Compliance | Accessibility Audit | Accessibility Specialist | Mid | 2 | 0 | 3 | 1.1.1 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.2 | 1.1.1 | Accessibility QA | Development | ADA Compliance | Accessibility QA | QA Engineer | Mid | 4 | 10 | 2 | 1.1.1.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.3 | 1.1.1 | Code Review | Development | ADA Compliance | Code Review | Frontend Engineer | Mid | 44 | 12 | 10 | 1.1.1.2 |  |  | 185 | 8140
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2 | 1.1 | Audit & Requirement gathering | Development | Audit & Requirement gathering |  |  |  | 17 | 0 | 3 | 1.1.1 |  |  | 185 | 3145
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.1 | 1.1.2 | Analytics Audit | Development | Audit & Requirement gathering | Analytics Audit | Business Analyst | Mid | 17 | 0 | 3 | 1.1.2 |  |  | 185 | 3145
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3 | 1.1 | Audit existing UA Property | Development | Audit existing UA Property |  |  |  | 17 | 0 | 3 | 1.1.2 |  |  | 185 | 3145
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.1 | 1.1.3 | Documentation | Development | Audit existing UA Property | Documentation | Business Analyst | Mid | 17 | 0 | 3 | 1.1.3 |  |  | 185 | 3145
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4 | 1.1 | Footer CTA | Development | Footer CTA |  |  |  | 43 | 3 | 19 | 1.1.3 |  |  | 185 | 7955
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.1 | 1.1.4 | Design Consult | Development | Footer CTA | Design Consult | UI Designer | Mid | 3 | 3 | 7 | 1.1.4 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.2 | 1.1.4 | Accessibility QA | Development | Footer CTA | Accessibility QA | QA Engineer | Mid | 6 | 10 | 2 | 1.1.4.1 |  |  | 185 | 1110
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.3 | 1.1.4 | Code Review | Development | Footer CTA | Code Review | Backend Engineer | Mid | 34 | 12 | 10 | 1.1.4.2 |  |  | 185 | 6290
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5 | 1.1 | Header & Footer Navigation | Development | Header & Footer Navigation |  |  |  | 43 | 3 | 19 | 1.1.4 |  |  | 185 | 7955
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.1 | 1.1.5 | Design Consult | Development | Header & Footer Navigation | Design Consult | UI Designer | Mid | 3 | 3 | 7 | 1.1.5 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.2 | 1.1.5 | Accessibility QA | Development | Header & Footer Navigation | Accessibility QA | QA Engineer | Mid | 6 | 10 | 2 | 1.1.5.1 |  |  | 185 | 1110
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.3 | 1.1.5 | Code Review | Development | Header & Footer Navigation | Code Review | Backend Engineer | Mid | 34 | 12 | 10 | 1.1.5.2 |  |  | 185 | 6290
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6 | 1.1 | Additional Goals Setup | Development | Additional Goals Setup |  |  |  | 7 | 10 | 12 | 1.1.5 |  |  | 185 | 1295
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.1 | 1.1.6 | QA Cycle | Development | Additional Goals Setup | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.6 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.2 | 1.1.6 | Define & Configure Goals | Development | Additional Goals Setup | Define & Configure Goals | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.6.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7 | 1.1 | Custom Event Tracking | Development | Custom Event Tracking |  |  |  | 7 | 10 | 12 | 1.1.6 |  |  | 185 | 1295
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.1 | 1.1.7 | QA Cycle | Development | Custom Event Tracking | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.7 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.2 | 1.1.7 | Event Schema & Tagging | Development | Custom Event Tracking | Event Schema & Tagging | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.7.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8 | 1.1 | Implement Paid Media Pixel on website w GTM-Google Ads | Development | Implement Paid Media Pixel on website w GTM-Google Ads |  |  |  | 5 | 10 | 12 | 1.1.7 |  |  | 185 | 925
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.1 | 1.1.8 | Spec QA | Development | Implement Paid Media Pixel on website w GTM-Google Ads | Spec QA | QA Engineer | Mid | 3 | 10 | 2 | 1.1.8 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.2 | 1.1.8 | Pixel Setup (GTM) | Development | Implement Paid Media Pixel on website w GTM-Google Ads | Pixel Setup (GTM) | Data/Analytics Engineer | Mid | 2 | 12 | 10 | 1.1.8.1 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9 | 1.1 | Implement goals listed in UA as Conversions in G4 | Development | Implement goals listed in UA as Conversions in G4 |  |  |  | 7 | 10 | 12 | 1.1.8 |  |  | 185 | 1295
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.1 | 1.1.9 | QA Cycle | Development | Implement goals listed in UA as Conversions in G4 | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.9 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.2 | 1.1.9 | Migrate UA Goals → GA4 Conversions | Development | Implement goals listed in UA as Conversions in G4 | Migrate UA Goals → GA4 Conversions | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.9.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10 | 1.1 | Implementation | Development | Implementation |  |  |  | 7 | 10 | 12 | 1.1.9 |  |  | 185 | 1295
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.1 | 1.1.10 | QA Cycle | Development | Implementation | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.10 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.2 | 1.1.10 | Implement Tags/Events | Development | Implementation | Implement Tags/Events | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.10.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11 | 1.1 | Outbound link clicks | Development | Outbound link clicks |  |  |  | 5 | 10 | 12 | 1.1.10 |  |  | 185 | 925
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11.1 | 1.1.11 | QA | Development | Outbound link clicks | QA | QA Engineer | Mid | 3 | 10 | 2 | 1.1.11 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11.2 | 1.1.11 | Event Config | Development | Outbound link clicks | Event Config | Data/Analytics Engineer | Mid | 2 | 12 | 10 | 1.1.11.1 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.12 | 1.1 | Publishing tags, Testing and Auditing | Development | Publishing tags, Testing and Auditing |  |  |  | 4 | 10 | 2 | 1.1.11 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.12.1 | 1.1.12 | Publish & Smoke Test | Development | Publishing tags, Testing and Auditing | Publish & Smoke Test | QA Engineer | Mid | 4 | 10 | 2 | 1.1.12 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.13 | 1.1 | Setup cross-domain tracking | Development | Setup cross-domain tracking |  |  |  | 4 | 10 | 12 | 1.1.12 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.13.1 | 1.1.13 | QA | Development | Setup cross-domain tracking | QA | QA Engineer | Mid | 2 | 10 | 2 | 1.1.13 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.13.2 | 1.1.13 | Cross-domain Config | Development | Setup cross-domain tracking | Cross-domain Config | Data/Analytics Engineer | Mid | 2 | 12 | 10 | 1.1.13.1 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.14 | 1.1 | Setup eCommerce tracking | Development | Setup eCommerce tracking |  |  |  | 4 | 10 | 12 | 1.1.13 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.14.1 | 1.1.14 | QA | Development | Setup eCommerce tracking | QA | QA Engineer | Mid | 2 | 10 | 2 | 1.1.14 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.14.2 | 1.1.14 | Ecommerce Data Layer | Development | Setup eCommerce tracking | Ecommerce Data Layer | Data/Analytics Engineer | Mid | 2 | 12 | 10 | 1.1.14.1 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.15 | 1.1 | Setup new GA4 acct for Caledera House | Development | Setup new GA4 acct for Caledera House |  |  |  | 7 | 10 | 12 | 1.1.14 |  |  | 185 | 1295
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.15.1 | 1.1.15 | QA Cycle | Development | Setup new GA4 acct for Caledera House | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.15 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.15.2 | 1.1.15 | GA4 Property Setup | Development | Setup new GA4 acct for Caledera House | GA4 Property Setup | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.15.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2 | 1 | Post-Production | Post-Production |  |  |  |  | 188 | 22 | 41 | 1.1 |  | Core/T2_MediumVolume | 185 | 34780
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1 | 1.2 | Content Licensing / Art Buying | Post-Production | Content Licensing / Art Buying |  |  |  | 2 | 22 | 3 | 1.2 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1.1 | 1.2.1 | Rights/License Research | Post-Production | Content Licensing / Art Buying | Rights/License Research | Producer | Mid | 1 | 22 | 3 | 1.2.1 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1.2 | 1.2.1 | Usage Notes | Post-Production | Content Licensing / Art Buying | Usage Notes | Account Manager | Mid | 1 | 63 | 0 | 1.2.1.1 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2 | 1.2 | VO Recording Sessions | Post-Production | VO Recording Sessions |  |  |  | 5 | 25 | 4 | 1.2.1 |  |  | 185 | 925
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.1 | 1.2.2 | Script Polish | Post-Production | VO Recording Sessions | Script Polish | Copywriter | Mid | 1 | 25 | 4 | 1.2.2 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.2 | 1.2.2 | VO Session | Post-Production | VO Recording Sessions | VO Session | Sound Designer | Mid | 4 | 63 | 0 | 1.2.2.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3 | 1.2 | Editing | Post-Production | Editing |  |  |  | 17 | 29 | 5 | 1.2.2 |  |  | 185 | 3145
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.1 | 1.2.3 | Client Review & Revisions | Post-Production | Editing | Client Review & Revisions | Editor | Mid | 17 | 29 | 5 | 1.2.3 |  |  | 185 | 3145
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4 | 1.2 | Video Editing | Post-Production | Video Editing |  |  |  | 25 | 29 | 5 | 1.2.3 |  |  | 185 | 4625
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.1 | 1.2.4 | Client Review & Revisions | Post-Production | Video Editing | Client Review & Revisions | Editor | Mid | 25 | 29 | 5 | 1.2.4 |  |  | 185 | 4625
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5 | 1.2 | Voice Over | Post-Production | Voice Over |  |  |  | 17 | 29 | 12 | 1.2.4 |  |  | 185 | 3145
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.1 | 1.2.5 | VO Edit | Post-Production | Voice Over | VO Edit | Editor | Mid | 9 | 29 | 5 | 1.2.5 |  |  | 185 | 1665
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.2 | 1.2.5 | Mix | Post-Production | Voice Over | Mix | Sound Designer | Mid | 2 | 46 | 2 | 1.2.5.1 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.3 | 1.2.5 | Internal Review & Critique | Post-Production | Voice Over | Internal Review & Critique | Producer | Mid | 1 | 53 | 2 | 1.2.5.2 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.4 | 1.2.5 | Client Review & Revisions | Post-Production | Voice Over | Client Review & Revisions | Account Manager | Mid | 3 | 55 | 3 | 1.2.5.3 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.5 | 1.2.5 | Final Packaging | Post-Production | Voice Over | Final Packaging | Designer | Mid | 2 | 63 | 0 | 1.2.5.4 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6 | 1.2 | Motion Design/VFX | Post-Production | Motion Design/VFX |  |  |  | 17 | 34 | 7 | 1.2.5 |  |  | 185 | 3145
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.1 | 1.2.6 | Client Review & Revisions | Post-Production | Motion Design/VFX | Client Review & Revisions | Editor | Mid | 17 | 34 | 7 | 1.2.6 |  |  | 185 | 3145
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7 | 1.2 | Color Correction | Post-Production | Color Correction |  |  |  | 11 | 41 | 2 | 1.2.6 |  |  | 185 | 2035
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.1 | 1.2.7 | Client Review & Revisions | Post-Production | Color Correction | Client Review & Revisions | Colorist | Mid | 11 | 41 | 2 | 1.2.7 |  |  | 185 | 2035
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8 | 1.2 | Color Grading | Post-Production | Color Grading |  |  |  | 11 | 41 | 2 | 1.2.7 |  |  | 185 | 2035
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.1 | 1.2.8 | Client Review & Revisions | Post-Production | Color Grading | Client Review & Revisions | Colorist | Mid | 11 | 41 | 2 | 1.2.8 |  |  | 185 | 2035
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9 | 1.2 | Final Retouched Stills Review | Post-Production | Final Retouched Stills Review |  |  |  | 10 | 43 | 8 | 1.2.8 |  |  | 185 | 1850
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.1 | 1.2.9 | Retouch | Post-Production | Final Retouched Stills Review | Retouch | Retoucher | Mid | 4 | 43 | 3 | 1.2.9 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.2 | 1.2.9 | Internal Review & Critique | Post-Production | Final Retouched Stills Review | Internal Review & Critique | Producer | Mid | 1 | 53 | 2 | 1.2.9.1 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.3 | 1.2.9 | Client Review & Revisions | Post-Production | Final Retouched Stills Review | Client Review & Revisions | Account Manager | Mid | 3 | 55 | 3 | 1.2.9.2 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.4 | 1.2.9 | Final Packaging | Post-Production | Final Retouched Stills Review | Final Packaging | Designer | Mid | 2 | 63 | 0 | 1.2.9.3 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10 | 1.2 | Retouching | Post-Production | Retouching |  |  |  | 10 | 43 | 8 | 1.2.9 |  |  | 185 | 1850
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.1 | 1.2.10 | Retouch | Post-Production | Retouching | Retouch | Retoucher | Mid | 4 | 43 | 3 | 1.2.10 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.2 | 1.2.10 | Internal Review & Critique | Post-Production | Retouching | Internal Review & Critique | Producer | Mid | 1 | 53 | 2 | 1.2.10.1 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.3 | 1.2.10 | Client Review & Revisions | Post-Production | Retouching | Client Review & Revisions | Account Manager | Mid | 3 | 55 | 3 | 1.2.10.2 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.4 | 1.2.10 | Final Packaging | Post-Production | Retouching | Final Packaging | Designer | Mid | 2 | 63 | 0 | 1.2.10.3 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.11 | 1.2 | Sound Mix | Post-Production | Sound Mix |  |  |  | 9 | 46 | 2 | 1.2.10 |  |  | 185 | 1665
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.11.1 | 1.2.11 | Client Review & Revisions | Post-Production | Sound Mix | Client Review & Revisions | Designer | Mid | 9 | 46 | 2 | 1.2.11 |  |  | 185 | 1665
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.12 | 1.2 | Sound Sourcing | Post-Production | Sound Sourcing |  |  |  | 3 | 46 | 2 | 1.2.11 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.12.1 | 1.2.12 | Music Search & License | Post-Production | Sound Sourcing | Music Search & License | Sound Designer | Mid | 3 | 46 | 2 | 1.2.12 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.13 | 1.2 | Final File Delivery | Post-Production | Final File Delivery |  |  |  | 7 | 48 | 2 | 1.2.12 |  |  | 185 | 1295
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.13.1 | 1.2.13 | QA (Tech & Content) | Post-Production | Final File Delivery | QA (Tech & Content) | QA Specialist | Mid | 3 | 48 | 2 | 1.2.13 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.13.2 | 1.2.13 | Final Checklist & Upload | Post-Production | Final File Delivery | Final Checklist & Upload | Media Manager / DIT | Mid | 4 | 63 | 0 | 1.2.13.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.14 | 1.2 | True-ups (for vendor costs) | Post-Production | True-ups (for vendor costs) |  |  |  | 10 | 50 | 8 | 1.2.13 |  |  | 185 | 1850
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.14.1 | 1.2.14 | Change Orders & Tracking | Post-Production | True-ups (for vendor costs) | Change Orders & Tracking | Project Manager | Mid | 1 | 50 | 3 | 1.2.14 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.14.2 | 1.2.14 | Internal Review & Critique | Post-Production | True-ups (for vendor costs) | Internal Review & Critique | Producer | Mid | 1 | 53 | 2 | 1.2.14.1 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.14.3 | 1.2.14 | Client Review & Revisions | Post-Production | True-ups (for vendor costs) | Client Review & Revisions | Account Manager | Mid | 3 | 55 | 3 | 1.2.14.2 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.14.4 | 1.2.14 | Invoice Reconciliation | Post-Production | True-ups (for vendor costs) | Invoice Reconciliation | Designer | Mid | 5 | 63 | 0 | 1.2.14.3 |  |  | 185 | 925
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.15 | 1.2 | Cutdowns | Post-Production | Cutdowns |  |  |  | 11 | 53 | 5 | 1.2.14 |  |  | 185 | 2035
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.15.1 | 1.2.15 | Internal Review & Critique | Post-Production | Cutdowns | Internal Review & Critique | Producer | Mid | 1 | 53 | 2 | 1.2.15 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.15.2 | 1.2.15 | Client Review & Revisions | Post-Production | Cutdowns | Client Review & Revisions | Account Manager | Mid | 3 | 55 | 3 | 1.2.15.1 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.15.3 | 1.2.15 | Cutdowns (2-3) | Post-Production | Cutdowns | Cutdowns (2-3) | Editor | Mid | 7 | 63 | 0 | 1.2.15.2 |  |  | 185 | 1295
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.16 | 1.2 | Client Review | Post-Production | Client Review |  |  |  | 4 | 55 | 3 | 1.2.15 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.16.1 | 1.2.16 | Client Review Coordination | Post-Production | Client Review | Client Review Coordination | Account Manager | Mid | 4 | 55 | 3 | 1.2.16 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.17 | 1.2 | Review & Sign-Off | Post-Production | Review & Sign-Off |  |  |  | 3 | 55 | 5 | 1.2.16 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.17.1 | 1.2.17 | Client Review Coordination | Post-Production | Review & Sign-Off | Client Review Coordination | Account Manager | Mid | 2 | 55 | 3 | 1.2.17 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.17.2 | 1.2.17 | Notes Triage | Post-Production | Review & Sign-Off | Notes Triage | Project Manager | Mid | 1 | 61 | 2 | 1.2.17.1 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.18 | 1.2 | Asset Library | Post-Production | Asset Library |  |  |  | 2 | 58 | 3 | 1.2.17 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.18.1 | 1.2.18 | Post Support | Post-Production | Asset Library | Post Support | Editor | Mid | 2 | 58 | 3 | 1.2.18 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.19 | 1.2 | Capture Library | Post-Production | Capture Library |  |  |  | 2 | 58 | 3 | 1.2.18 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.19.1 | 1.2.19 | Post Support | Post-Production | Capture Library | Post Support | Editor | Mid | 2 | 58 | 3 | 1.2.19 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.20 | 1.2 | Selects Deck | Post-Production | Selects Deck |  |  |  | 2 | 58 | 3 | 1.2.19 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.20.1 | 1.2.20 | Post Support | Post-Production | Selects Deck | Post Support | Editor | Mid | 2 | 58 | 3 | 1.2.20 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.21 | 1.2 | Delivery | Post-Production | Delivery |  |  |  | 5 | 63 | 0 | 1.2.20 |  |  | 185 | 925
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.21.1 | 1.2.21 | Post Support | Post-Production | Delivery | Post Support | Editor | Mid | 5 | 63 | 0 | 1.2.21 |  |  | 185 | 925
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.22 | 1.2 | Stills/Footage Selection | Post-Production | Stills/Footage Selection |  |  |  | 5 | 63 | 0 | 1.2.21 |  |  | 185 | 925
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.22.1 | 1.2.22 | Post Support | Post-Production | Stills/Footage Selection | Post Support | Editor | Mid | 5 | 63 | 0 | 1.2.22 |  |  | 185 | 925
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3 | 1 | Pre-Production | Pre-Production |  |  |  |  | 396 | 63 | 57 | 1.2 |  | Core/T2_MediumVolume | 185 | 73260
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1 | 1.3 | Wardrobe | Pre-Production | Wardrobe |  |  |  | 12 | 63 | 7 | 1.3 |  |  | 185 | 2220
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.1 | 1.3.1 | Wardrobe Brief | Pre-Production | Wardrobe | Wardrobe Brief | Art Director | Lead/Director | 3 | 63 | 2 | 1.3.1 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.2 | 1.3.1 | Internal Review & Critique | Pre-Production | Wardrobe | Internal Review & Critique | Producer | Mid | 1 | 113 | 2 | 1.3.1.1 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.3 | 1.3.1 | Client Review & Revisions | Pre-Production | Wardrobe | Client Review & Revisions | Account Manager | Mid | 3 | 115 | 3 | 1.3.1.2 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.4 | 1.3.1 | Final Packaging | Pre-Production | Wardrobe | Final Packaging | Designer | Mid | 5 | 120 | 0 | 1.3.1.3 |  |  | 185 | 925
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2 | 1.3 | Pre-Production Deck | Pre-Production | Pre-Production Deck |  |  |  | 26 | 65 | 14 | 1.3.1 |  |  | 185 | 4810
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2.1 | 1.3.2 | Content Draft | Pre-Production | Pre-Production Deck | Content Draft | Strategist | Mid | 21 | 65 | 5 | 1.3.2 |  |  | 185 | 3885
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2.2 | 1.3.2 | Deck Build | Pre-Production | Pre-Production Deck | Deck Build | Designer | Mid | 1 | 77 | 4 | 1.3.2.1 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2.3 | 1.3.2 | Internal Review & Critique | Pre-Production | Pre-Production Deck | Internal Review & Critique | Producer | Mid | 1 | 113 | 2 | 1.3.2.2 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2.4 | 1.3.2 | Client Review & Revisions | Pre-Production | Pre-Production Deck | Client Review & Revisions | Account Manager | Mid | 3 | 115 | 3 | 1.3.2.3 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3 | 1.3 | File Naming Convention & Storage | Pre-Production | File Naming Convention & Storage |  |  |  | 12 | 70 | 12 | 1.3.2 |  |  | 185 | 2220
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3.1 | 1.3.3 | Schema Design | Pre-Production | File Naming Convention & Storage | Schema Design | Media Manager / DIT | Mid | 3 | 70 | 7 | 1.3.3 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3.2 | 1.3.3 | Internal Review & Critique | Pre-Production | File Naming Convention & Storage | Internal Review & Critique | Producer | Mid | 1 | 113 | 2 | 1.3.3.1 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3.3 | 1.3.3 | Client Review & Revisions | Pre-Production | File Naming Convention & Storage | Client Review & Revisions | Account Manager | Mid | 3 | 115 | 3 | 1.3.3.2 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3.4 | 1.3.3 | Distribution & Notes | Pre-Production | File Naming Convention & Storage | Distribution & Notes | Designer | Mid | 5 | 120 | 0 | 1.3.3.3 |  |  | 185 | 925
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4 | 1.3 | R1 Pre-Production Deck/Shot List | Pre-Production | R1 Pre-Production Deck/Shot List |  |  |  | 17 | 77 | 4 | 1.3.3 |  |  | 185 | 3145
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.1 | 1.3.4 | Client Review & Revisions | Pre-Production | R1 Pre-Production Deck/Shot List | Client Review & Revisions | Producer | Mid | 17 | 77 | 4 | 1.3.4 |  |  | 185 | 3145
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5 | 1.3 | R2 Pre-Production Deck/Shot List | Pre-Production | R2 Pre-Production Deck/Shot List |  |  |  | 17 | 77 | 4 | 1.3.4 |  |  | 185 | 3145
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.1 | 1.3.5 | Client Review & Revisions | Pre-Production | R2 Pre-Production Deck/Shot List | Client Review & Revisions | Producer | Mid | 17 | 77 | 4 | 1.3.5 |  |  | 185 | 3145
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.6 | 1.3 | Run of Show & Call Sheet | Pre-Production | Run of Show & Call Sheet |  |  |  | 23 | 77 | 4 | 1.3.5 |  |  | 185 | 4255
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.6.1 | 1.3.6 | Client Review & Revisions | Pre-Production | Run of Show & Call Sheet | Client Review & Revisions | Producer | Mid | 23 | 77 | 4 | 1.3.6 |  |  | 185 | 4255
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.7 | 1.3 | Script & Storyboards | Pre-Production | Script & Storyboards |  |  |  | 31 | 77 | 4 | 1.3.6 |  |  | 185 | 5735
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.7.1 | 1.3.7 | Client Review & Revisions | Pre-Production | Script & Storyboards | Client Review & Revisions | Producer | Mid | 31 | 77 | 4 | 1.3.7 |  |  | 185 | 5735
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8 | 1.3 | Shoot Oversight & Direction | Pre-Production | Shoot Oversight & Direction |  |  |  | 12 | 77 | 6 | 1.3.7 |  |  | 185 | 2220
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8.1 | 1.3.8 | Schedule Management | Pre-Production | Shoot Oversight & Direction | Schedule Management | Producer | Mid | 3 | 77 | 4 | 1.3.8 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8.2 | 1.3.8 | Quality Check (QC) | Pre-Production | Shoot Oversight & Direction | Quality Check (QC) | QA Specialist | Mid | 2 | 93 | 2 | 1.3.8.1 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8.3 | 1.3.8 | Daily Wrap Notes | Pre-Production | Shoot Oversight & Direction | Daily Wrap Notes | Creative Director | Lead/Director | 7 | 120 | 0 | 1.3.8.2 |  |  | 185 | 1295
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.9 | 1.3 | Shot List | Pre-Production | Shot List |  |  |  | 20 | 77 | 4 | 1.3.8 |  |  | 185 | 3700
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.9.1 | 1.3.9 | Client Review & Revisions | Pre-Production | Shot List | Client Review & Revisions | Producer | Mid | 20 | 77 | 4 | 1.3.9 |  |  | 185 | 3700
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.10 | 1.3 | Storyboard Review | Pre-Production | Storyboard Review |  |  |  | 4 | 77 | 4 | 1.3.9 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.10.1 | 1.3.10 | Internal Crit | Pre-Production | Storyboard Review | Internal Crit | Art Director | Lead/Director | 4 | 77 | 4 | 1.3.10 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.11 | 1.3 | Storyboards & Script Writing | Pre-Production | Storyboards & Script Writing |  |  |  | 15 | 77 | 4 | 1.3.10 |  |  | 185 | 2775
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.11.1 | 1.3.11 | Client Review & Revisions | Pre-Production | Storyboards & Script Writing | Client Review & Revisions | Producer | Mid | 15 | 77 | 4 | 1.3.11 |  |  | 185 | 2775
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.12 | 1.3 | Casting | Pre-Production | Casting |  |  |  | 13 | 81 | 7 | 1.3.11 |  |  | 185 | 2405
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.12.1 | 1.3.12 | Approvals/Holds | Pre-Production | Casting | Approvals/Holds | Producer | Mid | 13 | 81 | 7 | 1.3.12 |  |  | 185 | 2405
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.13 | 1.3 | Load In & Pre-Lighting | Pre-Production | Load In & Pre-Lighting |  |  |  | 25 | 81 | 7 | 1.3.12 |  |  | 185 | 4625
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.13.1 | 1.3.13 | Client Review & Revisions | Pre-Production | Load In & Pre-Lighting | Client Review & Revisions | Producer | Mid | 25 | 81 | 7 | 1.3.13 |  |  | 185 | 4625
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.14 | 1.3 | Talent Casting | Pre-Production | Talent Casting |  |  |  | 25 | 81 | 7 | 1.3.13 |  |  | 185 | 4625
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.14.1 | 1.3.14 | Approvals & Holds | Pre-Production | Talent Casting | Approvals & Holds | Producer | Mid | 25 | 81 | 7 | 1.3.14 |  |  | 185 | 4625
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15 | 1.3 | Post Production Plan & Timeline | Pre-Production | Post Production Plan & Timeline |  |  |  | 21 | 88 | 10 | 1.3.14 |  |  | 185 | 3885
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15.1 | 1.3.15 | Editorial Milestones | Pre-Production | Post Production Plan & Timeline | Editorial Milestones | Editor | Mid | 10 | 88 | 5 | 1.3.15 |  |  | 185 | 1850
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15.2 | 1.3.15 | Internal Review & Critique | Pre-Production | Post Production Plan & Timeline | Internal Review & Critique | Producer | Mid | 1 | 113 | 2 | 1.3.15.1 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15.3 | 1.3.15 | Client Review & Revisions | Pre-Production | Post Production Plan & Timeline | Client Review & Revisions | Account Manager | Mid | 4 | 115 | 3 | 1.3.15.2 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15.4 | 1.3.15 | Delivery Timeline | Pre-Production | Post Production Plan & Timeline | Delivery Timeline | Producer | Mid | 6 | 120 | 0 | 1.3.15.3 |  |  | 185 | 1110
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.16 | 1.3 | Concept Development | Pre-Production | Concept Development |  |  |  | 17 | 95 | 15 | 1.3.15 |  |  | 185 | 3145
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.16.1 | 1.3.16 | Ideation Sprint | Pre-Production | Concept Development | Ideation Sprint | Designer | Mid | 12 | 95 | 10 | 1.3.16 |  |  | 185 | 2220
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.16.2 | 1.3.16 | Internal Review & Critique | Pre-Production | Concept Development | Internal Review & Critique | Producer | Mid | 2 | 113 | 2 | 1.3.16.1 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.16.3 | 1.3.16 | Client Review & Revisions | Pre-Production | Concept Development | Client Review & Revisions | Account Manager | Mid | 3 | 115 | 3 | 1.3.16.2 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.17 | 1.3 | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Pre-Production | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) |  |  |  | 10 | 105 | 8 | 1.3.16 |  |  | 185 | 1850
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.17.1 | 1.3.17 | Inventory & Tracking | Pre-Production | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Inventory & Tracking | Producer | Mid | 1 | 105 | 3 | 1.3.17 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.17.2 | 1.3.17 | Internal Review & Critique | Pre-Production | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Internal Review & Critique | Producer | Mid | 1 | 113 | 2 | 1.3.17.1 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.17.3 | 1.3.17 | Client Review & Revisions | Pre-Production | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Client Review & Revisions | Account Manager | Mid | 3 | 115 | 3 | 1.3.17.2 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.17.4 | 1.3.17 | Chain of Custody | Pre-Production | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Chain of Custody | Designer | Mid | 5 | 120 | 0 | 1.3.17.3 |  |  | 185 | 925
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.18 | 1.3 | Vendor Deal Memos & Contracts | Pre-Production | Vendor Deal Memos & Contracts |  |  |  | 3 | 105 | 3 | 1.3.17 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.18.1 | 1.3.18 | Filing & Tracking | Pre-Production | Vendor Deal Memos & Contracts | Filing & Tracking | Project Manager | Mid | 1 | 105 | 3 | 1.3.18 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.18.2 | 1.3.18 | Deal Memos & Contracts | Pre-Production | Vendor Deal Memos & Contracts | Deal Memos & Contracts | Account Manager | Mid | 2 | 120 | 0 | 1.3.18.1 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.19 | 1.3 | Vendor Engagement | Pre-Production | Vendor Engagement |  |  |  | 13 | 108 | 10 | 1.3.18 |  |  | 185 | 2405
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.19.1 | 1.3.19 | Briefing Docs | Pre-Production | Vendor Engagement | Briefing Docs | Designer | Mid | 9 | 108 | 5 | 1.3.19 |  |  | 185 | 1665
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.19.2 | 1.3.19 | Internal Review & Critique | Pre-Production | Vendor Engagement | Internal Review & Critique | Producer | Mid | 1 | 113 | 2 | 1.3.19.1 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.19.3 | 1.3.19 | Client Review & Revisions | Pre-Production | Vendor Engagement | Client Review & Revisions | Account Manager | Mid | 3 | 115 | 3 | 1.3.19.2 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.20 | 1.3 | Art Direction | Pre-Production | Art Direction |  |  |  | 19 | 113 | 5 | 1.3.19 |  |  | 185 | 3515
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.20.1 | 1.3.20 | Internal Review & Critique | Pre-Production | Art Direction | Internal Review & Critique | Producer | Mid | 1 | 113 | 2 | 1.3.20 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.20.2 | 1.3.20 | Client Review & Revisions | Pre-Production | Art Direction | Client Review & Revisions | Account Manager | Mid | 3 | 115 | 3 | 1.3.20.1 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.20.3 | 1.3.20 | Look Dev & References | Pre-Production | Art Direction | Look Dev & References | Designer | Mid | 5 | 120 | 0 | 1.3.20.2 |  |  | 185 | 925
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.20.4 | 1.3.20 | Style Guide (lite) | Pre-Production | Art Direction | Style Guide (lite) | Designer | Mid | 10 | 120 | 0 | 1.3.20.3 |  |  | 185 | 1850
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.21 | 1.3 | Concepting | Pre-Production | Concepting |  |  |  | 21 | 113 | 5 | 1.3.20 |  |  | 185 | 3885
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.21.1 | 1.3.21 | Internal Review & Critique | Pre-Production | Concepting | Internal Review & Critique | Producer | Mid | 2 | 113 | 2 | 1.3.21 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.21.2 | 1.3.21 | Client Review & Revisions | Pre-Production | Concepting | Client Review & Revisions | Account Manager | Mid | 3 | 115 | 3 | 1.3.21.1 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.21.3 | 1.3.21 | Ideation Sprint | Pre-Production | Concepting | Ideation Sprint | Strategist | Mid | 16 | 120 | 0 | 1.3.21.2 |  |  | 185 | 2960
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.22 | 1.3 | Vendor Contracting | Pre-Production | Vendor Contracting |  |  |  | 12 | 113 | 5 | 1.3.21 |  |  | 185 | 2220
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.22.1 | 1.3.22 | Internal Review & Critique | Pre-Production | Vendor Contracting | Internal Review & Critique | Producer | Mid | 1 | 113 | 2 | 1.3.22 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.22.2 | 1.3.22 | Client Review & Revisions | Pre-Production | Vendor Contracting | Client Review & Revisions | Account Manager | Mid | 4 | 115 | 3 | 1.3.22.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.22.3 | 1.3.22 | SOW/CO Draft & Negotiate | Pre-Production | Vendor Contracting | SOW/CO Draft & Negotiate | Account Manager | Mid | 7 | 120 | 0 | 1.3.22.2 |  |  | 185 | 1295
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.23 | 1.3 | Vendor Deal Memos | Pre-Production | Vendor Deal Memos |  |  |  | 10 | 113 | 5 | 1.3.22 |  |  | 185 | 1850
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.23.1 | 1.3.23 | Internal Review & Critique | Pre-Production | Vendor Deal Memos | Internal Review & Critique | Producer | Mid | 1 | 113 | 2 | 1.3.23 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.23.2 | 1.3.23 | Client Review & Revisions | Pre-Production | Vendor Deal Memos | Client Review & Revisions | Account Manager | Mid | 3 | 115 | 3 | 1.3.23.1 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.23.3 | 1.3.23 | Distribution & Confirmation | Pre-Production | Vendor Deal Memos | Distribution & Confirmation | Producer | Mid | 6 | 120 | 0 | 1.3.23.2 |  |  | 185 | 1110
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.24 | 1.3 | Vendor Pre-Production Meetings | Pre-Production | Vendor Pre-Production Meetings |  |  |  | 13 | 113 | 7 | 1.3.23 |  |  | 185 | 2405
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.24.1 | 1.3.24 | Internal Review & Critique | Pre-Production | Vendor Pre-Production Meetings | Internal Review & Critique | Producer | Mid | 1 | 113 | 2 | 1.3.24 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.24.2 | 1.3.24 | Client Review & Revisions | Pre-Production | Vendor Pre-Production Meetings | Client Review & Revisions | Account Manager | Mid | 2 | 115 | 3 | 1.3.24.1 |  |  | 185 | 370
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.24.3 | 1.3.24 | Run Meeting & Notes | Pre-Production | Vendor Pre-Production Meetings | Run Meeting & Notes | Creative Director | Lead/Director | 3 | 118 | 2 | 1.3.24.2 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.24.4 | 1.3.24 | Agenda & Materials | Pre-Production | Vendor Pre-Production Meetings | Agenda & Materials | Designer | Mid | 7 | 120 | 0 | 1.3.24.3 |  |  | 185 | 1295
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.25 | 1.3 | Pre-Interview Talent Calls | Pre-Production | Pre-Interview Talent Calls |  |  |  | 4 | 120 | 0 | 1.3.24 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.25.1 | 1.3.25 | Notes & Shareout | Pre-Production | Pre-Interview Talent Calls | Notes & Shareout | Producer | Mid | 4 | 120 | 0 | 1.3.25 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.26 | 1.3 | Wrap & File Organization | Pre-Production | Wrap & File Organization |  |  |  | 1 | 120 | 0 | 1.3.25 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.26.1 | 1.3.26 | Pre-Production Support | Pre-Production | Wrap & File Organization | Pre-Production Support | Producer | Mid | 1 | 120 | 0 | 1.3.26 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4 | 1 | Brand Identity Development | Brand Identity Development |  |  |  |  | 255 | 120 | 12 | 1.3 |  | Core/T2_MediumVolume | 185 | 47175
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1 | 1.4 | Color Palette | Brand Identity Development | Color Palette |  |  |  | 15 | 120 | 2 | 1.4 |  |  | 185 | 2775
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.1 | 1.4.1 | Client Review & Revisions | Brand Identity Development | Color Palette | Client Review & Revisions | Designer | Mid | 15 | 120 | 2 | 1.4.1 |  |  | 185 | 2775
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2 | 1.4 | Graphic Mock-Ups | Brand Identity Development | Graphic Mock-Ups |  |  |  | 25 | 122 | 8 | 1.4.1 |  |  | 185 | 4625
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.1 | 1.4.2 | Compositing/Retouch | Brand Identity Development | Graphic Mock-Ups | Compositing/Retouch | Retoucher | Mid | 4 | 122 | 3 | 1.4.2 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.2 | 1.4.2 | Internal Review & Critique | Brand Identity Development | Graphic Mock-Ups | Internal Review & Critique | Art Director | Lead/Director | 1 | 127 | 2 | 1.4.2.1 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.3 | 1.4.2 | Client Review & Revisions | Brand Identity Development | Graphic Mock-Ups | Client Review & Revisions | Account Manager | Mid | 4 | 129 | 3 | 1.4.2.2 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.4 | 1.4.2 | Mockup Scenarios (3-4) | Brand Identity Development | Graphic Mock-Ups | Mockup Scenarios (3-4) | Designer | Mid | 16 | 132 | 0 | 1.4.2.3 |  |  | 185 | 2960
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3 | 1.4 | Logo | Brand Identity Development | Logo |  |  |  | 37 | 125 | 7 | 1.4.2 |  |  | 185 | 6845
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.1 | 1.4.3 | Quality Check (Specs/Accessibility) | Brand Identity Development | Logo | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 | 125 | 2 | 1.4.3 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.2 | 1.4.3 | Internal Review & Critique | Brand Identity Development | Logo | Internal Review & Critique | Art Director | Lead/Director | 1 | 127 | 2 | 1.4.3.1 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.3 | 1.4.3 | Client Review & Revisions | Brand Identity Development | Logo | Client Review & Revisions | Account Manager | Mid | 3 | 129 | 3 | 1.4.3.2 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.4 | 1.4.3 | Logo Exploration (6-8 dirs) | Brand Identity Development | Logo | Logo Exploration (6-8 dirs) | Designer | Mid | 30 | 132 | 0 | 1.4.3.3 |  |  | 185 | 5550
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4 | 1.4 | Typography | Brand Identity Development | Typography |  |  |  | 34 | 125 | 7 | 1.4.3 |  |  | 185 | 6290
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.1 | 1.4.4 | Quality Check (Specs/Accessibility) | Brand Identity Development | Typography | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 | 125 | 2 | 1.4.4 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.2 | 1.4.4 | Internal Review & Critique | Brand Identity Development | Typography | Internal Review & Critique | Art Director | Lead/Director | 1 | 127 | 2 | 1.4.4.1 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.3 | 1.4.4 | Client Review & Revisions | Brand Identity Development | Typography | Client Review & Revisions | Account Manager | Mid | 3 | 129 | 3 | 1.4.4.2 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.4 | 1.4.4 | Final Packaging | Brand Identity Development | Typography | Final Packaging | Designer | Mid | 27 | 132 | 0 | 1.4.4.3 |  |  | 185 | 4995
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5 | 1.4 | Graphic & Copy Messaging Cornerstones | Brand Identity Development | Graphic & Copy Messaging Cornerstones |  |  |  | 23 | 127 | 5 | 1.4.4 |  |  | 185 | 4255
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.1 | 1.4.5 | Internal Review & Critique | Brand Identity Development | Graphic & Copy Messaging Cornerstones | Internal Review & Critique | Art Director | Lead/Director | 1 | 127 | 2 | 1.4.5 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.2 | 1.4.5 | Client Review & Revisions | Brand Identity Development | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Account Manager | Mid | 4 | 129 | 3 | 1.4.5.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.3 | 1.4.5 | Messaging Cornerstones Draft | Brand Identity Development | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft | Designer | Mid | 18 | 132 | 0 | 1.4.5.2 |  |  | 185 | 3330
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6 | 1.4 | Iconography | Brand Identity Development | Iconography |  |  |  | 27 | 127 | 5 | 1.4.5 |  |  | 185 | 4995
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.1 | 1.4.6 | Internal Review & Critique | Brand Identity Development | Iconography | Internal Review & Critique | Art Director | Lead/Director | 1 | 127 | 2 | 1.4.6 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.2 | 1.4.6 | Client Review & Revisions | Brand Identity Development | Iconography | Client Review & Revisions | Account Manager | Mid | 4 | 129 | 3 | 1.4.6.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.3 | 1.4.6 | Export & Spec | Brand Identity Development | Iconography | Export & Spec | Designer | Mid | 22 | 132 | 0 | 1.4.6.2 |  |  | 185 | 4070
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7 | 1.4 | Overarching Moodboard | Brand Identity Development | Overarching Moodboard |  |  |  | 23 | 127 | 5 | 1.4.6 |  |  | 185 | 4255
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.1 | 1.4.7 | Internal Review & Critique | Brand Identity Development | Overarching Moodboard | Internal Review & Critique | Art Director | Lead/Director | 1 | 127 | 2 | 1.4.7 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.2 | 1.4.7 | Client Review & Revisions | Brand Identity Development | Overarching Moodboard | Client Review & Revisions | Account Manager | Mid | 4 | 129 | 3 | 1.4.7.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.3 | 1.4.7 | Curate Moodboard | Brand Identity Development | Overarching Moodboard | Curate Moodboard | Designer | Mid | 18 | 132 | 0 | 1.4.7.2 |  |  | 185 | 3330
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8 | 1.4 | Tagline Copy Bank | Brand Identity Development | Tagline Copy Bank |  |  |  | 18 | 127 | 5 | 1.4.7 |  |  | 185 | 3330
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.1 | 1.4.8 | Internal Review & Critique | Brand Identity Development | Tagline Copy Bank | Internal Review & Critique | Art Director | Lead/Director | 1 | 127 | 2 | 1.4.8 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.2 | 1.4.8 | Client Review & Revisions | Brand Identity Development | Tagline Copy Bank | Client Review & Revisions | Account Manager | Mid | 4 | 129 | 3 | 1.4.8.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.3 | 1.4.8 | Shortlist & Rationale | Brand Identity Development | Tagline Copy Bank | Shortlist & Rationale | Designer | Mid | 13 | 132 | 0 | 1.4.8.2 |  |  | 185 | 2405
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9 | 1.4 | Textures/Patterns/Materials | Brand Identity Development | Textures/Patterns/Materials |  |  |  | 25 | 127 | 5 | 1.4.8 |  |  | 185 | 4625
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.1 | 1.4.9 | Internal Review & Critique | Brand Identity Development | Textures/Patterns/Materials | Internal Review & Critique | Art Director | Lead/Director | 1 | 127 | 2 | 1.4.9 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.2 | 1.4.9 | Client Review & Revisions | Brand Identity Development | Textures/Patterns/Materials | Client Review & Revisions | Account Manager | Mid | 4 | 129 | 3 | 1.4.9.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.3 | 1.4.9 | Build Repeating Tiles | Brand Identity Development | Textures/Patterns/Materials | Build Repeating Tiles | Designer | Mid | 20 | 132 | 0 | 1.4.9.2 |  |  | 185 | 3700
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10 | 1.4 | Visual Elements/Comps | Brand Identity Development | Visual Elements/Comps |  |  |  | 28 | 127 | 5 | 1.4.9 |  |  | 185 | 5180
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10.1 | 1.4.10 | Internal Review & Critique | Brand Identity Development | Visual Elements/Comps | Internal Review & Critique | Art Director | Lead/Director | 1 | 127 | 2 | 1.4.10 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10.2 | 1.4.10 | Client Review & Revisions | Brand Identity Development | Visual Elements/Comps | Client Review & Revisions | Account Manager | Mid | 4 | 129 | 3 | 1.4.10.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10.3 | 1.4.10 | Compositions (2-3) | Brand Identity Development | Visual Elements/Comps | Compositions (2-3) | Designer | Mid | 23 | 132 | 0 | 1.4.10.2 |  |  | 185 | 4255
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5 | 1 | Brand Style & Usage Guidelines | Brand Style & Usage Guidelines |  |  |  |  | 250 | 132 | 9 | 1.4 |  | Core/T2_MediumVolume | 185 | 46250
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.1 | 1.5 | Color Palettes | Brand Style & Usage Guidelines | Color Palettes |  |  |  | 13 | 132 | 2 | 1.5 |  |  | 185 | 2405
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.1.1 | 1.5.1 | Client Review & Revisions | Brand Style & Usage Guidelines | Color Palettes | Client Review & Revisions | Designer | Mid | 13 | 132 | 2 | 1.5.1 |  |  | 185 | 2405
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2 | 1.5 | Logo Lock-Ups | Brand Style & Usage Guidelines | Logo Lock-Ups |  |  |  | 28 | 134 | 7 | 1.5.1 |  |  | 185 | 5180
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.1 | 1.5.2 | Quality Check (Specs/Accessibility) | Brand Style & Usage Guidelines | Logo Lock-Ups | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 | 134 | 2 | 1.5.2 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.2 | 1.5.2 | Internal Review & Critique | Brand Style & Usage Guidelines | Logo Lock-Ups | Internal Review & Critique | Art Director | Lead/Director | 1 | 136 | 2 | 1.5.2.1 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.3 | 1.5.2 | Client Review & Revisions | Brand Style & Usage Guidelines | Logo Lock-Ups | Client Review & Revisions | Account Manager | Mid | 3 | 138 | 3 | 1.5.2.2 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.4 | 1.5.2 | Final Packaging | Brand Style & Usage Guidelines | Logo Lock-Ups | Final Packaging | Designer | Mid | 21 | 141 | 0 | 1.5.2.3 |  |  | 185 | 3885
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3 | 1.5 | Logo Placement | Brand Style & Usage Guidelines | Logo Placement |  |  |  | 27 | 134 | 7 | 1.5.2 |  |  | 185 | 4995
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.1 | 1.5.3 | Quality Check (Specs/Accessibility) | Brand Style & Usage Guidelines | Logo Placement | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 | 134 | 2 | 1.5.3 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.2 | 1.5.3 | Internal Review & Critique | Brand Style & Usage Guidelines | Logo Placement | Internal Review & Critique | Art Director | Lead/Director | 1 | 136 | 2 | 1.5.3.1 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.3 | 1.5.3 | Client Review & Revisions | Brand Style & Usage Guidelines | Logo Placement | Client Review & Revisions | Account Manager | Mid | 3 | 138 | 3 | 1.5.3.2 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.4 | 1.5.3 | Final Packaging | Brand Style & Usage Guidelines | Logo Placement | Final Packaging | Designer | Mid | 20 | 141 | 0 | 1.5.3.3 |  |  | 185 | 3700
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4 | 1.5 | Brand Do's & Dont's | Brand Style & Usage Guidelines | Brand Do's & Dont's |  |  |  | 33 | 136 | 5 | 1.5.3 |  |  | 185 | 6105
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.1 | 1.5.4 | Internal Review & Critique | Brand Style & Usage Guidelines | Brand Do's & Dont's | Internal Review & Critique | Art Director | Lead/Director | 1 | 136 | 2 | 1.5.4 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.2 | 1.5.4 | Client Review & Revisions | Brand Style & Usage Guidelines | Brand Do's & Dont's | Client Review & Revisions | Account Manager | Mid | 4 | 138 | 3 | 1.5.4.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.3 | 1.5.4 | Outline & Examples | Brand Style & Usage Guidelines | Brand Do's & Dont's | Outline & Examples | Designer | Mid | 28 | 141 | 0 | 1.5.4.2 |  |  | 185 | 5180
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5 | 1.5 | Design Style Tile | Brand Style & Usage Guidelines | Design Style Tile |  |  |  | 23 | 136 | 5 | 1.5.4 |  |  | 185 | 4255
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.1 | 1.5.5 | Internal Review & Critique | Brand Style & Usage Guidelines | Design Style Tile | Internal Review & Critique | Art Director | Lead/Director | 1 | 136 | 2 | 1.5.5 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.2 | 1.5.5 | Client Review & Revisions | Brand Style & Usage Guidelines | Design Style Tile | Client Review & Revisions | Account Manager | Mid | 4 | 138 | 3 | 1.5.5.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.3 | 1.5.5 | Style Tile Build | Brand Style & Usage Guidelines | Design Style Tile | Style Tile Build | Designer | Mid | 18 | 141 | 0 | 1.5.5.2 |  |  | 185 | 3330
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6 | 1.5 | Image Use Guidance | Brand Style & Usage Guidelines | Image Use Guidance |  |  |  | 23 | 136 | 5 | 1.5.5 |  |  | 185 | 4255
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.1 | 1.5.6 | Internal Review & Critique | Brand Style & Usage Guidelines | Image Use Guidance | Internal Review & Critique | Art Director | Lead/Director | 1 | 136 | 2 | 1.5.6 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.2 | 1.5.6 | Client Review & Revisions | Brand Style & Usage Guidelines | Image Use Guidance | Client Review & Revisions | Account Manager | Mid | 4 | 138 | 3 | 1.5.6.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.3 | 1.5.6 | Examples & Callouts | Brand Style & Usage Guidelines | Image Use Guidance | Examples & Callouts | Designer | Mid | 18 | 141 | 0 | 1.5.6.2 |  |  | 185 | 3330
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7 | 1.5 | Imagery Style | Brand Style & Usage Guidelines | Imagery Style |  |  |  | 23 | 136 | 5 | 1.5.6 |  |  | 185 | 4255
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.1 | 1.5.7 | Internal Review & Critique | Brand Style & Usage Guidelines | Imagery Style | Internal Review & Critique | Art Director | Lead/Director | 1 | 136 | 2 | 1.5.7 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.2 | 1.5.7 | Client Review & Revisions | Brand Style & Usage Guidelines | Imagery Style | Client Review & Revisions | Account Manager | Mid | 4 | 138 | 3 | 1.5.7.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.3 | 1.5.7 | Examples & Callouts | Brand Style & Usage Guidelines | Imagery Style | Examples & Callouts | Designer | Mid | 18 | 141 | 0 | 1.5.7.2 |  |  | 185 | 3330
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8 | 1.5 | Photo & Video Direction | Brand Style & Usage Guidelines | Photo & Video Direction |  |  |  | 25 | 136 | 5 | 1.5.7 |  |  | 185 | 4625
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.1 | 1.5.8 | Internal Review & Critique | Brand Style & Usage Guidelines | Photo & Video Direction | Internal Review & Critique | Art Director | Lead/Director | 1 | 136 | 2 | 1.5.8 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.2 | 1.5.8 | Client Review & Revisions | Brand Style & Usage Guidelines | Photo & Video Direction | Client Review & Revisions | Account Manager | Mid | 4 | 138 | 3 | 1.5.8.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.3 | 1.5.8 | Direction Pages | Brand Style & Usage Guidelines | Photo & Video Direction | Direction Pages | Designer | Mid | 20 | 141 | 0 | 1.5.8.2 |  |  | 185 | 3700
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9 | 1.5 | Typography | Brand Style & Usage Guidelines | Typography |  |  |  | 18 | 136 | 5 | 1.5.8 |  |  | 185 | 3330
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.1 | 1.5.9 | Internal Review & Critique | Brand Style & Usage Guidelines | Typography | Internal Review & Critique | Art Director | Lead/Director | 1 | 136 | 2 | 1.5.9 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.2 | 1.5.9 | Client Review & Revisions | Brand Style & Usage Guidelines | Typography | Client Review & Revisions | Account Manager | Mid | 3 | 138 | 3 | 1.5.9.1 |  |  | 185 | 555
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.3 | 1.5.9 | Final Packaging | Brand Style & Usage Guidelines | Typography | Final Packaging | Designer | Mid | 14 | 141 | 0 | 1.5.9.2 |  |  | 185 | 2590
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10 | 1.5 | Use Cases | Brand Style & Usage Guidelines | Use Cases |  |  |  | 22 | 136 | 5 | 1.5.9 |  |  | 185 | 4070
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.1 | 1.5.10 | Internal Review & Critique | Brand Style & Usage Guidelines | Use Cases | Internal Review & Critique | Art Director | Lead/Director | 1 | 136 | 2 | 1.5.10 |  |  | 185 | 185
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.2 | 1.5.10 | Client Review & Revisions | Brand Style & Usage Guidelines | Use Cases | Client Review & Revisions | Account Manager | Mid | 4 | 138 | 3 | 1.5.10.1 |  |  | 185 | 740
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.3 | 1.5.10 | Final Packaging | Brand Style & Usage Guidelines | Use Cases | Final Packaging | Designer | Mid | 17 | 141 | 0 | 1.5.10.2 |  |  | 185 | 3145
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.11 | 1.5 | Graphic Treatment Direction | Brand Style & Usage Guidelines | Graphic Treatment Direction |  |  |  | 15 | 141 | 0 | 1.5.10 |  |  | 185 | 2775
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.11.1 | 1.5.11 | Client Review & Revisions | Brand Style & Usage Guidelines | Graphic Treatment Direction | Client Review & Revisions | Creative Director | Lead/Director | 15 | 141 | 0 | 1.5.11 |  |  | 185 | 2775