## Sheet1
Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Deliverable | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes
Vascano Tequila - RFP Creative Services 2022 8 | 1.1 | 1 | Development | Development |  |  |  |  | 227.29 | 0 | 22 |  |  | Core / T2_MediumVolume
Vascano Tequila - RFP Creative Services 2022 8 | 1.1.1 | 1.1 | research | Development |  | research |  |  |  |  | 3
Vascano Tequila - RFP Creative Services 2022 8 | 1.1.2 | 1.1 | design_prod | Development |  | design_prod |  |  |  |  | 7
Vascano Tequila - RFP Creative Services 2022 8 | 1.1.3 | 1.1 | qa | Development |  | qa |  |  |  |  | 2
Vascano Tequila - RFP Creative Services 2022 8 | 1.1.4 | 1.1 | development | Development |  | development |  |  |  |  | 10
Vascano Tequila - RFP Creative Services 2022 8 | 1.2 | 1 | Brand Style & Usage Guidelines | Brand Style & Usage Guidelines |  |  |  |  | 249.8 | 0 | 9 |  |  | Core / T2_MediumVolume
Vascano Tequila - RFP Creative Services 2022 8 | 1.2.1 | 1.2 | color | Brand Style & Usage Guidelines |  | color |  |  |  |  | 2
Vascano Tequila - RFP Creative Services 2022 8 | 1.2.2 | 1.2 | qa | Brand Style & Usage Guidelines |  | qa |  |  |  |  | 2
Vascano Tequila - RFP Creative Services 2022 8 | 1.2.3 | 1.2 | internal_review | Brand Style & Usage Guidelines |  | internal_review |  |  |  |  | 2
Vascano Tequila - RFP Creative Services 2022 8 | 1.2.4 | 1.2 | client_review | Brand Style & Usage Guidelines |  | client_review |  |  |  |  | 3
Vascano Tequila - RFP Creative Services 2022 8 | 1.2.5 | 1.2 | brand_identity | Brand Style & Usage Guidelines |  | brand_identity |  |  |  |  | 0
Vascano Tequila - RFP Creative Services 2022 8 | 1.2.6 | 1.2 | style_guide | Brand Style & Usage Guidelines |  | style_guide |  |  |  |  | 0
Vascano Tequila - RFP Creative Services 2022 8 | 1.2.7 | 1.2 | treatment | Brand Style & Usage Guidelines |  | treatment |  |  |  |  | 0
Vascano Tequila - RFP Creative Services 2022 8 | 1.3 | 1 | Post-Production | Post-Production |  |  |  |  | 188.33 | 0 | 41 |  |  | Core / T2_MediumVolume
Vascano Tequila - RFP Creative Services 2022 8 | 1.3.1 | 1.3 | research | Post-Production |  | research |  |  |  |  | 3
Vascano Tequila - RFP Creative Services 2022 8 | 1.3.2 | 1.3 | prepro_docs | Post-Production |  | prepro_docs |  |  |  |  | 4
Vascano Tequila - RFP Creative Services 2022 8 | 1.3.3 | 1.3 | edit | Post-Production |  | edit |  |  |  |  | 5
Vascano Tequila - RFP Creative Services 2022 8 | 1.3.4 | 1.3 | motion | Post-Production |  | motion |  |  |  |  | 7
Vascano Tequila - RFP Creative Services 2022 8 | 1.3.5 | 1.3 | color | Post-Production |  | color |  |  |  |  | 2
Vascano Tequila - RFP Creative Services 2022 8 | 1.3.6 | 1.3 | retouch | Post-Production |  | retouch |  |  |  |  | 3
Vascano Tequila - RFP Creative Services 2022 8 | 1.3.7 | 1.3 | sound | Post-Production |  | sound |  |  |  |  | 2
Vascano Tequila - RFP Creative Services 2022 8 | 1.3.8 | 1.3 | qa | Post-Production |  | qa |  |  |  |  | 2
Vascano Tequila - RFP Creative Services 2022 8 | 1.3.9 | 1.3 | analytics_tagging | Post-Production |  | analytics_tagging |  |  |  |  | 3
Vascano Tequila - RFP Creative Services 2022 8 | 1.3.10 | 1.3 | internal_review | Post-Production |  | internal_review |  |  |  |  | 2
Vascano Tequila - RFP Creative Services 2022 8 | 1.3.11 | 1.3 | client_review | Post-Production |  | client_review |  |  |  |  | 3
Vascano Tequila - RFP Creative Services 2022 8 | 1.3.12 | 1.3 | library | Post-Production |  | library |  |  |  |  | 3
Vascano Tequila - RFP Creative Services 2022 8 | 1.3.13 | 1.3 | notes_triage | Post-Production |  | notes_triage |  |  |  |  | 2
Vascano Tequila - RFP Creative Services 2022 8 | 1.3.14 | 1.3 | general | Post-Production |  | general |  |  |  |  | 0
Vascano Tequila - RFP Creative Services 2022 8 | 1.4 | 1 | Brand Identity Development | Brand Identity Development |  |  |  |  | 255.36 | 0 | 12 |  |  | Core / T2_MediumVolume
Vascano Tequila - RFP Creative Services 2022 8 | 1.4.1 | 1.4 | color | Brand Identity Development |  | color |  |  |  |  | 2
Vascano Tequila - RFP Creative Services 2022 8 | 1.4.2 | 1.4 | retouch | Brand Identity Development |  | retouch |  |  |  |  | 3
Vascano Tequila - RFP Creative Services 2022 8 | 1.4.3 | 1.4 | qa | Brand Identity Development |  | qa |  |  |  |  | 2
Vascano Tequila - RFP Creative Services 2022 8 | 1.4.4 | 1.4 | internal_review | Brand Identity Development |  | internal_review |  |  |  |  | 2
Vascano Tequila - RFP Creative Services 2022 8 | 1.4.5 | 1.4 | client_review | Brand Identity Development |  | client_review |  |  |  |  | 3
Vascano Tequila - RFP Creative Services 2022 8 | 1.4.6 | 1.4 | brand_identity | Brand Identity Development |  | brand_identity |  |  |  |  | 0
Vascano Tequila - RFP Creative Services 2022 8 | 1.5 | 1 | Pre-Production | Pre-Production |  |  |  |  | 395.65 | 0 | 57 |  |  | Core / T2_MediumVolume
Vascano Tequila - RFP Creative Services 2022 8 | 1.5.1 | 1.5 | brief | Pre-Production |  | brief |  |  |  |  | 2
Vascano Tequila - RFP Creative Services 2022 8 | 1.5.2 | 1.5 | deck_build | Pre-Production |  | deck_build |  |  |  |  | 5
Vascano Tequila - RFP Creative Services 2022 8 | 1.5.3 | 1.5 | design_prod | Pre-Production |  | design_prod |  |  |  |  | 7
Vascano Tequila - RFP Creative Services 2022 8 | 1.5.4 | 1.5 | prepro_docs | Pre-Production |  | prepro_docs |  |  |  |  | 4
Vascano Tequila - RFP Creative Services 2022 8 | 1.5.5 | 1.5 | prepro_coord | Pre-Production |  | prepro_coord |  |  |  |  | 7
Vascano Tequila - RFP Creative Services 2022 8 | 1.5.6 | 1.5 | edit | Pre-Production |  | edit |  |  |  |  | 5
Vascano Tequila - RFP Creative Services 2022 8 | 1.5.7 | 1.5 | qa | Pre-Production |  | qa |  |  |  |  | 2
Vascano Tequila - RFP Creative Services 2022 8 | 1.5.8 | 1.5 | development | Pre-Production |  | development |  |  |  |  | 10
Vascano Tequila - RFP Creative Services 2022 8 | 1.5.9 | 1.5 | analytics_tagging | Pre-Production |  | analytics_tagging |  |  |  |  | 3
Vascano Tequila - RFP Creative Services 2022 8 | 1.5.10 | 1.5 | community_mgmt | Pre-Production |  | community_mgmt |  |  |  |  | 5
Vascano Tequila - RFP Creative Services 2022 8 | 1.5.11 | 1.5 | internal_review | Pre-Production |  | internal_review |  |  |  |  | 2
Vascano Tequila - RFP Creative Services 2022 8 | 1.5.12 | 1.5 | client_review | Pre-Production |  | client_review |  |  |  |  | 3
Vascano Tequila - RFP Creative Services 2022 8 | 1.5.13 | 1.5 | status_meeting | Pre-Production |  | status_meeting |  |  |  |  | 2
Vascano Tequila - RFP Creative Services 2022 8 | 1.5.14 | 1.5 | general | Pre-Production |  | general |  |  |  |  | 0
Vascano Tequila - RFP Creative Services 2022 8 | 1.5.15 | 1.5 | style_guide | Pre-Production |  | style_guide |  |  |  |  | 0