## Sheet1
Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Deliverable | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes | Service_Department | Rate_USD | Price_USD
RFP_Brief_ First on SoundCloud 2021 Campaign | 1 |  | RFP_Brief_ First on SoundCloud 2021 Campaign |  | Project |  |  |  | 0 | 0 | [5 empty] | 0 | 0
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1 | 1 | Development | Development |  |  |  |  | 227 | 0 | 22 |  |  | Core/T2_MediumVolume |  | 195 | 44265
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1 | 1.1 | ADA Compliance | Development | ADA Compliance |  |  |  | 50 | 0 | 15 | 1.1 |  |  |  | 195 | 9750
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.1 | 1.1.1 | Accessibility Audit | Development | ADA Compliance | Accessibility Audit | Accessibility Specialist | Mid | 2 | 0 | 3 | 1.1.1 |  |  |  | 195 | 390
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.2 | 1.1.1 | Accessibility QA | Development | ADA Compliance | Accessibility QA | QA Engineer | Mid | 4 | 10 | 2 | 1.1.1.1 |  |  |  | 195 | 780
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.1.3 | 1.1.1 | Code Review | Development | ADA Compliance | Code Review | Frontend Engineer | Mid | 44 | 12 | 10 | 1.1.1.2 |  |  |  | 195 | 8580
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2 | 1.1 | Audit & Requirement gathering | Development | Audit & Requirement gathering |  |  |  | 17 | 0 | 3 | 1.1.1 |  |  |  | 195 | 3315
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.2.1 | 1.1.2 | Analytics Audit | Development | Audit & Requirement gathering | Analytics Audit | Business Analyst | Mid | 17 | 0 | 3 | 1.1.2 |  |  |  | 195 | 3315
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3 | 1.1 | Audit existing UA Property | Development | Audit existing UA Property |  |  |  | 17 | 0 | 3 | 1.1.2 |  |  |  | 195 | 3315
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.3.1 | 1.1.3 | Documentation | Development | Audit existing UA Property | Documentation | Business Analyst | Mid | 17 | 0 | 3 | 1.1.3 |  |  |  | 195 | 3315
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4 | 1.1 | Footer CTA | Development | Footer CTA |  |  |  | 43 | 3 | 19 | 1.1.3 |  |  |  | 195 | 8385
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.1 | 1.1.4 | Design Consult | Development | Footer CTA | Design Consult | UI Designer | Mid | 3 | 3 | 7 | 1.1.4 |  |  |  | 195 | 585
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.2 | 1.1.4 | Accessibility QA | Development | Footer CTA | Accessibility QA | QA Engineer | Mid | 6 | 10 | 2 | 1.1.4.1 |  |  |  | 195 | 1170
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.4.3 | 1.1.4 | Code Review | Development | Footer CTA | Code Review | Backend Engineer | Mid | 34 | 12 | 10 | 1.1.4.2 |  |  |  | 195 | 6630
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5 | 1.1 | Header & Footer Navigation | Development | Header & Footer Navigation |  |  |  | 43 | 3 | 19 | 1.1.4 |  |  |  | 195 | 8385
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.1 | 1.1.5 | Design Consult | Development | Header & Footer Navigation | Design Consult | UI Designer | Mid | 3 | 3 | 7 | 1.1.5 |  |  |  | 195 | 585
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.2 | 1.1.5 | Accessibility QA | Development | Header & Footer Navigation | Accessibility QA | QA Engineer | Mid | 6 | 10 | 2 | 1.1.5.1 |  |  |  | 195 | 1170
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.5.3 | 1.1.5 | Code Review | Development | Header & Footer Navigation | Code Review | Backend Engineer | Mid | 34 | 12 | 10 | 1.1.5.2 |  |  |  | 195 | 6630
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6 | 1.1 | Additional Goals Setup | Development | Additional Goals Setup |  |  |  | 7 | 10 | 12 | 1.1.5 |  |  |  | 195 | 1365
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.1 | 1.1.6 | QA Cycle | Development | Additional Goals Setup | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.6 |  |  |  | 195 | 585
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.6.2 | 1.1.6 | Define & Configure Goals | Development | Additional Goals Setup | Define & Configure Goals | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.6.1 |  |  |  | 195 | 780
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.7 | 1.1 | Custom Event Tracking | Development | Custom Event Tracking |  |  |  | 7 | 10 | 12 | 1.1.6 |  |  |  | 195 | 1365
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.7.1 | 1.1.7 | QA Cycle | Development | Custom Event Tracking | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.7 |  |  |  | 195 | 585
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.7.2 | 1.1.7 | Event Schema & Tagging | Development | Custom Event Tracking | Event Schema & Tagging | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.7.1 |  |  |  | 195 | 780
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.8 | 1.1 | Implement Paid Media Pixel on website w GTM-Google Ads | Development | Implement Paid Media Pixel on website w GTM-Google Ads |  |  |  | 5 | 10 | 12 | 1.1.7 |  |  |  | 195 | 975
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.8.1 | 1.1.8 | Spec QA | Development | Implement Paid Media Pixel on website w GTM-Google Ads | Spec QA | QA Engineer | Mid | 3 | 10 | 2 | 1.1.8 |  |  |  | 195 | 585
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.8.2 | 1.1.8 | Pixel Setup (GTM) | Development | Implement Paid Media Pixel on website w GTM-Google Ads | Pixel Setup (GTM) | Data/Analytics Engineer | Mid | 2 | 12 | 10 | 1.1.8.1 |  |  |  | 195 | 390
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.9 | 1.1 | Implement goals listed in UA as Conversions in G4 | Development | Implement goals listed in UA as Conversions in G4 |  |  |  | 7 | 10 | 12 | 1.1.8 |  |  |  | 195 | 1365
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.9.1 | 1.1.9 | QA Cycle | Development | Implement goals listed in UA as Conversions in G4 | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.9 |  |  |  | 195 | 585
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.9.2 | 1.1.9 | Migrate UA Goals → GA4 Conversions | Development | Implement goals listed in UA as Conversions in G4 | Migrate UA Goals → GA4 Conversions | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.9.1 |  |  |  | 195 | 780
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.10 | 1.1 | Implementation | Development | Implementation |  |  |  | 7 | 10 | 12 | 1.1.9 |  |  |  | 195 | 1365
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.10.1 | 1.1.10 | QA Cycle | Development | Implementation | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.10 |  |  |  | 195 | 585
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.10.2 | 1.1.10 | Implement Tags/Events | Development | Implementation | Implement Tags/Events | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.10.1 |  |  |  | 195 | 780
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.11 | 1.1 | Outbound link clicks | Development | Outbound link clicks |  |  |  | 5 | 10 | 12 | 1.1.10 |  |  |  | 195 | 975
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.11.1 | 1.1.11 | QA | Development | Outbound link clicks | QA | QA Engineer | Mid | 3 | 10 | 2 | 1.1.11 |  |  |  | 195 | 585
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.11.2 | 1.1.11 | Event Config | Development | Outbound link clicks | Event Config | Data/Analytics Engineer | Mid | 2 | 12 | 10 | 1.1.11.1 |  |  |  | 195 | 390
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.12 | 1.1 | Publishing tags, Testing and Auditing | Development | Publishing tags, Testing and Auditing |  |  |  | 4 | 10 | 2 | 1.1.11 |  |  |  | 195 | 780
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.12.1 | 1.1.12 | Publish & Smoke Test | Development | Publishing tags, Testing and Auditing | Publish & Smoke Test | QA Engineer | Mid | 4 | 10 | 2 | 1.1.12 |  |  |  | 195 | 780
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.13 | 1.1 | Setup cross-domain tracking | Development | Setup cross-domain tracking |  |  |  | 4 | 10 | 12 | 1.1.12 |  |  |  | 195 | 780
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.13.1 | 1.1.13 | QA | Development | Setup cross-domain tracking | QA | QA Engineer | Mid | 2 | 10 | 2 | 1.1.13 |  |  |  | 195 | 390
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.13.2 | 1.1.13 | Cross-domain Config | Development | Setup cross-domain tracking | Cross-domain Config | Data/Analytics Engineer | Mid | 2 | 12 | 10 | 1.1.13.1 |  |  |  | 195 | 390
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.14 | 1.1 | Setup eCommerce tracking | Development | Setup eCommerce tracking |  |  |  | 4 | 10 | 12 | 1.1.13 |  |  |  | 195 | 780
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.14.1 | 1.1.14 | QA | Development | Setup eCommerce tracking | QA | QA Engineer | Mid | 2 | 10 | 2 | 1.1.14 |  |  |  | 195 | 390
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.14.2 | 1.1.14 | Ecommerce Data Layer | Development | Setup eCommerce tracking | Ecommerce Data Layer | Data/Analytics Engineer | Mid | 2 | 12 | 10 | 1.1.14.1 |  |  |  | 195 | 390
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.15 | 1.1 | Setup new GA4 acct for Caledera House | Development | Setup new GA4 acct for Caledera House |  |  |  | 7 | 10 | 12 | 1.1.14 |  |  |  | 195 | 1365
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.15.1 | 1.1.15 | QA Cycle | Development | Setup new GA4 acct for Caledera House | QA Cycle | QA Engineer | Mid | 3 | 10 | 2 | 1.1.15 |  |  |  | 195 | 585
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.1.15.2 | 1.1.15 | GA4 Property Setup | Development | Setup new GA4 acct for Caledera House | GA4 Property Setup | Data/Analytics Engineer | Mid | 4 | 12 | 10 | 1.1.15.1 |  |  |  | 195 | 780
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2 | 1 | Post-Production | Post-Production |  |  |  |  | 188 | 22 | 41 | 1.1 |  | Core/T2_MediumVolume |  | 195 | 36660
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1 | 1.2 | Content Licensing / Art Buying | Post-Production | Content Licensing / Art Buying |  |  |  | 2 | 22 | 3 | 1.2 |  |  |  | 195 | 390
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.1 | 1.2.1 | Rights/License Research | Post-Production | Content Licensing / Art Buying | Rights/License Research | Producer | Mid | 1 | 22 | 3 | 1.2.1 |  |  |  | 195 | 195
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.1.2 | 1.2.1 | Usage Notes | Post-Production | Content Licensing / Art Buying | Usage Notes | Account Manager | Mid | 1 | 63 | 0 | 1.2.1.1 |  |  |  | 195 | 195
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2 | 1.2 | VO Recording Sessions | Post-Production | VO Recording Sessions |  |  |  | 5 | 25 | 4 | 1.2.1 |  |  |  | 195 | 975
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.1 | 1.2.2 | Script Polish | Post-Production | VO Recording Sessions | Script Polish | Copywriter | Mid | 1 | 25 | 4 | 1.2.2 |  |  |  | 195 | 195
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.2.2 | 1.2.2 | VO Session | Post-Production | VO Recording Sessions | VO Session | Sound Designer | Mid | 4 | 63 | 0 | 1.2.2.1 |  |  |  | 195 | 780
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3 | 1.2 | Editing | Post-Production | Editing |  |  |  | 17 | 29 | 5 | 1.2.2 |  |  |  | 195 | 3315
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.3.1 | 1.2.3 | Client Review & Revisions | Post-Production | Editing | Client Review & Revisions | Editor | Mid | 17 | 29 | 5 | 1.2.3 |  |  |  | 195 | 3315
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4 | 1.2 | Video Editing | Post-Production | Video Editing |  |  |  | 25 | 29 | 5 | 1.2.3 |  |  |  | 195 | 4875
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.4.1 | 1.2.4 | Client Review & Revisions | Post-Production | Video Editing | Client Review & Revisions | Editor | Mid | 25 | 29 | 5 | 1.2.4 |  |  |  | 195 | 4875
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5 | 1.2 | Voice Over | Post-Production | Voice Over |  |  |  | 17 | 29 | 12 | 1.2.4 |  |  |  | 195 | 3315
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.1 | 1.2.5 | VO Edit | Post-Production | Voice Over | VO Edit | Editor | Mid | 9 | 29 | 5 | 1.2.5 |  |  |  | 195 | 1755
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.2 | 1.2.5 | Mix | Post-Production | Voice Over | Mix | Sound Designer | Mid | 2 | 46 | 2 | 1.2.5.1 |  |  |  | 195 | 390
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.3 | 1.2.5 | Internal Review & Critique | Post-Production | Voice Over | Internal Review & Critique | Producer | Mid | 1 | 53 | 2 | 1.2.5.2 |  |  |  | 195 | 195
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.4 | 1.2.5 | Client Review & Revisions | Post-Production | Voice Over | Client Review & Revisions | Account Manager | Mid | 3 | 55 | 3 | 1.2.5.3 |  |  |  | 195 | 585
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.5.5 | 1.2.5 | Final Packaging | Post-Production | Voice Over | Final Packaging | Designer | Mid | 2 | 63 | 0 | 1.2.5.4 |  |  |  | 195 | 390
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.6 | 1.2 | Motion Design/VFX | Post-Production | Motion Design/VFX |  |  |  | 17 | 34 | 7 | 1.2.5 |  |  |  | 195 | 3315
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.6.1 | 1.2.6 | Client Review & Revisions | Post-Production | Motion Design/VFX | Client Review & Revisions | Editor | Mid | 17 | 34 | 7 | 1.2.6 |  |  |  | 195 | 3315
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.7 | 1.2 | Color Correction | Post-Production | Color Correction |  |  |  | 11 | 41 | 2 | 1.2.6 |  |  |  | 195 | 2145
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.7.1 | 1.2.7 | Client Review & Revisions | Post-Production | Color Correction | Client Review & Revisions | Colorist | Mid | 11 | 41 | 2 | 1.2.7 |  |  |  | 195 | 2145
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.8 | 1.2 | Color Grading | Post-Production | Color Grading |  |  |  | 11 | 41 | 2 | 1.2.7 |  |  |  | 195 | 2145
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.8.1 | 1.2.8 | Client Review & Revisions | Post-Production | Color Grading | Client Review & Revisions | Colorist | Mid | 11 | 41 | 2 | 1.2.8 |  |  |  | 195 | 2145
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9 | 1.2 | Final Retouched Stills Review | Post-Production | Final Retouched Stills Review |  |  |  | 10 | 43 | 8 | 1.2.8 |  |  |  | 195 | 1950
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.1 | 1.2.9 | Retouch | Post-Production | Final Retouched Stills Review | Retouch | Retoucher | Mid | 4 | 43 | 3 | 1.2.9 |  |  |  | 195 | 780
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.2 | 1.2.9 | Internal Review & Critique | Post-Production | Final Retouched Stills Review | Internal Review & Critique | Producer | Mid | 1 | 53 | 2 | 1.2.9.1 |  |  |  | 195 | 195
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.3 | 1.2.9 | Client Review & Revisions | Post-Production | Final Retouched Stills Review | Client Review & Revisions | Account Manager | Mid | 3 | 55 | 3 | 1.2.9.2 |  |  |  | 195 | 585
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.9.4 | 1.2.9 | Final Packaging | Post-Production | Final Retouched Stills Review | Final Packaging | Designer | Mid | 2 | 63 | 0 | 1.2.9.3 |  |  |  | 195 | 390
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10 | 1.2 | Retouching | Post-Production | Retouching |  |  |  | 10 | 43 | 8 | 1.2.9 |  |  |  | 195 | 1950
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.1 | 1.2.10 | Retouch | Post-Production | Retouching | Retouch | Retoucher | Mid | 4 | 43 | 3 | 1.2.10 |  |  |  | 195 | 780
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.2 | 1.2.10 | Internal Review & Critique | Post-Production | Retouching | Internal Review & Critique | Producer | Mid | 1 | 53 | 2 | 1.2.10.1 |  |  |  | 195 | 195
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.3 | 1.2.10 | Client Review & Revisions | Post-Production | Retouching | Client Review & Revisions | Account Manager | Mid | 3 | 55 | 3 | 1.2.10.2 |  |  |  | 195 | 585
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.10.4 | 1.2.10 | Final Packaging | Post-Production | Retouching | Final Packaging | Designer | Mid | 2 | 63 | 0 | 1.2.10.3 |  |  |  | 195 | 390
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.11 | 1.2 | Sound Mix | Post-Production | Sound Mix |  |  |  | 9 | 46 | 2 | 1.2.10 |  |  |  | 195 | 1755
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.11.1 | 1.2.11 | Client Review & Revisions | Post-Production | Sound Mix | Client Review & Revisions | Designer | Mid | 9 | 46 | 2 | 1.2.11 |  |  |  | 195 | 1755
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.12 | 1.2 | Sound Sourcing | Post-Production | Sound Sourcing |  |  |  | 3 | 46 | 2 | 1.2.11 |  |  |  | 195 | 585
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.12.1 | 1.2.12 | Music Search & License | Post-Production | Sound Sourcing | Music Search & License | Sound Designer | Mid | 3 | 46 | 2 | 1.2.12 |  |  |  | 195 | 585
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13 | 1.2 | Final File Delivery | Post-Production | Final File Delivery |  |  |  | 7 | 48 | 2 | 1.2.12 |  |  |  | 195 | 1365
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13.1 | 1.2.13 | QA (Tech & Content) | Post-Production | Final File Delivery | QA (Tech & Content) | QA Specialist | Mid | 3 | 48 | 2 | 1.2.13 |  |  |  | 195 | 585
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.13.2 | 1.2.13 | Final Checklist & Upload | Post-Production | Final File Delivery | Final Checklist & Upload | Media Manager / DIT | Mid | 4 | 63 | 0 | 1.2.13.1 |  |  |  | 195 | 780
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14 | 1.2 | True-ups (for vendor costs) | Post-Production | True-ups (for vendor costs) |  |  |  | 10 | 50 | 8 | 1.2.13 |  |  |  | 195 | 1950
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.1 | 1.2.14 | Change Orders & Tracking | Post-Production | True-ups (for vendor costs) | Change Orders & Tracking | Project Manager | Mid | 1 | 50 | 3 | 1.2.14 |  |  |  | 195 | 195
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.2 | 1.2.14 | Internal Review & Critique | Post-Production | True-ups (for vendor costs) | Internal Review & Critique | Producer | Mid | 1 | 53 | 2 | 1.2.14.1 |  |  |  | 195 | 195
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.3 | 1.2.14 | Client Review & Revisions | Post-Production | True-ups (for vendor costs) | Client Review & Revisions | Account Manager | Mid | 3 | 55 | 3 | 1.2.14.2 |  |  |  | 195 | 585
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.14.4 | 1.2.14 | Invoice Reconciliation | Post-Production | True-ups (for vendor costs) | Invoice Reconciliation | Designer | Mid | 5 | 63 | 0 | 1.2.14.3 |  |  |  | 195 | 975
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15 | 1.2 | Cutdowns | Post-Production | Cutdowns |  |  |  | 11 | 53 | 5 | 1.2.14 |  |  |  | 195 | 2145
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15.1 | 1.2.15 | Internal Review & Critique | Post-Production | Cutdowns | Internal Review & Critique | Producer | Mid | 1 | 53 | 2 | 1.2.15 |  |  |  | 195 | 195
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15.2 | 1.2.15 | Client Review & Revisions | Post-Production | Cutdowns | Client Review & Revisions | Account Manager | Mid | 3 | 55 | 3 | 1.2.15.1 |  |  |  | 195 | 585
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.15.3 | 1.2.15 | Cutdowns (2-3) | Post-Production | Cutdowns | Cutdowns (2-3) | Editor | Mid | 7 | 63 | 0 | 1.2.15.2 |  |  |  | 195 | 1365
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.16 | 1.2 | Client Review | Post-Production | Client Review |  |  |  | 4 | 55 | 3 | 1.2.15 |  |  |  | 195 | 780
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.16.1 | 1.2.16 | Client Review Coordination | Post-Production | Client Review | Client Review Coordination | Account Manager | Mid | 4 | 55 | 3 | 1.2.16 |  |  |  | 195 | 780
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.17 | 1.2 | Review & Sign-Off | Post-Production | Review & Sign-Off |  |  |  | 3 | 55 | 5 | 1.2.16 |  |  |  | 195 | 585
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.17.1 | 1.2.17 | Client Review Coordination | Post-Production | Review & Sign-Off | Client Review Coordination | Account Manager | Mid | 2 | 55 | 3 | 1.2.17 |  |  |  | 195 | 390
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.17.2 | 1.2.17 | Notes Triage | Post-Production | Review & Sign-Off | Notes Triage | Project Manager | Mid | 1 | 61 | 2 | 1.2.17.1 |  |  |  | 195 | 195
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.18 | 1.2 | Asset Library | Post-Production | Asset Library |  |  |  | 2 | 58 | 3 | 1.2.17 |  |  |  | 195 | 390
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.18.1 | 1.2.18 | Post Support | Post-Production | Asset Library | Post Support | Editor | Mid | 2 | 58 | 3 | 1.2.18 |  |  |  | 195 | 390
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.19 | 1.2 | Capture Library | Post-Production | Capture Library |  |  |  | 2 | 58 | 3 | 1.2.18 |  |  |  | 195 | 390
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.19.1 | 1.2.19 | Post Support | Post-Production | Capture Library | Post Support | Editor | Mid | 2 | 58 | 3 | 1.2.19 |  |  |  | 195 | 390
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.20 | 1.2 | Selects Deck | Post-Production | Selects Deck |  |  |  | 2 | 58 | 3 | 1.2.19 |  |  |  | 195 | 390
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.20.1 | 1.2.20 | Post Support | Post-Production | Selects Deck | Post Support | Editor | Mid | 2 | 58 | 3 | 1.2.20 |  |  |  | 195 | 390
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.21 | 1.2 | Delivery | Post-Production | Delivery |  |  |  | 5 | 63 | 0 | 1.2.20 |  |  |  | 195 | 975
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.21.1 | 1.2.21 | Post Support | Post-Production | Delivery | Post Support | Editor | Mid | 5 | 63 | 0 | 1.2.21 |  |  |  | 195 | 975
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.22 | 1.2 | Stills/Footage Selection | Post-Production | Stills/Footage Selection |  |  |  | 5 | 63 | 0 | 1.2.21 |  |  |  | 195 | 975
RFP_Brief_ First on SoundCloud 2021 Campaign | 1.2.22.1 | 1.2.22 | Post Support | Post-Production | Stills/Footage Selection | Post Support | Editor | Mid | 5 | 63 | 0 | 1.2.22 |  |  |  | 195 | 975