## Sheet1
Row_ID | Deliverable_Code | Task_Code | Service_Department | Deliverable | Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes | Rate_USD | Price_USD
[5 empty] | Casa-Dragones-Digital-MKT-RFP | 1 |  | Project Summary |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0
|  |  | Strategy |  | Casa-Dragones-Digital-MKT-RFP | 1.1 | 1 | Strategy |  |  |  |  | 0 | 0 |  |  |  | Strategy Department | 0 | 0
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1 | 1.1 | Creative Strategy / Campaign Plan Deck |  |  |  |  | 582 | 0 | 28 |  |  | / | 195 | 113490
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1 | 1.1.1 | Activation Ideas | Activation Ideas |  |  |  | 40 | 0 | 11 | 1.1.1 |  |  | 195 | 7800
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.1 | 1.1.1.1 | deck_build | Activation Ideas | deck_build |  |  | 0 | 0 | 6 | 1.1.1.1 |  |  | 0 | 0
1475 | DEL-0036 | TSK-01466 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.1.1 | 1.1.1.1.1 | deck_build | Activation Ideas | deck_build | Copywriter | Mid | 4 |  |  | 1.1.1.1.1 |  |  | 195 | 780
1477 | DEL-0036 | TSK-01468 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.1.2 | 1.1.1.1.1 | deck_build | Activation Ideas | deck_build | Creative Director | Lead/Director | 3 |  |  | 1.1.1.1.1.1 |  |  | 195 | 585
1474 | DEL-0036 | TSK-01465 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.1.3 | 1.1.1.1.1 | deck_build | Activation Ideas | deck_build | Designer | Mid | 16 |  |  | 1.1.1.1.1.2 |  |  | 195 | 3120
1476 | DEL-0036 | TSK-01467 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.1.4 | 1.1.1.1.1 | deck_build | Activation Ideas | deck_build | Strategist | Mid | 12 |  |  | 1.1.1.1.1.3 |  |  | 195 | 2340
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.2 | 1.1.1.1 | internal_review | Activation Ideas | internal_review |  |  | 0 | 23 | 2 | 1.1.1.1.1.4 |  |  | 0 | 0
1479 | DEL-0036 | TSK-01470 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.2.1 | 1.1.1.1.2 | internal_review | Activation Ideas | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.1.1.1.2 |  |  | 195 | 195
1480 | DEL-0036 | TSK-01471 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.2.2 | 1.1.1.1.2 | internal_review | Activation Ideas | internal_review | Strategist | Mid | 1 |  |  | 1.1.1.1.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.3 | 1.1.1.1 | client_review | Activation Ideas | client_review |  |  | 0 | 25 | 3 | 1.1.1.1.2.2 |  |  | 0 | 0
1471 | DEL-0036 | TSK-01462 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.3.1 | 1.1.1.1.3 | client_review | Activation Ideas | client_review | Account Manager | Mid | 1 |  |  | 1.1.1.1.3 |  |  | 195 | 195
1472 | DEL-0036 | TSK-01463 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.3.2 | 1.1.1.1.3 | client_review | Activation Ideas | client_review | Copywriter | Mid | 1 |  |  | 1.1.1.1.3.1 |  |  | 195 | 195
1473 | DEL-0036 | TSK-01464 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.3.3 | 1.1.1.1.3 | client_review | Activation Ideas | client_review | Strategist | Mid | 1 |  |  | 1.1.1.1.3.2 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2 | 1.1.1 | Art Direction | Art Direction |  |  |  | 29 | 0 | 11 | 1.1.1.1 |  |  | 195 | 5655
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.1 | 1.1.1.2 | deck_build | Art Direction | deck_build |  |  | 0 | 0 | 6 | 1.1.1.2 |  |  | 0 | 0
1487 | DEL-0036 | TSK-01478 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.1.1 | 1.1.1.2.1 | deck_build | Art Direction | deck_build | Creative Director | Lead/Director | 3 |  |  | 1.1.1.2.1 |  |  | 195 | 585
1484 | DEL-0036 | TSK-01475 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.1.2 | 1.1.1.2.1 | deck_build | Art Direction | deck_build | Designer | Mid | 16 |  |  | 1.1.1.2.1.1 |  |  | 195 | 3120
1489 | DEL-0036 | TSK-01480 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.1.3 | 1.1.1.2.1 | deck_build | Art Direction | deck_build | Strategist | Mid | 6 |  |  | 1.1.1.2.1.2 |  |  | 195 | 1170
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.2 | 1.1.1.2 | internal_review | Art Direction | internal_review |  |  | 0 | 23 | 2 | 1.1.1.2.1.3 |  |  | 0 | 0
1485 | DEL-0036 | TSK-01476 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.2.1 | 1.1.1.2.2 | internal_review | Art Direction | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.1.1.2.2 |  |  | 195 | 195
1486 | DEL-0036 | TSK-01477 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.2.2 | 1.1.1.2.2 | internal_review | Art Direction | internal_review | Strategist | Mid | 1 |  |  | 1.1.1.2.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.3 | 1.1.1.2 | client_review | Art Direction | client_review |  |  | 0 | 25 | 3 | 1.1.1.2.2.2 |  |  | 0 | 0
1482 | DEL-0036 | TSK-01473 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.3.1 | 1.1.1.2.3 | client_review | Art Direction | client_review | Account Manager | Mid | 1 |  |  | 1.1.1.2.3 |  |  | 195 | 195
1483 | DEL-0036 | TSK-01474 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.3.2 | 1.1.1.2.3 | client_review | Art Direction | client_review | Strategist | Mid | 1 |  |  | 1.1.1.2.3.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3 | 1.1.1 | Brand Approach for Campaign Period | Brand Approach for Campaign Period |  |  |  | 32 | 0 | 11 | 1.1.1.2 |  |  | 195 | 6240
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.1 | 1.1.1.3 | deck_build | Brand Approach for Campaign Period | deck_build |  |  | 0 | 0 | 6 | 1.1.1.3 |  |  | 0 | 0
1494 | DEL-0036 | TSK-01485 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.1.1 | 1.1.1.3.1 | deck_build | Brand Approach for Campaign Period | deck_build | Designer | Mid | 16 |  |  | 1.1.1.3.1 |  |  | 195 | 3120
1490 | DEL-0036 | TSK-01481 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.1.2 | 1.1.1.3.1 | deck_build | Brand Approach for Campaign Period | deck_build | Strategist | Mid | 12 |  |  | 1.1.1.3.1.1 |  |  | 195 | 2340
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.2 | 1.1.1.3 | internal_review | Brand Approach for Campaign Period | internal_review |  |  | 0 | 23 | 2 | 1.1.1.3.1.2 |  |  | 0 | 0
1495 | DEL-0036 | TSK-01486 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.2.1 | 1.1.1.3.2 | internal_review | Brand Approach for Campaign Period | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.1.1.3.2 |  |  | 195 | 195
1496 | DEL-0036 | TSK-01487 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.2.2 | 1.1.1.3.2 | internal_review | Brand Approach for Campaign Period | internal_review | Strategist | Mid | 1 |  |  | 1.1.1.3.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.3 | 1.1.1.3 | client_review | Brand Approach for Campaign Period | client_review |  |  | 0 | 25 | 3 | 1.1.1.3.2.2 |  |  | 0 | 0
1491 | DEL-0036 | TSK-01482 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.3.1 | 1.1.1.3.3 | client_review | Brand Approach for Campaign Period | client_review | Account Manager | Mid | 1 |  |  | 1.1.1.3.3 |  |  | 195 | 195
1492 | DEL-0036 | TSK-01483 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.3.2 | 1.1.1.3.3 | client_review | Brand Approach for Campaign Period | client_review | Strategist | Mid | 1 |  |  | 1.1.1.3.3.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4 | 1.1.1 | Campaign Roll-Out/Launch Road Map | Campaign Roll-Out/Launch Road Map |  |  |  | 30 | 0 | 11 | 1.1.1.3 |  |  | 195 | 5850
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4.1 | 1.1.1.4 | deck_build | Campaign Roll-Out/Launch Road Map | deck_build |  |  | 0 | 0 | 6 | 1.1.1.4 |  |  | 0 | 0
1501 | DEL-0036 | TSK-01492 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4.1.1 | 1.1.1.4.1 | deck_build | Campaign Roll-Out/Launch Road Map | deck_build | Designer | Mid | 16 |  |  | 1.1.1.4.1 |  |  | 195 | 3120
1500 | DEL-0036 | TSK-01491 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4.1.2 | 1.1.1.4.1 | deck_build | Campaign Roll-Out/Launch Road Map | deck_build | Project Manager | Mid | 4 |  |  | 1.1.1.4.1.1 |  |  | 195 | 780
1505 | DEL-0036 | TSK-01496 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4.1.3 | 1.1.1.4.1 | deck_build | Campaign Roll-Out/Launch Road Map | deck_build | Strategist | Mid | 6 |  |  | 1.1.1.4.1.2 |  |  | 195 | 1170
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4.2 | 1.1.1.4 | internal_review | Campaign Roll-Out/Launch Road Map | internal_review |  |  | 0 | 23 | 2 | 1.1.1.4.1.3 |  |  | 0 | 0
1502 | DEL-0036 | TSK-01493 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4.2.1 | 1.1.1.4.2 | internal_review | Campaign Roll-Out/Launch Road Map | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.1.1.4.2 |  |  | 195 | 195
1503 | DEL-0036 | TSK-01494 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4.2.2 | 1.1.1.4.2 | internal_review | Campaign Roll-Out/Launch Road Map | internal_review | Strategist | Mid | 1 |  |  | 1.1.1.4.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4.3 | 1.1.1.4 | client_review | Campaign Roll-Out/Launch Road Map | client_review |  |  | 0 | 25 | 3 | 1.1.1.4.2.2 |  |  | 0 | 0
1498 | DEL-0036 | TSK-01489 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4.3.1 | 1.1.1.4.3 | client_review | Campaign Roll-Out/Launch Road Map | client_review | Account Manager | Mid | 1 |  |  | 1.1.1.4.3 |  |  | 195 | 195
1499 | DEL-0036 | TSK-01490 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4.3.2 | 1.1.1.4.3 | client_review | Campaign Roll-Out/Launch Road Map | client_review | Strategist | Mid | 1 |  |  | 1.1.1.4.3.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.5 | 1.1.1 | Content Plan | Content Plan |  |  |  | 37 | 0 | 11 | 1.1.1.4 |  |  | 195 | 7215
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.5.1 | 1.1.1.5 | deck_build | Content Plan | deck_build |  |  | 0 | 0 | 6 | 1.1.1.5 |  |  | 0 | 0
1507 | DEL-0036 | TSK-01498 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.5.1.1 | 1.1.1.5.1 | deck_build | Content Plan | deck_build | Copywriter | Mid | 8 |  |  | 1.1.1.5.1 |  |  | 195 | 1560
1513 | DEL-0036 | TSK-01504 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.5.1.2 | 1.1.1.5.1 | deck_build | Content Plan | deck_build | Designer | Mid | 16 |  |  | 1.1.1.5.1.1 |  |  | 195 | 3120
1508 | DEL-0036 | TSK-01499 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.5.1.3 | 1.1.1.5.1 | deck_build | Content Plan | deck_build | Project Manager | Mid | 2 |  |  | 1.1.1.5.1.2 |  |  | 195 | 390
1517 | DEL-0036 | TSK-01508 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.5.1.4 | 1.1.1.5.1 | deck_build | Content Plan | deck_build | Strategist | Mid | 6 |  |  | 1.1.1.5.1.3 |  |  | 195 | 1170
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.5.2 | 1.1.1.5 | internal_review | Content Plan | internal_review |  |  | 0 | 23 | 2 | 1.1.1.5.1.4 |  |  | 0 | 0
1515 | DEL-0036 | TSK-01506 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.5.2.1 | 1.1.1.5.2 | internal_review | Content Plan | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.1.1.5.2 |  |  | 195 | 195
1516 | DEL-0036 | TSK-01507 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.5.2.2 | 1.1.1.5.2 | internal_review | Content Plan | internal_review | Strategist | Mid | 1 |  |  | 1.1.1.5.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.5.3 | 1.1.1.5 | client_review | Content Plan | client_review |  |  | 0 | 25 | 3 | 1.1.1.5.2.2 |  |  | 0 | 0
1509 | DEL-0036 | TSK-01500 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.5.3.1 | 1.1.1.5.3 | client_review | Content Plan | client_review | Account Manager | Mid | 1 |  |  | 1.1.1.5.3 |  |  | 195 | 195
1510 | DEL-0036 | TSK-01501 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.5.3.2 | 1.1.1.5.3 | client_review | Content Plan | client_review | Copywriter | Mid | 1 |  |  | 1.1.1.5.3.1 |  |  | 195 | 195
1511 | DEL-0036 | TSK-01502 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.5.3.3 | 1.1.1.5.3 | client_review | Content Plan | client_review | Strategist | Mid | 1 |  |  | 1.1.1.5.3.2 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.6 | 1.1.1 | Content Production Shoot Approach | Content Production Shoot Approach |  |  |  | 26 | 0 | 19 | 1.1.1.5 |  |  | 195 | 5070
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.6.1 | 1.1.1.6 | deck_build | Content Production Shoot Approach | deck_build |  |  | 0 | 0 | 6 | 1.1.1.6 |  |  | 0 | 0
1520 | DEL-0036 | TSK-01511 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.6.1.1 | 1.1.1.6.1 | deck_build | Content Production Shoot Approach | deck_build | Designer | Mid | 16 |  |  | 1.1.1.6.1 |  |  | 195 | 3120
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.6.2 | 1.1.1.6 | prepro_coord | Content Production Shoot Approach | prepro_coord |  |  | 0 | 11 | 8 | 1.1.1.6.1.1 |  |  | 0 | 0
1523 | DEL-0036 | TSK-01514 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.6.2.1 | 1.1.1.6.2 | prepro_coord | Content Production Shoot Approach | prepro_coord | Creative Director | Lead/Director | 1 |  |  | 1.1.1.6.2 |  |  | 195 | 195
1524 | DEL-0036 | TSK-01515 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.6.2.2 | 1.1.1.6.2 | prepro_coord | Content Production Shoot Approach | prepro_coord | Project Manager | Mid | 4 |  |  | 1.1.1.6.2.1 |  |  | 195 | 780
1525 | DEL-0036 | TSK-01516 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.6.2.3 | 1.1.1.6.2 | prepro_coord | Content Production Shoot Approach | prepro_coord | Strategist | Mid | 1 |  |  | 1.1.1.6.2.2 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.6.3 | 1.1.1.6 | internal_review | Content Production Shoot Approach | internal_review |  |  | 0 | 23 | 2 | 1.1.1.6.2.3 |  |  | 0 | 0
1521 | DEL-0036 | TSK-01512 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.6.3.1 | 1.1.1.6.3 | internal_review | Content Production Shoot Approach | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.1.1.6.3 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.6.4 | 1.1.1.6 | client_review | Content Production Shoot Approach | client_review |  |  | 0 | 25 | 3 | 1.1.1.6.3.1 |  |  | 0 | 0
1518 | DEL-0036 | TSK-01509 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.6.4.1 | 1.1.1.6.4 | client_review | Content Production Shoot Approach | client_review | Account Manager | Mid | 2 |  |  | 1.1.1.6.4 |  |  | 195 | 390
1519 | DEL-0036 | TSK-01510 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.6.4.2 | 1.1.1.6.4 | client_review | Content Production Shoot Approach | client_review | Strategist | Mid | 1 |  |  | 1.1.1.6.4.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.7 | 1.1.1 | Content Types across Full Funnel | Content Types across Full Funnel |  |  |  | 37 | 0 | 11 | 1.1.1.6 |  |  | 195 | 7215
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.7.1 | 1.1.1.7 | deck_build | Content Types across Full Funnel | deck_build |  |  | 0 | 0 | 6 | 1.1.1.7 |  |  | 0 | 0
1537 | DEL-0036 | TSK-01528 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.7.1.1 | 1.1.1.7.1 | deck_build | Content Types across Full Funnel | deck_build | Copywriter | Mid | 4 |  |  | 1.1.1.7.1 |  |  | 195 | 780
1538 | DEL-0036 | TSK-01529 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.7.1.2 | 1.1.1.7.1 | deck_build | Content Types across Full Funnel | deck_build | Designer | Mid | 16 |  |  | 1.1.1.7.1.1 |  |  | 195 | 3120
1539 | DEL-0036 | TSK-01530 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.7.1.3 | 1.1.1.7.1 | deck_build | Content Types across Full Funnel | deck_build | Strategist | Mid | 12 |  |  | 1.1.1.7.1.2 |  |  | 195 | 2340
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.7.2 | 1.1.1.7 | internal_review | Content Types across Full Funnel | internal_review |  |  | 0 | 23 | 2 | 1.1.1.7.1.3 |  |  | 0 | 0
1542 | DEL-0036 | TSK-01533 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.7.2.1 | 1.1.1.7.2 | internal_review | Content Types across Full Funnel | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.1.1.7.2 |  |  | 195 | 195
1543 | DEL-0036 | TSK-01534 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.7.2.2 | 1.1.1.7.2 | internal_review | Content Types across Full Funnel | internal_review | Strategist | Mid | 1 |  |  | 1.1.1.7.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.7.3 | 1.1.1.7 | client_review | Content Types across Full Funnel | client_review |  |  | 0 | 25 | 3 | 1.1.1.7.2.2 |  |  | 0 | 0
1534 | DEL-0036 | TSK-01525 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.7.3.1 | 1.1.1.7.3 | client_review | Content Types across Full Funnel | client_review | Account Manager | Mid | 1 |  |  | 1.1.1.7.3 |  |  | 195 | 195
1535 | DEL-0036 | TSK-01526 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.7.3.2 | 1.1.1.7.3 | client_review | Content Types across Full Funnel | client_review | Copywriter | Mid | 1 |  |  | 1.1.1.7.3.1 |  |  | 195 | 195
1536 | DEL-0036 | TSK-01527 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.7.3.3 | 1.1.1.7.3 | client_review | Content Types across Full Funnel | client_review | Strategist | Mid | 1 |  |  | 1.1.1.7.3.2 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.8 | 1.1.1 | Copy Bank | Copy Bank |  |  |  | 17 | 0 | 11 | 1.1.1.7 |  |  | 195 | 3315
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.8.1 | 1.1.1.8 | deck_build | Copy Bank | deck_build |  |  | 0 | 0 | 6 | 1.1.1.8 |  |  | 0 | 0
1547 | DEL-0036 | TSK-01538 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.8.1.1 | 1.1.1.8.1 | deck_build | Copy Bank | deck_build | Copywriter | Mid | 4 |  |  | 1.1.1.8.1 |  |  | 195 | 780
1548 | DEL-0036 | TSK-01539 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.8.1.2 | 1.1.1.8.1 | deck_build | Copy Bank | deck_build | Designer | Mid | 8 |  |  | 1.1.1.8.1.1 |  |  | 195 | 1560
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.8.2 | 1.1.1.8 | internal_review | Copy Bank | internal_review |  |  | 0 | 23 | 2 | 1.1.1.8.1.2 |  |  | 0 | 0
1549 | DEL-0036 | TSK-01540 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.8.2.1 | 1.1.1.8.2 | internal_review | Copy Bank | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.1.1.8.2 |  |  | 195 | 195
1550 | DEL-0036 | TSK-01541 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.8.2.2 | 1.1.1.8.2 | internal_review | Copy Bank | internal_review | Strategist | Mid | 1 |  |  | 1.1.1.8.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.8.3 | 1.1.1.8 | client_review | Copy Bank | client_review |  |  | 0 | 25 | 3 | 1.1.1.8.2.2 |  |  | 0 | 0
1544 | DEL-0036 | TSK-01535 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.8.3.1 | 1.1.1.8.3 | client_review | Copy Bank | client_review | Account Manager | Mid | 1 |  |  | 1.1.1.8.3 |  |  | 195 | 195
1545 | DEL-0036 | TSK-01536 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.8.3.2 | 1.1.1.8.3 | client_review | Copy Bank | client_review | Copywriter | Mid | 1 |  |  | 1.1.1.8.3.1 |  |  | 195 | 195
1546 | DEL-0036 | TSK-01537 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.8.3.3 | 1.1.1.8.3 | client_review | Copy Bank | client_review | Strategist | Mid | 1 |  |  | 1.1.1.8.3.2 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.9 | 1.1.1 | Customer Journey | Customer Journey |  |  |  | 26 | 0 | 11 | 1.1.1.8 |  |  | 195 | 5070
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.9.1 | 1.1.1.9 | deck_build | Customer Journey | deck_build |  |  | 0 | 0 | 6 | 1.1.1.9 |  |  | 0 | 0
1553 | DEL-0036 | TSK-01544 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.9.1.1 | 1.1.1.9.1 | deck_build | Customer Journey | deck_build | Designer | Mid | 16 |  |  | 1.1.1.9.1 |  |  | 195 | 3120
1557 | DEL-0036 | TSK-01548 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.9.1.2 | 1.1.1.9.1 | deck_build | Customer Journey | deck_build | Strategist | Mid | 6 |  |  | 1.1.1.9.1.1 |  |  | 195 | 1170
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.9.2 | 1.1.1.9 | internal_review | Customer Journey | internal_review |  |  | 0 | 23 | 2 | 1.1.1.9.1.2 |  |  | 0 | 0
1554 | DEL-0036 | TSK-01545 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.9.2.1 | 1.1.1.9.2 | internal_review | Customer Journey | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.1.1.9.2 |  |  | 195 | 195
1555 | DEL-0036 | TSK-01546 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.9.2.2 | 1.1.1.9.2 | internal_review | Customer Journey | internal_review | Strategist | Mid | 1 |  |  | 1.1.1.9.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.9.3 | 1.1.1.9 | client_review | Customer Journey | client_review |  |  | 0 | 25 | 3 | 1.1.1.9.2.2 |  |  | 0 | 0
1551 | DEL-0036 | TSK-01542 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.9.3.1 | 1.1.1.9.3 | client_review | Customer Journey | client_review | Account Manager | Mid | 1 |  |  | 1.1.1.9.3 |  |  | 195 | 195
1552 | DEL-0036 | TSK-01543 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.9.3.2 | 1.1.1.9.3 | client_review | Customer Journey | client_review | Strategist | Mid | 1 |  |  | 1.1.1.9.3.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.10 | 1.1.1 | High-Fidelity Organic Social Mock-Ups | High-Fidelity Organic Social Mock-Ups |  |  |  | 28 | 0 | 11 | 1.1.1.9 |  |  | 195 | 5460
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.10.1 | 1.1.1.10 | deck_build | High-Fidelity Organic Social Mock-Ups | deck_build |  |  | 0 | 0 | 6 | 1.1.1.10 |  |  | 0 | 0
1561 | DEL-0036 | TSK-01552 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.10.1.1 | 1.1.1.10.1 | deck_build | High-Fidelity Organic Social Mock-Ups | deck_build | Copywriter | Mid | 4 |  |  | 1.1.1.10.1 |  |  | 195 | 780
1562 | DEL-0036 | TSK-01553 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.10.1.2 | 1.1.1.10.1 | deck_build | High-Fidelity Organic Social Mock-Ups | deck_build | Creative Director | Lead/Director | 3 |  |  | 1.1.1.10.1.1 |  |  | 195 | 585
1563 | DEL-0036 | TSK-01554 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.10.1.3 | 1.1.1.10.1 | deck_build | High-Fidelity Organic Social Mock-Ups | deck_build | Designer | Mid | 16 |  |  | 1.1.1.10.1.2 |  |  | 195 | 3120
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.10.2 | 1.1.1.10 | internal_review | High-Fidelity Organic Social Mock-Ups | internal_review |  |  | 0 | 23 | 2 | 1.1.1.10.1.3 |  |  | 0 | 0
1565 | DEL-0036 | TSK-01556 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.10.2.1 | 1.1.1.10.2 | internal_review | High-Fidelity Organic Social Mock-Ups | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.1.1.10.2 |  |  | 195 | 195
1566 | DEL-0036 | TSK-01557 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.10.2.2 | 1.1.1.10.2 | internal_review | High-Fidelity Organic Social Mock-Ups | internal_review | Strategist | Mid | 1 |  |  | 1.1.1.10.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.10.3 | 1.1.1.10 | client_review | High-Fidelity Organic Social Mock-Ups | client_review |  |  | 0 | 25 | 3 | 1.1.1.10.2.2 |  |  | 0 | 0
1558 | DEL-0036 | TSK-01549 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.10.3.1 | 1.1.1.10.3 | client_review | High-Fidelity Organic Social Mock-Ups | client_review | Account Manager | Mid | 1 |  |  | 1.1.1.10.3 |  |  | 195 | 195
1559 | DEL-0036 | TSK-01550 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.10.3.2 | 1.1.1.10.3 | client_review | High-Fidelity Organic Social Mock-Ups | client_review | Copywriter | Mid | 1 |  |  | 1.1.1.10.3.1 |  |  | 195 | 195
1560 | DEL-0036 | TSK-01551 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.10.3.3 | 1.1.1.10.3 | client_review | High-Fidelity Organic Social Mock-Ups | client_review | Strategist | Mid | 1 |  |  | 1.1.1.10.3.2 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.11 | 1.1.1 | High-Fidelity Paid Media Mock-Ups | High-Fidelity Paid Media Mock-Ups |  |  |  | 28 | 0 | 11 | 1.1.1.10 |  |  | 195 | 5460
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.11.1 | 1.1.1.11 | deck_build | High-Fidelity Paid Media Mock-Ups | deck_build |  |  | 0 | 0 | 6 | 1.1.1.11 |  |  | 0 | 0
1570 | DEL-0036 | TSK-01561 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.11.1.1 | 1.1.1.11.1 | deck_build | High-Fidelity Paid Media Mock-Ups | deck_build | Copywriter | Mid | 4 |  |  | 1.1.1.11.1 |  |  | 195 | 780
1571 | DEL-0036 | TSK-01562 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.11.1.2 | 1.1.1.11.1 | deck_build | High-Fidelity Paid Media Mock-Ups | deck_build | Creative Director | Lead/Director | 3 |  |  | 1.1.1.11.1.1 |  |  | 195 | 585
1572 | DEL-0036 | TSK-01563 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.11.1.3 | 1.1.1.11.1 | deck_build | High-Fidelity Paid Media Mock-Ups | deck_build | Designer | Mid | 16 |  |  | 1.1.1.11.1.2 |  |  | 195 | 3120
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.11.2 | 1.1.1.11 | internal_review | High-Fidelity Paid Media Mock-Ups | internal_review |  |  | 0 | 23 | 2 | 1.1.1.11.1.3 |  |  | 0 | 0
1574 | DEL-0036 | TSK-01565 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.11.2.1 | 1.1.1.11.2 | internal_review | High-Fidelity Paid Media Mock-Ups | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.1.1.11.2 |  |  | 195 | 195
1575 | DEL-0036 | TSK-01566 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.11.2.2 | 1.1.1.11.2 | internal_review | High-Fidelity Paid Media Mock-Ups | internal_review | Strategist | Mid | 1 |  |  | 1.1.1.11.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.11.3 | 1.1.1.11 | client_review | High-Fidelity Paid Media Mock-Ups | client_review |  |  | 0 | 25 | 3 | 1.1.1.11.2.2 |  |  | 0 | 0
1567 | DEL-0036 | TSK-01558 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.11.3.1 | 1.1.1.11.3 | client_review | High-Fidelity Paid Media Mock-Ups | client_review | Account Manager | Mid | 1 |  |  | 1.1.1.11.3 |  |  | 195 | 195
1568 | DEL-0036 | TSK-01559 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.11.3.2 | 1.1.1.11.3 | client_review | High-Fidelity Paid Media Mock-Ups | client_review | Copywriter | Mid | 1 |  |  | 1.1.1.11.3.1 |  |  | 195 | 195
1569 | DEL-0036 | TSK-01560 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.11.3.3 | 1.1.1.11.3 | client_review | High-Fidelity Paid Media Mock-Ups | client_review | Strategist | Mid | 1 |  |  | 1.1.1.11.3.2 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.12 | 1.1.1 | Influencer Partnership Approach | Influencer Partnership Approach |  |  |  | 31 | 0 | 11 | 1.1.1.11 |  |  | 195 | 6045
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.12.1 | 1.1.1.12 | deck_build | Influencer Partnership Approach | deck_build |  |  | 0 | 0 | 6 | 1.1.1.12 |  |  | 0 | 0
1583 | DEL-0036 | TSK-01574 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.12.1.1 | 1.1.1.12.1 | deck_build | Influencer Partnership Approach | deck_build | Account Manager | Mid | 2 |  |  | 1.1.1.12.1 |  |  | 195 | 390
1579 | DEL-0036 | TSK-01570 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.12.1.2 | 1.1.1.12.1 | deck_build | Influencer Partnership Approach | deck_build | Copywriter | Mid | 4 |  |  | 1.1.1.12.1.1 |  |  | 195 | 780
1580 | DEL-0036 | TSK-01571 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.12.1.3 | 1.1.1.12.1 | deck_build | Influencer Partnership Approach | deck_build | Designer | Mid | 8 |  |  | 1.1.1.12.1.2 |  |  | 195 | 1560
1584 | DEL-0036 | TSK-01575 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.12.1.4 | 1.1.1.12.1 | deck_build | Influencer Partnership Approach | deck_build | Strategist | Mid | 12 |  |  | 1.1.1.12.1.3 |  |  | 195 | 2340
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.12.2 | 1.1.1.12 | internal_review | Influencer Partnership Approach | internal_review |  |  | 0 | 23 | 2 | 1.1.1.12.1.4 |  |  | 0 | 0
1581 | DEL-0036 | TSK-01572 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.12.2.1 | 1.1.1.12.2 | internal_review | Influencer Partnership Approach | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.1.1.12.2 |  |  | 195 | 195
1582 | DEL-0036 | TSK-01573 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.12.2.2 | 1.1.1.12.2 | internal_review | Influencer Partnership Approach | internal_review | Strategist | Mid | 1 |  |  | 1.1.1.12.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.12.3 | 1.1.1.12 | client_review | Influencer Partnership Approach | client_review |  |  | 0 | 25 | 3 | 1.1.1.12.2.2 |  |  | 0 | 0
1576 | DEL-0036 | TSK-01567 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.12.3.1 | 1.1.1.12.3 | client_review | Influencer Partnership Approach | client_review | Account Manager | Mid | 1 |  |  | 1.1.1.12.3 |  |  | 195 | 195
1577 | DEL-0036 | TSK-01568 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.12.3.2 | 1.1.1.12.3 | client_review | Influencer Partnership Approach | client_review | Copywriter | Mid | 1 |  |  | 1.1.1.12.3.1 |  |  | 195 | 195
1578 | DEL-0036 | TSK-01569 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.12.3.3 | 1.1.1.12.3 | client_review | Influencer Partnership Approach | client_review | Strategist | Mid | 1 |  |  | 1.1.1.12.3.2 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.13 | 1.1.1 | Kick-Off Session | Kick-Off Session |  |  |  | 55 | 0 | 11 | 1.1.1.12 |  |  | 195 | 10725
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.13.1 | 1.1.1.13 | deck_build | Kick-Off Session | deck_build |  |  | 0 | 0 | 6 | 1.1.1.13 |  |  | 0 | 0
1586 | DEL-0036 | TSK-01577 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.13.1.1 | 1.1.1.13.1 | deck_build | Kick-Off Session | deck_build | Account Manager | Mid | 6 |  |  | 1.1.1.13.1 |  |  | 195 | 1170
1593 | DEL-0036 | TSK-01584 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.13.1.2 | 1.1.1.13.1 | deck_build | Kick-Off Session | deck_build | Creative Director | Lead/Director | 3 |  |  | 1.1.1.13.1.1 |  |  | 195 | 585
1587 | DEL-0036 | TSK-01578 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.13.1.3 | 1.1.1.13.1 | deck_build | Kick-Off Session | deck_build | Designer | Mid | 16 |  |  | 1.1.1.13.1.2 |  |  | 195 | 3120
1588 | DEL-0036 | TSK-01579 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.13.1.4 | 1.1.1.13.1 | deck_build | Kick-Off Session | deck_build | Project Manager | Mid | 2 |  |  | 1.1.1.13.1.3 |  |  | 195 | 390
1589 | DEL-0036 | TSK-01580 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.13.1.5 | 1.1.1.13.1 | deck_build | Kick-Off Session | deck_build | Strategist | Mid | 24 |  |  | 1.1.1.13.1.4 |  |  | 195 | 4680
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.13.2 | 1.1.1.13 | internal_review | Kick-Off Session | internal_review |  |  | 0 | 23 | 2 | 1.1.1.13.1.5 |  |  | 0 | 0
1596 | DEL-0036 | TSK-01587 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.13.2.1 | 1.1.1.13.2 | internal_review | Kick-Off Session | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.1.1.13.2 |  |  | 195 | 195
1597 | DEL-0036 | TSK-01588 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.13.2.2 | 1.1.1.13.2 | internal_review | Kick-Off Session | internal_review | Strategist | Mid | 1 |  |  | 1.1.1.13.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.13.3 | 1.1.1.13 | client_review | Kick-Off Session | client_review |  |  | 0 | 25 | 3 | 1.1.1.13.2.2 |  |  | 0 | 0
1590 | DEL-0036 | TSK-01581 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.13.3.1 | 1.1.1.13.3 | client_review | Kick-Off Session | client_review | Account Manager | Mid | 1 |  |  | 1.1.1.13.3 |  |  | 195 | 195
1591 | DEL-0036 | TSK-01582 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.13.3.2 | 1.1.1.13.3 | client_review | Kick-Off Session | client_review | Strategist | Mid | 1 |  |  | 1.1.1.13.3.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.14 | 1.1.1 | Messaging Framework (by Audience) | Messaging Framework (by Audience) |  |  |  | 37 | 0 | 11 | 1.1.1.13 |  |  | 195 | 7215
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.14.1 | 1.1.1.14 | deck_build | Messaging Framework (by Audience) | deck_build |  |  | 0 | 0 | 6 | 1.1.1.14 |  |  | 0 | 0
1605 | DEL-0036 | TSK-01596 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.14.1.1 | 1.1.1.14.1 | deck_build | Messaging Framework (by Audience) | deck_build | Copywriter | Mid | 4 |  |  | 1.1.1.14.1 |  |  | 195 | 780
1604 | DEL-0036 | TSK-01595 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.14.1.2 | 1.1.1.14.1 | deck_build | Messaging Framework (by Audience) | deck_build | Designer | Mid | 16 |  |  | 1.1.1.14.1.1 |  |  | 195 | 3120
1606 | DEL-0036 | TSK-01597 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.14.1.3 | 1.1.1.14.1 | deck_build | Messaging Framework (by Audience) | deck_build | Strategist | Mid | 12 |  |  | 1.1.1.14.1.2 |  |  | 195 | 2340
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.14.2 | 1.1.1.14 | internal_review | Messaging Framework (by Audience) | internal_review |  |  | 0 | 23 | 2 | 1.1.1.14.1.3 |  |  | 0 | 0
1608 | DEL-0036 | TSK-01599 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.14.2.1 | 1.1.1.14.2 | internal_review | Messaging Framework (by Audience) | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.1.1.14.2 |  |  | 195 | 195
1609 | DEL-0036 | TSK-01600 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.14.2.2 | 1.1.1.14.2 | internal_review | Messaging Framework (by Audience) | internal_review | Strategist | Mid | 1 |  |  | 1.1.1.14.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.14.3 | 1.1.1.14 | client_review | Messaging Framework (by Audience) | client_review |  |  | 0 | 25 | 3 | 1.1.1.14.2.2 |  |  | 0 | 0
1601 | DEL-0036 | TSK-01592 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.14.3.1 | 1.1.1.14.3 | client_review | Messaging Framework (by Audience) | client_review | Account Manager | Mid | 1 |  |  | 1.1.1.14.3 |  |  | 195 | 195
1602 | DEL-0036 | TSK-01593 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.14.3.2 | 1.1.1.14.3 | client_review | Messaging Framework (by Audience) | client_review | Copywriter | Mid | 1 |  |  | 1.1.1.14.3.1 |  |  | 195 | 195
1603 | DEL-0036 | TSK-01594 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.14.3.3 | 1.1.1.14.3 | client_review | Messaging Framework (by Audience) | client_review | Strategist | Mid | 1 |  |  | 1.1.1.14.3.2 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.15 | 1.1.1 | Platform/Channel Approach | Platform/Channel Approach |  |  |  | 29 | 0 | 15 | 1.1.1.14 |  |  | 195 | 5655
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.15.1 | 1.1.1.15 | deck_build | Platform/Channel Approach | deck_build |  |  | 0 | 0 | 6 | 1.1.1.15 |  |  | 0 | 0
1611 | DEL-0036 | TSK-01602 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.15.1.1 | 1.1.1.15.1 | deck_build | Platform/Channel Approach | deck_build | Analyst | Mid | 3 |  |  | 1.1.1.15.1 |  |  | 195 | 585
1616 | DEL-0036 | TSK-01607 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.15.1.2 | 1.1.1.15.1 | deck_build | Platform/Channel Approach | deck_build | Designer | Mid | 8 |  |  | 1.1.1.15.1.1 |  |  | 195 | 1560
1612 | DEL-0036 | TSK-01603 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.15.1.3 | 1.1.1.15.1 | deck_build | Platform/Channel Approach | deck_build | Strategist | Mid | 12 |  |  | 1.1.1.15.1.2 |  |  | 195 | 2340
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.15.2 | 1.1.1.15 | reporting | Platform/Channel Approach | reporting |  |  | 0 | 19 | 4 | 1.1.1.15.1.3 |  |  | 0 | 0
1619 | DEL-0036 | TSK-01610 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.15.2.1 | 1.1.1.15.2 | reporting | Platform/Channel Approach | reporting | Designer | Mid | 2 |  |  | 1.1.1.15.2 |  |  | 195 | 390
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.15.3 | 1.1.1.15 | internal_review | Platform/Channel Approach | internal_review |  |  | 0 | 23 | 2 | 1.1.1.15.2.1 |  |  | 0 | 0
1617 | DEL-0036 | TSK-01608 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.15.3.1 | 1.1.1.15.3 | internal_review | Platform/Channel Approach | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.1.1.15.3 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.15.4 | 1.1.1.15 | client_review | Platform/Channel Approach | client_review |  |  | 0 | 25 | 3 | 1.1.1.15.3.1 |  |  | 0 | 0
1614 | DEL-0036 | TSK-01605 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.15.4.1 | 1.1.1.15.4 | client_review | Platform/Channel Approach | client_review | Account Manager | Mid | 2 |  |  | 1.1.1.15.4 |  |  | 195 | 390
1615 | DEL-0036 | TSK-01606 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.15.4.2 | 1.1.1.15.4 | client_review | Platform/Channel Approach | client_review | Strategist | Mid | 1 |  |  | 1.1.1.15.4.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.16 | 1.1.1 | Social Templates | Social Templates |  |  |  | 31 | 0 | 11 | 1.1.1.15 |  |  | 195 | 6045
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.16.1 | 1.1.1.16 | deck_build | Social Templates | deck_build |  |  | 0 | 0 | 6 | 1.1.1.16 |  |  | 0 | 0
1626 | DEL-0036 | TSK-01617 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.16.1.1 | 1.1.1.16.1 | deck_build | Social Templates | deck_build | Creative Director | Lead/Director | 3 |  |  | 1.1.1.16.1 |  |  | 195 | 585
1622 | DEL-0036 | TSK-01613 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.16.1.2 | 1.1.1.16.1 | deck_build | Social Templates | deck_build | Designer | Mid | 24 |  |  | 1.1.1.16.1.1 |  |  | 195 | 4680
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.16.2 | 1.1.1.16 | internal_review | Social Templates | internal_review |  |  | 0 | 23 | 2 | 1.1.1.16.1.2 |  |  | 0 | 0
1623 | DEL-0036 | TSK-01614 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.16.2.1 | 1.1.1.16.2 | internal_review | Social Templates | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.1.1.16.2 |  |  | 195 | 195
1624 | DEL-0036 | TSK-01615 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.16.2.2 | 1.1.1.16.2 | internal_review | Social Templates | internal_review | Strategist | Mid | 1 |  |  | 1.1.1.16.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.16.3 | 1.1.1.16 | client_review | Social Templates | client_review |  |  | 0 | 25 | 3 | 1.1.1.16.2.2 |  |  | 0 | 0
1620 | DEL-0036 | TSK-01611 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.16.3.1 | 1.1.1.16.3 | client_review | Social Templates | client_review | Account Manager | Mid | 1 |  |  | 1.1.1.16.3 |  |  | 195 | 195
1621 | DEL-0036 | TSK-01612 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.16.3.2 | 1.1.1.16.3 | client_review | Social Templates | client_review | Strategist | Mid | 1 |  |  | 1.1.1.16.3.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.17 | 1.1.1 | Visual Approach | Visual Approach |  |  |  | 29 | 0 | 11 | 1.1.1.16 |  |  | 195 | 5655
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.17.1 | 1.1.1.17 | deck_build | Visual Approach | deck_build |  |  | 0 | 0 | 6 | 1.1.1.17 |  |  | 0 | 0
1633 | DEL-0036 | TSK-01624 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.17.1.1 | 1.1.1.17.1 | deck_build | Visual Approach | deck_build | Creative Director | Lead/Director | 3 |  |  | 1.1.1.17.1 |  |  | 195 | 585
1630 | DEL-0036 | TSK-01621 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.17.1.2 | 1.1.1.17.1 | deck_build | Visual Approach | deck_build | Designer | Mid | 16 |  |  | 1.1.1.17.1.1 |  |  | 195 | 3120
1635 | DEL-0036 | TSK-01626 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.17.1.3 | 1.1.1.17.1 | deck_build | Visual Approach | deck_build | Strategist | Mid | 6 |  |  | 1.1.1.17.1.2 |  |  | 195 | 1170
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.17.2 | 1.1.1.17 | internal_review | Visual Approach | internal_review |  |  | 0 | 23 | 2 | 1.1.1.17.1.3 |  |  | 0 | 0
1631 | DEL-0036 | TSK-01622 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.17.2.1 | 1.1.1.17.2 | internal_review | Visual Approach | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.1.1.17.2 |  |  | 195 | 195
1632 | DEL-0036 | TSK-01623 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.17.2.2 | 1.1.1.17.2 | internal_review | Visual Approach | internal_review | Strategist | Mid | 1 |  |  | 1.1.1.17.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.17.3 | 1.1.1.17 | client_review | Visual Approach | client_review |  |  | 0 | 25 | 3 | 1.1.1.17.2.2 |  |  | 0 | 0
1628 | DEL-0036 | TSK-01619 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.17.3.1 | 1.1.1.17.3 | client_review | Visual Approach | client_review | Account Manager | Mid | 1 |  |  | 1.1.1.17.3 |  |  | 195 | 195
1629 | DEL-0036 | TSK-01620 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.17.3.2 | 1.1.1.17.3 | client_review | Visual Approach | client_review | Strategist | Mid | 1 |  |  | 1.1.1.17.3.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.18 | 1.1.1 | Voice & Tone | Voice & Tone |  |  |  | 27 | 0 | 11 | 1.1.1.17 |  |  | 195 | 5265
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.18.1 | 1.1.1.18 | deck_build | Voice & Tone | deck_build |  |  | 0 | 0 | 6 | 1.1.1.18 |  |  | 0 | 0
1639 | DEL-0036 | TSK-01630 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.18.1.1 | 1.1.1.18.1 | deck_build | Voice & Tone | deck_build | Copywriter | Mid | 8 |  |  | 1.1.1.18.1 |  |  | 195 | 1560
1640 | DEL-0036 | TSK-01631 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.18.1.2 | 1.1.1.18.1 | deck_build | Voice & Tone | deck_build | Designer | Mid | 8 |  |  | 1.1.1.18.1.1 |  |  | 195 | 1560
1644 | DEL-0036 | TSK-01635 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.18.1.3 | 1.1.1.18.1 | deck_build | Voice & Tone | deck_build | Strategist | Mid | 6 |  |  | 1.1.1.18.1.2 |  |  | 195 | 1170
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.18.2 | 1.1.1.18 | internal_review | Voice & Tone | internal_review |  |  | 0 | 23 | 2 | 1.1.1.18.1.3 |  |  | 0 | 0
1641 | DEL-0036 | TSK-01632 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.18.2.1 | 1.1.1.18.2 | internal_review | Voice & Tone | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.1.1.18.2 |  |  | 195 | 195
1642 | DEL-0036 | TSK-01633 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.18.2.2 | 1.1.1.18.2 | internal_review | Voice & Tone | internal_review | Strategist | Mid | 1 |  |  | 1.1.1.18.2.1 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.18.3 | 1.1.1.18 | client_review | Voice & Tone | client_review |  |  | 0 | 25 | 3 | 1.1.1.18.2.2 |  |  | 0 | 0
1636 | DEL-0036 | TSK-01627 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.18.3.1 | 1.1.1.18.3 | client_review | Voice & Tone | client_review | Account Manager | Mid | 1 |  |  | 1.1.1.18.3 |  |  | 195 | 195
1637 | DEL-0036 | TSK-01628 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.18.3.2 | 1.1.1.18.3 | client_review | Voice & Tone | client_review | Copywriter | Mid | 1 |  |  | 1.1.1.18.3.1 |  |  | 195 | 195
1638 | DEL-0036 | TSK-01629 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.18.3.3 | 1.1.1.18.3 | client_review | Voice & Tone | client_review | Strategist | Mid | 1 |  |  | 1.1.1.18.3.2 |  |  | 195 | 195
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.19 | 1.1.1 | Content Production Shot List Review & Guidance | Content Production Shot List Review & Guidance |  |  |  | 13 | 6 | 5 | 1.1.1.18 |  |  | 195 | 2535
| DEL-0036 |  | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.19.1 | 1.1.1.19 | prepro_docs | Content Production Shot List Review & Guidance | prepro_docs |  |  | 0 | 6 | 5 | 1.1.1.19 |  |  | 0 | 0
1527 | DEL-0036 | TSK-01518 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.19.1.1 | 1.1.1.19.1 | prepro_docs | Content Production Shot List Review & Guidance | prepro_docs | Account Manager | Mid | 3 |  |  | 1.1.1.19.1 |  |  | 195 | 585
1530 | DEL-0036 | TSK-01521 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.19.1.2 | 1.1.1.19.1 | prepro_docs | Content Production Shot List Review & Guidance | prepro_docs | Creative Director | Lead/Director | 1 |  |  | 1.1.1.19.1.1 |  |  | 195 | 195
1529 | DEL-0036 | TSK-01520 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.19.1.3 | 1.1.1.19.1 | prepro_docs | Content Production Shot List Review & Guidance | prepro_docs | Designer | Mid | 3 |  |  | 1.1.1.19.1.2 |  |  | 195 | 585
1528 | DEL-0036 | TSK-01519 | Strategy | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1.19.1.4 | 1.1.1.19.1 | prepro_docs | Content Production Shot List Review & Guidance | prepro_docs | Strategist | Mid | 6 |  |  | 1.1.1.19.1.3 |  |  | 195 | 1170
|  |  | Paid Media |  | Casa-Dragones-Digital-MKT-RFP | 1.2 | 1 | Paid Media |  |  |  |  | 0 | 0 |  |  |  | Paid Media Department | 0 | 0
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1 | 1.2 | Paid Media Planning |  |  |  |  | 82 | 28 | 33 | 1.1.1 |  | / | 195 | 15990
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1 | 1.2.1 | Media Planning Deck | Media Planning Deck |  |  |  | 19 | 28 | 16 | 1.2.1 |  |  | 195 | 3705
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.1 | 1.2.1.1 | deck_build | Media Planning Deck | deck_build |  |  | 0 | 28 | 6 | 1.2.1.1 |  |  | 0 | 0
1241 | DEL-0029 | TSK-01232 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.1.1 | 1.2.1.1.1 | deck_build | Media Planning Deck | deck_build | Designer | Mid | 8 |  |  | 1.2.1.1.1 |  |  | 195 | 1560
1240 | DEL-0029 | TSK-01231 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.1.2 | 1.2.1.1.1 | deck_build | Media Planning Deck | deck_build | Media Strategist | Mid | 4 |  |  | 1.2.1.1.1.1 |  |  | 195 | 780
1244 | DEL-0029 | TSK-01235 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.1.3 | 1.2.1.1.1 | deck_build | Media Planning Deck | deck_build | Project Manager | Mid | 2 |  |  | 1.2.1.1.1.2 |  |  | 195 | 390
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.2 | 1.2.1.1 | prepro_docs | Media Planning Deck | prepro_docs |  |  | 0 | 40 | 5 | 1.2.1.1.1.3 |  |  | 0 | 0
1239 | DEL-0029 | TSK-01230 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.2.1 | 1.2.1.1.2 | prepro_docs | Media Planning Deck | prepro_docs | Designer | Mid | 2 |  |  | 1.2.1.1.2 |  |  | 195 | 390
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.3 | 1.2.1.1 | internal_review | Media Planning Deck | internal_review |  |  | 0 | 56 | 2 | 1.2.1.1.2.1 |  |  | 0 | 0
1242 | DEL-0029 | TSK-01233 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.3.1 | 1.2.1.1.3 | internal_review | Media Planning Deck | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.2.1.1.3 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.4 | 1.2.1.1 | client_review | Media Planning Deck | client_review |  |  | 0 | 58 | 3 | 1.2.1.1.3.1 |  |  | 0 | 0
1237 | DEL-0029 | TSK-01228 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.4.1 | 1.2.1.1.4 | client_review | Media Planning Deck | client_review | Account Manager | Mid | 1 |  |  | 1.2.1.1.4 |  |  | 195 | 195
1238 | DEL-0029 | TSK-01229 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.1.4.2 | 1.2.1.1.4 | client_review | Media Planning Deck | client_review | Media Strategist | Mid | 1 |  |  | 1.2.1.1.4.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.2 | 1.2.1 | Paid Media Plan | Paid Media Plan |  |  |  | 29 | 34 | 11 | 1.2.1.1 |  |  | 195 | 5655
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.2.1 | 1.2.1.2 | media_planning | Paid Media Plan | media_planning |  |  | 0 | 34 | 6 | 1.2.1.2 |  |  | 0 | 0
1248 | DEL-0029 | TSK-01239 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.2.1.1 | 1.2.1.2.1 | media_planning | Paid Media Plan | media_planning | Designer | Mid | 3 |  |  | 1.2.1.2.1 |  |  | 195 | 585
1252 | DEL-0029 | TSK-01243 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.2.1.2 | 1.2.1.2.1 | media_planning | Paid Media Plan | media_planning | Media Planner | Mid | 10 |  |  | 1.2.1.2.1.1 |  |  | 195 | 1950
1245 | DEL-0029 | TSK-01236 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.2.1.3 | 1.2.1.2.1 | media_planning | Paid Media Plan | media_planning | Media Strategist | Mid | 10 |  |  | 1.2.1.2.1.2 |  |  | 195 | 1950
1251 | DEL-0029 | TSK-01242 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.2.1.4 | 1.2.1.2.1 | media_planning | Paid Media Plan | media_planning | Project Manager | Mid | 2 |  |  | 1.2.1.2.1.3 |  |  | 195 | 390
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.2.2 | 1.2.1.2 | internal_review | Paid Media Plan | internal_review |  |  | 0 | 56 | 2 | 1.2.1.2.1.4 |  |  | 0 | 0
1249 | DEL-0029 | TSK-01240 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.2.2.1 | 1.2.1.2.2 | internal_review | Paid Media Plan | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.2.1.2.2 |  |  | 195 | 195
1250 | DEL-0029 | TSK-01241 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.2.2.2 | 1.2.1.2.2 | internal_review | Paid Media Plan | internal_review | Media Strategist | Mid | 1 |  |  | 1.2.1.2.2.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.2.3 | 1.2.1.2 | client_review | Paid Media Plan | client_review |  |  | 0 | 58 | 3 | 1.2.1.2.2.2 |  |  | 0 | 0
1246 | DEL-0029 | TSK-01237 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.2.3.1 | 1.2.1.2.3 | client_review | Paid Media Plan | client_review | Account Manager | Mid | 1 |  |  | 1.2.1.2.3 |  |  | 195 | 195
1247 | DEL-0029 | TSK-01238 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.2.3.2 | 1.2.1.2.3 | client_review | Paid Media Plan | client_review | Media Strategist | Mid | 1 |  |  | 1.2.1.2.3.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3 | 1.2.1 | Ad Unit & Format POV | Ad Unit & Format POV |  |  |  | 16 | 45 | 16 | 1.2.1.2 |  |  | 195 | 3120
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3.1 | 1.2.1.3 | development | Ad Unit & Format POV | development |  |  | 0 | 45 | 11 | 1.2.1.3 |  |  | 0 | 0
1227 | DEL-0029 | TSK-01218 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3.1.1 | 1.2.1.3.1 | development | Ad Unit & Format POV | development | Designer | Mid | 3 |  |  | 1.2.1.3.1 |  |  | 195 | 585
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3.2 | 1.2.1.3 | internal_review | Ad Unit & Format POV | internal_review |  |  | 0 | 56 | 2 | 1.2.1.3.1.1 |  |  | 0 | 0
1223 | DEL-0029 | TSK-01214 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3.2.1 | 1.2.1.3.2 | internal_review | Ad Unit & Format POV | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.2.1.3.2 |  |  | 195 | 195
1224 | DEL-0029 | TSK-01215 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3.2.2 | 1.2.1.3.2 | internal_review | Ad Unit & Format POV | internal_review | Media Strategist | Mid | 1 |  |  | 1.2.1.3.2.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3.3 | 1.2.1.3 | client_review | Ad Unit & Format POV | client_review |  |  | 0 | 58 | 3 | 1.2.1.3.2.2 |  |  | 0 | 0
1220 | DEL-0029 | TSK-01211 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3.3.1 | 1.2.1.3.3 | client_review | Ad Unit & Format POV | client_review | Account Manager | Mid | 1 |  |  | 1.2.1.3.3 |  |  | 195 | 195
1221 | DEL-0029 | TSK-01212 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3.3.2 | 1.2.1.3.3 | client_review | Ad Unit & Format POV | client_review | Media Strategist | Mid | 1 |  |  | 1.2.1.3.3.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3.4 | 1.2.1.3 | general | Ad Unit & Format POV | general |  |  | 0 | 61 | 0 | 1.2.1.3.3.2 |  |  | 0 | 0
1222 | DEL-0029 | TSK-01213 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3.4.1 | 1.2.1.3.4 | general | Ad Unit & Format POV | general | Designer | Mid | 3 |  |  | 1.2.1.3.4 |  |  | 195 | 585
1225 | DEL-0029 | TSK-01216 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3.4.2 | 1.2.1.3.4 | general | Ad Unit & Format POV | general | Media Planner | Mid | 3 |  |  | 1.2.1.3.4.1 |  |  | 195 | 585
1226 | DEL-0029 | TSK-01217 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.3.4.3 | 1.2.1.3.4 | general | Ad Unit & Format POV | general | Media Strategist | Mid | 3 |  |  | 1.2.1.3.4.2 |  |  | 195 | 585
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.4 | 1.2.1 | Channel & Vendor Evaluation | Channel & Vendor Evaluation |  |  |  | 18 | 56 | 5 | 1.2.1.3 |  |  | 195 | 3510
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.4.1 | 1.2.1.4 | internal_review | Channel & Vendor Evaluation | internal_review |  |  | 0 | 56 | 2 | 1.2.1.4 |  |  | 0 | 0
1231 | DEL-0029 | TSK-01222 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.4.1.1 | 1.2.1.4.1 | internal_review | Channel & Vendor Evaluation | internal_review | Creative Director | Lead/Director | 1 |  |  | 1.2.1.4.1 |  |  | 195 | 195
1232 | DEL-0029 | TSK-01223 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.4.1.2 | 1.2.1.4.1 | internal_review | Channel & Vendor Evaluation | internal_review | Media Strategist | Mid | 1 |  |  | 1.2.1.4.1.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.4.2 | 1.2.1.4 | client_review | Channel & Vendor Evaluation | client_review |  |  | 0 | 58 | 3 | 1.2.1.4.1.2 |  |  | 0 | 0
1228 | DEL-0029 | TSK-01219 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.4.2.1 | 1.2.1.4.2 | client_review | Channel & Vendor Evaluation | client_review | Account Manager | Mid | 1 |  |  | 1.2.1.4.2 |  |  | 195 | 195
1229 | DEL-0029 | TSK-01220 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.4.2.2 | 1.2.1.4.2 | client_review | Channel & Vendor Evaluation | client_review | Media Strategist | Mid | 1 |  |  | 1.2.1.4.2.1 |  |  | 195 | 195
| DEL-0029 |  | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.4.3 | 1.2.1.4 | general | Channel & Vendor Evaluation | general |  |  | 0 | 61 | 0 | 1.2.1.4.2.2 |  |  | 0 | 0
1236 | DEL-0029 | TSK-01227 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.4.3.1 | 1.2.1.4.3 | general | Channel & Vendor Evaluation | general | Account Manager | Mid | 2 |  |  | 1.2.1.4.3 |  |  | 195 | 390
1230 | DEL-0029 | TSK-01221 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.4.3.2 | 1.2.1.4.3 | general | Channel & Vendor Evaluation | general | Designer | Mid | 2 |  |  | 1.2.1.4.3.1 |  |  | 195 | 390
1233 | DEL-0029 | TSK-01224 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.4.3.3 | 1.2.1.4.3 | general | Channel & Vendor Evaluation | general | Media Planner | Mid | 7 |  |  | 1.2.1.4.3.2 |  |  | 195 | 1365
1234 | DEL-0029 | TSK-01225 | Paid Media | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.2.1.4.3.4 | 1.2.1.4.3 | general | Channel & Vendor Evaluation | general | Media Strategist | Mid | 3 |  |  | 1.2.1.4.3.3 |  |  | 195 | 585
|  |  | Integrated Marketing Management |  | Casa-Dragones-Digital-MKT-RFP | 1.3 | 1 | Integrated Marketing Management |  |  |  |  | 0 | 0 |  |  |  | Integrated Marketing Management Department | 0 | 0
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1 | 1.3 | Reporting |  |  |  |  | 128 | 61 | 7 | 1.2.1 |  | / | 195 | 24960
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.1 | 1.3.1 | Dashboards | Dashboards |  |  |  | 9 | 61 | 7 | 1.3.1 |  |  | 195 | 1755
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.1.1 | 1.3.1.1 | qa | Dashboards | qa |  |  | 0 | 61 | 3 | 1.3.1.1 |  |  | 0 | 0
1116 | DEL-0024 | TSK-01107 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.1.1.1 | 1.3.1.1.1 | qa | Dashboards | qa | QA Specialist | Mid | 3 |  |  | 1.3.1.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.1.2 | 1.3.1.1 | reporting | Dashboards | reporting |  |  | 0 | 64 | 4 | 1.3.1.1.1.1 |  |  | 0 | 0
1115 | DEL-0024 | TSK-01106 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.1.2.1 | 1.3.1.1.2 | reporting | Dashboards | reporting | Analyst | Mid | 6 |  |  | 1.3.1.1.2 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.2 | 1.3.1 | Engagement Rate | Engagement Rate |  |  |  | 6 | 61 | 3 | 1.3.1.1 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.2.1 | 1.3.1.2 | qa | Engagement Rate | qa |  |  | 0 | 61 | 3 | 1.3.1.2 |  |  | 0 | 0
1119 | DEL-0024 | TSK-01110 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.2.1.1 | 1.3.1.2.1 | qa | Engagement Rate | qa | Analyst | Mid | 3 |  |  | 1.3.1.2.1 |  |  | 195 | 585
1120 | DEL-0024 | TSK-01111 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.2.1.2 | 1.3.1.2.1 | qa | Engagement Rate | qa | QA Specialist | Mid | 3 |  |  | 1.3.1.2.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.3 | 1.3.1 | Emplifi Reports | Emplifi Reports |  |  |  | 7 | 64 | 4 | 1.3.1.2 |  |  | 195 | 1365
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.3.1 | 1.3.1.3 | reporting | Emplifi Reports | reporting |  |  | 0 | 64 | 4 | 1.3.1.3 |  |  | 0 | 0
1117 | DEL-0024 | TSK-01108 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.3.1.1 | 1.3.1.3.1 | reporting | Emplifi Reports | reporting | Account Manager | Mid | 1 |  |  | 1.3.1.3.1 |  |  | 195 | 195
1118 | DEL-0024 | TSK-01109 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.3.1.2 | 1.3.1.3.1 | reporting | Emplifi Reports | reporting | Analyst | Mid | 6 |  |  | 1.3.1.3.1.1 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.4 | 1.3.1 | Monthly Comprehensive Report | Monthly Comprehensive Report |  |  |  | 11 | 64 | 4 | 1.3.1.3 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.4.1 | 1.3.1.4 | reporting | Monthly Comprehensive Report | reporting |  |  | 0 | 64 | 4 | 1.3.1.4 |  |  | 0 | 0
1127 | DEL-0024 | TSK-01118 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.4.1.1 | 1.3.1.4.1 | reporting | Monthly Comprehensive Report | reporting | Analyst | Mid | 6 |  |  | 1.3.1.4.1 |  |  | 195 | 1170
1128 | DEL-0024 | TSK-01119 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.4.1.2 | 1.3.1.4.1 | reporting | Monthly Comprehensive Report | reporting | Designer | Mid | 2 |  |  | 1.3.1.4.1.1 |  |  | 195 | 390
1129 | DEL-0024 | TSK-01120 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.4.1.3 | 1.3.1.4.1 | reporting | Monthly Comprehensive Report | reporting | Social Strategist | Mid | 3 |  |  | 1.3.1.4.1.2 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.5 | 1.3.1 | Monthly Organic Social Report | Monthly Organic Social Report |  |  |  | 11 | 64 | 4 | 1.3.1.4 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.5.1 | 1.3.1.5 | reporting | Monthly Organic Social Report | reporting |  |  | 0 | 64 | 4 | 1.3.1.5 |  |  | 0 | 0
1130 | DEL-0024 | TSK-01121 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.5.1.1 | 1.3.1.5.1 | reporting | Monthly Organic Social Report | reporting | Analyst | Mid | 6 |  |  | 1.3.1.5.1 |  |  | 195 | 1170
1131 | DEL-0024 | TSK-01122 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.5.1.2 | 1.3.1.5.1 | reporting | Monthly Organic Social Report | reporting | Designer | Mid | 2 |  |  | 1.3.1.5.1.1 |  |  | 195 | 390
1132 | DEL-0024 | TSK-01123 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.5.1.3 | 1.3.1.5.1 | reporting | Monthly Organic Social Report | reporting | Social Strategist | Mid | 3 |  |  | 1.3.1.5.1.2 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.6 | 1.3.1 | Optimization Recommendations Report | Optimization Recommendations Report |  |  |  | 10 | 64 | 4 | 1.3.1.5 |  |  | 195 | 1950
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.6.1 | 1.3.1.6 | reporting | Optimization Recommendations Report | reporting |  |  | 0 | 64 | 4 | 1.3.1.6 |  |  | 0 | 0
1133 | DEL-0024 | TSK-01124 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.6.1.1 | 1.3.1.6.1 | reporting | Optimization Recommendations Report | reporting | Account Manager | Mid | 1 |  |  | 1.3.1.6.1 |  |  | 195 | 195
1134 | DEL-0024 | TSK-01125 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.6.1.2 | 1.3.1.6.1 | reporting | Optimization Recommendations Report | reporting | Analyst | Mid | 6 |  |  | 1.3.1.6.1.1 |  |  | 195 | 1170
1135 | DEL-0024 | TSK-01126 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.6.1.3 | 1.3.1.6.1 | reporting | Optimization Recommendations Report | reporting | Social Strategist | Mid | 3 |  |  | 1.3.1.6.1.2 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.7 | 1.3.1 | Quarterly Ad-Hoc Report | Quarterly Ad-Hoc Report |  |  |  | 9 | 64 | 4 | 1.3.1.6 |  |  | 195 | 1755
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.7.1 | 1.3.1.7 | reporting | Quarterly Ad-Hoc Report | reporting |  |  | 0 | 64 | 4 | 1.3.1.7 |  |  | 0 | 0
1138 | DEL-0024 | TSK-01129 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.7.1.1 | 1.3.1.7.1 | reporting | Quarterly Ad-Hoc Report | reporting | Analyst | Mid | 6 |  |  | 1.3.1.7.1 |  |  | 195 | 1170
1139 | DEL-0024 | TSK-01130 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.7.1.2 | 1.3.1.7.1 | reporting | Quarterly Ad-Hoc Report | reporting | QA Specialist | Mid | 3 |  |  | 1.3.1.7.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.8 | 1.3.1 | Quarterly Key Learnings & Insights Report | Quarterly Key Learnings & Insights Report |  |  |  | 11 | 64 | 4 | 1.3.1.7 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.8.1 | 1.3.1.8 | reporting | Quarterly Key Learnings & Insights Report | reporting |  |  | 0 | 64 | 4 | 1.3.1.8 |  |  | 0 | 0
1140 | DEL-0024 | TSK-01131 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.8.1.1 | 1.3.1.8.1 | reporting | Quarterly Key Learnings & Insights Report | reporting | Analyst | Mid | 6 |  |  | 1.3.1.8.1 |  |  | 195 | 1170
1141 | DEL-0024 | TSK-01132 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.8.1.2 | 1.3.1.8.1 | reporting | Quarterly Key Learnings & Insights Report | reporting | Designer | Mid | 2 |  |  | 1.3.1.8.1.1 |  |  | 195 | 390
1142 | DEL-0024 | TSK-01133 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.8.1.3 | 1.3.1.8.1 | reporting | Quarterly Key Learnings & Insights Report | reporting | Social Strategist | Mid | 3 |  |  | 1.3.1.8.1.2 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.9 | 1.3.1 | Quarterly Report | Quarterly Report |  |  |  | 11 | 64 | 4 | 1.3.1.8 |  |  | 195 | 2145
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.9.1 | 1.3.1.9 | reporting | Quarterly Report | reporting |  |  | 0 | 64 | 4 | 1.3.1.9 |  |  | 0 | 0
1143 | DEL-0024 | TSK-01134 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.9.1.1 | 1.3.1.9.1 | reporting | Quarterly Report | reporting | Analyst | Mid | 6 |  |  | 1.3.1.9.1 |  |  | 195 | 1170
1144 | DEL-0024 | TSK-01135 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.9.1.2 | 1.3.1.9.1 | reporting | Quarterly Report | reporting | Designer | Mid | 2 |  |  | 1.3.1.9.1.1 |  |  | 195 | 390
1145 | DEL-0024 | TSK-01136 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.9.1.3 | 1.3.1.9.1 | reporting | Quarterly Report | reporting | Social Strategist | Mid | 3 |  |  | 1.3.1.9.1.2 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.10 | 1.3.1 | Summary overview | Summary overview |  |  |  | 4 | 64 | 4 | 1.3.1.9 |  |  | 195 | 780
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.10.1 | 1.3.1.10 | reporting | Summary overview | reporting |  |  | 0 | 64 | 4 | 1.3.1.10 |  |  | 0 | 0
1150 | DEL-0024 | TSK-01141 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.10.1.1 | 1.3.1.10.1 | reporting | Summary overview | reporting | Account Manager | Mid | 1 |  |  | 1.3.1.10.1 |  |  | 195 | 195
1151 | DEL-0024 | TSK-01142 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.10.1.2 | 1.3.1.10.1 | reporting | Summary overview | reporting | Social Strategist | Mid | 3 |  |  | 1.3.1.10.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.11 | 1.3.1 | Weekly Activity Report | Weekly Activity Report |  |  |  | 7 | 64 | 4 | 1.3.1.10 |  |  | 195 | 1365
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.11.1 | 1.3.1.11 | reporting | Weekly Activity Report | reporting |  |  | 0 | 64 | 4 | 1.3.1.11 |  |  | 0 | 0
1153 | DEL-0024 | TSK-01144 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.11.1.1 | 1.3.1.11.1 | reporting | Weekly Activity Report | reporting | Account Manager | Mid | 1 |  |  | 1.3.1.11.1 |  |  | 195 | 195
1154 | DEL-0024 | TSK-01145 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.11.1.2 | 1.3.1.11.1 | reporting | Weekly Activity Report | reporting | Analyst | Mid | 6 |  |  | 1.3.1.11.1.1 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.12 | 1.3.1 | Follower Growth | Follower Growth |  |  |  | 6 | 68 | 0 | 1.3.1.11 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.12.1 | 1.3.1.12 | general | Follower Growth | general |  |  | 0 | 68 | 0 | 1.3.1.12 |  |  | 0 | 0
1121 | DEL-0024 | TSK-01112 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.12.1.1 | 1.3.1.12.1 | general | Follower Growth | general | Analyst | Mid | 3 |  |  | 1.3.1.12.1 |  |  | 195 | 585
1122 | DEL-0024 | TSK-01113 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.12.1.2 | 1.3.1.12.1 | general | Follower Growth | general | QA Specialist | Mid | 3 |  |  | 1.3.1.12.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.13 | 1.3.1 | Impressions | Impressions |  |  |  | 6 | 68 | 0 | 1.3.1.12 |  |  | 195 | 1170
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.13.1 | 1.3.1.13 | general | Impressions | general |  |  | 0 | 68 | 0 | 1.3.1.13 |  |  | 0 | 0
1123 | DEL-0024 | TSK-01114 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.13.1.1 | 1.3.1.13.1 | general | Impressions | general | Analyst | Mid | 3 |  |  | 1.3.1.13.1 |  |  | 195 | 585
1124 | DEL-0024 | TSK-01115 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.13.1.2 | 1.3.1.13.1 | general | Impressions | general | QA Specialist | Mid | 3 |  |  | 1.3.1.13.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.14 | 1.3.1 | Interactions | Interactions |  |  |  | 5 | 68 | 0 | 1.3.1.13 |  |  | 195 | 975
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.14.1 | 1.3.1.14 | general | Interactions | general |  |  | 0 | 68 | 0 | 1.3.1.14 |  |  | 0 | 0
1125 | DEL-0024 | TSK-01116 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.14.1.1 | 1.3.1.14.1 | general | Interactions | general | Analyst | Mid | 2 |  |  | 1.3.1.14.1 |  |  | 195 | 390
1126 | DEL-0024 | TSK-01117 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.14.1.2 | 1.3.1.14.1 | general | Interactions | general | QA Specialist | Mid | 3 |  |  | 1.3.1.14.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.15 | 1.3.1 | Profile Reach | Profile Reach |  |  |  | 5 | 68 | 0 | 1.3.1.14 |  |  | 195 | 975
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.15.1 | 1.3.1.15 | general | Profile Reach | general |  |  | 0 | 68 | 0 | 1.3.1.15 |  |  | 0 | 0
1136 | DEL-0024 | TSK-01127 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.15.1.1 | 1.3.1.15.1 | general | Profile Reach | general | Analyst | Mid | 2 |  |  | 1.3.1.15.1 |  |  | 195 | 390
1137 | DEL-0024 | TSK-01128 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.15.1.2 | 1.3.1.15.1 | general | Profile Reach | general | QA Specialist | Mid | 3 |  |  | 1.3.1.15.1.1 |  |  | 195 | 585
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.16 | 1.3.1 | Recap Reports | Recap Reports |  |  |  | 4 | 68 | 0 | 1.3.1.15 |  |  | 195 | 780
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.16.1 | 1.3.1.16 | general | Recap Reports | general |  |  | 0 | 68 | 0 | 1.3.1.16 |  |  | 0 | 0
1146 | DEL-0024 | TSK-01137 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.16.1.1 | 1.3.1.16.1 | general | Recap Reports | general | Account Manager | Mid | 2 |  |  | 1.3.1.16.1 |  |  | 195 | 390
1147 | DEL-0024 | TSK-01138 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.16.1.2 | 1.3.1.16.1 | general | Recap Reports | general | Analyst | Mid | 2 |  |  | 1.3.1.16.1.1 |  |  | 195 | 390
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.17 | 1.3.1 | Social Reporting | Social Reporting |  |  |  | 4 | 68 | 0 | 1.3.1.16 |  |  | 195 | 780
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.17.1 | 1.3.1.17 | general | Social Reporting | general |  |  | 0 | 68 | 0 | 1.3.1.17 |  |  | 0 | 0
1148 | DEL-0024 | TSK-01139 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.17.1.1 | 1.3.1.17.1 | general | Social Reporting | general | Account Manager | Mid | 2 |  |  | 1.3.1.17.1 |  |  | 195 | 390
1149 | DEL-0024 | TSK-01140 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.17.1.2 | 1.3.1.17.1 | general | Social Reporting | general | Analyst | Mid | 2 |  |  | 1.3.1.17.1.1 |  |  | 195 | 390
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.18 | 1.3.1 | Update/maintain Z/Russia tracker | Update/maintain Z/Russia tracker |  |  |  | 2 | 68 | 0 | 1.3.1.17 |  |  | 195 | 390
| DEL-0024 |  | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.18.1 | 1.3.1.18 | general | Update/maintain Z/Russia tracker | general |  |  | 0 | 68 | 0 | 1.3.1.18 |  |  | 0 | 0
1152 | DEL-0024 | TSK-01143 | Integrated Marketing Management | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.3.1.18.1.1 | 1.3.1.18.1 | general | Update/maintain Z/Russia tracker | general | Analyst | Mid | 2 |  |  | 1.3.1.18.1 |  |  | 195 | 390