## Scenario A
Row_ID | Deliverable_Code | Task_Code | Service_Department | Deliverable | Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes | Rate_USD | Price_USD
[5 empty] | Vascano Tequila - RFP Creative Services 2022 (8) | 1 |  | Vascano Tequila - RFP Creative Services 2022 (8) | Project |  |  |  | 0 | 0 |  |  |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1 | 1 | Brand Style & Usage Guidelines |  |  |  |  | 250 | 0 | 9 |  |  | Core/T2_MediumVolume | 195 | 48750
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1 | 1.1 | Color Palettes | Color Palettes |  |  |  | 13 | 0 | 2 | 1.1 |  |  | 195 | 2535
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.1 | 1.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions |  |  | 0 | 0 | 2 | 1.1.1 |  |  | 0 | 0
579 | DEL-0009 | TSK-00570 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.1.1 | 1.1.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.1.1.1 |  |  | 0 | 0
583 | DEL-0009 | TSK-00574 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.1.2 | 1.1.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Art Director | Lead/Director | 1 |  |  | 1.1.1.1.1 |  |  | 0 | 0
580 | DEL-0009 | TSK-00571 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.1.3 | 1.1.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Creative Director | Lead/Director | 3 |  |  | 1.1.1.1.2 |  |  | 0 | 0
582 | DEL-0009 | TSK-00573 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.1.4 | 1.1.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Designer | Mid | 4 |  |  | 1.1.1.1.3 |  |  | 0 | 0
581 | DEL-0009 | TSK-00572 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.1.5 | 1.1.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.1.1.4 |  |  | 0 | 0
578 | DEL-0009 | TSK-00569 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.1.6 | 1.1.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | QA Specialist | Mid | 3 |  |  | 1.1.1.1.5 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2 | 1.1 | Logo Lock-Ups | Logo Lock-Ups |  |  |  | 28 | 2 | 7 | 1.1.1 |  |  | 195 | 5460
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.1 | 1.1.2 | Quality Check (Specs/Accessibility) | Logo Lock-Ups | Quality Check (Specs/Accessibility) |  |  | 0 | 2 | 2 | 1.1.2 |  |  | 0 | 0
626 | DEL-0009 | TSK-00617 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.1.1 | 1.1.2.1 | Quality Check (Specs/Accessibility) | Logo Lock-Ups | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.1.2.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.2 | 1.1.2 | Internal Review & Critique | Logo Lock-Ups | Internal Review & Critique |  |  | 0 | 4 | 2 | 1.1.2.1.1 |  |  | 0 | 0
622 | DEL-0009 | TSK-00613 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.2.1 | 1.1.2.2 | Internal Review & Critique | Logo Lock-Ups | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.3 | 1.1.2 | Client Review & Revisions | Logo Lock-Ups | Client Review & Revisions |  |  | 0 | 6 | 3 | 1.1.2.2.1 |  |  | 0 | 0
618 | DEL-0009 | TSK-00609 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.3.1 | 1.1.2.3 | Client Review & Revisions | Logo Lock-Ups | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.1.2.3 |  |  | 0 | 0
619 | DEL-0009 | TSK-00610 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.3.2 | 1.1.2.3 | Client Review & Revisions | Logo Lock-Ups | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.2.3.1 |  |  | 0 | 0
620 | DEL-0009 | TSK-00611 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.3.3 | 1.1.2.3 | Client Review & Revisions | Logo Lock-Ups | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.2.3.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.4 | 1.1.2 | Final Packaging | Logo Lock-Ups | Final Packaging |  |  | 0 | 9 | 0 | 1.1.2.3.3 |  |  | 0 | 0
621 | DEL-0009 | TSK-00612 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.4.1 | 1.1.2.4 | Final Packaging | Logo Lock-Ups | Final Packaging | Designer | Mid | 21 |  |  | 1.1.2.4 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3 | 1.1 | Logo Placement | Logo Placement |  |  |  | 27 | 2 | 7 | 1.1.2 |  |  | 195 | 5265
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.1 | 1.1.3 | Quality Check (Specs/Accessibility) | Logo Placement | Quality Check (Specs/Accessibility) |  |  | 0 | 2 | 2 | 1.1.3 |  |  | 0 | 0
635 | DEL-0009 | TSK-00626 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.1.1 | 1.1.3.1 | Quality Check (Specs/Accessibility) | Logo Placement | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.1.3.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.2 | 1.1.3 | Internal Review & Critique | Logo Placement | Internal Review & Critique |  |  | 0 | 4 | 2 | 1.1.3.1.1 |  |  | 0 | 0
631 | DEL-0009 | TSK-00622 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.2.1 | 1.1.3.2 | Internal Review & Critique | Logo Placement | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.3.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.3 | 1.1.3 | Client Review & Revisions | Logo Placement | Client Review & Revisions |  |  | 0 | 6 | 3 | 1.1.3.2.1 |  |  | 0 | 0
627 | DEL-0009 | TSK-00618 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.3.1 | 1.1.3.3 | Client Review & Revisions | Logo Placement | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.1.3.3 |  |  | 0 | 0
628 | DEL-0009 | TSK-00619 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.3.2 | 1.1.3.3 | Client Review & Revisions | Logo Placement | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.3.3.1 |  |  | 0 | 0
629 | DEL-0009 | TSK-00620 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.3.3 | 1.1.3.3 | Client Review & Revisions | Logo Placement | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.3.3.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.4 | 1.1.3 | Final Packaging | Logo Placement | Final Packaging |  |  | 0 | 9 | 0 | 1.1.3.3.3 |  |  | 0 | 0
630 | DEL-0009 | TSK-00621 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.4.1 | 1.1.3.4 | Final Packaging | Logo Placement | Final Packaging | Designer | Mid | 20 |  |  | 1.1.3.4 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4 | 1.1 | Brand Do's & Dont's | Brand Do's & Dont's |  |  |  | 33 | 4 | 5 | 1.1.3 |  |  | 195 | 6435
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.1 | 1.1.4 | Internal Review & Critique | Brand Do's & Dont's | Internal Review & Critique |  |  | 0 | 4 | 2 | 1.1.4 |  |  | 0 | 0
573 | DEL-0009 | TSK-00564 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.1.1 | 1.1.4.1 | Internal Review & Critique | Brand Do's & Dont's | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.4.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.2 | 1.1.4 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions |  |  | 0 | 6 | 3 | 1.1.4.1.1 |  |  | 0 | 0
568 | DEL-0009 | TSK-00559 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.2.1 | 1.1.4.2 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.1.4.2 |  |  | 0 | 0
569 | DEL-0009 | TSK-00560 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.2.2 | 1.1.4.2 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.1.4.2.1 |  |  | 0 | 0
570 | DEL-0009 | TSK-00561 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.2.3 | 1.1.4.2 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.4.2.2 |  |  | 0 | 0
571 | DEL-0009 | TSK-00562 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.2.4 | 1.1.4.2 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.4.2.3 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.3 | 1.1.4 | Outline & Examples | Brand Do's & Dont's | Outline & Examples |  |  | 0 | 9 | 0 | 1.1.4.2.4 |  |  | 0 | 0
575 | DEL-0009 | TSK-00566 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.3.1 | 1.1.4.3 | Outline & Examples | Brand Do's & Dont's | Outline & Examples | Copywriter | Mid | 2 |  |  | 1.1.4.3 |  |  | 0 | 0
572 | DEL-0009 | TSK-00563 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.3.2 | 1.1.4.3 | Outline & Examples | Brand Do's & Dont's | Outline & Examples | Designer | Mid | 26 |  |  | 1.1.4.3.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5 | 1.1 | Design Style Tile | Design Style Tile |  |  |  | 23 | 4 | 5 | 1.1.4 |  |  | 195 | 4485
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.1 | 1.1.5 | Internal Review & Critique | Design Style Tile | Internal Review & Critique |  |  | 0 | 4 | 2 | 1.1.5 |  |  | 0 | 0
590 | DEL-0009 | TSK-00581 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.1.1 | 1.1.5.1 | Internal Review & Critique | Design Style Tile | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.5.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.2 | 1.1.5 | Client Review & Revisions | Design Style Tile | Client Review & Revisions |  |  | 0 | 6 | 3 | 1.1.5.1.1 |  |  | 0 | 0
586 | DEL-0009 | TSK-00577 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.2.1 | 1.1.5.2 | Client Review & Revisions | Design Style Tile | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.5.2 |  |  | 0 | 0
587 | DEL-0009 | TSK-00578 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.2.2 | 1.1.5.2 | Client Review & Revisions | Design Style Tile | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.5.2.1 |  |  | 0 | 0
588 | DEL-0009 | TSK-00579 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.2.3 | 1.1.5.2 | Client Review & Revisions | Design Style Tile | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.5.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.3 | 1.1.5 | Style Tile Build | Design Style Tile | Style Tile Build |  |  | 0 | 9 | 0 | 1.1.5.2.3 |  |  | 0 | 0
592 | DEL-0009 | TSK-00583 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.3.1 | 1.1.5.3 | Style Tile Build | Design Style Tile | Style Tile Build | Art Director | Lead/Director | 1 |  |  | 1.1.5.3 |  |  | 0 | 0
589 | DEL-0009 | TSK-00580 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.3.2 | 1.1.5.3 | Style Tile Build | Design Style Tile | Style Tile Build | Designer | Mid | 17 |  |  | 1.1.5.3.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6 | 1.1 | Image Use Guidance | Image Use Guidance |  |  |  | 23 | 4 | 5 | 1.1.5 |  |  | 195 | 4485
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.1 | 1.1.6 | Internal Review & Critique | Image Use Guidance | Internal Review & Critique |  |  | 0 | 4 | 2 | 1.1.6 |  |  | 0 | 0
608 | DEL-0009 | TSK-00599 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.1.1 | 1.1.6.1 | Internal Review & Critique | Image Use Guidance | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.6.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.2 | 1.1.6 | Client Review & Revisions | Image Use Guidance | Client Review & Revisions |  |  | 0 | 6 | 3 | 1.1.6.1.1 |  |  | 0 | 0
602 | DEL-0009 | TSK-00593 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.2.1 | 1.1.6.2 | Client Review & Revisions | Image Use Guidance | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.6.2 |  |  | 0 | 0
603 | DEL-0009 | TSK-00594 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.2.2 | 1.1.6.2 | Client Review & Revisions | Image Use Guidance | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.6.2.1 |  |  | 0 | 0
604 | DEL-0009 | TSK-00595 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.2.3 | 1.1.6.2 | Client Review & Revisions | Image Use Guidance | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.6.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.3 | 1.1.6 | Examples & Callouts | Image Use Guidance | Examples & Callouts |  |  | 0 | 9 | 0 | 1.1.6.2.3 |  |  | 0 | 0
607 | DEL-0009 | TSK-00598 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.3.1 | 1.1.6.3 | Examples & Callouts | Image Use Guidance | Examples & Callouts | Art Director | Lead/Director | 1 |  |  | 1.1.6.3 |  |  | 0 | 0
605 | DEL-0009 | TSK-00596 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.3.2 | 1.1.6.3 | Examples & Callouts | Image Use Guidance | Examples & Callouts | Designer | Mid | 17 |  |  | 1.1.6.3.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7 | 1.1 | Imagery Style | Imagery Style |  |  |  | 23 | 4 | 5 | 1.1.6 |  |  | 195 | 4485
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.1 | 1.1.7 | Internal Review & Critique | Imagery Style | Internal Review & Critique |  |  | 0 | 4 | 2 | 1.1.7 |  |  | 0 | 0
616 | DEL-0009 | TSK-00607 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.1.1 | 1.1.7.1 | Internal Review & Critique | Imagery Style | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.7.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.2 | 1.1.7 | Client Review & Revisions | Imagery Style | Client Review & Revisions |  |  | 0 | 6 | 3 | 1.1.7.1.1 |  |  | 0 | 0
610 | DEL-0009 | TSK-00601 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.2.1 | 1.1.7.2 | Client Review & Revisions | Imagery Style | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.7.2 |  |  | 0 | 0
611 | DEL-0009 | TSK-00602 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.2.2 | 1.1.7.2 | Client Review & Revisions | Imagery Style | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.7.2.1 |  |  | 0 | 0
612 | DEL-0009 | TSK-00603 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.2.3 | 1.1.7.2 | Client Review & Revisions | Imagery Style | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.7.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.3 | 1.1.7 | Examples & Callouts | Imagery Style | Examples & Callouts |  |  | 0 | 9 | 0 | 1.1.7.2.3 |  |  | 0 | 0
615 | DEL-0009 | TSK-00606 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.3.1 | 1.1.7.3 | Examples & Callouts | Imagery Style | Examples & Callouts | Art Director | Lead/Director | 1 |  |  | 1.1.7.3 |  |  | 0 | 0
613 | DEL-0009 | TSK-00604 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.3.2 | 1.1.7.3 | Examples & Callouts | Imagery Style | Examples & Callouts | Designer | Mid | 17 |  |  | 1.1.7.3.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8 | 1.1 | Photo & Video Direction | Photo & Video Direction |  |  |  | 25 | 4 | 5 | 1.1.7 |  |  | 195 | 4875
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.1 | 1.1.8 | Internal Review & Critique | Photo & Video Direction | Internal Review & Critique |  |  | 0 | 4 | 2 | 1.1.8 |  |  | 0 | 0
642 | DEL-0009 | TSK-00633 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.1.1 | 1.1.8.1 | Internal Review & Critique | Photo & Video Direction | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.8.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.2 | 1.1.8 | Client Review & Revisions | Photo & Video Direction | Client Review & Revisions |  |  | 0 | 6 | 3 | 1.1.8.1.1 |  |  | 0 | 0
636 | DEL-0009 | TSK-00627 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.2.1 | 1.1.8.2 | Client Review & Revisions | Photo & Video Direction | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.8.2 |  |  | 0 | 0
637 | DEL-0009 | TSK-00628 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.2.2 | 1.1.8.2 | Client Review & Revisions | Photo & Video Direction | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.8.2.1 |  |  | 0 | 0
638 | DEL-0009 | TSK-00629 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.2.3 | 1.1.8.2 | Client Review & Revisions | Photo & Video Direction | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.8.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.3 | 1.1.8 | Direction Pages | Photo & Video Direction | Direction Pages |  |  | 0 | 9 | 0 | 1.1.8.2.3 |  |  | 0 | 0
639 | DEL-0009 | TSK-00630 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.3.1 | 1.1.8.3 | Direction Pages | Photo & Video Direction | Direction Pages | Art Director | Lead/Director | 1 |  |  | 1.1.8.3 |  |  | 0 | 0
640 | DEL-0009 | TSK-00631 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.3.2 | 1.1.8.3 | Direction Pages | Photo & Video Direction | Direction Pages | Creative Director | Lead/Director | 2 |  |  | 1.1.8.3.1 |  |  | 0 | 0
641 | DEL-0009 | TSK-00632 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.3.3 | 1.1.8.3 | Direction Pages | Photo & Video Direction | Direction Pages | Designer | Mid | 17 |  |  | 1.1.8.3.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9 | 1.1 | Typography | Typography |  |  |  | 18 | 4 | 5 | 1.1.8 |  |  | 195 | 3510
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.1 | 1.1.9 | Internal Review & Critique | Typography | Internal Review & Critique |  |  | 0 | 4 | 2 | 1.1.9 |  |  | 0 | 0
649 | DEL-0009 | TSK-00640 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.1.1 | 1.1.9.1 | Internal Review & Critique | Typography | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.9.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.2 | 1.1.9 | Client Review & Revisions | Typography | Client Review & Revisions |  |  | 0 | 6 | 3 | 1.1.9.1.1 |  |  | 0 | 0
645 | DEL-0009 | TSK-00636 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.2.1 | 1.1.9.2 | Client Review & Revisions | Typography | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.1.9.2 |  |  | 0 | 0
646 | DEL-0009 | TSK-00637 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.2.2 | 1.1.9.2 | Client Review & Revisions | Typography | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.9.2.1 |  |  | 0 | 0
647 | DEL-0009 | TSK-00638 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.2.3 | 1.1.9.2 | Client Review & Revisions | Typography | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.9.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.3 | 1.1.9 | Final Packaging | Typography | Final Packaging |  |  | 0 | 9 | 0 | 1.1.9.2.3 |  |  | 0 | 0
648 | DEL-0009 | TSK-00639 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.3.1 | 1.1.9.3 | Final Packaging | Typography | Final Packaging | Designer | Mid | 14 |  |  | 1.1.9.3 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10 | 1.1 | Use Cases | Use Cases |  |  |  | 22 | 4 | 5 | 1.1.9 |  |  | 195 | 4290
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.1 | 1.1.10 | Internal Review & Critique | Use Cases | Internal Review & Critique |  |  | 0 | 4 | 2 | 1.1.10 |  |  | 0 | 0
656 | DEL-0009 | TSK-00647 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.1.1 | 1.1.10.1 | Internal Review & Critique | Use Cases | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.10.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.2 | 1.1.10 | Client Review & Revisions | Use Cases | Client Review & Revisions |  |  | 0 | 6 | 3 | 1.1.10.1.1 |  |  | 0 | 0
652 | DEL-0009 | TSK-00643 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.2.1 | 1.1.10.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.10.2 |  |  | 0 | 0
653 | DEL-0009 | TSK-00644 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.2.2 | 1.1.10.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.10.2.1 |  |  | 0 | 0
654 | DEL-0009 | TSK-00645 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.2.3 | 1.1.10.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.10.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.3 | 1.1.10 | Final Packaging | Use Cases | Final Packaging |  |  | 0 | 9 | 0 | 1.1.10.2.3 |  |  | 0 | 0
655 | DEL-0009 | TSK-00646 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.3.1 | 1.1.10.3 | Final Packaging | Use Cases | Final Packaging | Designer | Mid | 17 |  |  | 1.1.10.3 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11 | 1.1 | Graphic Treatment Direction | Graphic Treatment Direction |  |  |  | 15 | 9 | 0 | 1.1.10 |  |  | 195 | 2925
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11.1 | 1.1.11 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions |  |  | 0 | 9 | 0 | 1.1.11 |  |  | 0 | 0
594 | DEL-0009 | TSK-00585 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11.1.1 | 1.1.11.1 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.11.1 |  |  | 0 | 0
598 | DEL-0009 | TSK-00589 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11.1.2 | 1.1.11.1 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Art Director | Lead/Director | 2 |  |  | 1.1.11.1.1 |  |  | 0 | 0
595 | DEL-0009 | TSK-00586 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11.1.3 | 1.1.11.1 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Creative Director | Lead/Director | 7 |  |  | 1.1.11.1.2 |  |  | 0 | 0
597 | DEL-0009 | TSK-00588 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11.1.4 | 1.1.11.1 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.1.11.1.3 |  |  | 0 | 0
596 | DEL-0009 | TSK-00587 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11.1.5 | 1.1.11.1 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.1.11.1.4 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2 | 1 | Brand Identity Development |  |  |  |  | 255 | 9 | 12 | 1.1 |  | Core/T2_MediumVolume | 195 | 49725
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1 | 1.2 | Color Palette | Color Palette |  |  |  | 15 | 9 | 2 | 1.2 |  |  | 195 | 2925
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1.1 | 1.2.1 | Client Review & Revisions | Color Palette | Client Review & Revisions |  |  | 0 | 9 | 2 | 1.2.1 |  |  | 0 | 0
475 | DEL-0008 | TSK-00466 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1.1.1 | 1.2.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.1.1 |  |  | 0 | 0
480 | DEL-0008 | TSK-00471 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1.1.2 | 1.2.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Art Director | Lead/Director | 1 |  |  | 1.2.1.1.1 |  |  | 0 | 0
476 | DEL-0008 | TSK-00467 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1.1.3 | 1.2.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Creative Director | Lead/Director | 3 |  |  | 1.2.1.1.2 |  |  | 0 | 0
478 | DEL-0008 | TSK-00469 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1.1.4 | 1.2.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Designer | Mid | 6 |  |  | 1.2.1.1.3 |  |  | 0 | 0
477 | DEL-0008 | TSK-00468 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1.1.5 | 1.2.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.2.1.1.4 |  |  | 0 | 0
474 | DEL-0008 | TSK-00465 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1.1.6 | 1.2.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | QA Specialist | Mid | 3 |  |  | 1.2.1.1.5 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2 | 1.2 | Graphic Mock-Ups | Graphic Mock-Ups |  |  |  | 25 | 11 | 8 | 1.2.1 |  |  | 195 | 4875
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.1 | 1.2.2 | Compositing/Retouch | Graphic Mock-Ups | Compositing/Retouch |  |  | 0 | 11 | 3 | 1.2.2 |  |  | 0 | 0
496 | DEL-0008 | TSK-00487 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.1.1 | 1.2.2.1 | Compositing/Retouch | Graphic Mock-Ups | Compositing/Retouch | Retoucher | Mid | 4 |  |  | 1.2.2.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.2 | 1.2.2 | Internal Review & Critique | Graphic Mock-Ups | Internal Review & Critique |  |  | 0 | 16 | 2 | 1.2.2.1.1 |  |  | 0 | 0
498 | DEL-0008 | TSK-00489 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.2.1 | 1.2.2.2 | Internal Review & Critique | Graphic Mock-Ups | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.2.2.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.3 | 1.2.2 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions |  |  | 0 | 18 | 3 | 1.2.2.2.1 |  |  | 0 | 0
493 | DEL-0008 | TSK-00484 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.3.1 | 1.2.2.3 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.2.2.3 |  |  | 0 | 0
494 | DEL-0008 | TSK-00485 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.3.2 | 1.2.2.3 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.2.3.1 |  |  | 0 | 0
495 | DEL-0008 | TSK-00486 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.3.3 | 1.2.2.3 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.2.2.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.4 | 1.2.2 | Mockup Scenarios (3-4) | Graphic Mock-Ups | Mockup Scenarios (3-4) |  |  | 0 | 21 | 0 | 1.2.2.3.3 |  |  | 0 | 0
500 | DEL-0008 | TSK-00491 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.4.1 | 1.2.2.4 | Mockup Scenarios (3-4) | Graphic Mock-Ups | Mockup Scenarios (3-4) | Art Director | Lead/Director | 3 |  |  | 1.2.2.4 |  |  | 0 | 0
497 | DEL-0008 | TSK-00488 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.4.2 | 1.2.2.4 | Mockup Scenarios (3-4) | Graphic Mock-Ups | Mockup Scenarios (3-4) | Designer | Mid | 13 |  |  | 1.2.2.4.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3 | 1.2 | Logo | Logo |  |  |  | 37 | 14 | 7 | 1.2.2 |  |  | 195 | 7215
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.1 | 1.2.3 | Quality Check (Specs/Accessibility) | Logo | Quality Check (Specs/Accessibility) |  |  | 0 | 14 | 2 | 1.2.3 |  |  | 0 | 0
520 | DEL-0008 | TSK-00511 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.1.1 | 1.2.3.1 | Quality Check (Specs/Accessibility) | Logo | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.2.3.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.2 | 1.2.3 | Internal Review & Critique | Logo | Internal Review & Critique |  |  | 0 | 16 | 2 | 1.2.3.1.1 |  |  | 0 | 0
515 | DEL-0008 | TSK-00506 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.2.1 | 1.2.3.2 | Internal Review & Critique | Logo | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.2.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.3 | 1.2.3 | Client Review & Revisions | Logo | Client Review & Revisions |  |  | 0 | 18 | 3 | 1.2.3.2.1 |  |  | 0 | 0
511 | DEL-0008 | TSK-00502 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.3.1 | 1.2.3.3 | Client Review & Revisions | Logo | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.3.3 |  |  | 0 | 0
512 | DEL-0008 | TSK-00503 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.3.2 | 1.2.3.3 | Client Review & Revisions | Logo | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.3.3.1 |  |  | 0 | 0
513 | DEL-0008 | TSK-00504 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.3.3 | 1.2.3.3 | Client Review & Revisions | Logo | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.2.3.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.4 | 1.2.3 | Logo Exploration (6-8 dirs) | Logo | Logo Exploration (6-8 dirs) |  |  | 0 | 21 | 0 | 1.2.3.3.3 |  |  | 0 | 0
517 | DEL-0008 | TSK-00508 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.4.1 | 1.2.3.4 | Logo Exploration (6-8 dirs) | Logo | Logo Exploration (6-8 dirs) | Art Director | Lead/Director | 3 |  |  | 1.2.3.4 |  |  | 0 | 0
514 | DEL-0008 | TSK-00505 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.4.2 | 1.2.3.4 | Logo Exploration (6-8 dirs) | Logo | Logo Exploration (6-8 dirs) | Designer | Mid | 27 |  |  | 1.2.3.4.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4 | 1.2 | Typography | Typography |  |  |  | 34 | 14 | 7 | 1.2.3 |  |  | 195 | 6630
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.1 | 1.2.4 | Quality Check (Specs/Accessibility) | Typography | Quality Check (Specs/Accessibility) |  |  | 0 | 14 | 2 | 1.2.4 |  |  | 0 | 0
556 | DEL-0008 | TSK-00547 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.1.1 | 1.2.4.1 | Quality Check (Specs/Accessibility) | Typography | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.2.4.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.2 | 1.2.4 | Internal Review & Critique | Typography | Internal Review & Critique |  |  | 0 | 16 | 2 | 1.2.4.1.1 |  |  | 0 | 0
554 | DEL-0008 | TSK-00545 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.2.1 | 1.2.4.2 | Internal Review & Critique | Typography | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.2.4.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.3 | 1.2.4 | Client Review & Revisions | Typography | Client Review & Revisions |  |  | 0 | 18 | 3 | 1.2.4.2.1 |  |  | 0 | 0
549 | DEL-0008 | TSK-00540 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.3.1 | 1.2.4.3 | Client Review & Revisions | Typography | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.4.3 |  |  | 0 | 0
550 | DEL-0008 | TSK-00541 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.3.2 | 1.2.4.3 | Client Review & Revisions | Typography | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.4.3.1 |  |  | 0 | 0
551 | DEL-0008 | TSK-00542 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.3.3 | 1.2.4.3 | Client Review & Revisions | Typography | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.2.4.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.4 | 1.2.4 | Final Packaging | Typography | Final Packaging |  |  | 0 | 21 | 0 | 1.2.4.3.3 |  |  | 0 | 0
552 | DEL-0008 | TSK-00543 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.4.1 | 1.2.4.4 | Final Packaging | Typography | Final Packaging | Designer | Mid | 27 |  |  | 1.2.4.4 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5 | 1.2 | Graphic & Copy Messaging Cornerstones | Graphic & Copy Messaging Cornerstones |  |  |  | 23 | 16 | 5 | 1.2.4 |  |  | 195 | 4485
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.1 | 1.2.5 | Internal Review & Critique | Graphic & Copy Messaging Cornerstones | Internal Review & Critique |  |  | 0 | 16 | 2 | 1.2.5 |  |  | 0 | 0
489 | DEL-0008 | TSK-00480 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.1.1 | 1.2.5.1 | Internal Review & Critique | Graphic & Copy Messaging Cornerstones | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.2.5.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.2 | 1.2.5 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions |  |  | 0 | 18 | 3 | 1.2.5.1.1 |  |  | 0 | 0
483 | DEL-0008 | TSK-00474 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.2.1 | 1.2.5.2 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.5.2 |  |  | 0 | 0
484 | DEL-0008 | TSK-00475 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.2.2 | 1.2.5.2 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.5.2.1 |  |  | 0 | 0
485 | DEL-0008 | TSK-00476 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.2.3 | 1.2.5.2 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.5.2.2 |  |  | 0 | 0
486 | DEL-0008 | TSK-00477 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.2.4 | 1.2.5.2 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.2.5.2.3 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.3 | 1.2.5 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft |  |  | 0 | 21 | 0 | 1.2.5.2.4 |  |  | 0 | 0
491 | DEL-0008 | TSK-00482 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.3.1 | 1.2.5.3 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft | Copywriter | Mid | 2 |  |  | 1.2.5.3 |  |  | 0 | 0
492 | DEL-0008 | TSK-00483 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.3.2 | 1.2.5.3 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft | Creative Director | Lead/Director | 2 |  |  | 1.2.5.3.1 |  |  | 0 | 0
487 | DEL-0008 | TSK-00478 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.3.3 | 1.2.5.3 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft | Designer | Mid | 14 |  |  | 1.2.5.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6 | 1.2 | Iconography | Iconography |  |  |  | 27 | 16 | 5 | 1.2.5 |  |  | 195 | 5265
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.1 | 1.2.6 | Internal Review & Critique | Iconography | Internal Review & Critique |  |  | 0 | 16 | 2 | 1.2.6 |  |  | 0 | 0
509 | DEL-0008 | TSK-00500 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.1.1 | 1.2.6.1 | Internal Review & Critique | Iconography | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.2.6.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.2 | 1.2.6 | Client Review & Revisions | Iconography | Client Review & Revisions |  |  | 0 | 18 | 3 | 1.2.6.1.1 |  |  | 0 | 0
502 | DEL-0008 | TSK-00493 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.2.1 | 1.2.6.2 | Client Review & Revisions | Iconography | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.2.6.2 |  |  | 0 | 0
503 | DEL-0008 | TSK-00494 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.2.2 | 1.2.6.2 | Client Review & Revisions | Iconography | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.6.2.1 |  |  | 0 | 0
504 | DEL-0008 | TSK-00495 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.2.3 | 1.2.6.2 | Client Review & Revisions | Iconography | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.2.6.2.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.3 | 1.2.6 | Export & Spec | Iconography | Export & Spec |  |  | 0 | 21 | 0 | 1.2.6.2.3 |  |  | 0 | 0
505 | DEL-0008 | TSK-00496 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.3.1 | 1.2.6.3 | Export & Spec | Iconography | Export & Spec | Designer | Mid | 20 |  |  | 1.2.6.3 |  |  | 0 | 0
508 | DEL-0008 | TSK-00499 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.3.2 | 1.2.6.3 | Export & Spec | Iconography | Export & Spec | Illustrator | Mid | 2 |  |  | 1.2.6.3.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7 | 1.2 | Overarching Moodboard | Overarching Moodboard |  |  |  | 23 | 16 | 5 | 1.2.6 |  |  | 195 | 4485
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.1 | 1.2.7 | Internal Review & Critique | Overarching Moodboard | Internal Review & Critique |  |  | 0 | 16 | 2 | 1.2.7 |  |  | 0 | 0
528 | DEL-0008 | TSK-00519 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.1.1 | 1.2.7.1 | Internal Review & Critique | Overarching Moodboard | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.2.7.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.2 | 1.2.7 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions |  |  | 0 | 18 | 3 | 1.2.7.1.1 |  |  | 0 | 0
522 | DEL-0008 | TSK-00513 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.2.1 | 1.2.7.2 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.2.7.2 |  |  | 0 | 0
523 | DEL-0008 | TSK-00514 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.2.2 | 1.2.7.2 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.7.2.1 |  |  | 0 | 0
524 | DEL-0008 | TSK-00515 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.2.3 | 1.2.7.2 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.2.7.2.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.3 | 1.2.7 | Curate Moodboard | Overarching Moodboard | Curate Moodboard |  |  | 0 | 21 | 0 | 1.2.7.2.3 |  |  | 0 | 0
526 | DEL-0008 | TSK-00517 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.3.1 | 1.2.7.3 | Curate Moodboard | Overarching Moodboard | Curate Moodboard | Art Director | Lead/Director | 2 |  |  | 1.2.7.3 |  |  | 0 | 0
530 | DEL-0008 | TSK-00521 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.3.2 | 1.2.7.3 | Curate Moodboard | Overarching Moodboard | Curate Moodboard | Copywriter | Mid | 2 |  |  | 1.2.7.3.1 |  |  | 0 | 0
525 | DEL-0008 | TSK-00516 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.3.3 | 1.2.7.3 | Curate Moodboard | Overarching Moodboard | Curate Moodboard | Designer | Mid | 14 |  |  | 1.2.7.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8 | 1.2 | Tagline Copy Bank | Tagline Copy Bank |  |  |  | 18 | 16 | 5 | 1.2.7 |  |  | 195 | 3510
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.1 | 1.2.8 | Internal Review & Critique | Tagline Copy Bank | Internal Review & Critique |  |  | 0 | 16 | 2 | 1.2.8 |  |  | 0 | 0
536 | DEL-0008 | TSK-00527 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.1.1 | 1.2.8.1 | Internal Review & Critique | Tagline Copy Bank | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.2.8.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.2 | 1.2.8 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions |  |  | 0 | 18 | 3 | 1.2.8.1.1 |  |  | 0 | 0
531 | DEL-0008 | TSK-00522 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.2.1 | 1.2.8.2 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.8.2 |  |  | 0 | 0
532 | DEL-0008 | TSK-00523 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.2.2 | 1.2.8.2 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.8.2.1 |  |  | 0 | 0
533 | DEL-0008 | TSK-00524 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.2.3 | 1.2.8.2 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.8.2.2 |  |  | 0 | 0
534 | DEL-0008 | TSK-00525 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.2.4 | 1.2.8.2 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.2.8.2.3 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.3 | 1.2.8 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale |  |  | 0 | 21 | 0 | 1.2.8.2.4 |  |  | 0 | 0
538 | DEL-0008 | TSK-00529 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.3.1 | 1.2.8.3 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale | Copywriter | Mid | 3 |  |  | 1.2.8.3 |  |  | 0 | 0
539 | DEL-0008 | TSK-00530 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.3.2 | 1.2.8.3 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale | Creative Director | Lead/Director | 3 |  |  | 1.2.8.3.1 |  |  | 0 | 0
535 | DEL-0008 | TSK-00526 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.3.3 | 1.2.8.3 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale | Designer | Mid | 7 |  |  | 1.2.8.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9 | 1.2 | Textures/Patterns/Materials | Textures/Patterns/Materials |  |  |  | 25 | 16 | 5 | 1.2.8 |  |  | 195 | 4875
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.1 | 1.2.9 | Internal Review & Critique | Textures/Patterns/Materials | Internal Review & Critique |  |  | 0 | 16 | 2 | 1.2.9 |  |  | 0 | 0
546 | DEL-0008 | TSK-00537 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.1.1 | 1.2.9.1 | Internal Review & Critique | Textures/Patterns/Materials | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.2.9.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.2 | 1.2.9 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions |  |  | 0 | 18 | 3 | 1.2.9.1.1 |  |  | 0 | 0
542 | DEL-0008 | TSK-00533 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.2.1 | 1.2.9.2 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.2.9.2 |  |  | 0 | 0
543 | DEL-0008 | TSK-00534 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.2.2 | 1.2.9.2 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.9.2.1 |  |  | 0 | 0
544 | DEL-0008 | TSK-00535 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.2.3 | 1.2.9.2 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.2.9.2.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.3 | 1.2.9 | Build Repeating Tiles | Textures/Patterns/Materials | Build Repeating Tiles |  |  | 0 | 21 | 0 | 1.2.9.2.3 |  |  | 0 | 0
541 | DEL-0008 | TSK-00532 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.3.1 | 1.2.9.3 | Build Repeating Tiles | Textures/Patterns/Materials | Build Repeating Tiles | Designer | Mid | 20 |  |  | 1.2.9.3 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10 | 1.2 | Visual Elements/Comps | Visual Elements/Comps |  |  |  | 28 | 16 | 5 | 1.2.9 |  |  | 195 | 5460
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.1 | 1.2.10 | Internal Review & Critique | Visual Elements/Comps | Internal Review & Critique |  |  | 0 | 16 | 2 | 1.2.10 |  |  | 0 | 0
566 | DEL-0008 | TSK-00557 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.1.1 | 1.2.10.1 | Internal Review & Critique | Visual Elements/Comps | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.2.10.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.2 | 1.2.10 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions |  |  | 0 | 18 | 3 | 1.2.10.1.1 |  |  | 0 | 0
559 | DEL-0008 | TSK-00550 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.2.1 | 1.2.10.2 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.2.10.2 |  |  | 0 | 0
560 | DEL-0008 | TSK-00551 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.2.2 | 1.2.10.2 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.10.2.1 |  |  | 0 | 0
561 | DEL-0008 | TSK-00552 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.2.3 | 1.2.10.2 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.2.10.2.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.3 | 1.2.10 | Compositions (2-3) | Visual Elements/Comps | Compositions (2-3) |  |  | 0 | 21 | 0 | 1.2.10.2.3 |  |  | 0 | 0
562 | DEL-0008 | TSK-00553 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.3.1 | 1.2.10.3 | Compositions (2-3) | Visual Elements/Comps | Compositions (2-3) | Art Director | Lead/Director | 3 |  |  | 1.2.10.3 |  |  | 0 | 0
563 | DEL-0008 | TSK-00554 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.3.2 | 1.2.10.3 | Compositions (2-3) | Visual Elements/Comps | Compositions (2-3) | Designer | Mid | 20 |  |  | 1.2.10.3.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3 | 1 | Development |  |  |  |  | 227 | 21 | 22 | 1.2 |  | Core/T2_MediumVolume | 195 | 44265
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1 | 1.3 | ADA Compliance | ADA Compliance |  |  |  | 50 | 21 | 15 | 1.3 |  |  | 195 | 9750
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.1 | 1.3.1 | Accessibility Audit | ADA Compliance | Accessibility Audit |  |  | 0 | 21 | 3 | 1.3.1 |  |  | 0 | 0
1738 | DEL-0044 | TSK-01729 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.1.1 | 1.3.1.1 | Accessibility Audit | ADA Compliance | Accessibility Audit | Accessibility Specialist | Mid | 2 |  |  | 1.3.1.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.2 | 1.3.1 | Accessibility QA | ADA Compliance | Accessibility QA |  |  | 0 | 31 | 2 | 1.3.1.1.1 |  |  | 0 | 0
1739 | DEL-0044 | TSK-01730 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.2.1 | 1.3.1.2 | Accessibility QA | ADA Compliance | Accessibility QA | Accessibility Specialist | Mid | 2 |  |  | 1.3.1.2 |  |  | 0 | 0
1744 | DEL-0044 | TSK-01735 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.2.2 | 1.3.1.2 | Accessibility QA | ADA Compliance | Accessibility QA | QA Engineer | Mid | 2 |  |  | 1.3.1.2.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.3 | 1.3.1 | Code Review | ADA Compliance | Code Review |  |  | 0 | 33 | 10 | 1.3.1.2.2 |  |  | 0 | 0
1740 | DEL-0044 | TSK-01731 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.3.1 | 1.3.1.3 | Code Review | ADA Compliance | Code Review | Backend Engineer | Mid | 10 |  |  | 1.3.1.3 |  |  | 0 | 0
1742 | DEL-0044 | TSK-01733 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.3.2 | 1.3.1.3 | Code Review | ADA Compliance | Code Review | DevOps Engineer | Mid | 10 |  |  | 1.3.1.3.1 |  |  | 0 | 0
1741 | DEL-0044 | TSK-01732 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.3.3 | 1.3.1.3 | Code Review | ADA Compliance | Code Review | Frontend Engineer | Mid | 20 |  |  | 1.3.1.3.2 |  |  | 0 | 0
1743 | DEL-0044 | TSK-01734 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.3.4 | 1.3.1.3 | Code Review | ADA Compliance | Code Review | Project Manager | Mid | 4 |  |  | 1.3.1.3.3 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2 | 1.3 | Audit & Requirement gathering | Audit & Requirement gathering |  |  |  | 17 | 21 | 3 | 1.3.1 |  |  | 195 | 3315
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2.1 | 1.3.2 | Analytics Audit | Audit & Requirement gathering | Analytics Audit |  |  | 0 | 21 | 3 | 1.3.2 |  |  | 0 | 0
1750 | DEL-0044 | TSK-01741 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2.1.1 | 1.3.2.1 | Analytics Audit | Audit & Requirement gathering | Analytics Audit | Business Analyst | Mid | 9 |  |  | 1.3.2.1 |  |  | 0 | 0
1749 | DEL-0044 | TSK-01740 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2.1.2 | 1.3.2.1 | Analytics Audit | Audit & Requirement gathering | Analytics Audit | Data/Analytics Engineer | Mid | 8 |  |  | 1.3.2.1.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3 | 1.3 | Audit existing UA Property | Audit existing UA Property |  |  |  | 17 | 21 | 3 | 1.3.2 |  |  | 195 | 3315
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3.1 | 1.3.3 | Documentation | Audit existing UA Property | Documentation |  |  | 0 | 21 | 3 | 1.3.3 |  |  | 0 | 0
1753 | DEL-0044 | TSK-01744 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3.1.1 | 1.3.3.1 | Documentation | Audit existing UA Property | Documentation | Business Analyst | Mid | 9 |  |  | 1.3.3.1 |  |  | 0 | 0
1755 | DEL-0044 | TSK-01746 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3.1.2 | 1.3.3.1 | Documentation | Audit existing UA Property | Documentation | Data/Analytics Engineer | Mid | 8 |  |  | 1.3.3.1.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4 | 1.3 | Footer CTA | Footer CTA |  |  |  | 43 | 24 | 19 | 1.3.3 |  |  | 195 | 8385
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.1 | 1.3.4 | Design Consult | Footer CTA | Design Consult |  |  | 0 | 24 | 7 | 1.3.4 |  |  | 0 | 0
1765 | DEL-0044 | TSK-01756 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.1.1 | 1.3.4.1 | Design Consult | Footer CTA | Design Consult | UI Designer | Mid | 3 |  |  | 1.3.4.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.2 | 1.3.4 | Accessibility QA | Footer CTA | Accessibility QA |  |  | 0 | 31 | 2 | 1.3.4.1.1 |  |  | 0 | 0
1760 | DEL-0044 | TSK-01751 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.2.1 | 1.3.4.2 | Accessibility QA | Footer CTA | Accessibility QA | Accessibility Specialist | Mid | 2 |  |  | 1.3.4.2 |  |  | 0 | 0
1767 | DEL-0044 | TSK-01758 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.2.2 | 1.3.4.2 | Accessibility QA | Footer CTA | Accessibility QA | Frontend Engineer | Mid | 1 |  |  | 1.3.4.2.1 |  |  | 0 | 0
1766 | DEL-0044 | TSK-01757 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.2.3 | 1.3.4.2 | Accessibility QA | Footer CTA | Accessibility QA | QA Engineer | Mid | 3 |  |  | 1.3.4.2.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.3 | 1.3.4 | Code Review | Footer CTA | Code Review |  |  | 0 | 33 | 10 | 1.3.4.2.3 |  |  | 0 | 0
1761 | DEL-0044 | TSK-01752 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.3.1 | 1.3.4.3 | Code Review | Footer CTA | Code Review | Backend Engineer | Mid | 10 |  |  | 1.3.4.3 |  |  | 0 | 0
1763 | DEL-0044 | TSK-01754 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.3.2 | 1.3.4.3 | Code Review | Footer CTA | Code Review | DevOps Engineer | Mid | 10 |  |  | 1.3.4.3.1 |  |  | 0 | 0
1762 | DEL-0044 | TSK-01753 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.3.3 | 1.3.4.3 | Code Review | Footer CTA | Code Review | Frontend Engineer | Mid | 10 |  |  | 1.3.4.3.2 |  |  | 0 | 0
1764 | DEL-0044 | TSK-01755 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.3.4 | 1.3.4.3 | Code Review | Footer CTA | Code Review | Project Manager | Mid | 4 |  |  | 1.3.4.3.3 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5 | 1.3 | Header & Footer Navigation | Header & Footer Navigation |  |  |  | 43 | 24 | 19 | 1.3.4 |  |  | 195 | 8385
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.1 | 1.3.5 | Design Consult | Header & Footer Navigation | Design Consult |  |  | 0 | 24 | 7 | 1.3.5 |  |  | 0 | 0
1773 | DEL-0044 | TSK-01764 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.1.1 | 1.3.5.1 | Design Consult | Header & Footer Navigation | Design Consult | UI Designer | Mid | 3 |  |  | 1.3.5.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.2 | 1.3.5 | Accessibility QA | Header & Footer Navigation | Accessibility QA |  |  | 0 | 31 | 2 | 1.3.5.1.1 |  |  | 0 | 0
1768 | DEL-0044 | TSK-01759 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.2.1 | 1.3.5.2 | Accessibility QA | Header & Footer Navigation | Accessibility QA | Accessibility Specialist | Mid | 2 |  |  | 1.3.5.2 |  |  | 0 | 0
1775 | DEL-0044 | TSK-01766 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.2.2 | 1.3.5.2 | Accessibility QA | Header & Footer Navigation | Accessibility QA | Frontend Engineer | Mid | 1 |  |  | 1.3.5.2.1 |  |  | 0 | 0
1774 | DEL-0044 | TSK-01765 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.2.3 | 1.3.5.2 | Accessibility QA | Header & Footer Navigation | Accessibility QA | QA Engineer | Mid | 3 |  |  | 1.3.5.2.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.3 | 1.3.5 | Code Review | Header & Footer Navigation | Code Review |  |  | 0 | 33 | 10 | 1.3.5.2.3 |  |  | 0 | 0
1769 | DEL-0044 | TSK-01760 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.3.1 | 1.3.5.3 | Code Review | Header & Footer Navigation | Code Review | Backend Engineer | Mid | 10 |  |  | 1.3.5.3 |  |  | 0 | 0
1771 | DEL-0044 | TSK-01762 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.3.2 | 1.3.5.3 | Code Review | Header & Footer Navigation | Code Review | DevOps Engineer | Mid | 10 |  |  | 1.3.5.3.1 |  |  | 0 | 0
1770 | DEL-0044 | TSK-01761 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.3.3 | 1.3.5.3 | Code Review | Header & Footer Navigation | Code Review | Frontend Engineer | Mid | 10 |  |  | 1.3.5.3.2 |  |  | 0 | 0
1772 | DEL-0044 | TSK-01763 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.3.4 | 1.3.5.3 | Code Review | Header & Footer Navigation | Code Review | Project Manager | Mid | 4 |  |  | 1.3.5.3.3 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.6 | 1.3 | Additional Goals Setup | Additional Goals Setup |  |  |  | 7 | 31 | 12 | 1.3.5 |  |  | 195 | 1365
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.6.1 | 1.3.6 | QA Cycle | Additional Goals Setup | QA Cycle |  |  | 0 | 31 | 2 | 1.3.6 |  |  | 0 | 0
1747 | DEL-0044 | TSK-01738 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.6.1.1 | 1.3.6.1 | QA Cycle | Additional Goals Setup | QA Cycle | QA Engineer | Mid | 3 |  |  | 1.3.6.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.6.2 | 1.3.6 | Define & Configure Goals | Additional Goals Setup | Define & Configure Goals |  |  | 0 | 33 | 10 | 1.3.6.1.1 |  |  | 0 | 0
1746 | DEL-0044 | TSK-01737 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.6.2.1 | 1.3.6.2 | Define & Configure Goals | Additional Goals Setup | Define & Configure Goals | Data/Analytics Engineer | Mid | 4 |  |  | 1.3.6.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.7 | 1.3 | Custom Event Tracking | Custom Event Tracking |  |  |  | 7 | 31 | 12 | 1.3.6 |  |  | 195 | 1365
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.7.1 | 1.3.7 | QA Cycle | Custom Event Tracking | QA Cycle |  |  | 0 | 31 | 2 | 1.3.7 |  |  | 0 | 0
1758 | DEL-0044 | TSK-01749 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.7.1.1 | 1.3.7.1 | QA Cycle | Custom Event Tracking | QA Cycle | QA Engineer | Mid | 3 |  |  | 1.3.7.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.7.2 | 1.3.7 | Event Schema & Tagging | Custom Event Tracking | Event Schema & Tagging |  |  | 0 | 33 | 10 | 1.3.7.1.1 |  |  | 0 | 0
1757 | DEL-0044 | TSK-01748 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.7.2.1 | 1.3.7.2 | Event Schema & Tagging | Custom Event Tracking | Event Schema & Tagging | Data/Analytics Engineer | Mid | 4 |  |  | 1.3.7.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8 | 1.3 | Implement Paid Media Pixel on website w GTM-Google Ads | Implement Paid Media Pixel on website w GTM-Google Ads |  |  |  | 5 | 31 | 12 | 1.3.7 |  |  | 195 | 975
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8.1 | 1.3.8 | Spec QA | Implement Paid Media Pixel on website w GTM-Google Ads | Spec QA |  |  | 0 | 31 | 2 | 1.3.8 |  |  | 0 | 0
1777 | DEL-0044 | TSK-01768 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8.1.1 | 1.3.8.1 | Spec QA | Implement Paid Media Pixel on website w GTM-Google Ads | Spec QA | QA Engineer | Mid | 3 |  |  | 1.3.8.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8.2 | 1.3.8 | Pixel Setup (GTM) | Implement Paid Media Pixel on website w GTM-Google Ads | Pixel Setup (GTM) |  |  | 0 | 33 | 10 | 1.3.8.1.1 |  |  | 0 | 0
1776 | DEL-0044 | TSK-01767 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8.2.1 | 1.3.8.2 | Pixel Setup (GTM) | Implement Paid Media Pixel on website w GTM-Google Ads | Pixel Setup (GTM) | Data/Analytics Engineer | Mid | 2 |  |  | 1.3.8.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.9 | 1.3 | Implement goals listed in UA as Conversions in G4 | Implement goals listed in UA as Conversions in G4 |  |  |  | 7 | 31 | 12 | 1.3.8 |  |  | 195 | 1365
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.9.1 | 1.3.9 | QA Cycle | Implement goals listed in UA as Conversions in G4 | QA Cycle |  |  | 0 | 31 | 2 | 1.3.9 |  |  | 0 | 0
1779 | DEL-0044 | TSK-01770 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.9.1.1 | 1.3.9.1 | QA Cycle | Implement goals listed in UA as Conversions in G4 | QA Cycle | QA Engineer | Mid | 3 |  |  | 1.3.9.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.9.2 | 1.3.9 | Migrate UA Goals → GA4 Conversions | Implement goals listed in UA as Conversions in G4 | Migrate UA Goals → GA4 Conversions |  |  | 0 | 33 | 10 | 1.3.9.1.1 |  |  | 0 | 0
1778 | DEL-0044 | TSK-01769 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.9.2.1 | 1.3.9.2 | Migrate UA Goals → GA4 Conversions | Implement goals listed in UA as Conversions in G4 | Migrate UA Goals → GA4 Conversions | Data/Analytics Engineer | Mid | 4 |  |  | 1.3.9.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.10 | 1.3 | Implementation | Implementation |  |  |  | 7 | 31 | 12 | 1.3.9 |  |  | 195 | 1365
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.10.1 | 1.3.10 | QA Cycle | Implementation | QA Cycle |  |  | 0 | 31 | 2 | 1.3.10 |  |  | 0 | 0
1782 | DEL-0044 | TSK-01773 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.10.1.1 | 1.3.10.1 | QA Cycle | Implementation | QA Cycle | QA Engineer | Mid | 3 |  |  | 1.3.10.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.10.2 | 1.3.10 | Implement Tags/Events | Implementation | Implement Tags/Events |  |  | 0 | 33 | 10 | 1.3.10.1.1 |  |  | 0 | 0
1781 | DEL-0044 | TSK-01772 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.10.2.1 | 1.3.10.2 | Implement Tags/Events | Implementation | Implement Tags/Events | Data/Analytics Engineer | Mid | 4 |  |  | 1.3.10.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.11 | 1.3 | Outbound link clicks | Outbound link clicks |  |  |  | 5 | 31 | 12 | 1.3.10 |  |  | 195 | 975
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.11.1 | 1.3.11 | QA | Outbound link clicks | QA |  |  | 0 | 31 | 2 | 1.3.11 |  |  | 0 | 0
1785 | DEL-0044 | TSK-01776 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.11.1.1 | 1.3.11.1 | QA | Outbound link clicks | QA | QA Engineer | Mid | 3 |  |  | 1.3.11.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.11.2 | 1.3.11 | Event Config | Outbound link clicks | Event Config |  |  | 0 | 33 | 10 | 1.3.11.1.1 |  |  | 0 | 0
1784 | DEL-0044 | TSK-01775 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.11.2.1 | 1.3.11.2 | Event Config | Outbound link clicks | Event Config | Data/Analytics Engineer | Mid | 2 |  |  | 1.3.11.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.12 | 1.3 | Publishing tags, Testing and Auditing | Publishing tags, Testing and Auditing |  |  |  | 4 | 31 | 2 | 1.3.11 |  |  | 195 | 780
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.12.1 | 1.3.12 | Publish & Smoke Test | Publishing tags, Testing and Auditing | Publish & Smoke Test |  |  | 0 | 31 | 2 | 1.3.12 |  |  | 0 | 0
1786 | DEL-0044 | TSK-01777 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.12.1.1 | 1.3.12.1 | Publish & Smoke Test | Publishing tags, Testing and Auditing | Publish & Smoke Test | Data/Analytics Engineer | Mid | 2 |  |  | 1.3.12.1 |  |  | 0 | 0
1787 | DEL-0044 | TSK-01778 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.12.1.2 | 1.3.12.1 | Publish & Smoke Test | Publishing tags, Testing and Auditing | Publish & Smoke Test | QA Engineer | Mid | 2 |  |  | 1.3.12.1.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.13 | 1.3 | Setup cross-domain tracking | Setup cross-domain tracking |  |  |  | 4 | 31 | 12 | 1.3.12 |  |  | 195 | 780
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.13.1 | 1.3.13 | QA | Setup cross-domain tracking | QA |  |  | 0 | 31 | 2 | 1.3.13 |  |  | 0 | 0
1789 | DEL-0044 | TSK-01780 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.13.1.1 | 1.3.13.1 | QA | Setup cross-domain tracking | QA | QA Engineer | Mid | 2 |  |  | 1.3.13.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.13.2 | 1.3.13 | Cross-domain Config | Setup cross-domain tracking | Cross-domain Config |  |  | 0 | 33 | 10 | 1.3.13.1.1 |  |  | 0 | 0
1788 | DEL-0044 | TSK-01779 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.13.2.1 | 1.3.13.2 | Cross-domain Config | Setup cross-domain tracking | Cross-domain Config | Data/Analytics Engineer | Mid | 2 |  |  | 1.3.13.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.14 | 1.3 | Setup eCommerce tracking | Setup eCommerce tracking |  |  |  | 4 | 31 | 12 | 1.3.13 |  |  | 195 | 780
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.14.1 | 1.3.14 | QA | Setup eCommerce tracking | QA |  |  | 0 | 31 | 2 | 1.3.14 |  |  | 0 | 0
1791 | DEL-0044 | TSK-01782 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.14.1.1 | 1.3.14.1 | QA | Setup eCommerce tracking | QA | QA Engineer | Mid | 2 |  |  | 1.3.14.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.14.2 | 1.3.14 | Ecommerce Data Layer | Setup eCommerce tracking | Ecommerce Data Layer |  |  | 0 | 33 | 10 | 1.3.14.1.1 |  |  | 0 | 0
1790 | DEL-0044 | TSK-01781 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.14.2.1 | 1.3.14.2 | Ecommerce Data Layer | Setup eCommerce tracking | Ecommerce Data Layer | Data/Analytics Engineer | Mid | 2 |  |  | 1.3.14.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15 | 1.3 | Setup new GA4 acct for Caledera House | Setup new GA4 acct for Caledera House |  |  |  | 7 | 31 | 12 | 1.3.14 |  |  | 195 | 1365
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15.1 | 1.3.15 | QA Cycle | Setup new GA4 acct for Caledera House | QA Cycle |  |  | 0 | 31 | 2 | 1.3.15 |  |  | 0 | 0
1793 | DEL-0044 | TSK-01784 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15.1.1 | 1.3.15.1 | QA Cycle | Setup new GA4 acct for Caledera House | QA Cycle | QA Engineer | Mid | 3 |  |  | 1.3.15.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15.2 | 1.3.15 | GA4 Property Setup | Setup new GA4 acct for Caledera House | GA4 Property Setup |  |  | 0 | 33 | 10 | 1.3.15.1.1 |  |  | 0 | 0
1792 | DEL-0044 | TSK-01783 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15.2.1 | 1.3.15.2 | GA4 Property Setup | Setup new GA4 acct for Caledera House | GA4 Property Setup | Data/Analytics Engineer | Mid | 4 |  |  | 1.3.15.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4 | 1 | Pre-Production |  |  |  |  | 396 | 43 | 57 | 1.3 |  | Core/T2_MediumVolume | 195 | 77220
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1 | 1.4 | Wardrobe | Wardrobe |  |  |  | 12 | 43 | 7 | 1.4 |  |  | 195 | 2340
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.1 | 1.4.1 | Wardrobe Brief | Wardrobe | Wardrobe Brief |  |  | 0 | 43 | 2 | 1.4.1 |  |  | 0 | 0
361 | DEL-0004 | TSK-00352 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.1.1 | 1.4.1.1 | Wardrobe Brief | Wardrobe | Wardrobe Brief | Art Director | Lead/Director | 2 |  |  | 1.4.1.1 |  |  | 0 | 0
362 | DEL-0004 | TSK-00353 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.1.2 | 1.4.1.1 | Wardrobe Brief | Wardrobe | Wardrobe Brief | Producer | Mid | 1 |  |  | 1.4.1.1.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.2 | 1.4.1 | Internal Review & Critique | Wardrobe | Internal Review & Critique |  |  | 0 | 93 | 2 | 1.4.1.1.2 |  |  | 0 | 0
359 | DEL-0004 | TSK-00350 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.2.1 | 1.4.1.2 | Internal Review & Critique | Wardrobe | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.1.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.3 | 1.4.1 | Client Review & Revisions | Wardrobe | Client Review & Revisions |  |  | 0 | 95 | 3 | 1.4.1.2.1 |  |  | 0 | 0
354 | DEL-0004 | TSK-00345 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.3.1 | 1.4.1.3 | Client Review & Revisions | Wardrobe | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.1.3 |  |  | 0 | 0
355 | DEL-0004 | TSK-00346 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.3.2 | 1.4.1.3 | Client Review & Revisions | Wardrobe | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.4.1.3.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.4 | 1.4.1 | Final Packaging | Wardrobe | Final Packaging |  |  | 0 | 100 | 0 | 1.4.1.3.2 |  |  | 0 | 0
356 | DEL-0004 | TSK-00347 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.4.1 | 1.4.1.4 | Final Packaging | Wardrobe | Final Packaging | Designer | Mid | 4 |  |  | 1.4.1.4 |  |  | 0 | 0
357 | DEL-0004 | TSK-00348 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.4.2 | 1.4.1.4 | Final Packaging | Wardrobe | Final Packaging | Producer | Mid | 1 |  |  | 1.4.1.4.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2 | 1.4 | Pre-Production Deck | Pre-Production Deck |  |  |  | 26 | 45 | 14 | 1.4.1 |  |  | 195 | 5070
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.1 | 1.4.2 | Content Draft | Pre-Production Deck | Content Draft |  |  | 0 | 45 | 5 | 1.4.2 |  |  | 0 | 0
217 | DEL-0004 | TSK-00217 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.1.1 | 1.4.2.1 | Content Draft | Pre-Production Deck | Content Draft | Designer | Mid | 7 |  |  | 1.4.2.1 |  |  | 0 | 0
214 | DEL-0004 | TSK-00214 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.1.2 | 1.4.2.1 | Content Draft | Pre-Production Deck | Content Draft | Producer | Mid | 4 |  |  | 1.4.2.1.1 |  |  | 0 | 0
215 | DEL-0004 | TSK-00215 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.1.3 | 1.4.2.1 | Content Draft | Pre-Production Deck | Content Draft | Strategist | Mid | 10 |  |  | 1.4.2.1.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.2 | 1.4.2 | Deck Build | Pre-Production Deck | Deck Build |  |  | 0 | 57 | 4 | 1.4.2.1.3 |  |  | 0 | 0
216 | DEL-0004 | TSK-00216 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.2.1 | 1.4.2.2 | Deck Build | Pre-Production Deck | Deck Build | Designer | Mid | 1 |  |  | 1.4.2.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.3 | 1.4.2 | Internal Review & Critique | Pre-Production Deck | Internal Review & Critique |  |  | 0 | 93 | 2 | 1.4.2.2.1 |  |  | 0 | 0
219 | DEL-0004 | TSK-00219 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.3.1 | 1.4.2.3 | Internal Review & Critique | Pre-Production Deck | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.2.3 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.4 | 1.4.2 | Client Review & Revisions | Pre-Production Deck | Client Review & Revisions |  |  | 0 | 95 | 3 | 1.4.2.3.1 |  |  | 0 | 0
212 | DEL-0004 | TSK-00212 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.4.1 | 1.4.2.4 | Client Review & Revisions | Pre-Production Deck | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.2.4 |  |  | 0 | 0
213 | DEL-0004 | TSK-00213 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.4.2 | 1.4.2.4 | Client Review & Revisions | Pre-Production Deck | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.4.2.4.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3 | 1.4 | File Naming Convention & Storage | File Naming Convention & Storage |  |  |  | 12 | 50 | 12 | 1.4.2 |  |  | 195 | 2340
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.1 | 1.4.3 | Schema Design | File Naming Convention & Storage | Schema Design |  |  | 0 | 50 | 7 | 1.4.3 |  |  | 0 | 0
186 | DEL-0004 | TSK-00186 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.1.1 | 1.4.3.1 | Schema Design | File Naming Convention & Storage | Schema Design | Media Manager / DIT | Mid | 2 |  |  | 1.4.3.1 |  |  | 0 | 0
187 | DEL-0004 | TSK-00187 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.1.2 | 1.4.3.1 | Schema Design | File Naming Convention & Storage | Schema Design | Producer | Mid | 1 |  |  | 1.4.3.1.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.2 | 1.4.3 | Internal Review & Critique | File Naming Convention & Storage | Internal Review & Critique |  |  | 0 | 93 | 2 | 1.4.3.1.2 |  |  | 0 | 0
185 | DEL-0004 | TSK-00185 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.2.1 | 1.4.3.2 | Internal Review & Critique | File Naming Convention & Storage | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.3.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.3 | 1.4.3 | Client Review & Revisions | File Naming Convention & Storage | Client Review & Revisions |  |  | 0 | 95 | 3 | 1.4.3.2.1 |  |  | 0 | 0
179 | DEL-0004 | TSK-00179 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.3.1 | 1.4.3.3 | Client Review & Revisions | File Naming Convention & Storage | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.3.3 |  |  | 0 | 0
180 | DEL-0004 | TSK-00180 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.3.2 | 1.4.3.3 | Client Review & Revisions | File Naming Convention & Storage | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.4.3.3.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.4 | 1.4.3 | Distribution & Notes | File Naming Convention & Storage | Distribution & Notes |  |  | 0 | 100 | 0 | 1.4.3.3.2 |  |  | 0 | 0
182 | DEL-0004 | TSK-00182 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.4.1 | 1.4.3.4 | Distribution & Notes | File Naming Convention & Storage | Distribution & Notes | Designer | Mid | 2 |  |  | 1.4.3.4 |  |  | 0 | 0
183 | DEL-0004 | TSK-00183 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.4.2 | 1.4.3.4 | Distribution & Notes | File Naming Convention & Storage | Distribution & Notes | Media Manager / DIT | Mid | 2 |  |  | 1.4.3.4.1 |  |  | 0 | 0
181 | DEL-0004 | TSK-00181 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.4.3 | 1.4.3.4 | Distribution & Notes | File Naming Convention & Storage | Distribution & Notes | Producer | Mid | 1 |  |  | 1.4.3.4.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4 | 1.4 | R1 Pre-Production Deck/Shot List | R1 Pre-Production Deck/Shot List |  |  |  | 17 | 57 | 4 | 1.4.3 |  |  | 195 | 3315
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.1 | 1.4.4 | Client Review & Revisions | R1 Pre-Production Deck/Shot List | Client Review & Revisions |  |  | 0 | 57 | 4 | 1.4.4 |  |  | 0 | 0
230 | DEL-0004 | TSK-00230 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.1.1 | 1.4.4.1 | Client Review & Revisions | R1 Pre-Production Deck/Shot List | Client Review & Revisions | Account Manager | Mid | 3 |  |  | 1.4.4.1 |  |  | 0 | 0
236 | DEL-0004 | TSK-00236 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.1.2 | 1.4.4.1 | Client Review & Revisions | R1 Pre-Production Deck/Shot List | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.4.4.1.1 |  |  | 0 | 0
232 | DEL-0004 | TSK-00232 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.1.3 | 1.4.4.1 | Client Review & Revisions | R1 Pre-Production Deck/Shot List | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.4.4.1.2 |  |  | 0 | 0
231 | DEL-0004 | TSK-00231 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.1.4 | 1.4.4.1 | Client Review & Revisions | R1 Pre-Production Deck/Shot List | Client Review & Revisions | Producer | Mid | 8 |  |  | 1.4.4.1.3 |  |  | 0 | 0
234 | DEL-0004 | TSK-00234 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.1.5 | 1.4.4.1 | Client Review & Revisions | R1 Pre-Production Deck/Shot List | Client Review & Revisions | Project Manager | Mid | 3 |  |  | 1.4.4.1.4 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5 | 1.4 | R2 Pre-Production Deck/Shot List | R2 Pre-Production Deck/Shot List |  |  |  | 17 | 57 | 4 | 1.4.4 |  |  | 195 | 3315
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.1 | 1.4.5 | Client Review & Revisions | R2 Pre-Production Deck/Shot List | Client Review & Revisions |  |  | 0 | 57 | 4 | 1.4.5 |  |  | 0 | 0
238 | DEL-0004 | TSK-00238 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.1.1 | 1.4.5.1 | Client Review & Revisions | R2 Pre-Production Deck/Shot List | Client Review & Revisions | Account Manager | Mid | 3 |  |  | 1.4.5.1 |  |  | 0 | 0
244 | DEL-0004 | TSK-00244 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.1.2 | 1.4.5.1 | Client Review & Revisions | R2 Pre-Production Deck/Shot List | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.4.5.1.1 |  |  | 0 | 0
240 | DEL-0004 | TSK-00240 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.1.3 | 1.4.5.1 | Client Review & Revisions | R2 Pre-Production Deck/Shot List | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.4.5.1.2 |  |  | 0 | 0
239 | DEL-0004 | TSK-00239 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.1.4 | 1.4.5.1 | Client Review & Revisions | R2 Pre-Production Deck/Shot List | Client Review & Revisions | Producer | Mid | 8 |  |  | 1.4.5.1.3 |  |  | 0 | 0
242 | DEL-0004 | TSK-00242 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.1.5 | 1.4.5.1 | Client Review & Revisions | R2 Pre-Production Deck/Shot List | Client Review & Revisions | Project Manager | Mid | 3 |  |  | 1.4.5.1.4 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6 | 1.4 | Run of Show & Call Sheet | Run of Show & Call Sheet |  |  |  | 23 | 57 | 4 | 1.4.5 |  |  | 195 | 4485
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.1 | 1.4.6 | Client Review & Revisions | Run of Show & Call Sheet | Client Review & Revisions |  |  | 0 | 57 | 4 | 1.4.6 |  |  | 0 | 0
246 | DEL-0004 | TSK-00246 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.1.1 | 1.4.6.1 | Client Review & Revisions | Run of Show & Call Sheet | Client Review & Revisions | Account Manager | Mid | 3 |  |  | 1.4.6.1 |  |  | 0 | 0
253 | DEL-0004 | TSK-00253 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.1.2 | 1.4.6.1 | Client Review & Revisions | Run of Show & Call Sheet | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.4.6.1.1 |  |  | 0 | 0
252 | DEL-0004 | TSK-00252 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.1.3 | 1.4.6.1 | Client Review & Revisions | Run of Show & Call Sheet | Client Review & Revisions | Designer | Mid | 1 |  |  | 1.4.6.1.2 |  |  | 0 | 0
247 | DEL-0004 | TSK-00247 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.1.4 | 1.4.6.1 | Client Review & Revisions | Run of Show & Call Sheet | Client Review & Revisions | Producer | Mid | 10 |  |  | 1.4.6.1.3 |  |  | 0 | 0
248 | DEL-0004 | TSK-00248 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.1.5 | 1.4.6.1 | Client Review & Revisions | Run of Show & Call Sheet | Client Review & Revisions | Project Manager | Mid | 8 |  |  | 1.4.6.1.4 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7 | 1.4 | Script & Storyboards | Script & Storyboards |  |  |  | 31 | 57 | 4 | 1.4.6 |  |  | 195 | 6045
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.1 | 1.4.7 | Client Review & Revisions | Script & Storyboards | Client Review & Revisions |  |  | 0 | 57 | 4 | 1.4.7 |  |  | 0 | 0
256 | DEL-0004 | TSK-00256 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.1.1 | 1.4.7.1 | Client Review & Revisions | Script & Storyboards | Client Review & Revisions | Account Manager | Mid | 5 |  |  | 1.4.7.1 |  |  | 0 | 0
270 | DEL-0004 | TSK-00263 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.1.2 | 1.4.7.1 | Client Review & Revisions | Script & Storyboards | Client Review & Revisions | Art Director | Lead/Director | 3 |  |  | 1.4.7.1.1 |  |  | 0 | 0
258 | DEL-0004 | TSK-00257 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.1.3 | 1.4.7.1 | Client Review & Revisions | Script & Storyboards | Client Review & Revisions | Copywriter | Mid | 5 |  |  | 1.4.7.1.2 |  |  | 0 | 0
264 | DEL-0004 | TSK-00260 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.1.4 | 1.4.7.1 | Client Review & Revisions | Script & Storyboards | Client Review & Revisions | Creative Director | Lead/Director | 3 |  |  | 1.4.7.1.3 |  |  | 0 | 0
262 | DEL-0004 | TSK-00259 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.1.5 | 1.4.7.1 | Client Review & Revisions | Script & Storyboards | Client Review & Revisions | Designer | Mid | 5 |  |  | 1.4.7.1.4 |  |  | 0 | 0
260 | DEL-0004 | TSK-00258 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.1.6 | 1.4.7.1 | Client Review & Revisions | Script & Storyboards | Client Review & Revisions | Producer | Mid | 10 |  |  | 1.4.7.1.5 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8 | 1.4 | Shoot Oversight & Direction | Shoot Oversight & Direction |  |  |  | 12 | 57 | 6 | 1.4.7 |  |  | 195 | 2340
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.1 | 1.4.8 | Schedule Management | Shoot Oversight & Direction | Schedule Management |  |  | 0 | 57 | 4 | 1.4.8 |  |  | 0 | 0
280 | DEL-0004 | TSK-00271 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.1.1 | 1.4.8.1 | Schedule Management | Shoot Oversight & Direction | Schedule Management | Producer | Mid | 3 |  |  | 1.4.8.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.2 | 1.4.8 | Quality Check (QC) | Shoot Oversight & Direction | Quality Check (QC) |  |  | 0 | 73 | 2 | 1.4.8.1.1 |  |  | 0 | 0
279 | DEL-0004 | TSK-00270 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.2.1 | 1.4.8.2 | Quality Check (QC) | Shoot Oversight & Direction | Quality Check (QC) | QA Specialist | Mid | 2 |  |  | 1.4.8.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.3 | 1.4.8 | Daily Wrap Notes | Shoot Oversight & Direction | Daily Wrap Notes |  |  | 0 | 100 | 0 | 1.4.8.2.1 |  |  | 0 | 0
274 | DEL-0004 | TSK-00265 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.3.1 | 1.4.8.3 | Daily Wrap Notes | Shoot Oversight & Direction | Daily Wrap Notes | Account Manager | Mid | 2 |  |  | 1.4.8.3 |  |  | 0 | 0
277 | DEL-0004 | TSK-00268 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.3.2 | 1.4.8.3 | Daily Wrap Notes | Shoot Oversight & Direction | Daily Wrap Notes | Art Director | Lead/Director | 1 |  |  | 1.4.8.3.1 |  |  | 0 | 0
278 | DEL-0004 | TSK-00269 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.3.3 | 1.4.8.3 | Daily Wrap Notes | Shoot Oversight & Direction | Daily Wrap Notes | Creative Director | Lead/Director | 2 |  |  | 1.4.8.3.2 |  |  | 0 | 0
275 | DEL-0004 | TSK-00266 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.3.4 | 1.4.8.3 | Daily Wrap Notes | Shoot Oversight & Direction | Daily Wrap Notes | Producer | Mid | 1 |  |  | 1.4.8.3.3 |  |  | 0 | 0
276 | DEL-0004 | TSK-00267 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.3.5 | 1.4.8.3 | Daily Wrap Notes | Shoot Oversight & Direction | Daily Wrap Notes | Project Manager | Mid | 1 |  |  | 1.4.8.3.4 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9 | 1.4 | Shot List | Shot List |  |  |  | 20 | 57 | 4 | 1.4.8 |  |  | 195 | 3900
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.1 | 1.4.9 | Client Review & Revisions | Shot List | Client Review & Revisions |  |  | 0 | 57 | 4 | 1.4.9 |  |  | 0 | 0
281 | DEL-0004 | TSK-00272 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.1.1 | 1.4.9.1 | Client Review & Revisions | Shot List | Client Review & Revisions | Account Manager | Mid | 3 |  |  | 1.4.9.1 |  |  | 0 | 0
283 | DEL-0004 | TSK-00274 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.1.2 | 1.4.9.1 | Client Review & Revisions | Shot List | Client Review & Revisions | Art Director | Lead/Director | 2 |  |  | 1.4.9.1.1 |  |  | 0 | 0
287 | DEL-0004 | TSK-00278 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.1.3 | 1.4.9.1 | Client Review & Revisions | Shot List | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.4.9.1.2 |  |  | 0 | 0
284 | DEL-0004 | TSK-00275 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.1.4 | 1.4.9.1 | Client Review & Revisions | Shot List | Client Review & Revisions | Designer | Mid | 1 |  |  | 1.4.9.1.3 |  |  | 0 | 0
282 | DEL-0004 | TSK-00273 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.1.5 | 1.4.9.1 | Client Review & Revisions | Shot List | Client Review & Revisions | Producer | Mid | 10 |  |  | 1.4.9.1.4 |  |  | 0 | 0
286 | DEL-0004 | TSK-00277 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.1.6 | 1.4.9.1 | Client Review & Revisions | Shot List | Client Review & Revisions | Project Manager | Mid | 3 |  |  | 1.4.9.1.5 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10 | 1.4 | Storyboard Review | Storyboard Review |  |  |  | 4 | 57 | 4 | 1.4.9 |  |  | 195 | 780
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10.1 | 1.4.10 | Internal Crit | Storyboard Review | Internal Crit |  |  | 0 | 57 | 4 | 1.4.10 |  |  | 0 | 0
291 | DEL-0004 | TSK-00282 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10.1.1 | 1.4.10.1 | Internal Crit | Storyboard Review | Internal Crit | Art Director | Lead/Director | 2 |  |  | 1.4.10.1 |  |  | 0 | 0
292 | DEL-0004 | TSK-00283 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10.1.2 | 1.4.10.1 | Internal Crit | Storyboard Review | Internal Crit | Creative Director | Lead/Director | 1 |  |  | 1.4.10.1.1 |  |  | 0 | 0
293 | DEL-0004 | TSK-00284 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10.1.3 | 1.4.10.1 | Internal Crit | Storyboard Review | Internal Crit | Designer | Mid | 1 |  |  | 1.4.10.1.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.11 | 1.4 | Storyboards & Script Writing | Storyboards & Script Writing |  |  |  | 15 | 57 | 4 | 1.4.10 |  |  | 195 | 2925
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.11.1 | 1.4.11 | Client Review & Revisions | Storyboards & Script Writing | Client Review & Revisions |  |  | 0 | 57 | 4 | 1.4.11 |  |  | 0 | 0
294 | DEL-0004 | TSK-00285 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.11.1.1 | 1.4.11.1 | Client Review & Revisions | Storyboards & Script Writing | Client Review & Revisions | Account Manager | Mid | 3 |  |  | 1.4.11.1 |  |  | 0 | 0
301 | DEL-0004 | TSK-00292 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.11.1.2 | 1.4.11.1 | Client Review & Revisions | Storyboards & Script Writing | Client Review & Revisions | Art Director | Lead/Director | 1 |  |  | 1.4.11.1.1 |  |  | 0 | 0
295 | DEL-0004 | TSK-00286 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.11.1.3 | 1.4.11.1 | Client Review & Revisions | Storyboards & Script Writing | Client Review & Revisions | Copywriter | Mid | 3 |  |  | 1.4.11.1.2 |  |  | 0 | 0
298 | DEL-0004 | TSK-00289 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.11.1.4 | 1.4.11.1 | Client Review & Revisions | Storyboards & Script Writing | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.4.11.1.3 |  |  | 0 | 0
297 | DEL-0004 | TSK-00288 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.11.1.5 | 1.4.11.1 | Client Review & Revisions | Storyboards & Script Writing | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.4.11.1.4 |  |  | 0 | 0
296 | DEL-0004 | TSK-00287 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.11.1.6 | 1.4.11.1 | Client Review & Revisions | Storyboards & Script Writing | Client Review & Revisions | Producer | Mid | 5 |  |  | 1.4.11.1.5 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.12 | 1.4 | Casting | Casting |  |  |  | 13 | 61 | 7 | 1.4.11 |  |  | 195 | 2535
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.12.1 | 1.4.12 | Approvals/Holds | Casting | Approvals/Holds |  |  | 0 | 61 | 7 | 1.4.12 |  |  | 0 | 0
150 | DEL-0004 | TSK-00150 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.12.1.1 | 1.4.12.1 | Approvals/Holds | Casting | Approvals/Holds | Account Manager | Mid | 3 |  |  | 1.4.12.1 |  |  | 0 | 0
152 | DEL-0004 | TSK-00152 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.12.1.2 | 1.4.12.1 | Approvals/Holds | Casting | Approvals/Holds | Creative Director | Lead/Director | 1 |  |  | 1.4.12.1.1 |  |  | 0 | 0
151 | DEL-0004 | TSK-00151 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.12.1.3 | 1.4.12.1 | Approvals/Holds | Casting | Approvals/Holds | Producer | Mid | 9 |  |  | 1.4.12.1.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.13 | 1.4 | Load In & Pre-Lighting | Load In & Pre-Lighting |  |  |  | 25 | 61 | 7 | 1.4.12 |  |  | 195 | 4875
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.13.1 | 1.4.13 | Client Review & Revisions | Load In & Pre-Lighting | Client Review & Revisions |  |  | 0 | 61 | 7 | 1.4.13 |  |  | 0 | 0
188 | DEL-0004 | TSK-00188 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.13.1.1 | 1.4.13.1 | Client Review & Revisions | Load In & Pre-Lighting | Client Review & Revisions | Account Manager | Mid | 3 |  |  | 1.4.13.1 |  |  | 0 | 0
196 | DEL-0004 | TSK-00196 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.13.1.2 | 1.4.13.1 | Client Review & Revisions | Load In & Pre-Lighting | Client Review & Revisions | Art Director | Lead/Director | 1 |  |  | 1.4.13.1.1 |  |  | 0 | 0
192 | DEL-0004 | TSK-00192 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.13.1.3 | 1.4.13.1 | Client Review & Revisions | Load In & Pre-Lighting | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.4.13.1.2 |  |  | 0 | 0
191 | DEL-0004 | TSK-00191 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.13.1.4 | 1.4.13.1 | Client Review & Revisions | Load In & Pre-Lighting | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.4.13.1.3 |  |  | 0 | 0
189 | DEL-0004 | TSK-00189 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.13.1.5 | 1.4.13.1 | Client Review & Revisions | Load In & Pre-Lighting | Client Review & Revisions | Producer | Mid | 12 |  |  | 1.4.13.1.4 |  |  | 0 | 0
190 | DEL-0004 | TSK-00190 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.13.1.6 | 1.4.13.1 | Client Review & Revisions | Load In & Pre-Lighting | Client Review & Revisions | Project Manager | Mid | 6 |  |  | 1.4.13.1.5 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.14 | 1.4 | Talent Casting | Talent Casting |  |  |  | 25 | 61 | 7 | 1.4.13 |  |  | 195 | 4875
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.14.1 | 1.4.14 | Approvals & Holds | Talent Casting | Approvals & Holds |  |  | 0 | 61 | 7 | 1.4.14 |  |  | 0 | 0
303 | DEL-0004 | TSK-00294 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.14.1.1 | 1.4.14.1 | Approvals & Holds | Talent Casting | Approvals & Holds | Account Manager | Mid | 6 |  |  | 1.4.14.1 |  |  | 0 | 0
305 | DEL-0004 | TSK-00296 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.14.1.2 | 1.4.14.1 | Approvals & Holds | Talent Casting | Approvals & Holds | Creative Director | Lead/Director | 2 |  |  | 1.4.14.1.1 |  |  | 0 | 0
309 | DEL-0004 | TSK-00300 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.14.1.3 | 1.4.14.1 | Approvals & Holds | Talent Casting | Approvals & Holds | Designer | Mid | 2 |  |  | 1.4.14.1.2 |  |  | 0 | 0
304 | DEL-0004 | TSK-00295 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.14.1.4 | 1.4.14.1 | Approvals & Holds | Talent Casting | Approvals & Holds | Producer | Mid | 15 |  |  | 1.4.14.1.3 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15 | 1.4 | Post Production Plan & Timeline | Post Production Plan & Timeline |  |  |  | 21 | 68 | 10 | 1.4.14 |  |  | 195 | 4095
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.1 | 1.4.15 | Editorial Milestones | Post Production Plan & Timeline | Editorial Milestones |  |  | 0 | 68 | 5 | 1.4.15 |  |  | 0 | 0
203 | DEL-0004 | TSK-00203 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.1.1 | 1.4.15.1 | Editorial Milestones | Post Production Plan & Timeline | Editorial Milestones | Editor | Mid | 8 |  |  | 1.4.15.1 |  |  | 0 | 0
204 | DEL-0004 | TSK-00204 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.1.2 | 1.4.15.1 | Editorial Milestones | Post Production Plan & Timeline | Editorial Milestones | Producer | Mid | 2 |  |  | 1.4.15.1.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.2 | 1.4.15 | Internal Review & Critique | Post Production Plan & Timeline | Internal Review & Critique |  |  | 0 | 93 | 2 | 1.4.15.1.2 |  |  | 0 | 0
207 | DEL-0004 | TSK-00207 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.2.1 | 1.4.15.2 | Internal Review & Critique | Post Production Plan & Timeline | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.15.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.3 | 1.4.15 | Client Review & Revisions | Post Production Plan & Timeline | Client Review & Revisions |  |  | 0 | 95 | 3 | 1.4.15.2.1 |  |  | 0 | 0
198 | DEL-0004 | TSK-00198 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.3.1 | 1.4.15.3 | Client Review & Revisions | Post Production Plan & Timeline | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.15.3 |  |  | 0 | 0
199 | DEL-0004 | TSK-00199 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.3.2 | 1.4.15.3 | Client Review & Revisions | Post Production Plan & Timeline | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.4.15.3.1 |  |  | 0 | 0
200 | DEL-0004 | TSK-00200 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.3.3 | 1.4.15.3 | Client Review & Revisions | Post Production Plan & Timeline | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.4.15.3.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.4 | 1.4.15 | Delivery Timeline | Post Production Plan & Timeline | Delivery Timeline |  |  | 0 | 100 | 0 | 1.4.15.3.3 |  |  | 0 | 0
205 | DEL-0004 | TSK-00205 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.4.1 | 1.4.15.4 | Delivery Timeline | Post Production Plan & Timeline | Delivery Timeline | Designer | Mid | 2 |  |  | 1.4.15.4 |  |  | 0 | 0
201 | DEL-0004 | TSK-00201 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.4.2 | 1.4.15.4 | Delivery Timeline | Post Production Plan & Timeline | Delivery Timeline | Producer | Mid | 3 |  |  | 1.4.15.4.1 |  |  | 0 | 0
202 | DEL-0004 | TSK-00202 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.4.3 | 1.4.15.4 | Delivery Timeline | Post Production Plan & Timeline | Delivery Timeline | Project Manager | Mid | 1 |  |  | 1.4.15.4.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16 | 1.4 | Concept Development | Concept Development |  |  |  | 17 | 75 | 15 | 1.4.15 |  |  | 195 | 3315
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.1 | 1.4.16 | Ideation Sprint | Concept Development | Ideation Sprint |  |  | 0 | 75 | 10 | 1.4.16 |  |  | 0 | 0
160 | DEL-0004 | TSK-00160 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.1.1 | 1.4.16.1 | Ideation Sprint | Concept Development | Ideation Sprint | Art Director | Lead/Director | 1 |  |  | 1.4.16.1 |  |  | 0 | 0
158 | DEL-0004 | TSK-00158 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.1.2 | 1.4.16.1 | Ideation Sprint | Concept Development | Ideation Sprint | Copywriter | Mid | 2 |  |  | 1.4.16.1.1 |  |  | 0 | 0
161 | DEL-0004 | TSK-00161 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.1.3 | 1.4.16.1 | Ideation Sprint | Concept Development | Ideation Sprint | Creative Director | Lead/Director | 2 |  |  | 1.4.16.1.2 |  |  | 0 | 0
159 | DEL-0004 | TSK-00159 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.1.4 | 1.4.16.1 | Ideation Sprint | Concept Development | Ideation Sprint | Designer | Mid | 4 |  |  | 1.4.16.1.3 |  |  | 0 | 0
162 | DEL-0004 | TSK-00162 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.1.5 | 1.4.16.1 | Ideation Sprint | Concept Development | Ideation Sprint | Strategist | Mid | 3 |  |  | 1.4.16.1.4 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.2 | 1.4.16 | Internal Review & Critique | Concept Development | Internal Review & Critique |  |  | 0 | 93 | 2 | 1.4.16.1.5 |  |  | 0 | 0
163 | DEL-0004 | TSK-00163 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.2.1 | 1.4.16.2 | Internal Review & Critique | Concept Development | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.16.2 |  |  | 0 | 0
164 | DEL-0004 | TSK-00164 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.2.2 | 1.4.16.2 | Internal Review & Critique | Concept Development | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.16.2.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.3 | 1.4.16 | Client Review & Revisions | Concept Development | Client Review & Revisions |  |  | 0 | 95 | 3 | 1.4.16.2.2 |  |  | 0 | 0
155 | DEL-0004 | TSK-00155 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.3.1 | 1.4.16.3 | Client Review & Revisions | Concept Development | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.4.16.3 |  |  | 0 | 0
156 | DEL-0004 | TSK-00156 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.3.2 | 1.4.16.3 | Client Review & Revisions | Concept Development | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.4.16.3.1 |  |  | 0 | 0
157 | DEL-0004 | TSK-00157 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.3.3 | 1.4.16.3 | Client Review & Revisions | Concept Development | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.4.16.3.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17 | 1.4 | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) |  |  |  | 10 | 85 | 8 | 1.4.16 |  |  | 195 | 1950
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.1 | 1.4.17 | Inventory & Tracking | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Inventory & Tracking |  |  | 0 | 85 | 3 | 1.4.17 |  |  | 0 | 0
228 | DEL-0004 | TSK-00228 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.1.1 | 1.4.17.1 | Inventory & Tracking | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Inventory & Tracking | Producer | Mid | 1 |  |  | 1.4.17.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.2 | 1.4.17 | Internal Review & Critique | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Internal Review & Critique |  |  | 0 | 93 | 2 | 1.4.17.1.1 |  |  | 0 | 0
227 | DEL-0004 | TSK-00227 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.2.1 | 1.4.17.2 | Internal Review & Critique | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.17.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.3 | 1.4.17 | Client Review & Revisions | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Client Review & Revisions |  |  | 0 | 95 | 3 | 1.4.17.2.1 |  |  | 0 | 0
223 | DEL-0004 | TSK-00223 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.3.1 | 1.4.17.3 | Client Review & Revisions | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.17.3 |  |  | 0 | 0
224 | DEL-0004 | TSK-00224 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.3.2 | 1.4.17.3 | Client Review & Revisions | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.4.17.3.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.4 | 1.4.17 | Chain of Custody | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Chain of Custody |  |  | 0 | 100 | 0 | 1.4.17.3.2 |  |  | 0 | 0
225 | DEL-0004 | TSK-00225 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.4.1 | 1.4.17.4 | Chain of Custody | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Chain of Custody | Designer | Mid | 2 |  |  | 1.4.17.4 |  |  | 0 | 0
229 | DEL-0004 | TSK-00229 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.4.2 | 1.4.17.4 | Chain of Custody | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Chain of Custody | Producer | Mid | 2 |  |  | 1.4.17.4.1 |  |  | 0 | 0
222 | DEL-0004 | TSK-00222 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.4.3 | 1.4.17.4 | Chain of Custody | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Chain of Custody | Project Manager | Mid | 1 |  |  | 1.4.17.4.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.18 | 1.4 | Vendor Deal Memos & Contracts | Vendor Deal Memos & Contracts |  |  |  | 3 | 85 | 3 | 1.4.17 |  |  | 195 | 585
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.18.1 | 1.4.18 | Filing & Tracking | Vendor Deal Memos & Contracts | Filing & Tracking |  |  | 0 | 85 | 3 | 1.4.18 |  |  | 0 | 0
333 | DEL-0004 | TSK-00324 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.18.1.1 | 1.4.18.1 | Filing & Tracking | Vendor Deal Memos & Contracts | Filing & Tracking | Project Manager | Mid | 1 |  |  | 1.4.18.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.18.2 | 1.4.18 | Deal Memos & Contracts | Vendor Deal Memos & Contracts | Deal Memos & Contracts |  |  | 0 | 100 | 0 | 1.4.18.1.1 |  |  | 0 | 0
331 | DEL-0004 | TSK-00322 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.18.2.1 | 1.4.18.2 | Deal Memos & Contracts | Vendor Deal Memos & Contracts | Deal Memos & Contracts | Account Manager | Mid | 1 |  |  | 1.4.18.2 |  |  | 0 | 0
332 | DEL-0004 | TSK-00323 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.18.2.2 | 1.4.18.2 | Deal Memos & Contracts | Vendor Deal Memos & Contracts | Deal Memos & Contracts | Producer | Mid | 1 |  |  | 1.4.18.2.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19 | 1.4 | Vendor Engagement | Vendor Engagement |  |  |  | 13 | 88 | 10 | 1.4.18 |  |  | 195 | 2535
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19.1 | 1.4.19 | Briefing Docs | Vendor Engagement | Briefing Docs |  |  | 0 | 88 | 5 | 1.4.19 |  |  | 0 | 0
339 | DEL-0004 | TSK-00330 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19.1.1 | 1.4.19.1 | Briefing Docs | Vendor Engagement | Briefing Docs | Account Manager | Mid | 1 |  |  | 1.4.19.1 |  |  | 0 | 0
334 | DEL-0004 | TSK-00325 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19.1.2 | 1.4.19.1 | Briefing Docs | Vendor Engagement | Briefing Docs | Designer | Mid | 4 |  |  | 1.4.19.1.1 |  |  | 0 | 0
335 | DEL-0004 | TSK-00326 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19.1.3 | 1.4.19.1 | Briefing Docs | Vendor Engagement | Briefing Docs | Producer | Mid | 4 |  |  | 1.4.19.1.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19.2 | 1.4.19 | Internal Review & Critique | Vendor Engagement | Internal Review & Critique |  |  | 0 | 93 | 2 | 1.4.19.1.3 |  |  | 0 | 0
343 | DEL-0004 | TSK-00334 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19.2.1 | 1.4.19.2 | Internal Review & Critique | Vendor Engagement | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.19.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19.3 | 1.4.19 | Client Review & Revisions | Vendor Engagement | Client Review & Revisions |  |  | 0 | 95 | 3 | 1.4.19.2.1 |  |  | 0 | 0
336 | DEL-0004 | TSK-00327 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19.3.1 | 1.4.19.3 | Client Review & Revisions | Vendor Engagement | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.19.3 |  |  | 0 | 0
337 | DEL-0004 | TSK-00328 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19.3.2 | 1.4.19.3 | Client Review & Revisions | Vendor Engagement | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.4.19.3.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20 | 1.4 | Art Direction | Art Direction |  |  |  | 19 | 93 | 5 | 1.4.19 |  |  | 195 | 3705
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.1 | 1.4.20 | Internal Review & Critique | Art Direction | Internal Review & Critique |  |  | 0 | 93 | 2 | 1.4.20 |  |  | 0 | 0
145 | DEL-0004 | TSK-00145 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.1.1 | 1.4.20.1 | Internal Review & Critique | Art Direction | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.20.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.2 | 1.4.20 | Client Review & Revisions | Art Direction | Client Review & Revisions |  |  | 0 | 95 | 3 | 1.4.20.1.1 |  |  | 0 | 0
141 | DEL-0004 | TSK-00141 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.2.1 | 1.4.20.2 | Client Review & Revisions | Art Direction | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.20.2 |  |  | 0 | 0
142 | DEL-0004 | TSK-00142 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.2.2 | 1.4.20.2 | Client Review & Revisions | Art Direction | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.4.20.2.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.3 | 1.4.20 | Look Dev & References | Art Direction | Look Dev & References |  |  | 0 | 100 | 0 | 1.4.20.2.2 |  |  | 0 | 0
146 | DEL-0004 | TSK-00146 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.3.1 | 1.4.20.3 | Look Dev & References | Art Direction | Look Dev & References | Art Director | Lead/Director | 1 |  |  | 1.4.20.3 |  |  | 0 | 0
143 | DEL-0004 | TSK-00143 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.3.2 | 1.4.20.3 | Look Dev & References | Art Direction | Look Dev & References | Designer | Mid | 4 |  |  | 1.4.20.3.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.4 | 1.4.20 | Style Guide (lite) | Art Direction | Style Guide (lite) |  |  | 0 | 100 | 0 | 1.4.20.3.2 |  |  | 0 | 0
148 | DEL-0004 | TSK-00148 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.4.1 | 1.4.20.4 | Style Guide (lite) | Art Direction | Style Guide (lite) | Art Director | Lead/Director | 1 |  |  | 1.4.20.4 |  |  | 0 | 0
149 | DEL-0004 | TSK-00149 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.4.2 | 1.4.20.4 | Style Guide (lite) | Art Direction | Style Guide (lite) | Designer | Mid | 9 |  |  | 1.4.20.4.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21 | 1.4 | Concepting | Concepting |  |  |  | 21 | 93 | 5 | 1.4.20 |  |  | 195 | 4095
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.1 | 1.4.21 | Internal Review & Critique | Concepting | Internal Review & Critique |  |  | 0 | 93 | 2 | 1.4.21 |  |  | 0 | 0
175 | DEL-0004 | TSK-00175 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.1.1 | 1.4.21.1 | Internal Review & Critique | Concepting | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.21.1 |  |  | 0 | 0
176 | DEL-0004 | TSK-00176 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.1.2 | 1.4.21.1 | Internal Review & Critique | Concepting | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.21.1.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.2 | 1.4.21 | Client Review & Revisions | Concepting | Client Review & Revisions |  |  | 0 | 95 | 3 | 1.4.21.1.2 |  |  | 0 | 0
166 | DEL-0004 | TSK-00166 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.2.1 | 1.4.21.2 | Client Review & Revisions | Concepting | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.4.21.2 |  |  | 0 | 0
167 | DEL-0004 | TSK-00167 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.2.2 | 1.4.21.2 | Client Review & Revisions | Concepting | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.4.21.2.1 |  |  | 0 | 0
168 | DEL-0004 | TSK-00168 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.2.3 | 1.4.21.2 | Client Review & Revisions | Concepting | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.4.21.2.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.3 | 1.4.21 | Ideation Sprint | Concepting | Ideation Sprint |  |  | 0 | 100 | 0 | 1.4.21.2.3 |  |  | 0 | 0
172 | DEL-0004 | TSK-00172 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.3.1 | 1.4.21.3 | Ideation Sprint | Concepting | Ideation Sprint | Art Director | Lead/Director | 2 |  |  | 1.4.21.3 |  |  | 0 | 0
170 | DEL-0004 | TSK-00170 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.3.2 | 1.4.21.3 | Ideation Sprint | Concepting | Ideation Sprint | Copywriter | Mid | 2 |  |  | 1.4.21.3.1 |  |  | 0 | 0
173 | DEL-0004 | TSK-00173 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.3.3 | 1.4.21.3 | Ideation Sprint | Concepting | Ideation Sprint | Creative Director | Lead/Director | 2 |  |  | 1.4.21.3.2 |  |  | 0 | 0
169 | DEL-0004 | TSK-00169 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.3.4 | 1.4.21.3 | Ideation Sprint | Concepting | Ideation Sprint | Designer | Mid | 4 |  |  | 1.4.21.3.3 |  |  | 0 | 0
171 | DEL-0004 | TSK-00171 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.3.5 | 1.4.21.3 | Ideation Sprint | Concepting | Ideation Sprint | Strategist | Mid | 6 |  |  | 1.4.21.3.4 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22 | 1.4 | Vendor Contracting | Vendor Contracting |  |  |  | 12 | 93 | 5 | 1.4.21 |  |  | 195 | 2340
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.1 | 1.4.22 | Internal Review & Critique | Vendor Contracting | Internal Review & Critique |  |  | 0 | 93 | 2 | 1.4.22 |  |  | 0 | 0
320 | DEL-0004 | TSK-00311 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.1.1 | 1.4.22.1 | Internal Review & Critique | Vendor Contracting | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.22.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.2 | 1.4.22 | Client Review & Revisions | Vendor Contracting | Client Review & Revisions |  |  | 0 | 95 | 3 | 1.4.22.1.1 |  |  | 0 | 0
313 | DEL-0004 | TSK-00304 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.2.1 | 1.4.22.2 | Client Review & Revisions | Vendor Contracting | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.22.2 |  |  | 0 | 0
314 | DEL-0004 | TSK-00305 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.2.2 | 1.4.22.2 | Client Review & Revisions | Vendor Contracting | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.4.22.2.1 |  |  | 0 | 0
315 | DEL-0004 | TSK-00306 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.2.3 | 1.4.22.2 | Client Review & Revisions | Vendor Contracting | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.4.22.2.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.3 | 1.4.22 | SOW/CO Draft & Negotiate | Vendor Contracting | SOW/CO Draft & Negotiate |  |  | 0 | 100 | 0 | 1.4.22.2.3 |  |  | 0 | 0
317 | DEL-0004 | TSK-00308 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.3.1 | 1.4.22.3 | SOW/CO Draft & Negotiate | Vendor Contracting | SOW/CO Draft & Negotiate | Account Manager | Mid | 3 |  |  | 1.4.22.3 |  |  | 0 | 0
318 | DEL-0004 | TSK-00309 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.3.2 | 1.4.22.3 | SOW/CO Draft & Negotiate | Vendor Contracting | SOW/CO Draft & Negotiate | Designer | Mid | 2 |  |  | 1.4.22.3.1 |  |  | 0 | 0
322 | DEL-0004 | TSK-00313 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.3.3 | 1.4.22.3 | SOW/CO Draft & Negotiate | Vendor Contracting | SOW/CO Draft & Negotiate | Producer | Mid | 1 |  |  | 1.4.22.3.2 |  |  | 0 | 0
316 | DEL-0004 | TSK-00307 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.3.4 | 1.4.22.3 | SOW/CO Draft & Negotiate | Vendor Contracting | SOW/CO Draft & Negotiate | Project Manager | Mid | 1 |  |  | 1.4.22.3.3 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23 | 1.4 | Vendor Deal Memos | Vendor Deal Memos |  |  |  | 10 | 93 | 5 | 1.4.22 |  |  | 195 | 1950
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23.1 | 1.4.23 | Internal Review & Critique | Vendor Deal Memos | Internal Review & Critique |  |  | 0 | 93 | 2 | 1.4.23 |  |  | 0 | 0
330 | DEL-0004 | TSK-00321 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23.1.1 | 1.4.23.1 | Internal Review & Critique | Vendor Deal Memos | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.23.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23.2 | 1.4.23 | Client Review & Revisions | Vendor Deal Memos | Client Review & Revisions |  |  | 0 | 95 | 3 | 1.4.23.1.1 |  |  | 0 | 0
323 | DEL-0004 | TSK-00314 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23.2.1 | 1.4.23.2 | Client Review & Revisions | Vendor Deal Memos | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.23.2 |  |  | 0 | 0
324 | DEL-0004 | TSK-00315 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23.2.2 | 1.4.23.2 | Client Review & Revisions | Vendor Deal Memos | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.4.23.2.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23.3 | 1.4.23 | Distribution & Confirmation | Vendor Deal Memos | Distribution & Confirmation |  |  | 0 | 100 | 0 | 1.4.23.2.2 |  |  | 0 | 0
328 | DEL-0004 | TSK-00319 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23.3.1 | 1.4.23.3 | Distribution & Confirmation | Vendor Deal Memos | Distribution & Confirmation | Designer | Mid | 2 |  |  | 1.4.23.3 |  |  | 0 | 0
325 | DEL-0004 | TSK-00316 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23.3.2 | 1.4.23.3 | Distribution & Confirmation | Vendor Deal Memos | Distribution & Confirmation | Producer | Mid | 3 |  |  | 1.4.23.3.1 |  |  | 0 | 0
327 | DEL-0004 | TSK-00318 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23.3.3 | 1.4.23.3 | Distribution & Confirmation | Vendor Deal Memos | Distribution & Confirmation | Project Manager | Mid | 1 |  |  | 1.4.23.3.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24 | 1.4 | Vendor Pre-Production Meetings | Vendor Pre-Production Meetings |  |  |  | 13 | 93 | 7 | 1.4.23 |  |  | 195 | 2535
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.1 | 1.4.24 | Internal Review & Critique | Vendor Pre-Production Meetings | Internal Review & Critique |  |  | 0 | 93 | 2 | 1.4.24 |  |  | 0 | 0
350 | DEL-0004 | TSK-00341 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.1.1 | 1.4.24.1 | Internal Review & Critique | Vendor Pre-Production Meetings | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.24.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.2 | 1.4.24 | Client Review & Revisions | Vendor Pre-Production Meetings | Client Review & Revisions |  |  | 0 | 95 | 3 | 1.4.24.1.1 |  |  | 0 | 0
346 | DEL-0004 | TSK-00337 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.2.1 | 1.4.24.2 | Client Review & Revisions | Vendor Pre-Production Meetings | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.4.24.2 |  |  | 0 | 0
347 | DEL-0004 | TSK-00338 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.2.2 | 1.4.24.2 | Client Review & Revisions | Vendor Pre-Production Meetings | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.4.24.2.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.3 | 1.4.24 | Run Meeting & Notes | Vendor Pre-Production Meetings | Run Meeting & Notes |  |  | 0 | 98 | 2 | 1.4.24.2.2 |  |  | 0 | 0
351 | DEL-0004 | TSK-00342 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.3.1 | 1.4.24.3 | Run Meeting & Notes | Vendor Pre-Production Meetings | Run Meeting & Notes | Creative Director | Lead/Director | 2 |  |  | 1.4.24.3 |  |  | 0 | 0
352 | DEL-0004 | TSK-00343 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.3.2 | 1.4.24.3 | Run Meeting & Notes | Vendor Pre-Production Meetings | Run Meeting & Notes | Producer | Mid | 1 |  |  | 1.4.24.3.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.4 | 1.4.24 | Agenda & Materials | Vendor Pre-Production Meetings | Agenda & Materials |  |  | 0 | 100 | 0 | 1.4.24.3.2 |  |  | 0 | 0
344 | DEL-0004 | TSK-00335 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.4.1 | 1.4.24.4 | Agenda & Materials | Vendor Pre-Production Meetings | Agenda & Materials | Designer | Mid | 5 |  |  | 1.4.24.4 |  |  | 0 | 0
345 | DEL-0004 | TSK-00336 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.4.2 | 1.4.24.4 | Agenda & Materials | Vendor Pre-Production Meetings | Agenda & Materials | Producer | Mid | 1 |  |  | 1.4.24.4.1 |  |  | 0 | 0
353 | DEL-0004 | TSK-00344 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.4.3 | 1.4.24.4 | Agenda & Materials | Vendor Pre-Production Meetings | Agenda & Materials | Project Manager | Mid | 1 |  |  | 1.4.24.4.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.25 | 1.4 | Pre-Interview Talent Calls | Pre-Interview Talent Calls |  |  |  | 4 | 100 | 0 | 1.4.24 |  |  | 195 | 780
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.25.1 | 1.4.25 | Notes & Shareout | Pre-Interview Talent Calls | Notes & Shareout |  |  | 0 | 100 | 0 | 1.4.25 |  |  | 0 | 0
209 | DEL-0004 | TSK-00209 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.25.1.1 | 1.4.25.1 | Notes & Shareout | Pre-Interview Talent Calls | Notes & Shareout | Producer | Mid | 3 |  |  | 1.4.25.1 |  |  | 0 | 0
210 | DEL-0004 | TSK-00210 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.25.1.2 | 1.4.25.1 | Notes & Shareout | Pre-Interview Talent Calls | Notes & Shareout | Project Manager | Mid | 1 |  |  | 1.4.25.1.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.26 | 1.4 | Wrap & File Organization | Wrap & File Organization |  |  |  | 1 | 100 | 0 | 1.4.25 |  |  | 195 | 195
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.26.1 | 1.4.26 | Pre-Production Support | Wrap & File Organization | Pre-Production Support |  |  | 0 | 100 | 0 | 1.4.26 |  |  | 0 | 0
363 | DEL-0004 | TSK-00354 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.26.1.1 | 1.4.26.1 | Pre-Production Support | Wrap & File Organization | Pre-Production Support | Producer | Mid | 1 |  |  | 1.4.26.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5 | 1 | Post-Production |  |  |  |  | 188 | 100 | 41 | 1.4 |  | Core/T2_MediumVolume | 195 | 36660
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.1 | 1.5 | Content Licensing / Art Buying | Content Licensing / Art Buying |  |  |  | 2 | 100 | 3 | 1.5 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.1.1 | 1.5.1 | Rights/License Research | Content Licensing / Art Buying | Rights/License Research |  |  | 0 | 100 | 3 | 1.5.1 |  |  | 0 | 0
65 | DEL-0003 | TSK-00065 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.1.1.1 | 1.5.1.1 | Rights/License Research | Content Licensing / Art Buying | Rights/License Research | Producer | Mid | 1 |  |  | 1.5.1.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.1.2 | 1.5.1 | Usage Notes | Content Licensing / Art Buying | Usage Notes |  |  | 0 | 141 | 0 | 1.5.1.1.1 |  |  | 0 | 0
66 | DEL-0003 | TSK-00066 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.1.2.1 | 1.5.1.2 | Usage Notes | Content Licensing / Art Buying | Usage Notes | Account Manager | Mid | 1 |  |  | 1.5.1.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2 | 1.5 | VO Recording Sessions | VO Recording Sessions |  |  |  | 5 | 103 | 4 | 1.5.1 |  |  | 195 | 975
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.1 | 1.5.2 | Script Polish | VO Recording Sessions | Script Polish |  |  | 0 | 103 | 4 | 1.5.2 |  |  | 0 | 0
124 | DEL-0003 | TSK-00124 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.1.1 | 1.5.2.1 | Script Polish | VO Recording Sessions | Script Polish | Copywriter | Mid | 1 |  |  | 1.5.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.2 | 1.5.2 | VO Session | VO Recording Sessions | VO Session |  |  | 0 | 141 | 0 | 1.5.2.1.1 |  |  | 0 | 0
125 | DEL-0003 | TSK-00125 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.2.1 | 1.5.2.2 | VO Session | VO Recording Sessions | VO Session | Producer | Mid | 1 |  |  | 1.5.2.2 |  |  | 0 | 0
126 | DEL-0003 | TSK-00126 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.2.2 | 1.5.2.2 | VO Session | VO Recording Sessions | VO Session | Sound Designer | Mid | 3 |  |  | 1.5.2.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3 | 1.5 | Editing | Editing |  |  |  | 17 | 107 | 5 | 1.5.2 |  |  | 195 | 3315
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.1 | 1.5.3 | Client Review & Revisions | Editing | Client Review & Revisions |  |  | 0 | 107 | 5 | 1.5.3 |  |  | 0 | 0
74 | DEL-0003 | TSK-00074 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.1.1 | 1.5.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.3.1 |  |  | 0 | 0
77 | DEL-0003 | TSK-00077 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.1.2 | 1.5.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.5.3.1.1 |  |  | 0 | 0
76 | DEL-0003 | TSK-00076 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.1.3 | 1.5.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.5.3.1.2 |  |  | 0 | 0
79 | DEL-0003 | TSK-00079 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.1.4 | 1.5.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Editor | Mid | 8 |  |  | 1.5.3.1.3 |  |  | 0 | 0
75 | DEL-0003 | TSK-00075 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.1.5 | 1.5.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Producer | Mid | 3 |  |  | 1.5.3.1.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4 | 1.5 | Video Editing | Video Editing |  |  |  | 25 | 107 | 5 | 1.5.3 |  |  | 195 | 4875
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.1 | 1.5.4 | Client Review & Revisions | Video Editing | Client Review & Revisions |  |  | 0 | 107 | 5 | 1.5.4 |  |  | 0 | 0
127 | DEL-0003 | TSK-00127 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.1.1 | 1.5.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.4.1 |  |  | 0 | 0
131 | DEL-0003 | TSK-00131 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.1.2 | 1.5.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.5.4.1.1 |  |  | 0 | 0
129 | DEL-0003 | TSK-00129 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.1.3 | 1.5.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.5.4.1.2 |  |  | 0 | 0
130 | DEL-0003 | TSK-00130 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.1.4 | 1.5.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Editor | Mid | 16 |  |  | 1.5.4.1.3 |  |  | 0 | 0
128 | DEL-0003 | TSK-00128 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.1.5 | 1.5.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Producer | Mid | 3 |  |  | 1.5.4.1.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5 | 1.5 | Voice Over | Voice Over |  |  |  | 17 | 107 | 12 | 1.5.4 |  |  | 195 | 3315
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.1 | 1.5.5 | VO Edit | Voice Over | VO Edit |  |  | 0 | 107 | 5 | 1.5.5 |  |  | 0 | 0
140 | DEL-0003 | TSK-00140 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.1.1 | 1.5.5.1 | VO Edit | Voice Over | VO Edit | Editor | Mid | 9 |  |  | 1.5.5.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.2 | 1.5.5 | Mix | Voice Over | Mix |  |  | 0 | 124 | 2 | 1.5.5.1.1 |  |  | 0 | 0
139 | DEL-0003 | TSK-00139 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.2.1 | 1.5.5.2 | Mix | Voice Over | Mix | Sound Designer | Mid | 2 |  |  | 1.5.5.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.3 | 1.5.5 | Internal Review & Critique | Voice Over | Internal Review & Critique |  |  | 0 | 131 | 2 | 1.5.5.2.1 |  |  | 0 | 0
138 | DEL-0003 | TSK-00138 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.3.1 | 1.5.5.3 | Internal Review & Critique | Voice Over | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.5.5.3 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.4 | 1.5.5 | Client Review & Revisions | Voice Over | Client Review & Revisions |  |  | 0 | 133 | 3 | 1.5.5.3.1 |  |  | 0 | 0
134 | DEL-0003 | TSK-00134 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.4.1 | 1.5.5.4 | Client Review & Revisions | Voice Over | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.5.4 |  |  | 0 | 0
135 | DEL-0003 | TSK-00135 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.4.2 | 1.5.5.4 | Client Review & Revisions | Voice Over | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.5.5.4.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.5 | 1.5.5 | Final Packaging | Voice Over | Final Packaging |  |  | 0 | 141 | 0 | 1.5.5.4.2 |  |  | 0 | 0
136 | DEL-0003 | TSK-00136 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.5.1 | 1.5.5.5 | Final Packaging | Voice Over | Final Packaging | Designer | Mid | 2 |  |  | 1.5.5.5 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6 | 1.5 | Motion Design/VFX | Motion Design/VFX |  |  |  | 17 | 112 | 7 | 1.5.5 |  |  | 195 | 3315
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.1 | 1.5.6 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions |  |  | 0 | 112 | 7 | 1.5.6 |  |  | 0 | 0
90 | DEL-0003 | TSK-00090 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.1.1 | 1.5.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.6.1 |  |  | 0 | 0
94 | DEL-0003 | TSK-00094 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.1.2 | 1.5.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.5.6.1.1 |  |  | 0 | 0
92 | DEL-0003 | TSK-00092 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.1.3 | 1.5.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.5.6.1.2 |  |  | 0 | 0
96 | DEL-0003 | TSK-00096 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.1.4 | 1.5.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Editor | Mid | 5 |  |  | 1.5.6.1.3 |  |  | 0 | 0
93 | DEL-0003 | TSK-00093 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.1.5 | 1.5.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Motion Designer | Mid | 2 |  |  | 1.5.6.1.4 |  |  | 0 | 0
91 | DEL-0003 | TSK-00091 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.1.6 | 1.5.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Producer | Mid | 3 |  |  | 1.5.6.1.5 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7 | 1.5 | Color Correction | Color Correction |  |  |  | 11 | 119 | 2 | 1.5.6 |  |  | 195 | 2145
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.1 | 1.5.7 | Client Review & Revisions | Color Correction | Client Review & Revisions |  |  | 0 | 119 | 2 | 1.5.7 |  |  | 0 | 0
53 | DEL-0003 | TSK-00053 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.1.1 | 1.5.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.5.7.1 |  |  | 0 | 0
55 | DEL-0003 | TSK-00055 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.1.2 | 1.5.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Colorist | Mid | 5 |  |  | 1.5.7.1.1 |  |  | 0 | 0
57 | DEL-0003 | TSK-00057 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.1.3 | 1.5.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.5.7.1.2 |  |  | 0 | 0
56 | DEL-0003 | TSK-00056 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.1.4 | 1.5.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.5.7.1.3 |  |  | 0 | 0
54 | DEL-0003 | TSK-00054 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.1.5 | 1.5.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.5.7.1.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8 | 1.5 | Color Grading | Color Grading |  |  |  | 11 | 119 | 2 | 1.5.7 |  |  | 195 | 2145
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.1 | 1.5.8 | Client Review & Revisions | Color Grading | Client Review & Revisions |  |  | 0 | 119 | 2 | 1.5.8 |  |  | 0 | 0
59 | DEL-0003 | TSK-00059 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.1.1 | 1.5.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.5.8.1 |  |  | 0 | 0
61 | DEL-0003 | TSK-00061 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.1.2 | 1.5.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Colorist | Mid | 5 |  |  | 1.5.8.1.1 |  |  | 0 | 0
63 | DEL-0003 | TSK-00063 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.1.3 | 1.5.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.5.8.1.2 |  |  | 0 | 0
62 | DEL-0003 | TSK-00062 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.1.4 | 1.5.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.5.8.1.3 |  |  | 0 | 0
60 | DEL-0003 | TSK-00060 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.1.5 | 1.5.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.5.8.1.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9 | 1.5 | Final Retouched Stills Review | Final Retouched Stills Review |  |  |  | 10 | 121 | 8 | 1.5.8 |  |  | 195 | 1950
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.1 | 1.5.9 | Retouch | Final Retouched Stills Review | Retouch |  |  | 0 | 121 | 3 | 1.5.9 |  |  | 0 | 0
89 | DEL-0003 | TSK-00089 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.1.1 | 1.5.9.1 | Retouch | Final Retouched Stills Review | Retouch | Retoucher | Mid | 4 |  |  | 1.5.9.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.2 | 1.5.9 | Internal Review & Critique | Final Retouched Stills Review | Internal Review & Critique |  |  | 0 | 131 | 2 | 1.5.9.1.1 |  |  | 0 | 0
88 | DEL-0003 | TSK-00088 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.2.1 | 1.5.9.2 | Internal Review & Critique | Final Retouched Stills Review | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.5.9.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.3 | 1.5.9 | Client Review & Revisions | Final Retouched Stills Review | Client Review & Revisions |  |  | 0 | 133 | 3 | 1.5.9.2.1 |  |  | 0 | 0
84 | DEL-0003 | TSK-00084 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.3.1 | 1.5.9.3 | Client Review & Revisions | Final Retouched Stills Review | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.9.3 |  |  | 0 | 0
85 | DEL-0003 | TSK-00085 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.3.2 | 1.5.9.3 | Client Review & Revisions | Final Retouched Stills Review | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.5.9.3.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.4 | 1.5.9 | Final Packaging | Final Retouched Stills Review | Final Packaging |  |  | 0 | 141 | 0 | 1.5.9.3.2 |  |  | 0 | 0
86 | DEL-0003 | TSK-00086 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.4.1 | 1.5.9.4 | Final Packaging | Final Retouched Stills Review | Final Packaging | Designer | Mid | 2 |  |  | 1.5.9.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10 | 1.5 | Retouching | Retouching |  |  |  | 10 | 121 | 8 | 1.5.9 |  |  | 195 | 1950
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.1 | 1.5.10 | Retouch | Retouching | Retouch |  |  | 0 | 121 | 3 | 1.5.10 |  |  | 0 | 0
102 | DEL-0003 | TSK-00102 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.1.1 | 1.5.10.1 | Retouch | Retouching | Retouch | Retoucher | Mid | 4 |  |  | 1.5.10.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.2 | 1.5.10 | Internal Review & Critique | Retouching | Internal Review & Critique |  |  | 0 | 131 | 2 | 1.5.10.1.1 |  |  | 0 | 0
101 | DEL-0003 | TSK-00101 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.2.1 | 1.5.10.2 | Internal Review & Critique | Retouching | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.5.10.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.3 | 1.5.10 | Client Review & Revisions | Retouching | Client Review & Revisions |  |  | 0 | 133 | 3 | 1.5.10.2.1 |  |  | 0 | 0
97 | DEL-0003 | TSK-00097 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.3.1 | 1.5.10.3 | Client Review & Revisions | Retouching | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.10.3 |  |  | 0 | 0
98 | DEL-0003 | TSK-00098 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.3.2 | 1.5.10.3 | Client Review & Revisions | Retouching | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.5.10.3.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.4 | 1.5.10 | Final Packaging | Retouching | Final Packaging |  |  | 0 | 141 | 0 | 1.5.10.3.2 |  |  | 0 | 0
99 | DEL-0003 | TSK-00099 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.4.1 | 1.5.10.4 | Final Packaging | Retouching | Final Packaging | Designer | Mid | 2 |  |  | 1.5.10.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.11 | 1.5 | Sound Mix | Sound Mix |  |  |  | 9 | 124 | 2 | 1.5.10 |  |  | 195 | 1755
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.11.1 | 1.5.11 | Client Review & Revisions | Sound Mix | Client Review & Revisions |  |  | 0 | 124 | 2 | 1.5.11 |  |  | 0 | 0
107 | DEL-0003 | TSK-00107 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.11.1.1 | 1.5.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.5.11.1 |  |  | 0 | 0
110 | DEL-0003 | TSK-00110 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.11.1.2 | 1.5.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.5.11.1.1 |  |  | 0 | 0
109 | DEL-0003 | TSK-00109 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.11.1.3 | 1.5.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.5.11.1.2 |  |  | 0 | 0
108 | DEL-0003 | TSK-00108 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.11.1.4 | 1.5.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.5.11.1.3 |  |  | 0 | 0
112 | DEL-0003 | TSK-00112 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.11.1.5 | 1.5.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Sound Designer | Mid | 2 |  |  | 1.5.11.1.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.12 | 1.5 | Sound Sourcing | Sound Sourcing |  |  |  | 3 | 124 | 2 | 1.5.11 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.12.1 | 1.5.12 | Music Search & License | Sound Sourcing | Music Search & License |  |  | 0 | 124 | 2 | 1.5.12 |  |  | 0 | 0
113 | DEL-0003 | TSK-00113 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.12.1.1 | 1.5.12.1 | Music Search & License | Sound Sourcing | Music Search & License | Producer | Mid | 1 |  |  | 1.5.12.1 |  |  | 0 | 0
114 | DEL-0003 | TSK-00114 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.12.1.2 | 1.5.12.1 | Music Search & License | Sound Sourcing | Music Search & License | Sound Designer | Mid | 2 |  |  | 1.5.12.1.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.13 | 1.5 | Final File Delivery | Final File Delivery |  |  |  | 7 | 126 | 2 | 1.5.12 |  |  | 195 | 1365
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.13.1 | 1.5.13 | QA (Tech & Content) | Final File Delivery | QA (Tech & Content) |  |  | 0 | 126 | 2 | 1.5.13 |  |  | 0 | 0
83 | DEL-0003 | TSK-00083 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.13.1.1 | 1.5.13.1 | QA (Tech & Content) | Final File Delivery | QA (Tech & Content) | QA Specialist | Mid | 3 |  |  | 1.5.13.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.13.2 | 1.5.13 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload |  |  | 0 | 141 | 0 | 1.5.13.1.1 |  |  | 0 | 0
80 | DEL-0003 | TSK-00080 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.13.2.1 | 1.5.13.2 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload | Media Manager / DIT | Mid | 2 |  |  | 1.5.13.2 |  |  | 0 | 0
81 | DEL-0003 | TSK-00081 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.13.2.2 | 1.5.13.2 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload | Producer | Mid | 1 |  |  | 1.5.13.2.1 |  |  | 0 | 0
82 | DEL-0003 | TSK-00082 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.13.2.3 | 1.5.13.2 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload | Project Manager | Mid | 1 |  |  | 1.5.13.2.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14 | 1.5 | True-ups (for vendor costs) | True-ups (for vendor costs) |  |  |  | 10 | 128 | 8 | 1.5.13 |  |  | 195 | 1950
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.1 | 1.5.14 | Change Orders & Tracking | True-ups (for vendor costs) | Change Orders & Tracking |  |  | 0 | 128 | 3 | 1.5.14 |  |  | 0 | 0
116 | DEL-0003 | TSK-00116 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.1.1 | 1.5.14.1 | Change Orders & Tracking | True-ups (for vendor costs) | Change Orders & Tracking | Project Manager | Mid | 1 |  |  | 1.5.14.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.2 | 1.5.14 | Internal Review & Critique | True-ups (for vendor costs) | Internal Review & Critique |  |  | 0 | 131 | 2 | 1.5.14.1.1 |  |  | 0 | 0
121 | DEL-0003 | TSK-00121 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.2.1 | 1.5.14.2 | Internal Review & Critique | True-ups (for vendor costs) | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.5.14.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.3 | 1.5.14 | Client Review & Revisions | True-ups (for vendor costs) | Client Review & Revisions |  |  | 0 | 133 | 3 | 1.5.14.2.1 |  |  | 0 | 0
117 | DEL-0003 | TSK-00117 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.3.1 | 1.5.14.3 | Client Review & Revisions | True-ups (for vendor costs) | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.14.3 |  |  | 0 | 0
118 | DEL-0003 | TSK-00118 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.3.2 | 1.5.14.3 | Client Review & Revisions | True-ups (for vendor costs) | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.5.14.3.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.4 | 1.5.14 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation |  |  | 0 | 141 | 0 | 1.5.14.3.2 |  |  | 0 | 0
122 | DEL-0003 | TSK-00122 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.4.1 | 1.5.14.4 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation | Account Manager | Mid | 2 |  |  | 1.5.14.4 |  |  | 0 | 0
119 | DEL-0003 | TSK-00119 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.4.2 | 1.5.14.4 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation | Designer | Mid | 2 |  |  | 1.5.14.4.1 |  |  | 0 | 0
123 | DEL-0003 | TSK-00123 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.4.3 | 1.5.14.4 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation | Producer | Mid | 1 |  |  | 1.5.14.4.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.15 | 1.5 | Cutdowns | Cutdowns |  |  |  | 11 | 131 | 5 | 1.5.14 |  |  | 195 | 2145
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.15.1 | 1.5.15 | Internal Review & Critique | Cutdowns | Internal Review & Critique |  |  | 0 | 131 | 2 | 1.5.15 |  |  | 0 | 0
72 | DEL-0003 | TSK-00072 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.15.1.1 | 1.5.15.1 | Internal Review & Critique | Cutdowns | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.5.15.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.15.2 | 1.5.15 | Client Review & Revisions | Cutdowns | Client Review & Revisions |  |  | 0 | 133 | 3 | 1.5.15.1.1 |  |  | 0 | 0
67 | DEL-0003 | TSK-00067 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.15.2.1 | 1.5.15.2 | Client Review & Revisions | Cutdowns | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.15.2 |  |  | 0 | 0
68 | DEL-0003 | TSK-00068 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.15.2.2 | 1.5.15.2 | Client Review & Revisions | Cutdowns | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.5.15.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.15.3 | 1.5.15 | Cutdowns (2-3) | Cutdowns | Cutdowns (2-3) |  |  | 0 | 141 | 0 | 1.5.15.2.2 |  |  | 0 | 0
70 | DEL-0003 | TSK-00070 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.15.3.1 | 1.5.15.3 | Cutdowns (2-3) | Cutdowns | Cutdowns (2-3) | Designer | Mid | 2 |  |  | 1.5.15.3 |  |  | 0 | 0
69 | DEL-0003 | TSK-00069 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.15.3.2 | 1.5.15.3 | Cutdowns (2-3) | Cutdowns | Cutdowns (2-3) | Editor | Mid | 5 |  |  | 1.5.15.3.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.16 | 1.5 | Client Review | Client Review |  |  |  | 4 | 133 | 3 | 1.5.15 |  |  | 195 | 780
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.16.1 | 1.5.16 | Client Review Coordination | Client Review | Client Review Coordination |  |  | 0 | 133 | 3 | 1.5.16 |  |  | 0 | 0
50 | DEL-0003 | TSK-00050 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.16.1.1 | 1.5.16.1 | Client Review Coordination | Client Review | Client Review Coordination | Account Manager | Mid | 2 |  |  | 1.5.16.1 |  |  | 0 | 0
51 | DEL-0003 | TSK-00051 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.16.1.2 | 1.5.16.1 | Client Review Coordination | Client Review | Client Review Coordination | Producer | Mid | 1 |  |  | 1.5.16.1.1 |  |  | 0 | 0
52 | DEL-0003 | TSK-00052 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.16.1.3 | 1.5.16.1 | Client Review Coordination | Client Review | Client Review Coordination | Project Manager | Mid | 1 |  |  | 1.5.16.1.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.17 | 1.5 | Review & Sign-Off | Review & Sign-Off |  |  |  | 3 | 133 | 5 | 1.5.16 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.17.1 | 1.5.17 | Client Review Coordination | Review & Sign-Off | Client Review Coordination |  |  | 0 | 133 | 3 | 1.5.17 |  |  | 0 | 0
103 | DEL-0003 | TSK-00103 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.17.1.1 | 1.5.17.1 | Client Review Coordination | Review & Sign-Off | Client Review Coordination | Account Manager | Mid | 1 |  |  | 1.5.17.1 |  |  | 0 | 0
104 | DEL-0003 | TSK-00104 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.17.1.2 | 1.5.17.1 | Client Review Coordination | Review & Sign-Off | Client Review Coordination | Producer | Mid | 1 |  |  | 1.5.17.1.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.17.2 | 1.5.17 | Notes Triage | Review & Sign-Off | Notes Triage |  |  | 0 | 139 | 2 | 1.5.17.1.2 |  |  | 0 | 0
105 | DEL-0003 | TSK-00105 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.17.2.1 | 1.5.17.2 | Notes Triage | Review & Sign-Off | Notes Triage | Project Manager | Mid | 1 |  |  | 1.5.17.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.18 | 1.5 | Asset Library | Asset Library |  |  |  | 2 | 136 | 3 | 1.5.17 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.18.1 | 1.5.18 | Post Support | Asset Library | Post Support |  |  | 0 | 136 | 3 | 1.5.18 |  |  | 0 | 0
48 | DEL-0003 | TSK-00048 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.18.1.1 | 1.5.18.1 | Post Support | Asset Library | Post Support | Editor | Mid | 2 |  |  | 1.5.18.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.19 | 1.5 | Capture Library | Capture Library |  |  |  | 2 | 136 | 3 | 1.5.18 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.19.1 | 1.5.19 | Post Support | Capture Library | Post Support |  |  | 0 | 136 | 3 | 1.5.19 |  |  | 0 | 0
49 | DEL-0003 | TSK-00049 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.19.1.1 | 1.5.19.1 | Post Support | Capture Library | Post Support | Editor | Mid | 2 |  |  | 1.5.19.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.20 | 1.5 | Selects Deck | Selects Deck |  |  |  | 2 | 136 | 3 | 1.5.19 |  |  | 195 | 390
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.20.1 | 1.5.20 | Post Support | Selects Deck | Post Support |  |  | 0 | 136 | 3 | 1.5.20 |  |  | 0 | 0
106 | DEL-0003 | TSK-00106 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.20.1.1 | 1.5.20.1 | Post Support | Selects Deck | Post Support | Editor | Mid | 2 |  |  | 1.5.20.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.21 | 1.5 | Delivery | Delivery |  |  |  | 5 | 141 | 0 | 1.5.20 |  |  | 195 | 975
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.21.1 | 1.5.21 | Post Support | Delivery | Post Support |  |  | 0 | 141 | 0 | 1.5.21 |  |  | 0 | 0
73 | DEL-0003 | TSK-00073 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.21.1.1 | 1.5.21.1 | Post Support | Delivery | Post Support | Editor | Mid | 5 |  |  | 1.5.21.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.22 | 1.5 | Stills/Footage Selection | Stills/Footage Selection |  |  |  | 5 | 141 | 0 | 1.5.21 |  |  | 195 | 975
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.22.1 | 1.5.22 | Post Support | Stills/Footage Selection | Post Support |  |  | 0 | 141 | 0 | 1.5.22 |  |  | 0 | 0
115 | DEL-0003 | TSK-00115 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.22.1.1 | 1.5.22.1 | Post Support | Stills/Footage Selection | Post Support | Editor | Mid | 5 |  |  | 1.5.22.1 |  |  | 0 | 0

## Scenario B
Row_ID | Deliverable_Code | Task_Code | Service_Department | Deliverable | Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes | Rate_USD | Price_USD
[5 empty] | Vascano Tequila - RFP Creative Services 2022 (8) | 1 |  | Vascano Tequila - RFP Creative Services 2022 (8) | Project |  |  |  | 0 | 0 |  |  |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1 | 1 | Brand Style & Usage Guidelines |  |  |  |  | 382 | 0 | 11 |  |  | Advanced/T1_LargeVolume | 195 | 74490
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1 | 1.1 | Color Palettes | Color Palettes |  |  |  | 20 | 0 | 3 | 1.1 |  |  | 195 | 3900
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.1 | 1.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions |  |  | 0 | 0 | 3 | 1.1.1 |  |  | 0 | 0
579 | DEL-0009 | TSK-00570 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.1.1 | 1.1.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.1.1.1 |  |  | 0 | 0
583 | DEL-0009 | TSK-00574 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.1.2 | 1.1.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Art Director | Lead/Director | 2 |  |  | 1.1.1.1.1 |  |  | 0 | 0
580 | DEL-0009 | TSK-00571 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.1.3 | 1.1.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Creative Director | Lead/Director | 5 |  |  | 1.1.1.1.2 |  |  | 0 | 0
582 | DEL-0009 | TSK-00573 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.1.4 | 1.1.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Designer | Mid | 7 |  |  | 1.1.1.1.3 |  |  | 0 | 0
581 | DEL-0009 | TSK-00572 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.1.5 | 1.1.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.1.1.4 |  |  | 0 | 0
578 | DEL-0009 | TSK-00569 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1.1.6 | 1.1.1.1 | Client Review & Revisions | Color Palettes | Client Review & Revisions | QA Specialist | Mid | 4 |  |  | 1.1.1.1.5 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2 | 1.1 | Logo Lock-Ups | Logo Lock-Ups |  |  |  | 42 | 3 | 8 | 1.1.1 |  |  | 195 | 8190
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.1 | 1.1.2 | Quality Check (Specs/Accessibility) | Logo Lock-Ups | Quality Check (Specs/Accessibility) |  |  | 0 | 3 | 3 | 1.1.2 |  |  | 0 | 0
626 | DEL-0009 | TSK-00617 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.1.1 | 1.1.2.1 | Quality Check (Specs/Accessibility) | Logo Lock-Ups | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 4 |  |  | 1.1.2.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.2 | 1.1.2 | Internal Review & Critique | Logo Lock-Ups | Internal Review & Critique |  |  | 0 | 6 | 2 | 1.1.2.1.1 |  |  | 0 | 0
622 | DEL-0009 | TSK-00613 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.2.1 | 1.1.2.2 | Internal Review & Critique | Logo Lock-Ups | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.2.2 |  |  | 0 | 0
623 | DEL-0009 | TSK-00614 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.2.2 | 1.1.2.2 | Internal Review & Critique | Logo Lock-Ups | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.2.2.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.3 | 1.1.2 | Client Review & Revisions | Logo Lock-Ups | Client Review & Revisions |  |  | 0 | 8 | 3 | 1.1.2.2.2 |  |  | 0 | 0
618 | DEL-0009 | TSK-00609 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.3.1 | 1.1.2.3 | Client Review & Revisions | Logo Lock-Ups | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.2.3 |  |  | 0 | 0
619 | DEL-0009 | TSK-00610 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.3.2 | 1.1.2.3 | Client Review & Revisions | Logo Lock-Ups | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.2.3.1 |  |  | 0 | 0
620 | DEL-0009 | TSK-00611 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.3.3 | 1.1.2.3 | Client Review & Revisions | Logo Lock-Ups | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.1.2.3.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.4 | 1.1.2 | Final Packaging | Logo Lock-Ups | Final Packaging |  |  | 0 | 11 | 0 | 1.1.2.3.3 |  |  | 0 | 0
621 | DEL-0009 | TSK-00612 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2.4.1 | 1.1.2.4 | Final Packaging | Logo Lock-Ups | Final Packaging | Designer | Mid | 31 |  |  | 1.1.2.4 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3 | 1.1 | Logo Placement | Logo Placement |  |  |  | 42 | 3 | 8 | 1.1.2 |  |  | 195 | 8190
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.1 | 1.1.3 | Quality Check (Specs/Accessibility) | Logo Placement | Quality Check (Specs/Accessibility) |  |  | 0 | 3 | 3 | 1.1.3 |  |  | 0 | 0
635 | DEL-0009 | TSK-00626 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.1.1 | 1.1.3.1 | Quality Check (Specs/Accessibility) | Logo Placement | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 4 |  |  | 1.1.3.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.2 | 1.1.3 | Internal Review & Critique | Logo Placement | Internal Review & Critique |  |  | 0 | 6 | 2 | 1.1.3.1.1 |  |  | 0 | 0
631 | DEL-0009 | TSK-00622 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.2.1 | 1.1.3.2 | Internal Review & Critique | Logo Placement | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.3.2 |  |  | 0 | 0
632 | DEL-0009 | TSK-00623 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.2.2 | 1.1.3.2 | Internal Review & Critique | Logo Placement | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.3.2.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.3 | 1.1.3 | Client Review & Revisions | Logo Placement | Client Review & Revisions |  |  | 0 | 8 | 3 | 1.1.3.2.2 |  |  | 0 | 0
627 | DEL-0009 | TSK-00618 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.3.1 | 1.1.3.3 | Client Review & Revisions | Logo Placement | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.3.3 |  |  | 0 | 0
628 | DEL-0009 | TSK-00619 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.3.2 | 1.1.3.3 | Client Review & Revisions | Logo Placement | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.3.3.1 |  |  | 0 | 0
629 | DEL-0009 | TSK-00620 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.3.3 | 1.1.3.3 | Client Review & Revisions | Logo Placement | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.1.3.3.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.4 | 1.1.3 | Final Packaging | Logo Placement | Final Packaging |  |  | 0 | 11 | 0 | 1.1.3.3.3 |  |  | 0 | 0
630 | DEL-0009 | TSK-00621 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3.4.1 | 1.1.3.4 | Final Packaging | Logo Placement | Final Packaging | Designer | Mid | 31 |  |  | 1.1.3.4 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4 | 1.1 | Brand Do's & Dont's | Brand Do's & Dont's |  |  |  | 50 | 6 | 5 | 1.1.3 |  |  | 195 | 9750
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.1 | 1.1.4 | Internal Review & Critique | Brand Do's & Dont's | Internal Review & Critique |  |  | 0 | 6 | 2 | 1.1.4 |  |  | 0 | 0
573 | DEL-0009 | TSK-00564 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.1.1 | 1.1.4.1 | Internal Review & Critique | Brand Do's & Dont's | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.4.1 |  |  | 0 | 0
574 | DEL-0009 | TSK-00565 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.1.2 | 1.1.4.1 | Internal Review & Critique | Brand Do's & Dont's | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.4.1.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.2 | 1.1.4 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions |  |  | 0 | 8 | 3 | 1.1.4.1.2 |  |  | 0 | 0
568 | DEL-0009 | TSK-00559 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.2.1 | 1.1.4.2 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.4.2 |  |  | 0 | 0
569 | DEL-0009 | TSK-00560 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.2.2 | 1.1.4.2 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.1.4.2.1 |  |  | 0 | 0
570 | DEL-0009 | TSK-00561 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.2.3 | 1.1.4.2 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.4.2.2 |  |  | 0 | 0
571 | DEL-0009 | TSK-00562 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.2.4 | 1.1.4.2 | Client Review & Revisions | Brand Do's & Dont's | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.1.4.2.3 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.3 | 1.1.4 | Outline & Examples | Brand Do's & Dont's | Outline & Examples |  |  | 0 | 11 | 0 | 1.1.4.2.4 |  |  | 0 | 0
575 | DEL-0009 | TSK-00566 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.3.1 | 1.1.4.3 | Outline & Examples | Brand Do's & Dont's | Outline & Examples | Copywriter | Mid | 3 |  |  | 1.1.4.3 |  |  | 0 | 0
572 | DEL-0009 | TSK-00563 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4.3.2 | 1.1.4.3 | Outline & Examples | Brand Do's & Dont's | Outline & Examples | Designer | Mid | 39 |  |  | 1.1.4.3.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5 | 1.1 | Design Style Tile | Design Style Tile |  |  |  | 35 | 6 | 5 | 1.1.4 |  |  | 195 | 6825
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.1 | 1.1.5 | Internal Review & Critique | Design Style Tile | Internal Review & Critique |  |  | 0 | 6 | 2 | 1.1.5 |  |  | 0 | 0
590 | DEL-0009 | TSK-00581 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.1.1 | 1.1.5.1 | Internal Review & Critique | Design Style Tile | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.5.1 |  |  | 0 | 0
591 | DEL-0009 | TSK-00582 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.1.2 | 1.1.5.1 | Internal Review & Critique | Design Style Tile | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.5.1.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.2 | 1.1.5 | Client Review & Revisions | Design Style Tile | Client Review & Revisions |  |  | 0 | 8 | 3 | 1.1.5.1.2 |  |  | 0 | 0
586 | DEL-0009 | TSK-00577 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.2.1 | 1.1.5.2 | Client Review & Revisions | Design Style Tile | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.5.2 |  |  | 0 | 0
587 | DEL-0009 | TSK-00578 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.2.2 | 1.1.5.2 | Client Review & Revisions | Design Style Tile | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.5.2.1 |  |  | 0 | 0
588 | DEL-0009 | TSK-00579 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.2.3 | 1.1.5.2 | Client Review & Revisions | Design Style Tile | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.1.5.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.3 | 1.1.5 | Style Tile Build | Design Style Tile | Style Tile Build |  |  | 0 | 11 | 0 | 1.1.5.2.3 |  |  | 0 | 0
592 | DEL-0009 | TSK-00583 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.3.1 | 1.1.5.3 | Style Tile Build | Design Style Tile | Style Tile Build | Art Director | Lead/Director | 2 |  |  | 1.1.5.3 |  |  | 0 | 0
589 | DEL-0009 | TSK-00580 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.5.3.2 | 1.1.5.3 | Style Tile Build | Design Style Tile | Style Tile Build | Designer | Mid | 26 |  |  | 1.1.5.3.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6 | 1.1 | Image Use Guidance | Image Use Guidance |  |  |  | 35 | 6 | 5 | 1.1.5 |  |  | 195 | 6825
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.1 | 1.1.6 | Internal Review & Critique | Image Use Guidance | Internal Review & Critique |  |  | 0 | 6 | 2 | 1.1.6 |  |  | 0 | 0
608 | DEL-0009 | TSK-00599 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.1.1 | 1.1.6.1 | Internal Review & Critique | Image Use Guidance | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.6.1 |  |  | 0 | 0
609 | DEL-0009 | TSK-00600 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.1.2 | 1.1.6.1 | Internal Review & Critique | Image Use Guidance | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.6.1.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.2 | 1.1.6 | Client Review & Revisions | Image Use Guidance | Client Review & Revisions |  |  | 0 | 8 | 3 | 1.1.6.1.2 |  |  | 0 | 0
602 | DEL-0009 | TSK-00593 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.2.1 | 1.1.6.2 | Client Review & Revisions | Image Use Guidance | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.6.2 |  |  | 0 | 0
603 | DEL-0009 | TSK-00594 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.2.2 | 1.1.6.2 | Client Review & Revisions | Image Use Guidance | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.6.2.1 |  |  | 0 | 0
604 | DEL-0009 | TSK-00595 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.2.3 | 1.1.6.2 | Client Review & Revisions | Image Use Guidance | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.1.6.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.3 | 1.1.6 | Examples & Callouts | Image Use Guidance | Examples & Callouts |  |  | 0 | 11 | 0 | 1.1.6.2.3 |  |  | 0 | 0
607 | DEL-0009 | TSK-00598 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.3.1 | 1.1.6.3 | Examples & Callouts | Image Use Guidance | Examples & Callouts | Art Director | Lead/Director | 2 |  |  | 1.1.6.3 |  |  | 0 | 0
605 | DEL-0009 | TSK-00596 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.6.3.2 | 1.1.6.3 | Examples & Callouts | Image Use Guidance | Examples & Callouts | Designer | Mid | 26 |  |  | 1.1.6.3.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7 | 1.1 | Imagery Style | Imagery Style |  |  |  | 35 | 6 | 5 | 1.1.6 |  |  | 195 | 6825
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.1 | 1.1.7 | Internal Review & Critique | Imagery Style | Internal Review & Critique |  |  | 0 | 6 | 2 | 1.1.7 |  |  | 0 | 0
616 | DEL-0009 | TSK-00607 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.1.1 | 1.1.7.1 | Internal Review & Critique | Imagery Style | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.7.1 |  |  | 0 | 0
617 | DEL-0009 | TSK-00608 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.1.2 | 1.1.7.1 | Internal Review & Critique | Imagery Style | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.7.1.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.2 | 1.1.7 | Client Review & Revisions | Imagery Style | Client Review & Revisions |  |  | 0 | 8 | 3 | 1.1.7.1.2 |  |  | 0 | 0
610 | DEL-0009 | TSK-00601 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.2.1 | 1.1.7.2 | Client Review & Revisions | Imagery Style | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.7.2 |  |  | 0 | 0
611 | DEL-0009 | TSK-00602 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.2.2 | 1.1.7.2 | Client Review & Revisions | Imagery Style | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.7.2.1 |  |  | 0 | 0
612 | DEL-0009 | TSK-00603 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.2.3 | 1.1.7.2 | Client Review & Revisions | Imagery Style | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.1.7.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.3 | 1.1.7 | Examples & Callouts | Imagery Style | Examples & Callouts |  |  | 0 | 11 | 0 | 1.1.7.2.3 |  |  | 0 | 0
615 | DEL-0009 | TSK-00606 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.3.1 | 1.1.7.3 | Examples & Callouts | Imagery Style | Examples & Callouts | Art Director | Lead/Director | 2 |  |  | 1.1.7.3 |  |  | 0 | 0
613 | DEL-0009 | TSK-00604 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.7.3.2 | 1.1.7.3 | Examples & Callouts | Imagery Style | Examples & Callouts | Designer | Mid | 26 |  |  | 1.1.7.3.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8 | 1.1 | Photo & Video Direction | Photo & Video Direction |  |  |  | 38 | 6 | 5 | 1.1.7 |  |  | 195 | 7410
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.1 | 1.1.8 | Internal Review & Critique | Photo & Video Direction | Internal Review & Critique |  |  | 0 | 6 | 2 | 1.1.8 |  |  | 0 | 0
642 | DEL-0009 | TSK-00633 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.1.1 | 1.1.8.1 | Internal Review & Critique | Photo & Video Direction | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.8.1 |  |  | 0 | 0
643 | DEL-0009 | TSK-00634 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.1.2 | 1.1.8.1 | Internal Review & Critique | Photo & Video Direction | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.8.1.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.2 | 1.1.8 | Client Review & Revisions | Photo & Video Direction | Client Review & Revisions |  |  | 0 | 8 | 3 | 1.1.8.1.2 |  |  | 0 | 0
636 | DEL-0009 | TSK-00627 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.2.1 | 1.1.8.2 | Client Review & Revisions | Photo & Video Direction | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.8.2 |  |  | 0 | 0
637 | DEL-0009 | TSK-00628 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.2.2 | 1.1.8.2 | Client Review & Revisions | Photo & Video Direction | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.8.2.1 |  |  | 0 | 0
638 | DEL-0009 | TSK-00629 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.2.3 | 1.1.8.2 | Client Review & Revisions | Photo & Video Direction | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.1.8.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.3 | 1.1.8 | Direction Pages | Photo & Video Direction | Direction Pages |  |  | 0 | 11 | 0 | 1.1.8.2.3 |  |  | 0 | 0
639 | DEL-0009 | TSK-00630 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.3.1 | 1.1.8.3 | Direction Pages | Photo & Video Direction | Direction Pages | Art Director | Lead/Director | 2 |  |  | 1.1.8.3 |  |  | 0 | 0
640 | DEL-0009 | TSK-00631 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.3.2 | 1.1.8.3 | Direction Pages | Photo & Video Direction | Direction Pages | Creative Director | Lead/Director | 3 |  |  | 1.1.8.3.1 |  |  | 0 | 0
641 | DEL-0009 | TSK-00632 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.8.3.3 | 1.1.8.3 | Direction Pages | Photo & Video Direction | Direction Pages | Designer | Mid | 26 |  |  | 1.1.8.3.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9 | 1.1 | Typography | Typography |  |  |  | 28 | 6 | 5 | 1.1.8 |  |  | 195 | 5460
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.1 | 1.1.9 | Internal Review & Critique | Typography | Internal Review & Critique |  |  | 0 | 6 | 2 | 1.1.9 |  |  | 0 | 0
649 | DEL-0009 | TSK-00640 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.1.1 | 1.1.9.1 | Internal Review & Critique | Typography | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.9.1 |  |  | 0 | 0
650 | DEL-0009 | TSK-00641 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.1.2 | 1.1.9.1 | Internal Review & Critique | Typography | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.9.1.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.2 | 1.1.9 | Client Review & Revisions | Typography | Client Review & Revisions |  |  | 0 | 8 | 3 | 1.1.9.1.2 |  |  | 0 | 0
645 | DEL-0009 | TSK-00636 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.2.1 | 1.1.9.2 | Client Review & Revisions | Typography | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.9.2 |  |  | 0 | 0
646 | DEL-0009 | TSK-00637 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.2.2 | 1.1.9.2 | Client Review & Revisions | Typography | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.9.2.1 |  |  | 0 | 0
647 | DEL-0009 | TSK-00638 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.2.3 | 1.1.9.2 | Client Review & Revisions | Typography | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.1.9.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.3 | 1.1.9 | Final Packaging | Typography | Final Packaging |  |  | 0 | 11 | 0 | 1.1.9.2.3 |  |  | 0 | 0
648 | DEL-0009 | TSK-00639 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.9.3.1 | 1.1.9.3 | Final Packaging | Typography | Final Packaging | Designer | Mid | 21 |  |  | 1.1.9.3 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10 | 1.1 | Use Cases | Use Cases |  |  |  | 33 | 6 | 5 | 1.1.9 |  |  | 195 | 6435
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.1 | 1.1.10 | Internal Review & Critique | Use Cases | Internal Review & Critique |  |  | 0 | 6 | 2 | 1.1.10 |  |  | 0 | 0
656 | DEL-0009 | TSK-00647 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.1.1 | 1.1.10.1 | Internal Review & Critique | Use Cases | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.10.1 |  |  | 0 | 0
657 | DEL-0009 | TSK-00648 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.1.2 | 1.1.10.1 | Internal Review & Critique | Use Cases | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.10.1.1 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.2 | 1.1.10 | Client Review & Revisions | Use Cases | Client Review & Revisions |  |  | 0 | 8 | 3 | 1.1.10.1.2 |  |  | 0 | 0
652 | DEL-0009 | TSK-00643 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.2.1 | 1.1.10.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.10.2 |  |  | 0 | 0
653 | DEL-0009 | TSK-00644 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.2.2 | 1.1.10.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.10.2.1 |  |  | 0 | 0
654 | DEL-0009 | TSK-00645 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.2.3 | 1.1.10.2 | Client Review & Revisions | Use Cases | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.1.10.2.2 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.3 | 1.1.10 | Final Packaging | Use Cases | Final Packaging |  |  | 0 | 11 | 0 | 1.1.10.2.3 |  |  | 0 | 0
655 | DEL-0009 | TSK-00646 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.10.3.1 | 1.1.10.3 | Final Packaging | Use Cases | Final Packaging | Designer | Mid | 26 |  |  | 1.1.10.3 |  |  | 0 | 0
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11 | 1.1 | Graphic Treatment Direction | Graphic Treatment Direction |  |  |  | 24 | 11 | 0 | 1.1.10 |  |  | 195 | 4680
| DEL-0009 |  | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11.1 | 1.1.11 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions |  |  | 0 | 11 | 0 | 1.1.11 |  |  | 0 | 0
594 | DEL-0009 | TSK-00585 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11.1.1 | 1.1.11.1 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Account Manager | Mid | 3 |  |  | 1.1.11.1 |  |  | 0 | 0
598 | DEL-0009 | TSK-00589 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11.1.2 | 1.1.11.1 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Art Director | Lead/Director | 4 |  |  | 1.1.11.1.1 |  |  | 0 | 0
595 | DEL-0009 | TSK-00586 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11.1.3 | 1.1.11.1 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Creative Director | Lead/Director | 11 |  |  | 1.1.11.1.2 |  |  | 0 | 0
597 | DEL-0009 | TSK-00588 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11.1.4 | 1.1.11.1 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Designer | Mid | 4 |  |  | 1.1.11.1.3 |  |  | 0 | 0
596 | DEL-0009 | TSK-00587 | Creative | Brand Style & Usage Guidelines | Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.11.1.5 | 1.1.11.1 | Client Review & Revisions | Graphic Treatment Direction | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.1.11.1.4 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2 | 1 | Brand Identity Development |  |  |  |  | 391 | 11 | 15 | 1.1 |  | Advanced/T1_LargeVolume | 195 | 76245
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1 | 1.2 | Color Palette | Color Palette |  |  |  | 23 | 11 | 3 | 1.2 |  |  | 195 | 4485
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1.1 | 1.2.1 | Client Review & Revisions | Color Palette | Client Review & Revisions |  |  | 0 | 11 | 3 | 1.2.1 |  |  | 0 | 0
475 | DEL-0008 | TSK-00466 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1.1.1 | 1.2.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.2.1.1 |  |  | 0 | 0
480 | DEL-0008 | TSK-00471 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1.1.2 | 1.2.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Art Director | Lead/Director | 2 |  |  | 1.2.1.1.1 |  |  | 0 | 0
476 | DEL-0008 | TSK-00467 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1.1.3 | 1.2.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Creative Director | Lead/Director | 5 |  |  | 1.2.1.1.2 |  |  | 0 | 0
478 | DEL-0008 | TSK-00469 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1.1.4 | 1.2.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Designer | Mid | 10 |  |  | 1.2.1.1.3 |  |  | 0 | 0
477 | DEL-0008 | TSK-00468 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1.1.5 | 1.2.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.2.1.1.4 |  |  | 0 | 0
474 | DEL-0008 | TSK-00465 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1.1.6 | 1.2.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | QA Specialist | Mid | 4 |  |  | 1.2.1.1.5 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2 | 1.2 | Graphic Mock-Ups | Graphic Mock-Ups |  |  |  | 38 | 14 | 9 | 1.2.1 |  |  | 195 | 7410
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.1 | 1.2.2 | Compositing/Retouch | Graphic Mock-Ups | Compositing/Retouch |  |  | 0 | 14 | 4 | 1.2.2 |  |  | 0 | 0
496 | DEL-0008 | TSK-00487 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.1.1 | 1.2.2.1 | Compositing/Retouch | Graphic Mock-Ups | Compositing/Retouch | Retoucher | Mid | 6 |  |  | 1.2.2.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.2 | 1.2.2 | Internal Review & Critique | Graphic Mock-Ups | Internal Review & Critique |  |  | 0 | 21 | 2 | 1.2.2.1.1 |  |  | 0 | 0
498 | DEL-0008 | TSK-00489 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.2.1 | 1.2.2.2 | Internal Review & Critique | Graphic Mock-Ups | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.2.2.2 |  |  | 0 | 0
499 | DEL-0008 | TSK-00490 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.2.2 | 1.2.2.2 | Internal Review & Critique | Graphic Mock-Ups | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.2.2.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.3 | 1.2.2 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions |  |  | 0 | 23 | 3 | 1.2.2.2.2 |  |  | 0 | 0
493 | DEL-0008 | TSK-00484 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.3.1 | 1.2.2.3 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.2.2.3 |  |  | 0 | 0
494 | DEL-0008 | TSK-00485 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.3.2 | 1.2.2.3 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.2.3.1 |  |  | 0 | 0
495 | DEL-0008 | TSK-00486 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.3.3 | 1.2.2.3 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.2.2.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.4 | 1.2.2 | Mockup Scenarios (3-4) | Graphic Mock-Ups | Mockup Scenarios (3-4) |  |  | 0 | 26 | 0 | 1.2.2.3.3 |  |  | 0 | 0
500 | DEL-0008 | TSK-00491 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.4.1 | 1.2.2.4 | Mockup Scenarios (3-4) | Graphic Mock-Ups | Mockup Scenarios (3-4) | Art Director | Lead/Director | 4 |  |  | 1.2.2.4 |  |  | 0 | 0
497 | DEL-0008 | TSK-00488 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2.4.2 | 1.2.2.4 | Mockup Scenarios (3-4) | Graphic Mock-Ups | Mockup Scenarios (3-4) | Designer | Mid | 21 |  |  | 1.2.2.4.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3 | 1.2 | Logo | Logo |  |  |  | 57 | 18 | 8 | 1.2.2 |  |  | 195 | 11115
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.1 | 1.2.3 | Quality Check (Specs/Accessibility) | Logo | Quality Check (Specs/Accessibility) |  |  | 0 | 18 | 3 | 1.2.3 |  |  | 0 | 0
520 | DEL-0008 | TSK-00511 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.1.1 | 1.2.3.1 | Quality Check (Specs/Accessibility) | Logo | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 4 |  |  | 1.2.3.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.2 | 1.2.3 | Internal Review & Critique | Logo | Internal Review & Critique |  |  | 0 | 21 | 2 | 1.2.3.1.1 |  |  | 0 | 0
515 | DEL-0008 | TSK-00506 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.2.1 | 1.2.3.2 | Internal Review & Critique | Logo | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.2.3.2 |  |  | 0 | 0
516 | DEL-0008 | TSK-00507 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.2.2 | 1.2.3.2 | Internal Review & Critique | Logo | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.3.2.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.3 | 1.2.3 | Client Review & Revisions | Logo | Client Review & Revisions |  |  | 0 | 23 | 3 | 1.2.3.2.2 |  |  | 0 | 0
511 | DEL-0008 | TSK-00502 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.3.1 | 1.2.3.3 | Client Review & Revisions | Logo | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.2.3.3 |  |  | 0 | 0
512 | DEL-0008 | TSK-00503 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.3.2 | 1.2.3.3 | Client Review & Revisions | Logo | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.3.3.1 |  |  | 0 | 0
513 | DEL-0008 | TSK-00504 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.3.3 | 1.2.3.3 | Client Review & Revisions | Logo | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.2.3.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.4 | 1.2.3 | Logo Exploration (6-8 dirs) | Logo | Logo Exploration (6-8 dirs) |  |  | 0 | 26 | 0 | 1.2.3.3.3 |  |  | 0 | 0
517 | DEL-0008 | TSK-00508 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.4.1 | 1.2.3.4 | Logo Exploration (6-8 dirs) | Logo | Logo Exploration (6-8 dirs) | Art Director | Lead/Director | 4 |  |  | 1.2.3.4 |  |  | 0 | 0
514 | DEL-0008 | TSK-00505 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3.4.2 | 1.2.3.4 | Logo Exploration (6-8 dirs) | Logo | Logo Exploration (6-8 dirs) | Designer | Mid | 42 |  |  | 1.2.3.4.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4 | 1.2 | Typography | Typography |  |  |  | 53 | 18 | 8 | 1.2.3 |  |  | 195 | 10335
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.1 | 1.2.4 | Quality Check (Specs/Accessibility) | Typography | Quality Check (Specs/Accessibility) |  |  | 0 | 18 | 3 | 1.2.4 |  |  | 0 | 0
556 | DEL-0008 | TSK-00547 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.1.1 | 1.2.4.1 | Quality Check (Specs/Accessibility) | Typography | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 4 |  |  | 1.2.4.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.2 | 1.2.4 | Internal Review & Critique | Typography | Internal Review & Critique |  |  | 0 | 21 | 2 | 1.2.4.1.1 |  |  | 0 | 0
554 | DEL-0008 | TSK-00545 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.2.1 | 1.2.4.2 | Internal Review & Critique | Typography | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.2.4.2 |  |  | 0 | 0
555 | DEL-0008 | TSK-00546 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.2.2 | 1.2.4.2 | Internal Review & Critique | Typography | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.4.2.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.3 | 1.2.4 | Client Review & Revisions | Typography | Client Review & Revisions |  |  | 0 | 23 | 3 | 1.2.4.2.2 |  |  | 0 | 0
549 | DEL-0008 | TSK-00540 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.3.1 | 1.2.4.3 | Client Review & Revisions | Typography | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.2.4.3 |  |  | 0 | 0
550 | DEL-0008 | TSK-00541 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.3.2 | 1.2.4.3 | Client Review & Revisions | Typography | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.4.3.1 |  |  | 0 | 0
551 | DEL-0008 | TSK-00542 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.3.3 | 1.2.4.3 | Client Review & Revisions | Typography | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.2.4.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.4 | 1.2.4 | Final Packaging | Typography | Final Packaging |  |  | 0 | 26 | 0 | 1.2.4.3.3 |  |  | 0 | 0
552 | DEL-0008 | TSK-00543 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4.4.1 | 1.2.4.4 | Final Packaging | Typography | Final Packaging | Designer | Mid | 42 |  |  | 1.2.4.4 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5 | 1.2 | Graphic & Copy Messaging Cornerstones | Graphic & Copy Messaging Cornerstones |  |  |  | 36 | 21 | 5 | 1.2.4 |  |  | 195 | 7020
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.1 | 1.2.5 | Internal Review & Critique | Graphic & Copy Messaging Cornerstones | Internal Review & Critique |  |  | 0 | 21 | 2 | 1.2.5 |  |  | 0 | 0
489 | DEL-0008 | TSK-00480 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.1.1 | 1.2.5.1 | Internal Review & Critique | Graphic & Copy Messaging Cornerstones | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.2.5.1 |  |  | 0 | 0
490 | DEL-0008 | TSK-00481 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.1.2 | 1.2.5.1 | Internal Review & Critique | Graphic & Copy Messaging Cornerstones | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.5.1.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.2 | 1.2.5 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions |  |  | 0 | 23 | 3 | 1.2.5.1.2 |  |  | 0 | 0
483 | DEL-0008 | TSK-00474 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.2.1 | 1.2.5.2 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.2.5.2 |  |  | 0 | 0
484 | DEL-0008 | TSK-00475 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.2.2 | 1.2.5.2 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Copywriter | Mid | 2 |  |  | 1.2.5.2.1 |  |  | 0 | 0
485 | DEL-0008 | TSK-00476 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.2.3 | 1.2.5.2 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.5.2.2 |  |  | 0 | 0
486 | DEL-0008 | TSK-00477 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.2.4 | 1.2.5.2 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.2.5.2.3 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.3 | 1.2.5 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft |  |  | 0 | 26 | 0 | 1.2.5.2.4 |  |  | 0 | 0
491 | DEL-0008 | TSK-00482 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.3.1 | 1.2.5.3 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft | Copywriter | Mid | 3 |  |  | 1.2.5.3 |  |  | 0 | 0
492 | DEL-0008 | TSK-00483 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.3.2 | 1.2.5.3 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft | Creative Director | Lead/Director | 4 |  |  | 1.2.5.3.1 |  |  | 0 | 0
487 | DEL-0008 | TSK-00478 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5.3.3 | 1.2.5.3 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft | Designer | Mid | 20 |  |  | 1.2.5.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6 | 1.2 | Iconography | Iconography |  |  |  | 41 | 21 | 5 | 1.2.5 |  |  | 195 | 7995
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.1 | 1.2.6 | Internal Review & Critique | Iconography | Internal Review & Critique |  |  | 0 | 21 | 2 | 1.2.6 |  |  | 0 | 0
509 | DEL-0008 | TSK-00500 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.1.1 | 1.2.6.1 | Internal Review & Critique | Iconography | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.2.6.1 |  |  | 0 | 0
510 | DEL-0008 | TSK-00501 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.1.2 | 1.2.6.1 | Internal Review & Critique | Iconography | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.6.1.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.2 | 1.2.6 | Client Review & Revisions | Iconography | Client Review & Revisions |  |  | 0 | 23 | 3 | 1.2.6.1.2 |  |  | 0 | 0
502 | DEL-0008 | TSK-00493 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.2.1 | 1.2.6.2 | Client Review & Revisions | Iconography | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.2.6.2 |  |  | 0 | 0
503 | DEL-0008 | TSK-00494 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.2.2 | 1.2.6.2 | Client Review & Revisions | Iconography | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.6.2.1 |  |  | 0 | 0
504 | DEL-0008 | TSK-00495 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.2.3 | 1.2.6.2 | Client Review & Revisions | Iconography | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.2.6.2.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.3 | 1.2.6 | Export & Spec | Iconography | Export & Spec |  |  | 0 | 26 | 0 | 1.2.6.2.3 |  |  | 0 | 0
505 | DEL-0008 | TSK-00496 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.3.1 | 1.2.6.3 | Export & Spec | Iconography | Export & Spec | Designer | Mid | 31 |  |  | 1.2.6.3 |  |  | 0 | 0
508 | DEL-0008 | TSK-00499 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6.3.2 | 1.2.6.3 | Export & Spec | Iconography | Export & Spec | Illustrator | Mid | 3 |  |  | 1.2.6.3.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7 | 1.2 | Overarching Moodboard | Overarching Moodboard |  |  |  | 35 | 21 | 5 | 1.2.6 |  |  | 195 | 6825
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.1 | 1.2.7 | Internal Review & Critique | Overarching Moodboard | Internal Review & Critique |  |  | 0 | 21 | 2 | 1.2.7 |  |  | 0 | 0
528 | DEL-0008 | TSK-00519 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.1.1 | 1.2.7.1 | Internal Review & Critique | Overarching Moodboard | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.2.7.1 |  |  | 0 | 0
529 | DEL-0008 | TSK-00520 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.1.2 | 1.2.7.1 | Internal Review & Critique | Overarching Moodboard | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.7.1.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.2 | 1.2.7 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions |  |  | 0 | 23 | 3 | 1.2.7.1.2 |  |  | 0 | 0
522 | DEL-0008 | TSK-00513 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.2.1 | 1.2.7.2 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.2.7.2 |  |  | 0 | 0
523 | DEL-0008 | TSK-00514 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.2.2 | 1.2.7.2 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.7.2.1 |  |  | 0 | 0
524 | DEL-0008 | TSK-00515 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.2.3 | 1.2.7.2 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.2.7.2.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.3 | 1.2.7 | Curate Moodboard | Overarching Moodboard | Curate Moodboard |  |  | 0 | 26 | 0 | 1.2.7.2.3 |  |  | 0 | 0
526 | DEL-0008 | TSK-00517 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.3.1 | 1.2.7.3 | Curate Moodboard | Overarching Moodboard | Curate Moodboard | Art Director | Lead/Director | 4 |  |  | 1.2.7.3 |  |  | 0 | 0
530 | DEL-0008 | TSK-00521 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.3.2 | 1.2.7.3 | Curate Moodboard | Overarching Moodboard | Curate Moodboard | Copywriter | Mid | 3 |  |  | 1.2.7.3.1 |  |  | 0 | 0
525 | DEL-0008 | TSK-00516 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7.3.3 | 1.2.7.3 | Curate Moodboard | Overarching Moodboard | Curate Moodboard | Designer | Mid | 21 |  |  | 1.2.7.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8 | 1.2 | Tagline Copy Bank | Tagline Copy Bank |  |  |  | 28 | 21 | 5 | 1.2.7 |  |  | 195 | 5460
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.1 | 1.2.8 | Internal Review & Critique | Tagline Copy Bank | Internal Review & Critique |  |  | 0 | 21 | 2 | 1.2.8 |  |  | 0 | 0
536 | DEL-0008 | TSK-00527 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.1.1 | 1.2.8.1 | Internal Review & Critique | Tagline Copy Bank | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.2.8.1 |  |  | 0 | 0
537 | DEL-0008 | TSK-00528 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.1.2 | 1.2.8.1 | Internal Review & Critique | Tagline Copy Bank | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.8.1.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.2 | 1.2.8 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions |  |  | 0 | 23 | 3 | 1.2.8.1.2 |  |  | 0 | 0
531 | DEL-0008 | TSK-00522 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.2.1 | 1.2.8.2 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.2.8.2 |  |  | 0 | 0
532 | DEL-0008 | TSK-00523 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.2.2 | 1.2.8.2 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.2.8.2.1 |  |  | 0 | 0
533 | DEL-0008 | TSK-00524 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.2.3 | 1.2.8.2 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.8.2.2 |  |  | 0 | 0
534 | DEL-0008 | TSK-00525 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.2.4 | 1.2.8.2 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.2.8.2.3 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.3 | 1.2.8 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale |  |  | 0 | 26 | 0 | 1.2.8.2.4 |  |  | 0 | 0
538 | DEL-0008 | TSK-00529 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.3.1 | 1.2.8.3 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale | Copywriter | Mid | 5 |  |  | 1.2.8.3 |  |  | 0 | 0
539 | DEL-0008 | TSK-00530 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.3.2 | 1.2.8.3 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale | Creative Director | Lead/Director | 4 |  |  | 1.2.8.3.1 |  |  | 0 | 0
535 | DEL-0008 | TSK-00526 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8.3.3 | 1.2.8.3 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale | Designer | Mid | 11 |  |  | 1.2.8.3.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9 | 1.2 | Textures/Patterns/Materials | Textures/Patterns/Materials |  |  |  | 38 | 21 | 5 | 1.2.8 |  |  | 195 | 7410
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.1 | 1.2.9 | Internal Review & Critique | Textures/Patterns/Materials | Internal Review & Critique |  |  | 0 | 21 | 2 | 1.2.9 |  |  | 0 | 0
546 | DEL-0008 | TSK-00537 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.1.1 | 1.2.9.1 | Internal Review & Critique | Textures/Patterns/Materials | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.2.9.1 |  |  | 0 | 0
547 | DEL-0008 | TSK-00538 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.1.2 | 1.2.9.1 | Internal Review & Critique | Textures/Patterns/Materials | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.9.1.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.2 | 1.2.9 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions |  |  | 0 | 23 | 3 | 1.2.9.1.2 |  |  | 0 | 0
542 | DEL-0008 | TSK-00533 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.2.1 | 1.2.9.2 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.2.9.2 |  |  | 0 | 0
543 | DEL-0008 | TSK-00534 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.2.2 | 1.2.9.2 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.9.2.1 |  |  | 0 | 0
544 | DEL-0008 | TSK-00535 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.2.3 | 1.2.9.2 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.2.9.2.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.3 | 1.2.9 | Build Repeating Tiles | Textures/Patterns/Materials | Build Repeating Tiles |  |  | 0 | 26 | 0 | 1.2.9.2.3 |  |  | 0 | 0
541 | DEL-0008 | TSK-00532 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9.3.1 | 1.2.9.3 | Build Repeating Tiles | Textures/Patterns/Materials | Build Repeating Tiles | Designer | Mid | 31 |  |  | 1.2.9.3 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10 | 1.2 | Visual Elements/Comps | Visual Elements/Comps |  |  |  | 42 | 21 | 5 | 1.2.9 |  |  | 195 | 8190
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.1 | 1.2.10 | Internal Review & Critique | Visual Elements/Comps | Internal Review & Critique |  |  | 0 | 21 | 2 | 1.2.10 |  |  | 0 | 0
566 | DEL-0008 | TSK-00557 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.1.1 | 1.2.10.1 | Internal Review & Critique | Visual Elements/Comps | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.2.10.1 |  |  | 0 | 0
567 | DEL-0008 | TSK-00558 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.1.2 | 1.2.10.1 | Internal Review & Critique | Visual Elements/Comps | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.2.10.1.1 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.2 | 1.2.10 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions |  |  | 0 | 23 | 3 | 1.2.10.1.2 |  |  | 0 | 0
559 | DEL-0008 | TSK-00550 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.2.1 | 1.2.10.2 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.2.10.2 |  |  | 0 | 0
560 | DEL-0008 | TSK-00551 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.2.2 | 1.2.10.2 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.2.10.2.1 |  |  | 0 | 0
561 | DEL-0008 | TSK-00552 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.2.3 | 1.2.10.2 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.2.10.2.2 |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.3 | 1.2.10 | Compositions (2-3) | Visual Elements/Comps | Compositions (2-3) |  |  | 0 | 26 | 0 | 1.2.10.2.3 |  |  | 0 | 0
562 | DEL-0008 | TSK-00553 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.3.1 | 1.2.10.3 | Compositions (2-3) | Visual Elements/Comps | Compositions (2-3) | Art Director | Lead/Director | 4 |  |  | 1.2.10.3 |  |  | 0 | 0
563 | DEL-0008 | TSK-00554 | Creative | Brand Identity Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10.3.2 | 1.2.10.3 | Compositions (2-3) | Visual Elements/Comps | Compositions (2-3) | Designer | Mid | 31 |  |  | 1.2.10.3.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3 | 1 | Development |  |  |  |  | 348 | 26 | 28 | 1.2 |  | Advanced/T1_LargeVolume | 195 | 67860
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1 | 1.3 | ADA Compliance | ADA Compliance |  |  |  | 77 | 26 | 19 | 1.3 |  |  | 195 | 15015
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.1 | 1.3.1 | Accessibility Audit | ADA Compliance | Accessibility Audit |  |  | 0 | 26 | 4 | 1.3.1 |  |  | 0 | 0
1738 | DEL-0044 | TSK-01729 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.1.1 | 1.3.1.1 | Accessibility Audit | ADA Compliance | Accessibility Audit | Accessibility Specialist | Mid | 3 |  |  | 1.3.1.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.2 | 1.3.1 | Accessibility QA | ADA Compliance | Accessibility QA |  |  | 0 | 39 | 3 | 1.3.1.1.1 |  |  | 0 | 0
1739 | DEL-0044 | TSK-01730 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.2.1 | 1.3.1.2 | Accessibility QA | ADA Compliance | Accessibility QA | Accessibility Specialist | Mid | 2 |  |  | 1.3.1.2 |  |  | 0 | 0
1744 | DEL-0044 | TSK-01735 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.2.2 | 1.3.1.2 | Accessibility QA | ADA Compliance | Accessibility QA | QA Engineer | Mid | 4 |  |  | 1.3.1.2.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.3 | 1.3.1 | Code Review | ADA Compliance | Code Review |  |  | 0 | 42 | 12 | 1.3.1.2.2 |  |  | 0 | 0
1740 | DEL-0044 | TSK-01731 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.3.1 | 1.3.1.3 | Code Review | ADA Compliance | Code Review | Backend Engineer | Mid | 16 |  |  | 1.3.1.3 |  |  | 0 | 0
1742 | DEL-0044 | TSK-01733 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.3.2 | 1.3.1.3 | Code Review | ADA Compliance | Code Review | DevOps Engineer | Mid | 16 |  |  | 1.3.1.3.1 |  |  | 0 | 0
1741 | DEL-0044 | TSK-01732 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.3.3 | 1.3.1.3 | Code Review | ADA Compliance | Code Review | Frontend Engineer | Mid | 31 |  |  | 1.3.1.3.2 |  |  | 0 | 0
1743 | DEL-0044 | TSK-01734 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1.3.4 | 1.3.1.3 | Code Review | ADA Compliance | Code Review | Project Manager | Mid | 5 |  |  | 1.3.1.3.3 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2 | 1.3 | Audit & Requirement gathering | Audit & Requirement gathering |  |  |  | 26 | 26 | 4 | 1.3.1 |  |  | 195 | 5070
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2.1 | 1.3.2 | Analytics Audit | Audit & Requirement gathering | Analytics Audit |  |  | 0 | 26 | 4 | 1.3.2 |  |  | 0 | 0
1750 | DEL-0044 | TSK-01741 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2.1.1 | 1.3.2.1 | Analytics Audit | Audit & Requirement gathering | Analytics Audit | Business Analyst | Mid | 13 |  |  | 1.3.2.1 |  |  | 0 | 0
1749 | DEL-0044 | TSK-01740 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2.1.2 | 1.3.2.1 | Analytics Audit | Audit & Requirement gathering | Analytics Audit | Data/Analytics Engineer | Mid | 13 |  |  | 1.3.2.1.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3 | 1.3 | Audit existing UA Property | Audit existing UA Property |  |  |  | 26 | 26 | 4 | 1.3.2 |  |  | 195 | 5070
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3.1 | 1.3.3 | Documentation | Audit existing UA Property | Documentation |  |  | 0 | 26 | 4 | 1.3.3 |  |  | 0 | 0
1753 | DEL-0044 | TSK-01744 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3.1.1 | 1.3.3.1 | Documentation | Audit existing UA Property | Documentation | Business Analyst | Mid | 13 |  |  | 1.3.3.1 |  |  | 0 | 0
1755 | DEL-0044 | TSK-01746 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3.1.2 | 1.3.3.1 | Documentation | Audit existing UA Property | Documentation | Data/Analytics Engineer | Mid | 13 |  |  | 1.3.3.1.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4 | 1.3 | Footer CTA | Footer CTA |  |  |  | 66 | 30 | 24 | 1.3.3 |  |  | 195 | 12870
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.1 | 1.3.4 | Design Consult | Footer CTA | Design Consult |  |  | 0 | 30 | 9 | 1.3.4 |  |  | 0 | 0
1765 | DEL-0044 | TSK-01756 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.1.1 | 1.3.4.1 | Design Consult | Footer CTA | Design Consult | UI Designer | Mid | 5 |  |  | 1.3.4.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.2 | 1.3.4 | Accessibility QA | Footer CTA | Accessibility QA |  |  | 0 | 39 | 3 | 1.3.4.1.1 |  |  | 0 | 0
1760 | DEL-0044 | TSK-01751 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.2.1 | 1.3.4.2 | Accessibility QA | Footer CTA | Accessibility QA | Accessibility Specialist | Mid | 3 |  |  | 1.3.4.2 |  |  | 0 | 0
1767 | DEL-0044 | TSK-01758 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.2.2 | 1.3.4.2 | Accessibility QA | Footer CTA | Accessibility QA | Frontend Engineer | Mid | 2 |  |  | 1.3.4.2.1 |  |  | 0 | 0
1766 | DEL-0044 | TSK-01757 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.2.3 | 1.3.4.2 | Accessibility QA | Footer CTA | Accessibility QA | QA Engineer | Mid | 4 |  |  | 1.3.4.2.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.3 | 1.3.4 | Code Review | Footer CTA | Code Review |  |  | 0 | 42 | 12 | 1.3.4.2.3 |  |  | 0 | 0
1761 | DEL-0044 | TSK-01752 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.3.1 | 1.3.4.3 | Code Review | Footer CTA | Code Review | Backend Engineer | Mid | 16 |  |  | 1.3.4.3 |  |  | 0 | 0
1763 | DEL-0044 | TSK-01754 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.3.2 | 1.3.4.3 | Code Review | Footer CTA | Code Review | DevOps Engineer | Mid | 16 |  |  | 1.3.4.3.1 |  |  | 0 | 0
1762 | DEL-0044 | TSK-01753 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.3.3 | 1.3.4.3 | Code Review | Footer CTA | Code Review | Frontend Engineer | Mid | 15 |  |  | 1.3.4.3.2 |  |  | 0 | 0
1764 | DEL-0044 | TSK-01755 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4.3.4 | 1.3.4.3 | Code Review | Footer CTA | Code Review | Project Manager | Mid | 5 |  |  | 1.3.4.3.3 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5 | 1.3 | Header & Footer Navigation | Header & Footer Navigation |  |  |  | 66 | 30 | 24 | 1.3.4 |  |  | 195 | 12870
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.1 | 1.3.5 | Design Consult | Header & Footer Navigation | Design Consult |  |  | 0 | 30 | 9 | 1.3.5 |  |  | 0 | 0
1773 | DEL-0044 | TSK-01764 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.1.1 | 1.3.5.1 | Design Consult | Header & Footer Navigation | Design Consult | UI Designer | Mid | 5 |  |  | 1.3.5.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.2 | 1.3.5 | Accessibility QA | Header & Footer Navigation | Accessibility QA |  |  | 0 | 39 | 3 | 1.3.5.1.1 |  |  | 0 | 0
1768 | DEL-0044 | TSK-01759 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.2.1 | 1.3.5.2 | Accessibility QA | Header & Footer Navigation | Accessibility QA | Accessibility Specialist | Mid | 3 |  |  | 1.3.5.2 |  |  | 0 | 0
1775 | DEL-0044 | TSK-01766 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.2.2 | 1.3.5.2 | Accessibility QA | Header & Footer Navigation | Accessibility QA | Frontend Engineer | Mid | 2 |  |  | 1.3.5.2.1 |  |  | 0 | 0
1774 | DEL-0044 | TSK-01765 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.2.3 | 1.3.5.2 | Accessibility QA | Header & Footer Navigation | Accessibility QA | QA Engineer | Mid | 4 |  |  | 1.3.5.2.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.3 | 1.3.5 | Code Review | Header & Footer Navigation | Code Review |  |  | 0 | 42 | 12 | 1.3.5.2.3 |  |  | 0 | 0
1769 | DEL-0044 | TSK-01760 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.3.1 | 1.3.5.3 | Code Review | Header & Footer Navigation | Code Review | Backend Engineer | Mid | 16 |  |  | 1.3.5.3 |  |  | 0 | 0
1771 | DEL-0044 | TSK-01762 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.3.2 | 1.3.5.3 | Code Review | Header & Footer Navigation | Code Review | DevOps Engineer | Mid | 16 |  |  | 1.3.5.3.1 |  |  | 0 | 0
1770 | DEL-0044 | TSK-01761 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.3.3 | 1.3.5.3 | Code Review | Header & Footer Navigation | Code Review | Frontend Engineer | Mid | 15 |  |  | 1.3.5.3.2 |  |  | 0 | 0
1772 | DEL-0044 | TSK-01763 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5.3.4 | 1.3.5.3 | Code Review | Header & Footer Navigation | Code Review | Project Manager | Mid | 5 |  |  | 1.3.5.3.3 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.6 | 1.3 | Additional Goals Setup | Additional Goals Setup |  |  |  | 11 | 39 | 15 | 1.3.5 |  |  | 195 | 2145
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.6.1 | 1.3.6 | QA Cycle | Additional Goals Setup | QA Cycle |  |  | 0 | 39 | 3 | 1.3.6 |  |  | 0 | 0
1747 | DEL-0044 | TSK-01738 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.6.1.1 | 1.3.6.1 | QA Cycle | Additional Goals Setup | QA Cycle | QA Engineer | Mid | 4 |  |  | 1.3.6.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.6.2 | 1.3.6 | Define & Configure Goals | Additional Goals Setup | Define & Configure Goals |  |  | 0 | 42 | 12 | 1.3.6.1.1 |  |  | 0 | 0
1746 | DEL-0044 | TSK-01737 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.6.2.1 | 1.3.6.2 | Define & Configure Goals | Additional Goals Setup | Define & Configure Goals | Data/Analytics Engineer | Mid | 7 |  |  | 1.3.6.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.7 | 1.3 | Custom Event Tracking | Custom Event Tracking |  |  |  | 11 | 39 | 15 | 1.3.6 |  |  | 195 | 2145
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.7.1 | 1.3.7 | QA Cycle | Custom Event Tracking | QA Cycle |  |  | 0 | 39 | 3 | 1.3.7 |  |  | 0 | 0
1758 | DEL-0044 | TSK-01749 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.7.1.1 | 1.3.7.1 | QA Cycle | Custom Event Tracking | QA Cycle | QA Engineer | Mid | 4 |  |  | 1.3.7.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.7.2 | 1.3.7 | Event Schema & Tagging | Custom Event Tracking | Event Schema & Tagging |  |  | 0 | 42 | 12 | 1.3.7.1.1 |  |  | 0 | 0
1757 | DEL-0044 | TSK-01748 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.7.2.1 | 1.3.7.2 | Event Schema & Tagging | Custom Event Tracking | Event Schema & Tagging | Data/Analytics Engineer | Mid | 7 |  |  | 1.3.7.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8 | 1.3 | Implement Paid Media Pixel on website w GTM-Google Ads | Implement Paid Media Pixel on website w GTM-Google Ads |  |  |  | 7 | 39 | 15 | 1.3.7 |  |  | 195 | 1365
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8.1 | 1.3.8 | Spec QA | Implement Paid Media Pixel on website w GTM-Google Ads | Spec QA |  |  | 0 | 39 | 3 | 1.3.8 |  |  | 0 | 0
1777 | DEL-0044 | TSK-01768 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8.1.1 | 1.3.8.1 | Spec QA | Implement Paid Media Pixel on website w GTM-Google Ads | Spec QA | QA Engineer | Mid | 4 |  |  | 1.3.8.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8.2 | 1.3.8 | Pixel Setup (GTM) | Implement Paid Media Pixel on website w GTM-Google Ads | Pixel Setup (GTM) |  |  | 0 | 42 | 12 | 1.3.8.1.1 |  |  | 0 | 0
1776 | DEL-0044 | TSK-01767 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8.2.1 | 1.3.8.2 | Pixel Setup (GTM) | Implement Paid Media Pixel on website w GTM-Google Ads | Pixel Setup (GTM) | Data/Analytics Engineer | Mid | 3 |  |  | 1.3.8.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.9 | 1.3 | Implement goals listed in UA as Conversions in G4 | Implement goals listed in UA as Conversions in G4 |  |  |  | 10 | 39 | 15 | 1.3.8 |  |  | 195 | 1950
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.9.1 | 1.3.9 | QA Cycle | Implement goals listed in UA as Conversions in G4 | QA Cycle |  |  | 0 | 39 | 3 | 1.3.9 |  |  | 0 | 0
1779 | DEL-0044 | TSK-01770 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.9.1.1 | 1.3.9.1 | QA Cycle | Implement goals listed in UA as Conversions in G4 | QA Cycle | QA Engineer | Mid | 4 |  |  | 1.3.9.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.9.2 | 1.3.9 | Migrate UA Goals → GA4 Conversions | Implement goals listed in UA as Conversions in G4 | Migrate UA Goals → GA4 Conversions |  |  | 0 | 42 | 12 | 1.3.9.1.1 |  |  | 0 | 0
1778 | DEL-0044 | TSK-01769 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.9.2.1 | 1.3.9.2 | Migrate UA Goals → GA4 Conversions | Implement goals listed in UA as Conversions in G4 | Migrate UA Goals → GA4 Conversions | Data/Analytics Engineer | Mid | 6 |  |  | 1.3.9.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.10 | 1.3 | Implementation | Implementation |  |  |  | 10 | 39 | 15 | 1.3.9 |  |  | 195 | 1950
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.10.1 | 1.3.10 | QA Cycle | Implementation | QA Cycle |  |  | 0 | 39 | 3 | 1.3.10 |  |  | 0 | 0
1782 | DEL-0044 | TSK-01773 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.10.1.1 | 1.3.10.1 | QA Cycle | Implementation | QA Cycle | QA Engineer | Mid | 4 |  |  | 1.3.10.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.10.2 | 1.3.10 | Implement Tags/Events | Implementation | Implement Tags/Events |  |  | 0 | 42 | 12 | 1.3.10.1.1 |  |  | 0 | 0
1781 | DEL-0044 | TSK-01772 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.10.2.1 | 1.3.10.2 | Implement Tags/Events | Implementation | Implement Tags/Events | Data/Analytics Engineer | Mid | 6 |  |  | 1.3.10.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.11 | 1.3 | Outbound link clicks | Outbound link clicks |  |  |  | 7 | 39 | 15 | 1.3.10 |  |  | 195 | 1365
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.11.1 | 1.3.11 | QA | Outbound link clicks | QA |  |  | 0 | 39 | 3 | 1.3.11 |  |  | 0 | 0
1785 | DEL-0044 | TSK-01776 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.11.1.1 | 1.3.11.1 | QA | Outbound link clicks | QA | QA Engineer | Mid | 4 |  |  | 1.3.11.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.11.2 | 1.3.11 | Event Config | Outbound link clicks | Event Config |  |  | 0 | 42 | 12 | 1.3.11.1.1 |  |  | 0 | 0
1784 | DEL-0044 | TSK-01775 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.11.2.1 | 1.3.11.2 | Event Config | Outbound link clicks | Event Config | Data/Analytics Engineer | Mid | 3 |  |  | 1.3.11.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.12 | 1.3 | Publishing tags, Testing and Auditing | Publishing tags, Testing and Auditing |  |  |  | 7 | 39 | 3 | 1.3.11 |  |  | 195 | 1365
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.12.1 | 1.3.12 | Publish & Smoke Test | Publishing tags, Testing and Auditing | Publish & Smoke Test |  |  | 0 | 39 | 3 | 1.3.12 |  |  | 0 | 0
1786 | DEL-0044 | TSK-01777 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.12.1.1 | 1.3.12.1 | Publish & Smoke Test | Publishing tags, Testing and Auditing | Publish & Smoke Test | Data/Analytics Engineer | Mid | 3 |  |  | 1.3.12.1 |  |  | 0 | 0
1787 | DEL-0044 | TSK-01778 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.12.1.2 | 1.3.12.1 | Publish & Smoke Test | Publishing tags, Testing and Auditing | Publish & Smoke Test | QA Engineer | Mid | 4 |  |  | 1.3.12.1.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.13 | 1.3 | Setup cross-domain tracking | Setup cross-domain tracking |  |  |  | 7 | 39 | 15 | 1.3.12 |  |  | 195 | 1365
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.13.1 | 1.3.13 | QA | Setup cross-domain tracking | QA |  |  | 0 | 39 | 3 | 1.3.13 |  |  | 0 | 0
1789 | DEL-0044 | TSK-01780 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.13.1.1 | 1.3.13.1 | QA | Setup cross-domain tracking | QA | QA Engineer | Mid | 4 |  |  | 1.3.13.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.13.2 | 1.3.13 | Cross-domain Config | Setup cross-domain tracking | Cross-domain Config |  |  | 0 | 42 | 12 | 1.3.13.1.1 |  |  | 0 | 0
1788 | DEL-0044 | TSK-01779 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.13.2.1 | 1.3.13.2 | Cross-domain Config | Setup cross-domain tracking | Cross-domain Config | Data/Analytics Engineer | Mid | 3 |  |  | 1.3.13.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.14 | 1.3 | Setup eCommerce tracking | Setup eCommerce tracking |  |  |  | 7 | 39 | 15 | 1.3.13 |  |  | 195 | 1365
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.14.1 | 1.3.14 | QA | Setup eCommerce tracking | QA |  |  | 0 | 39 | 3 | 1.3.14 |  |  | 0 | 0
1791 | DEL-0044 | TSK-01782 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.14.1.1 | 1.3.14.1 | QA | Setup eCommerce tracking | QA | QA Engineer | Mid | 4 |  |  | 1.3.14.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.14.2 | 1.3.14 | Ecommerce Data Layer | Setup eCommerce tracking | Ecommerce Data Layer |  |  | 0 | 42 | 12 | 1.3.14.1.1 |  |  | 0 | 0
1790 | DEL-0044 | TSK-01781 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.14.2.1 | 1.3.14.2 | Ecommerce Data Layer | Setup eCommerce tracking | Ecommerce Data Layer | Data/Analytics Engineer | Mid | 3 |  |  | 1.3.14.2 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15 | 1.3 | Setup new GA4 acct for Caledera House | Setup new GA4 acct for Caledera House |  |  |  | 10 | 39 | 15 | 1.3.14 |  |  | 195 | 1950
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15.1 | 1.3.15 | QA Cycle | Setup new GA4 acct for Caledera House | QA Cycle |  |  | 0 | 39 | 3 | 1.3.15 |  |  | 0 | 0
1793 | DEL-0044 | TSK-01784 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15.1.1 | 1.3.15.1 | QA Cycle | Setup new GA4 acct for Caledera House | QA Cycle | QA Engineer | Mid | 4 |  |  | 1.3.15.1 |  |  | 0 | 0
| DEL-0044 |  | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15.2 | 1.3.15 | GA4 Property Setup | Setup new GA4 acct for Caledera House | GA4 Property Setup |  |  | 0 | 42 | 12 | 1.3.15.1.1 |  |  | 0 | 0
1792 | DEL-0044 | TSK-01783 | Technology | Development | Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15.2.1 | 1.3.15.2 | GA4 Property Setup | Setup new GA4 acct for Caledera House | GA4 Property Setup | Data/Analytics Engineer | Mid | 6 |  |  | 1.3.15.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4 | 1 | Pre-Production |  |  |  |  | 606 | 54 | 69 | 1.3 |  | Advanced/T1_LargeVolume | 195 | 118170
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1 | 1.4 | Wardrobe | Wardrobe |  |  |  | 19 | 54 | 8 | 1.4 |  |  | 195 | 3705
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.1 | 1.4.1 | Wardrobe Brief | Wardrobe | Wardrobe Brief |  |  | 0 | 54 | 3 | 1.4.1 |  |  | 0 | 0
361 | DEL-0004 | TSK-00352 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.1.1 | 1.4.1.1 | Wardrobe Brief | Wardrobe | Wardrobe Brief | Art Director | Lead/Director | 2 |  |  | 1.4.1.1 |  |  | 0 | 0
362 | DEL-0004 | TSK-00353 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.1.2 | 1.4.1.1 | Wardrobe Brief | Wardrobe | Wardrobe Brief | Producer | Mid | 2 |  |  | 1.4.1.1.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.2 | 1.4.1 | Internal Review & Critique | Wardrobe | Internal Review & Critique |  |  | 0 | 116 | 2 | 1.4.1.1.2 |  |  | 0 | 0
358 | DEL-0004 | TSK-00349 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.2.1 | 1.4.1.2 | Internal Review & Critique | Wardrobe | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.1.2 |  |  | 0 | 0
359 | DEL-0004 | TSK-00350 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.2.2 | 1.4.1.2 | Internal Review & Critique | Wardrobe | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.1.2.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.3 | 1.4.1 | Client Review & Revisions | Wardrobe | Client Review & Revisions |  |  | 0 | 118 | 3 | 1.4.1.2.2 |  |  | 0 | 0
354 | DEL-0004 | TSK-00345 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.3.1 | 1.4.1.3 | Client Review & Revisions | Wardrobe | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.1.3 |  |  | 0 | 0
355 | DEL-0004 | TSK-00346 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.3.2 | 1.4.1.3 | Client Review & Revisions | Wardrobe | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.4.1.3.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.4 | 1.4.1 | Final Packaging | Wardrobe | Final Packaging |  |  | 0 | 123 | 0 | 1.4.1.3.2 |  |  | 0 | 0
356 | DEL-0004 | TSK-00347 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.4.1 | 1.4.1.4 | Final Packaging | Wardrobe | Final Packaging | Designer | Mid | 7 |  |  | 1.4.1.4 |  |  | 0 | 0
357 | DEL-0004 | TSK-00348 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1.4.2 | 1.4.1.4 | Final Packaging | Wardrobe | Final Packaging | Producer | Mid | 2 |  |  | 1.4.1.4.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2 | 1.4 | Pre-Production Deck | Pre-Production Deck |  |  |  | 39 | 57 | 16 | 1.4.1 |  |  | 195 | 7605
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.1 | 1.4.2 | Content Draft | Pre-Production Deck | Content Draft |  |  | 0 | 57 | 6 | 1.4.2 |  |  | 0 | 0
217 | DEL-0004 | TSK-00217 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.1.1 | 1.4.2.1 | Content Draft | Pre-Production Deck | Content Draft | Designer | Mid | 10 |  |  | 1.4.2.1 |  |  | 0 | 0
214 | DEL-0004 | TSK-00214 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.1.2 | 1.4.2.1 | Content Draft | Pre-Production Deck | Content Draft | Producer | Mid | 5 |  |  | 1.4.2.1.1 |  |  | 0 | 0
215 | DEL-0004 | TSK-00215 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.1.3 | 1.4.2.1 | Content Draft | Pre-Production Deck | Content Draft | Strategist | Mid | 16 |  |  | 1.4.2.1.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.2 | 1.4.2 | Deck Build | Pre-Production Deck | Deck Build |  |  | 0 | 72 | 5 | 1.4.2.1.3 |  |  | 0 | 0
216 | DEL-0004 | TSK-00216 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.2.1 | 1.4.2.2 | Deck Build | Pre-Production Deck | Deck Build | Designer | Mid | 2 |  |  | 1.4.2.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.3 | 1.4.2 | Internal Review & Critique | Pre-Production Deck | Internal Review & Critique |  |  | 0 | 116 | 2 | 1.4.2.2.1 |  |  | 0 | 0
218 | DEL-0004 | TSK-00218 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.3.1 | 1.4.2.3 | Internal Review & Critique | Pre-Production Deck | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.2.3 |  |  | 0 | 0
219 | DEL-0004 | TSK-00219 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.3.2 | 1.4.2.3 | Internal Review & Critique | Pre-Production Deck | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.2.3.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.4 | 1.4.2 | Client Review & Revisions | Pre-Production Deck | Client Review & Revisions |  |  | 0 | 118 | 3 | 1.4.2.3.2 |  |  | 0 | 0
212 | DEL-0004 | TSK-00212 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.4.1 | 1.4.2.4 | Client Review & Revisions | Pre-Production Deck | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.2.4 |  |  | 0 | 0
213 | DEL-0004 | TSK-00213 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2.4.2 | 1.4.2.4 | Client Review & Revisions | Pre-Production Deck | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.4.2.4.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3 | 1.4 | File Naming Convention & Storage | File Naming Convention & Storage |  |  |  | 18 | 63 | 14 | 1.4.2 |  |  | 195 | 3510
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.1 | 1.4.3 | Schema Design | File Naming Convention & Storage | Schema Design |  |  | 0 | 63 | 9 | 1.4.3 |  |  | 0 | 0
186 | DEL-0004 | TSK-00186 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.1.1 | 1.4.3.1 | Schema Design | File Naming Convention & Storage | Schema Design | Media Manager / DIT | Mid | 3 |  |  | 1.4.3.1 |  |  | 0 | 0
187 | DEL-0004 | TSK-00187 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.1.2 | 1.4.3.1 | Schema Design | File Naming Convention & Storage | Schema Design | Producer | Mid | 1 |  |  | 1.4.3.1.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.2 | 1.4.3 | Internal Review & Critique | File Naming Convention & Storage | Internal Review & Critique |  |  | 0 | 116 | 2 | 1.4.3.1.2 |  |  | 0 | 0
184 | DEL-0004 | TSK-00184 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.2.1 | 1.4.3.2 | Internal Review & Critique | File Naming Convention & Storage | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.3.2 |  |  | 0 | 0
185 | DEL-0004 | TSK-00185 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.2.2 | 1.4.3.2 | Internal Review & Critique | File Naming Convention & Storage | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.3.2.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.3 | 1.4.3 | Client Review & Revisions | File Naming Convention & Storage | Client Review & Revisions |  |  | 0 | 118 | 3 | 1.4.3.2.2 |  |  | 0 | 0
179 | DEL-0004 | TSK-00179 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.3.1 | 1.4.3.3 | Client Review & Revisions | File Naming Convention & Storage | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.3.3 |  |  | 0 | 0
180 | DEL-0004 | TSK-00180 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.3.2 | 1.4.3.3 | Client Review & Revisions | File Naming Convention & Storage | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.4.3.3.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.4 | 1.4.3 | Distribution & Notes | File Naming Convention & Storage | Distribution & Notes |  |  | 0 | 123 | 0 | 1.4.3.3.2 |  |  | 0 | 0
182 | DEL-0004 | TSK-00182 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.4.1 | 1.4.3.4 | Distribution & Notes | File Naming Convention & Storage | Distribution & Notes | Designer | Mid | 3 |  |  | 1.4.3.4 |  |  | 0 | 0
183 | DEL-0004 | TSK-00183 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.4.2 | 1.4.3.4 | Distribution & Notes | File Naming Convention & Storage | Distribution & Notes | Media Manager / DIT | Mid | 3 |  |  | 1.4.3.4.1 |  |  | 0 | 0
181 | DEL-0004 | TSK-00181 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3.4.3 | 1.4.3.4 | Distribution & Notes | File Naming Convention & Storage | Distribution & Notes | Producer | Mid | 2 |  |  | 1.4.3.4.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4 | 1.4 | R1 Pre-Production Deck/Shot List | R1 Pre-Production Deck/Shot List |  |  |  | 25 | 72 | 5 | 1.4.3 |  |  | 195 | 4875
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.1 | 1.4.4 | Client Review & Revisions | R1 Pre-Production Deck/Shot List | Client Review & Revisions |  |  | 0 | 72 | 5 | 1.4.4 |  |  | 0 | 0
230 | DEL-0004 | TSK-00230 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.1.1 | 1.4.4.1 | Client Review & Revisions | R1 Pre-Production Deck/Shot List | Client Review & Revisions | Account Manager | Mid | 4 |  |  | 1.4.4.1 |  |  | 0 | 0
236 | DEL-0004 | TSK-00236 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.1.2 | 1.4.4.1 | Client Review & Revisions | R1 Pre-Production Deck/Shot List | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.4.4.1.1 |  |  | 0 | 0
232 | DEL-0004 | TSK-00232 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.1.3 | 1.4.4.1 | Client Review & Revisions | R1 Pre-Production Deck/Shot List | Client Review & Revisions | Designer | Mid | 4 |  |  | 1.4.4.1.2 |  |  | 0 | 0
231 | DEL-0004 | TSK-00231 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.1.4 | 1.4.4.1 | Client Review & Revisions | R1 Pre-Production Deck/Shot List | Client Review & Revisions | Producer | Mid | 11 |  |  | 1.4.4.1.3 |  |  | 0 | 0
234 | DEL-0004 | TSK-00234 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4.1.5 | 1.4.4.1 | Client Review & Revisions | R1 Pre-Production Deck/Shot List | Client Review & Revisions | Project Manager | Mid | 4 |  |  | 1.4.4.1.4 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5 | 1.4 | R2 Pre-Production Deck/Shot List | R2 Pre-Production Deck/Shot List |  |  |  | 25 | 72 | 5 | 1.4.4 |  |  | 195 | 4875
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.1 | 1.4.5 | Client Review & Revisions | R2 Pre-Production Deck/Shot List | Client Review & Revisions |  |  | 0 | 72 | 5 | 1.4.5 |  |  | 0 | 0
238 | DEL-0004 | TSK-00238 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.1.1 | 1.4.5.1 | Client Review & Revisions | R2 Pre-Production Deck/Shot List | Client Review & Revisions | Account Manager | Mid | 4 |  |  | 1.4.5.1 |  |  | 0 | 0
244 | DEL-0004 | TSK-00244 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.1.2 | 1.4.5.1 | Client Review & Revisions | R2 Pre-Production Deck/Shot List | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.4.5.1.1 |  |  | 0 | 0
240 | DEL-0004 | TSK-00240 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.1.3 | 1.4.5.1 | Client Review & Revisions | R2 Pre-Production Deck/Shot List | Client Review & Revisions | Designer | Mid | 4 |  |  | 1.4.5.1.2 |  |  | 0 | 0
239 | DEL-0004 | TSK-00239 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.1.4 | 1.4.5.1 | Client Review & Revisions | R2 Pre-Production Deck/Shot List | Client Review & Revisions | Producer | Mid | 11 |  |  | 1.4.5.1.3 |  |  | 0 | 0
242 | DEL-0004 | TSK-00242 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5.1.5 | 1.4.5.1 | Client Review & Revisions | R2 Pre-Production Deck/Shot List | Client Review & Revisions | Project Manager | Mid | 4 |  |  | 1.4.5.1.4 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6 | 1.4 | Run of Show & Call Sheet | Run of Show & Call Sheet |  |  |  | 35 | 72 | 5 | 1.4.5 |  |  | 195 | 6825
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.1 | 1.4.6 | Client Review & Revisions | Run of Show & Call Sheet | Client Review & Revisions |  |  | 0 | 72 | 5 | 1.4.6 |  |  | 0 | 0
246 | DEL-0004 | TSK-00246 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.1.1 | 1.4.6.1 | Client Review & Revisions | Run of Show & Call Sheet | Client Review & Revisions | Account Manager | Mid | 4 |  |  | 1.4.6.1 |  |  | 0 | 0
253 | DEL-0004 | TSK-00253 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.1.2 | 1.4.6.1 | Client Review & Revisions | Run of Show & Call Sheet | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.4.6.1.1 |  |  | 0 | 0
252 | DEL-0004 | TSK-00252 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.1.3 | 1.4.6.1 | Client Review & Revisions | Run of Show & Call Sheet | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.4.6.1.2 |  |  | 0 | 0
247 | DEL-0004 | TSK-00247 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.1.4 | 1.4.6.1 | Client Review & Revisions | Run of Show & Call Sheet | Client Review & Revisions | Producer | Mid | 15 |  |  | 1.4.6.1.3 |  |  | 0 | 0
248 | DEL-0004 | TSK-00248 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6.1.5 | 1.4.6.1 | Client Review & Revisions | Run of Show & Call Sheet | Client Review & Revisions | Project Manager | Mid | 12 |  |  | 1.4.6.1.4 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7 | 1.4 | Script & Storyboards | Script & Storyboards |  |  |  | 47 | 72 | 5 | 1.4.6 |  |  | 195 | 9165
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.1 | 1.4.7 | Client Review & Revisions | Script & Storyboards | Client Review & Revisions |  |  | 0 | 72 | 5 | 1.4.7 |  |  | 0 | 0
256 | DEL-0004 | TSK-00256 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.1.1 | 1.4.7.1 | Client Review & Revisions | Script & Storyboards | Client Review & Revisions | Account Manager | Mid | 8 |  |  | 1.4.7.1 |  |  | 0 | 0
270 | DEL-0004 | TSK-00263 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.1.2 | 1.4.7.1 | Client Review & Revisions | Script & Storyboards | Client Review & Revisions | Art Director | Lead/Director | 4 |  |  | 1.4.7.1.1 |  |  | 0 | 0
258 | DEL-0004 | TSK-00257 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.1.3 | 1.4.7.1 | Client Review & Revisions | Script & Storyboards | Client Review & Revisions | Copywriter | Mid | 8 |  |  | 1.4.7.1.2 |  |  | 0 | 0
264 | DEL-0004 | TSK-00260 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.1.4 | 1.4.7.1 | Client Review & Revisions | Script & Storyboards | Client Review & Revisions | Creative Director | Lead/Director | 4 |  |  | 1.4.7.1.3 |  |  | 0 | 0
262 | DEL-0004 | TSK-00259 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.1.5 | 1.4.7.1 | Client Review & Revisions | Script & Storyboards | Client Review & Revisions | Designer | Mid | 8 |  |  | 1.4.7.1.4 |  |  | 0 | 0
260 | DEL-0004 | TSK-00258 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.7.1.6 | 1.4.7.1 | Client Review & Revisions | Script & Storyboards | Client Review & Revisions | Producer | Mid | 15 |  |  | 1.4.7.1.5 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8 | 1.4 | Shoot Oversight & Direction | Shoot Oversight & Direction |  |  |  | 18 | 72 | 8 | 1.4.7 |  |  | 195 | 3510
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.1 | 1.4.8 | Schedule Management | Shoot Oversight & Direction | Schedule Management |  |  | 0 | 72 | 5 | 1.4.8 |  |  | 0 | 0
280 | DEL-0004 | TSK-00271 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.1.1 | 1.4.8.1 | Schedule Management | Shoot Oversight & Direction | Schedule Management | Producer | Mid | 4 |  |  | 1.4.8.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.2 | 1.4.8 | Quality Check (QC) | Shoot Oversight & Direction | Quality Check (QC) |  |  | 0 | 91 | 3 | 1.4.8.1.1 |  |  | 0 | 0
279 | DEL-0004 | TSK-00270 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.2.1 | 1.4.8.2 | Quality Check (QC) | Shoot Oversight & Direction | Quality Check (QC) | QA Specialist | Mid | 4 |  |  | 1.4.8.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.3 | 1.4.8 | Daily Wrap Notes | Shoot Oversight & Direction | Daily Wrap Notes |  |  | 0 | 123 | 0 | 1.4.8.2.1 |  |  | 0 | 0
274 | DEL-0004 | TSK-00265 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.3.1 | 1.4.8.3 | Daily Wrap Notes | Shoot Oversight & Direction | Daily Wrap Notes | Account Manager | Mid | 2 |  |  | 1.4.8.3 |  |  | 0 | 0
277 | DEL-0004 | TSK-00268 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.3.2 | 1.4.8.3 | Daily Wrap Notes | Shoot Oversight & Direction | Daily Wrap Notes | Art Director | Lead/Director | 2 |  |  | 1.4.8.3.1 |  |  | 0 | 0
278 | DEL-0004 | TSK-00269 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.3.3 | 1.4.8.3 | Daily Wrap Notes | Shoot Oversight & Direction | Daily Wrap Notes | Creative Director | Lead/Director | 2 |  |  | 1.4.8.3.2 |  |  | 0 | 0
275 | DEL-0004 | TSK-00266 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.3.4 | 1.4.8.3 | Daily Wrap Notes | Shoot Oversight & Direction | Daily Wrap Notes | Producer | Mid | 2 |  |  | 1.4.8.3.3 |  |  | 0 | 0
276 | DEL-0004 | TSK-00267 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.8.3.5 | 1.4.8.3 | Daily Wrap Notes | Shoot Oversight & Direction | Daily Wrap Notes | Project Manager | Mid | 2 |  |  | 1.4.8.3.4 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9 | 1.4 | Shot List | Shot List |  |  |  | 31 | 72 | 5 | 1.4.8 |  |  | 195 | 6045
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.1 | 1.4.9 | Client Review & Revisions | Shot List | Client Review & Revisions |  |  | 0 | 72 | 5 | 1.4.9 |  |  | 0 | 0
281 | DEL-0004 | TSK-00272 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.1.1 | 1.4.9.1 | Client Review & Revisions | Shot List | Client Review & Revisions | Account Manager | Mid | 4 |  |  | 1.4.9.1 |  |  | 0 | 0
283 | DEL-0004 | TSK-00274 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.1.2 | 1.4.9.1 | Client Review & Revisions | Shot List | Client Review & Revisions | Art Director | Lead/Director | 4 |  |  | 1.4.9.1.1 |  |  | 0 | 0
287 | DEL-0004 | TSK-00278 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.1.3 | 1.4.9.1 | Client Review & Revisions | Shot List | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.4.9.1.2 |  |  | 0 | 0
284 | DEL-0004 | TSK-00275 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.1.4 | 1.4.9.1 | Client Review & Revisions | Shot List | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.4.9.1.3 |  |  | 0 | 0
282 | DEL-0004 | TSK-00273 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.1.5 | 1.4.9.1 | Client Review & Revisions | Shot List | Client Review & Revisions | Producer | Mid | 15 |  |  | 1.4.9.1.4 |  |  | 0 | 0
286 | DEL-0004 | TSK-00277 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.9.1.6 | 1.4.9.1 | Client Review & Revisions | Shot List | Client Review & Revisions | Project Manager | Mid | 4 |  |  | 1.4.9.1.5 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10 | 1.4 | Storyboard Review | Storyboard Review |  |  |  | 6 | 72 | 5 | 1.4.9 |  |  | 195 | 1170
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10.1 | 1.4.10 | Internal Crit | Storyboard Review | Internal Crit |  |  | 0 | 72 | 5 | 1.4.10 |  |  | 0 | 0
291 | DEL-0004 | TSK-00282 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10.1.1 | 1.4.10.1 | Internal Crit | Storyboard Review | Internal Crit | Art Director | Lead/Director | 2 |  |  | 1.4.10.1 |  |  | 0 | 0
292 | DEL-0004 | TSK-00283 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10.1.2 | 1.4.10.1 | Internal Crit | Storyboard Review | Internal Crit | Creative Director | Lead/Director | 2 |  |  | 1.4.10.1.1 |  |  | 0 | 0
293 | DEL-0004 | TSK-00284 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.10.1.3 | 1.4.10.1 | Internal Crit | Storyboard Review | Internal Crit | Designer | Mid | 2 |  |  | 1.4.10.1.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.11 | 1.4 | Storyboards & Script Writing | Storyboards & Script Writing |  |  |  | 23 | 72 | 5 | 1.4.10 |  |  | 195 | 4485
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.11.1 | 1.4.11 | Client Review & Revisions | Storyboards & Script Writing | Client Review & Revisions |  |  | 0 | 72 | 5 | 1.4.11 |  |  | 0 | 0
294 | DEL-0004 | TSK-00285 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.11.1.1 | 1.4.11.1 | Client Review & Revisions | Storyboards & Script Writing | Client Review & Revisions | Account Manager | Mid | 4 |  |  | 1.4.11.1 |  |  | 0 | 0
301 | DEL-0004 | TSK-00292 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.11.1.2 | 1.4.11.1 | Client Review & Revisions | Storyboards & Script Writing | Client Review & Revisions | Art Director | Lead/Director | 2 |  |  | 1.4.11.1.1 |  |  | 0 | 0
295 | DEL-0004 | TSK-00286 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.11.1.3 | 1.4.11.1 | Client Review & Revisions | Storyboards & Script Writing | Client Review & Revisions | Copywriter | Mid | 4 |  |  | 1.4.11.1.2 |  |  | 0 | 0
298 | DEL-0004 | TSK-00289 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.11.1.4 | 1.4.11.1 | Client Review & Revisions | Storyboards & Script Writing | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.4.11.1.3 |  |  | 0 | 0
297 | DEL-0004 | TSK-00288 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.11.1.5 | 1.4.11.1 | Client Review & Revisions | Storyboards & Script Writing | Client Review & Revisions | Designer | Mid | 4 |  |  | 1.4.11.1.4 |  |  | 0 | 0
296 | DEL-0004 | TSK-00287 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.11.1.6 | 1.4.11.1 | Client Review & Revisions | Storyboards & Script Writing | Client Review & Revisions | Producer | Mid | 7 |  |  | 1.4.11.1.5 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.12 | 1.4 | Casting | Casting |  |  |  | 20 | 77 | 8 | 1.4.11 |  |  | 195 | 3900
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.12.1 | 1.4.12 | Approvals/Holds | Casting | Approvals/Holds |  |  | 0 | 77 | 8 | 1.4.12 |  |  | 0 | 0
150 | DEL-0004 | TSK-00150 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.12.1.1 | 1.4.12.1 | Approvals/Holds | Casting | Approvals/Holds | Account Manager | Mid | 5 |  |  | 1.4.12.1 |  |  | 0 | 0
152 | DEL-0004 | TSK-00152 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.12.1.2 | 1.4.12.1 | Approvals/Holds | Casting | Approvals/Holds | Creative Director | Lead/Director | 1 |  |  | 1.4.12.1.1 |  |  | 0 | 0
151 | DEL-0004 | TSK-00151 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.12.1.3 | 1.4.12.1 | Approvals/Holds | Casting | Approvals/Holds | Producer | Mid | 14 |  |  | 1.4.12.1.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.13 | 1.4 | Load In & Pre-Lighting | Load In & Pre-Lighting |  |  |  | 38 | 77 | 8 | 1.4.12 |  |  | 195 | 7410
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.13.1 | 1.4.13 | Client Review & Revisions | Load In & Pre-Lighting | Client Review & Revisions |  |  | 0 | 77 | 8 | 1.4.13 |  |  | 0 | 0
188 | DEL-0004 | TSK-00188 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.13.1.1 | 1.4.13.1 | Client Review & Revisions | Load In & Pre-Lighting | Client Review & Revisions | Account Manager | Mid | 5 |  |  | 1.4.13.1 |  |  | 0 | 0
196 | DEL-0004 | TSK-00196 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.13.1.2 | 1.4.13.1 | Client Review & Revisions | Load In & Pre-Lighting | Client Review & Revisions | Art Director | Lead/Director | 2 |  |  | 1.4.13.1.1 |  |  | 0 | 0
192 | DEL-0004 | TSK-00192 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.13.1.3 | 1.4.13.1 | Client Review & Revisions | Load In & Pre-Lighting | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.4.13.1.2 |  |  | 0 | 0
191 | DEL-0004 | TSK-00191 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.13.1.4 | 1.4.13.1 | Client Review & Revisions | Load In & Pre-Lighting | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.4.13.1.3 |  |  | 0 | 0
189 | DEL-0004 | TSK-00189 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.13.1.5 | 1.4.13.1 | Client Review & Revisions | Load In & Pre-Lighting | Client Review & Revisions | Producer | Mid | 18 |  |  | 1.4.13.1.4 |  |  | 0 | 0
190 | DEL-0004 | TSK-00190 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.13.1.6 | 1.4.13.1 | Client Review & Revisions | Load In & Pre-Lighting | Client Review & Revisions | Project Manager | Mid | 9 |  |  | 1.4.13.1.5 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.14 | 1.4 | Talent Casting | Talent Casting |  |  |  | 38 | 77 | 8 | 1.4.13 |  |  | 195 | 7410
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.14.1 | 1.4.14 | Approvals & Holds | Talent Casting | Approvals & Holds |  |  | 0 | 77 | 8 | 1.4.14 |  |  | 0 | 0
303 | DEL-0004 | TSK-00294 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.14.1.1 | 1.4.14.1 | Approvals & Holds | Talent Casting | Approvals & Holds | Account Manager | Mid | 9 |  |  | 1.4.14.1 |  |  | 0 | 0
305 | DEL-0004 | TSK-00296 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.14.1.2 | 1.4.14.1 | Approvals & Holds | Talent Casting | Approvals & Holds | Creative Director | Lead/Director | 3 |  |  | 1.4.14.1.1 |  |  | 0 | 0
309 | DEL-0004 | TSK-00300 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.14.1.3 | 1.4.14.1 | Approvals & Holds | Talent Casting | Approvals & Holds | Designer | Mid | 3 |  |  | 1.4.14.1.2 |  |  | 0 | 0
304 | DEL-0004 | TSK-00295 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.14.1.4 | 1.4.14.1 | Approvals & Holds | Talent Casting | Approvals & Holds | Producer | Mid | 23 |  |  | 1.4.14.1.3 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15 | 1.4 | Post Production Plan & Timeline | Post Production Plan & Timeline |  |  |  | 33 | 85 | 11 | 1.4.14 |  |  | 195 | 6435
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.1 | 1.4.15 | Editorial Milestones | Post Production Plan & Timeline | Editorial Milestones |  |  | 0 | 85 | 6 | 1.4.15 |  |  | 0 | 0
203 | DEL-0004 | TSK-00203 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.1.1 | 1.4.15.1 | Editorial Milestones | Post Production Plan & Timeline | Editorial Milestones | Editor | Mid | 13 |  |  | 1.4.15.1 |  |  | 0 | 0
204 | DEL-0004 | TSK-00204 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.1.2 | 1.4.15.1 | Editorial Milestones | Post Production Plan & Timeline | Editorial Milestones | Producer | Mid | 3 |  |  | 1.4.15.1.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.2 | 1.4.15 | Internal Review & Critique | Post Production Plan & Timeline | Internal Review & Critique |  |  | 0 | 116 | 2 | 1.4.15.1.2 |  |  | 0 | 0
206 | DEL-0004 | TSK-00206 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.2.1 | 1.4.15.2 | Internal Review & Critique | Post Production Plan & Timeline | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.15.2 |  |  | 0 | 0
207 | DEL-0004 | TSK-00207 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.2.2 | 1.4.15.2 | Internal Review & Critique | Post Production Plan & Timeline | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.15.2.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.3 | 1.4.15 | Client Review & Revisions | Post Production Plan & Timeline | Client Review & Revisions |  |  | 0 | 118 | 3 | 1.4.15.2.2 |  |  | 0 | 0
198 | DEL-0004 | TSK-00198 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.3.1 | 1.4.15.3 | Client Review & Revisions | Post Production Plan & Timeline | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.15.3 |  |  | 0 | 0
199 | DEL-0004 | TSK-00199 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.3.2 | 1.4.15.3 | Client Review & Revisions | Post Production Plan & Timeline | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.4.15.3.1 |  |  | 0 | 0
200 | DEL-0004 | TSK-00200 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.3.3 | 1.4.15.3 | Client Review & Revisions | Post Production Plan & Timeline | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.4.15.3.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.4 | 1.4.15 | Delivery Timeline | Post Production Plan & Timeline | Delivery Timeline |  |  | 0 | 123 | 0 | 1.4.15.3.3 |  |  | 0 | 0
205 | DEL-0004 | TSK-00205 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.4.1 | 1.4.15.4 | Delivery Timeline | Post Production Plan & Timeline | Delivery Timeline | Designer | Mid | 3 |  |  | 1.4.15.4 |  |  | 0 | 0
201 | DEL-0004 | TSK-00201 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.4.2 | 1.4.15.4 | Delivery Timeline | Post Production Plan & Timeline | Delivery Timeline | Producer | Mid | 4 |  |  | 1.4.15.4.1 |  |  | 0 | 0
202 | DEL-0004 | TSK-00202 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.15.4.3 | 1.4.15.4 | Delivery Timeline | Post Production Plan & Timeline | Delivery Timeline | Project Manager | Mid | 2 |  |  | 1.4.15.4.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16 | 1.4 | Concept Development | Concept Development |  |  |  | 26 | 94 | 17 | 1.4.15 |  |  | 195 | 5070
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.1 | 1.4.16 | Ideation Sprint | Concept Development | Ideation Sprint |  |  | 0 | 94 | 12 | 1.4.16 |  |  | 0 | 0
160 | DEL-0004 | TSK-00160 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.1.1 | 1.4.16.1 | Ideation Sprint | Concept Development | Ideation Sprint | Art Director | Lead/Director | 2 |  |  | 1.4.16.1 |  |  | 0 | 0
158 | DEL-0004 | TSK-00158 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.1.2 | 1.4.16.1 | Ideation Sprint | Concept Development | Ideation Sprint | Copywriter | Mid | 3 |  |  | 1.4.16.1.1 |  |  | 0 | 0
161 | DEL-0004 | TSK-00161 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.1.3 | 1.4.16.1 | Ideation Sprint | Concept Development | Ideation Sprint | Creative Director | Lead/Director | 2 |  |  | 1.4.16.1.2 |  |  | 0 | 0
159 | DEL-0004 | TSK-00159 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.1.4 | 1.4.16.1 | Ideation Sprint | Concept Development | Ideation Sprint | Designer | Mid | 7 |  |  | 1.4.16.1.3 |  |  | 0 | 0
162 | DEL-0004 | TSK-00162 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.1.5 | 1.4.16.1 | Ideation Sprint | Concept Development | Ideation Sprint | Strategist | Mid | 5 |  |  | 1.4.16.1.4 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.2 | 1.4.16 | Internal Review & Critique | Concept Development | Internal Review & Critique |  |  | 0 | 116 | 2 | 1.4.16.1.5 |  |  | 0 | 0
163 | DEL-0004 | TSK-00163 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.2.1 | 1.4.16.2 | Internal Review & Critique | Concept Development | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.16.2 |  |  | 0 | 0
164 | DEL-0004 | TSK-00164 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.2.2 | 1.4.16.2 | Internal Review & Critique | Concept Development | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.16.2.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.3 | 1.4.16 | Client Review & Revisions | Concept Development | Client Review & Revisions |  |  | 0 | 118 | 3 | 1.4.16.2.2 |  |  | 0 | 0
155 | DEL-0004 | TSK-00155 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.3.1 | 1.4.16.3 | Client Review & Revisions | Concept Development | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.16.3 |  |  | 0 | 0
156 | DEL-0004 | TSK-00156 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.3.2 | 1.4.16.3 | Client Review & Revisions | Concept Development | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.4.16.3.1 |  |  | 0 | 0
157 | DEL-0004 | TSK-00157 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.16.3.3 | 1.4.16.3 | Client Review & Revisions | Concept Development | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.4.16.3.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17 | 1.4 | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) |  |  |  | 15 | 106 | 9 | 1.4.16 |  |  | 195 | 2925
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.1 | 1.4.17 | Inventory & Tracking | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Inventory & Tracking |  |  | 0 | 106 | 4 | 1.4.17 |  |  | 0 | 0
228 | DEL-0004 | TSK-00228 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.1.1 | 1.4.17.1 | Inventory & Tracking | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Inventory & Tracking | Producer | Mid | 1 |  |  | 1.4.17.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.2 | 1.4.17 | Internal Review & Critique | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Internal Review & Critique |  |  | 0 | 116 | 2 | 1.4.17.1.1 |  |  | 0 | 0
226 | DEL-0004 | TSK-00226 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.2.1 | 1.4.17.2 | Internal Review & Critique | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.17.2 |  |  | 0 | 0
227 | DEL-0004 | TSK-00227 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.2.2 | 1.4.17.2 | Internal Review & Critique | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Internal Review & Critique | Producer | Mid | 2 |  |  | 1.4.17.2.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.3 | 1.4.17 | Client Review & Revisions | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Client Review & Revisions |  |  | 0 | 118 | 3 | 1.4.17.2.2 |  |  | 0 | 0
223 | DEL-0004 | TSK-00223 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.3.1 | 1.4.17.3 | Client Review & Revisions | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.17.3 |  |  | 0 | 0
224 | DEL-0004 | TSK-00224 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.3.2 | 1.4.17.3 | Client Review & Revisions | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.4.17.3.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.4 | 1.4.17 | Chain of Custody | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Chain of Custody |  |  | 0 | 123 | 0 | 1.4.17.3.2 |  |  | 0 | 0
225 | DEL-0004 | TSK-00225 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.4.1 | 1.4.17.4 | Chain of Custody | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Chain of Custody | Designer | Mid | 3 |  |  | 1.4.17.4 |  |  | 0 | 0
229 | DEL-0004 | TSK-00229 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.4.2 | 1.4.17.4 | Chain of Custody | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Chain of Custody | Producer | Mid | 2 |  |  | 1.4.17.4.1 |  |  | 0 | 0
222 | DEL-0004 | TSK-00222 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.17.4.3 | 1.4.17.4 | Chain of Custody | Product Organization (this refers to the actual products being shot for CPG brands, hair, skin, beauty, etc.) | Chain of Custody | Project Manager | Mid | 2 |  |  | 1.4.17.4.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.18 | 1.4 | Vendor Deal Memos & Contracts | Vendor Deal Memos & Contracts |  |  |  | 5 | 106 | 4 | 1.4.17 |  |  | 195 | 975
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.18.1 | 1.4.18 | Filing & Tracking | Vendor Deal Memos & Contracts | Filing & Tracking |  |  | 0 | 106 | 4 | 1.4.18 |  |  | 0 | 0
333 | DEL-0004 | TSK-00324 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.18.1.1 | 1.4.18.1 | Filing & Tracking | Vendor Deal Memos & Contracts | Filing & Tracking | Project Manager | Mid | 1 |  |  | 1.4.18.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.18.2 | 1.4.18 | Deal Memos & Contracts | Vendor Deal Memos & Contracts | Deal Memos & Contracts |  |  | 0 | 123 | 0 | 1.4.18.1.1 |  |  | 0 | 0
331 | DEL-0004 | TSK-00322 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.18.2.1 | 1.4.18.2 | Deal Memos & Contracts | Vendor Deal Memos & Contracts | Deal Memos & Contracts | Account Manager | Mid | 2 |  |  | 1.4.18.2 |  |  | 0 | 0
332 | DEL-0004 | TSK-00323 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.18.2.2 | 1.4.18.2 | Deal Memos & Contracts | Vendor Deal Memos & Contracts | Deal Memos & Contracts | Producer | Mid | 2 |  |  | 1.4.18.2.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19 | 1.4 | Vendor Engagement | Vendor Engagement |  |  |  | 21 | 110 | 11 | 1.4.18 |  |  | 195 | 4095
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19.1 | 1.4.19 | Briefing Docs | Vendor Engagement | Briefing Docs |  |  | 0 | 110 | 6 | 1.4.19 |  |  | 0 | 0
339 | DEL-0004 | TSK-00330 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19.1.1 | 1.4.19.1 | Briefing Docs | Vendor Engagement | Briefing Docs | Account Manager | Mid | 2 |  |  | 1.4.19.1 |  |  | 0 | 0
334 | DEL-0004 | TSK-00325 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19.1.2 | 1.4.19.1 | Briefing Docs | Vendor Engagement | Briefing Docs | Designer | Mid | 7 |  |  | 1.4.19.1.1 |  |  | 0 | 0
335 | DEL-0004 | TSK-00326 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19.1.3 | 1.4.19.1 | Briefing Docs | Vendor Engagement | Briefing Docs | Producer | Mid | 6 |  |  | 1.4.19.1.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19.2 | 1.4.19 | Internal Review & Critique | Vendor Engagement | Internal Review & Critique |  |  | 0 | 116 | 2 | 1.4.19.1.3 |  |  | 0 | 0
342 | DEL-0004 | TSK-00333 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19.2.1 | 1.4.19.2 | Internal Review & Critique | Vendor Engagement | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.19.2 |  |  | 0 | 0
343 | DEL-0004 | TSK-00334 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19.2.2 | 1.4.19.2 | Internal Review & Critique | Vendor Engagement | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.19.2.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19.3 | 1.4.19 | Client Review & Revisions | Vendor Engagement | Client Review & Revisions |  |  | 0 | 118 | 3 | 1.4.19.2.2 |  |  | 0 | 0
336 | DEL-0004 | TSK-00327 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19.3.1 | 1.4.19.3 | Client Review & Revisions | Vendor Engagement | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.19.3 |  |  | 0 | 0
337 | DEL-0004 | TSK-00328 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.19.3.2 | 1.4.19.3 | Client Review & Revisions | Vendor Engagement | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.4.19.3.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20 | 1.4 | Art Direction | Art Direction |  |  |  | 30 | 116 | 5 | 1.4.19 |  |  | 195 | 5850
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.1 | 1.4.20 | Internal Review & Critique | Art Direction | Internal Review & Critique |  |  | 0 | 116 | 2 | 1.4.20 |  |  | 0 | 0
144 | DEL-0004 | TSK-00144 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.1.1 | 1.4.20.1 | Internal Review & Critique | Art Direction | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.20.1 |  |  | 0 | 0
145 | DEL-0004 | TSK-00145 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.1.2 | 1.4.20.1 | Internal Review & Critique | Art Direction | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.20.1.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.2 | 1.4.20 | Client Review & Revisions | Art Direction | Client Review & Revisions |  |  | 0 | 118 | 3 | 1.4.20.1.2 |  |  | 0 | 0
141 | DEL-0004 | TSK-00141 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.2.1 | 1.4.20.2 | Client Review & Revisions | Art Direction | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.20.2 |  |  | 0 | 0
142 | DEL-0004 | TSK-00142 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.2.2 | 1.4.20.2 | Client Review & Revisions | Art Direction | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.4.20.2.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.3 | 1.4.20 | Look Dev & References | Art Direction | Look Dev & References |  |  | 0 | 123 | 0 | 1.4.20.2.2 |  |  | 0 | 0
146 | DEL-0004 | TSK-00146 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.3.1 | 1.4.20.3 | Look Dev & References | Art Direction | Look Dev & References | Art Director | Lead/Director | 2 |  |  | 1.4.20.3 |  |  | 0 | 0
143 | DEL-0004 | TSK-00143 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.3.2 | 1.4.20.3 | Look Dev & References | Art Direction | Look Dev & References | Designer | Mid | 7 |  |  | 1.4.20.3.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.4 | 1.4.20 | Style Guide (lite) | Art Direction | Style Guide (lite) |  |  | 0 | 123 | 0 | 1.4.20.3.2 |  |  | 0 | 0
148 | DEL-0004 | TSK-00148 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.4.1 | 1.4.20.4 | Style Guide (lite) | Art Direction | Style Guide (lite) | Art Director | Lead/Director | 2 |  |  | 1.4.20.4 |  |  | 0 | 0
149 | DEL-0004 | TSK-00149 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.20.4.2 | 1.4.20.4 | Style Guide (lite) | Art Direction | Style Guide (lite) | Designer | Mid | 13 |  |  | 1.4.20.4.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21 | 1.4 | Concepting | Concepting |  |  |  | 32 | 116 | 5 | 1.4.20 |  |  | 195 | 6240
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.1 | 1.4.21 | Internal Review & Critique | Concepting | Internal Review & Critique |  |  | 0 | 116 | 2 | 1.4.21 |  |  | 0 | 0
175 | DEL-0004 | TSK-00175 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.1.1 | 1.4.21.1 | Internal Review & Critique | Concepting | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.21.1 |  |  | 0 | 0
176 | DEL-0004 | TSK-00176 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.1.2 | 1.4.21.1 | Internal Review & Critique | Concepting | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.21.1.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.2 | 1.4.21 | Client Review & Revisions | Concepting | Client Review & Revisions |  |  | 0 | 118 | 3 | 1.4.21.1.2 |  |  | 0 | 0
166 | DEL-0004 | TSK-00166 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.2.1 | 1.4.21.2 | Client Review & Revisions | Concepting | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.21.2 |  |  | 0 | 0
167 | DEL-0004 | TSK-00167 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.2.2 | 1.4.21.2 | Client Review & Revisions | Concepting | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.4.21.2.1 |  |  | 0 | 0
168 | DEL-0004 | TSK-00168 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.2.3 | 1.4.21.2 | Client Review & Revisions | Concepting | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.4.21.2.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.3 | 1.4.21 | Ideation Sprint | Concepting | Ideation Sprint |  |  | 0 | 123 | 0 | 1.4.21.2.3 |  |  | 0 | 0
172 | DEL-0004 | TSK-00172 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.3.1 | 1.4.21.3 | Ideation Sprint | Concepting | Ideation Sprint | Art Director | Lead/Director | 4 |  |  | 1.4.21.3 |  |  | 0 | 0
170 | DEL-0004 | TSK-00170 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.3.2 | 1.4.21.3 | Ideation Sprint | Concepting | Ideation Sprint | Copywriter | Mid | 3 |  |  | 1.4.21.3.1 |  |  | 0 | 0
173 | DEL-0004 | TSK-00173 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.3.3 | 1.4.21.3 | Ideation Sprint | Concepting | Ideation Sprint | Creative Director | Lead/Director | 3 |  |  | 1.4.21.3.2 |  |  | 0 | 0
169 | DEL-0004 | TSK-00169 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.3.4 | 1.4.21.3 | Ideation Sprint | Concepting | Ideation Sprint | Designer | Mid | 6 |  |  | 1.4.21.3.3 |  |  | 0 | 0
171 | DEL-0004 | TSK-00171 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.21.3.5 | 1.4.21.3 | Ideation Sprint | Concepting | Ideation Sprint | Strategist | Mid | 9 |  |  | 1.4.21.3.4 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22 | 1.4 | Vendor Contracting | Vendor Contracting |  |  |  | 19 | 116 | 5 | 1.4.21 |  |  | 195 | 3705
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.1 | 1.4.22 | Internal Review & Critique | Vendor Contracting | Internal Review & Critique |  |  | 0 | 116 | 2 | 1.4.22 |  |  | 0 | 0
319 | DEL-0004 | TSK-00310 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.1.1 | 1.4.22.1 | Internal Review & Critique | Vendor Contracting | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.22.1 |  |  | 0 | 0
320 | DEL-0004 | TSK-00311 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.1.2 | 1.4.22.1 | Internal Review & Critique | Vendor Contracting | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.22.1.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.2 | 1.4.22 | Client Review & Revisions | Vendor Contracting | Client Review & Revisions |  |  | 0 | 118 | 3 | 1.4.22.1.2 |  |  | 0 | 0
313 | DEL-0004 | TSK-00304 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.2.1 | 1.4.22.2 | Client Review & Revisions | Vendor Contracting | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.22.2 |  |  | 0 | 0
314 | DEL-0004 | TSK-00305 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.2.2 | 1.4.22.2 | Client Review & Revisions | Vendor Contracting | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.4.22.2.1 |  |  | 0 | 0
315 | DEL-0004 | TSK-00306 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.2.3 | 1.4.22.2 | Client Review & Revisions | Vendor Contracting | Client Review & Revisions | Project Manager | Mid | 2 |  |  | 1.4.22.2.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.3 | 1.4.22 | SOW/CO Draft & Negotiate | Vendor Contracting | SOW/CO Draft & Negotiate |  |  | 0 | 123 | 0 | 1.4.22.2.3 |  |  | 0 | 0
317 | DEL-0004 | TSK-00308 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.3.1 | 1.4.22.3 | SOW/CO Draft & Negotiate | Vendor Contracting | SOW/CO Draft & Negotiate | Account Manager | Mid | 4 |  |  | 1.4.22.3 |  |  | 0 | 0
318 | DEL-0004 | TSK-00309 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.3.2 | 1.4.22.3 | SOW/CO Draft & Negotiate | Vendor Contracting | SOW/CO Draft & Negotiate | Designer | Mid | 3 |  |  | 1.4.22.3.1 |  |  | 0 | 0
322 | DEL-0004 | TSK-00313 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.3.3 | 1.4.22.3 | SOW/CO Draft & Negotiate | Vendor Contracting | SOW/CO Draft & Negotiate | Producer | Mid | 2 |  |  | 1.4.22.3.2 |  |  | 0 | 0
316 | DEL-0004 | TSK-00307 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.22.3.4 | 1.4.22.3 | SOW/CO Draft & Negotiate | Vendor Contracting | SOW/CO Draft & Negotiate | Project Manager | Mid | 2 |  |  | 1.4.22.3.3 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23 | 1.4 | Vendor Deal Memos | Vendor Deal Memos |  |  |  | 15 | 116 | 5 | 1.4.22 |  |  | 195 | 2925
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23.1 | 1.4.23 | Internal Review & Critique | Vendor Deal Memos | Internal Review & Critique |  |  | 0 | 116 | 2 | 1.4.23 |  |  | 0 | 0
329 | DEL-0004 | TSK-00320 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23.1.1 | 1.4.23.1 | Internal Review & Critique | Vendor Deal Memos | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.23.1 |  |  | 0 | 0
330 | DEL-0004 | TSK-00321 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23.1.2 | 1.4.23.1 | Internal Review & Critique | Vendor Deal Memos | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.23.1.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23.2 | 1.4.23 | Client Review & Revisions | Vendor Deal Memos | Client Review & Revisions |  |  | 0 | 118 | 3 | 1.4.23.1.2 |  |  | 0 | 0
323 | DEL-0004 | TSK-00314 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23.2.1 | 1.4.23.2 | Client Review & Revisions | Vendor Deal Memos | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.23.2 |  |  | 0 | 0
324 | DEL-0004 | TSK-00315 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23.2.2 | 1.4.23.2 | Client Review & Revisions | Vendor Deal Memos | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.4.23.2.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23.3 | 1.4.23 | Distribution & Confirmation | Vendor Deal Memos | Distribution & Confirmation |  |  | 0 | 123 | 0 | 1.4.23.2.2 |  |  | 0 | 0
328 | DEL-0004 | TSK-00319 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23.3.1 | 1.4.23.3 | Distribution & Confirmation | Vendor Deal Memos | Distribution & Confirmation | Designer | Mid | 3 |  |  | 1.4.23.3 |  |  | 0 | 0
325 | DEL-0004 | TSK-00316 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23.3.2 | 1.4.23.3 | Distribution & Confirmation | Vendor Deal Memos | Distribution & Confirmation | Producer | Mid | 4 |  |  | 1.4.23.3.1 |  |  | 0 | 0
327 | DEL-0004 | TSK-00318 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.23.3.3 | 1.4.23.3 | Distribution & Confirmation | Vendor Deal Memos | Distribution & Confirmation | Project Manager | Mid | 2 |  |  | 1.4.23.3.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24 | 1.4 | Vendor Pre-Production Meetings | Vendor Pre-Production Meetings |  |  |  | 20 | 116 | 7 | 1.4.23 |  |  | 195 | 3900
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.1 | 1.4.24 | Internal Review & Critique | Vendor Pre-Production Meetings | Internal Review & Critique |  |  | 0 | 116 | 2 | 1.4.24 |  |  | 0 | 0
349 | DEL-0004 | TSK-00340 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.1.1 | 1.4.24.1 | Internal Review & Critique | Vendor Pre-Production Meetings | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.4.24.1 |  |  | 0 | 0
350 | DEL-0004 | TSK-00341 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.1.2 | 1.4.24.1 | Internal Review & Critique | Vendor Pre-Production Meetings | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.4.24.1.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.2 | 1.4.24 | Client Review & Revisions | Vendor Pre-Production Meetings | Client Review & Revisions |  |  | 0 | 118 | 3 | 1.4.24.1.2 |  |  | 0 | 0
346 | DEL-0004 | TSK-00337 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.2.1 | 1.4.24.2 | Client Review & Revisions | Vendor Pre-Production Meetings | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.4.24.2 |  |  | 0 | 0
347 | DEL-0004 | TSK-00338 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.2.2 | 1.4.24.2 | Client Review & Revisions | Vendor Pre-Production Meetings | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.4.24.2.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.3 | 1.4.24 | Run Meeting & Notes | Vendor Pre-Production Meetings | Run Meeting & Notes |  |  | 0 | 121 | 2 | 1.4.24.2.2 |  |  | 0 | 0
351 | DEL-0004 | TSK-00342 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.3.1 | 1.4.24.3 | Run Meeting & Notes | Vendor Pre-Production Meetings | Run Meeting & Notes | Creative Director | Lead/Director | 3 |  |  | 1.4.24.3 |  |  | 0 | 0
352 | DEL-0004 | TSK-00343 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.3.2 | 1.4.24.3 | Run Meeting & Notes | Vendor Pre-Production Meetings | Run Meeting & Notes | Producer | Mid | 1 |  |  | 1.4.24.3.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.4 | 1.4.24 | Agenda & Materials | Vendor Pre-Production Meetings | Agenda & Materials |  |  | 0 | 123 | 0 | 1.4.24.3.2 |  |  | 0 | 0
344 | DEL-0004 | TSK-00335 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.4.1 | 1.4.24.4 | Agenda & Materials | Vendor Pre-Production Meetings | Agenda & Materials | Designer | Mid | 6 |  |  | 1.4.24.4 |  |  | 0 | 0
345 | DEL-0004 | TSK-00336 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.4.2 | 1.4.24.4 | Agenda & Materials | Vendor Pre-Production Meetings | Agenda & Materials | Producer | Mid | 2 |  |  | 1.4.24.4.1 |  |  | 0 | 0
353 | DEL-0004 | TSK-00344 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.24.4.3 | 1.4.24.4 | Agenda & Materials | Vendor Pre-Production Meetings | Agenda & Materials | Project Manager | Mid | 2 |  |  | 1.4.24.4.2 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.25 | 1.4 | Pre-Interview Talent Calls | Pre-Interview Talent Calls |  |  |  | 6 | 123 | 0 | 1.4.24 |  |  | 195 | 1170
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.25.1 | 1.4.25 | Notes & Shareout | Pre-Interview Talent Calls | Notes & Shareout |  |  | 0 | 123 | 0 | 1.4.25 |  |  | 0 | 0
209 | DEL-0004 | TSK-00209 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.25.1.1 | 1.4.25.1 | Notes & Shareout | Pre-Interview Talent Calls | Notes & Shareout | Producer | Mid | 4 |  |  | 1.4.25.1 |  |  | 0 | 0
210 | DEL-0004 | TSK-00210 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.25.1.2 | 1.4.25.1 | Notes & Shareout | Pre-Interview Talent Calls | Notes & Shareout | Project Manager | Mid | 2 |  |  | 1.4.25.1.1 |  |  | 0 | 0
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.26 | 1.4 | Wrap & File Organization | Wrap & File Organization |  |  |  | 2 | 123 | 0 | 1.4.25 |  |  | 195 | 390
| DEL-0004 |  | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.26.1 | 1.4.26 | Pre-Production Support | Wrap & File Organization | Pre-Production Support |  |  | 0 | 123 | 0 | 1.4.26 |  |  | 0 | 0
363 | DEL-0004 | TSK-00354 | Content | Pre-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.26.1.1 | 1.4.26.1 | Pre-Production Support | Wrap & File Organization | Pre-Production Support | Producer | Mid | 2 |  |  | 1.4.26.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5 | 1 | Post-Production |  |  |  |  | 288 | 123 | 51 | 1.4 |  | Advanced/T1_LargeVolume | 195 | 56160
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.1 | 1.5 | Content Licensing / Art Buying | Content Licensing / Art Buying |  |  |  | 3 | 123 | 4 | 1.5 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.1.1 | 1.5.1 | Rights/License Research | Content Licensing / Art Buying | Rights/License Research |  |  | 0 | 123 | 4 | 1.5.1 |  |  | 0 | 0
65 | DEL-0003 | TSK-00065 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.1.1.1 | 1.5.1.1 | Rights/License Research | Content Licensing / Art Buying | Rights/License Research | Producer | Mid | 1 |  |  | 1.5.1.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.1.2 | 1.5.1 | Usage Notes | Content Licensing / Art Buying | Usage Notes |  |  | 0 | 174 | 0 | 1.5.1.1.1 |  |  | 0 | 0
66 | DEL-0003 | TSK-00066 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.1.2.1 | 1.5.1.2 | Usage Notes | Content Licensing / Art Buying | Usage Notes | Account Manager | Mid | 2 |  |  | 1.5.1.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2 | 1.5 | VO Recording Sessions | VO Recording Sessions |  |  |  | 7 | 127 | 5 | 1.5.1 |  |  | 195 | 1365
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.1 | 1.5.2 | Script Polish | VO Recording Sessions | Script Polish |  |  | 0 | 127 | 5 | 1.5.2 |  |  | 0 | 0
124 | DEL-0003 | TSK-00124 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.1.1 | 1.5.2.1 | Script Polish | VO Recording Sessions | Script Polish | Copywriter | Mid | 2 |  |  | 1.5.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.2 | 1.5.2 | VO Session | VO Recording Sessions | VO Session |  |  | 0 | 174 | 0 | 1.5.2.1.1 |  |  | 0 | 0
125 | DEL-0003 | TSK-00125 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.2.1 | 1.5.2.2 | VO Session | VO Recording Sessions | VO Session | Producer | Mid | 2 |  |  | 1.5.2.2 |  |  | 0 | 0
126 | DEL-0003 | TSK-00126 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2.2.2 | 1.5.2.2 | VO Session | VO Recording Sessions | VO Session | Sound Designer | Mid | 3 |  |  | 1.5.2.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3 | 1.5 | Editing | Editing |  |  |  | 26 | 132 | 6 | 1.5.2 |  |  | 195 | 5070
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.1 | 1.5.3 | Client Review & Revisions | Editing | Client Review & Revisions |  |  | 0 | 132 | 6 | 1.5.3 |  |  | 0 | 0
74 | DEL-0003 | TSK-00074 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.1.1 | 1.5.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Account Manager | Mid | 3 |  |  | 1.5.3.1 |  |  | 0 | 0
77 | DEL-0003 | TSK-00077 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.1.2 | 1.5.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Creative Director | Lead/Director | 3 |  |  | 1.5.3.1.1 |  |  | 0 | 0
76 | DEL-0003 | TSK-00076 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.1.3 | 1.5.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.5.3.1.2 |  |  | 0 | 0
79 | DEL-0003 | TSK-00079 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.1.4 | 1.5.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Editor | Mid | 13 |  |  | 1.5.3.1.3 |  |  | 0 | 0
75 | DEL-0003 | TSK-00075 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3.1.5 | 1.5.3.1 | Client Review & Revisions | Editing | Client Review & Revisions | Producer | Mid | 5 |  |  | 1.5.3.1.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4 | 1.5 | Video Editing | Video Editing |  |  |  | 39 | 132 | 6 | 1.5.3 |  |  | 195 | 7605
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.1 | 1.5.4 | Client Review & Revisions | Video Editing | Client Review & Revisions |  |  | 0 | 132 | 6 | 1.5.4 |  |  | 0 | 0
127 | DEL-0003 | TSK-00127 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.1.1 | 1.5.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Account Manager | Mid | 3 |  |  | 1.5.4.1 |  |  | 0 | 0
131 | DEL-0003 | TSK-00131 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.1.2 | 1.5.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Creative Director | Lead/Director | 3 |  |  | 1.5.4.1.1 |  |  | 0 | 0
129 | DEL-0003 | TSK-00129 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.1.3 | 1.5.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Designer | Mid | 2 |  |  | 1.5.4.1.2 |  |  | 0 | 0
130 | DEL-0003 | TSK-00130 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.1.4 | 1.5.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Editor | Mid | 26 |  |  | 1.5.4.1.3 |  |  | 0 | 0
128 | DEL-0003 | TSK-00128 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4.1.5 | 1.5.4.1 | Client Review & Revisions | Video Editing | Client Review & Revisions | Producer | Mid | 5 |  |  | 1.5.4.1.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5 | 1.5 | Voice Over | Voice Over |  |  |  | 26 | 132 | 14 | 1.5.4 |  |  | 195 | 5070
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.1 | 1.5.5 | VO Edit | Voice Over | VO Edit |  |  | 0 | 132 | 6 | 1.5.5 |  |  | 0 | 0
140 | DEL-0003 | TSK-00140 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.1.1 | 1.5.5.1 | VO Edit | Voice Over | VO Edit | Editor | Mid | 13 |  |  | 1.5.5.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.2 | 1.5.5 | Mix | Voice Over | Mix |  |  | 0 | 154 | 3 | 1.5.5.1.1 |  |  | 0 | 0
139 | DEL-0003 | TSK-00139 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.2.1 | 1.5.5.2 | Mix | Voice Over | Mix | Sound Designer | Mid | 3 |  |  | 1.5.5.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.3 | 1.5.5 | Internal Review & Critique | Voice Over | Internal Review & Critique |  |  | 0 | 164 | 2 | 1.5.5.2.1 |  |  | 0 | 0
137 | DEL-0003 | TSK-00137 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.3.1 | 1.5.5.3 | Internal Review & Critique | Voice Over | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.5.5.3 |  |  | 0 | 0
138 | DEL-0003 | TSK-00138 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.3.2 | 1.5.5.3 | Internal Review & Critique | Voice Over | Internal Review & Critique | Producer | Mid | 2 |  |  | 1.5.5.3.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.4 | 1.5.5 | Client Review & Revisions | Voice Over | Client Review & Revisions |  |  | 0 | 166 | 3 | 1.5.5.3.2 |  |  | 0 | 0
134 | DEL-0003 | TSK-00134 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.4.1 | 1.5.5.4 | Client Review & Revisions | Voice Over | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.5.4 |  |  | 0 | 0
135 | DEL-0003 | TSK-00135 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.4.2 | 1.5.5.4 | Client Review & Revisions | Voice Over | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.5.5.4.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.5 | 1.5.5 | Final Packaging | Voice Over | Final Packaging |  |  | 0 | 174 | 0 | 1.5.5.4.2 |  |  | 0 | 0
136 | DEL-0003 | TSK-00136 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5.5.1 | 1.5.5.5 | Final Packaging | Voice Over | Final Packaging | Designer | Mid | 3 |  |  | 1.5.5.5 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6 | 1.5 | Motion Design/VFX | Motion Design/VFX |  |  |  | 26 | 138 | 9 | 1.5.5 |  |  | 195 | 5070
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.1 | 1.5.6 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions |  |  | 0 | 138 | 9 | 1.5.6 |  |  | 0 | 0
90 | DEL-0003 | TSK-00090 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.1.1 | 1.5.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Account Manager | Mid | 3 |  |  | 1.5.6.1 |  |  | 0 | 0
94 | DEL-0003 | TSK-00094 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.1.2 | 1.5.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Creative Director | Lead/Director | 2 |  |  | 1.5.6.1.1 |  |  | 0 | 0
92 | DEL-0003 | TSK-00092 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.1.3 | 1.5.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Designer | Mid | 4 |  |  | 1.5.6.1.2 |  |  | 0 | 0
96 | DEL-0003 | TSK-00096 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.1.4 | 1.5.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Editor | Mid | 8 |  |  | 1.5.6.1.3 |  |  | 0 | 0
93 | DEL-0003 | TSK-00093 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.1.5 | 1.5.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Motion Designer | Mid | 4 |  |  | 1.5.6.1.4 |  |  | 0 | 0
91 | DEL-0003 | TSK-00091 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6.1.6 | 1.5.6.1 | Client Review & Revisions | Motion Design/VFX | Client Review & Revisions | Producer | Mid | 5 |  |  | 1.5.6.1.5 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7 | 1.5 | Color Correction | Color Correction |  |  |  | 17 | 147 | 3 | 1.5.6 |  |  | 195 | 3315
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.1 | 1.5.7 | Client Review & Revisions | Color Correction | Client Review & Revisions |  |  | 0 | 147 | 3 | 1.5.7 |  |  | 0 | 0
53 | DEL-0003 | TSK-00053 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.1.1 | 1.5.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.5.7.1 |  |  | 0 | 0
55 | DEL-0003 | TSK-00055 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.1.2 | 1.5.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Colorist | Mid | 8 |  |  | 1.5.7.1.1 |  |  | 0 | 0
57 | DEL-0003 | TSK-00057 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.1.3 | 1.5.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Creative Director | Lead/Director | 3 |  |  | 1.5.7.1.2 |  |  | 0 | 0
56 | DEL-0003 | TSK-00056 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.1.4 | 1.5.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.5.7.1.3 |  |  | 0 | 0
54 | DEL-0003 | TSK-00054 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7.1.5 | 1.5.7.1 | Client Review & Revisions | Color Correction | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.5.7.1.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8 | 1.5 | Color Grading | Color Grading |  |  |  | 17 | 147 | 3 | 1.5.7 |  |  | 195 | 3315
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.1 | 1.5.8 | Client Review & Revisions | Color Grading | Client Review & Revisions |  |  | 0 | 147 | 3 | 1.5.8 |  |  | 0 | 0
59 | DEL-0003 | TSK-00059 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.1.1 | 1.5.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.5.8.1 |  |  | 0 | 0
61 | DEL-0003 | TSK-00061 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.1.2 | 1.5.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Colorist | Mid | 8 |  |  | 1.5.8.1.1 |  |  | 0 | 0
63 | DEL-0003 | TSK-00063 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.1.3 | 1.5.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Creative Director | Lead/Director | 3 |  |  | 1.5.8.1.2 |  |  | 0 | 0
62 | DEL-0003 | TSK-00062 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.1.4 | 1.5.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.5.8.1.3 |  |  | 0 | 0
60 | DEL-0003 | TSK-00060 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.8.1.5 | 1.5.8.1 | Client Review & Revisions | Color Grading | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.5.8.1.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9 | 1.5 | Final Retouched Stills Review | Final Retouched Stills Review |  |  |  | 16 | 150 | 9 | 1.5.8 |  |  | 195 | 3120
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.1 | 1.5.9 | Retouch | Final Retouched Stills Review | Retouch |  |  | 0 | 150 | 4 | 1.5.9 |  |  | 0 | 0
89 | DEL-0003 | TSK-00089 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.1.1 | 1.5.9.1 | Retouch | Final Retouched Stills Review | Retouch | Retoucher | Mid | 7 |  |  | 1.5.9.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.2 | 1.5.9 | Internal Review & Critique | Final Retouched Stills Review | Internal Review & Critique |  |  | 0 | 164 | 2 | 1.5.9.1.1 |  |  | 0 | 0
87 | DEL-0003 | TSK-00087 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.2.1 | 1.5.9.2 | Internal Review & Critique | Final Retouched Stills Review | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.5.9.2 |  |  | 0 | 0
88 | DEL-0003 | TSK-00088 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.2.2 | 1.5.9.2 | Internal Review & Critique | Final Retouched Stills Review | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.5.9.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.3 | 1.5.9 | Client Review & Revisions | Final Retouched Stills Review | Client Review & Revisions |  |  | 0 | 166 | 3 | 1.5.9.2.2 |  |  | 0 | 0
84 | DEL-0003 | TSK-00084 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.3.1 | 1.5.9.3 | Client Review & Revisions | Final Retouched Stills Review | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.9.3 |  |  | 0 | 0
85 | DEL-0003 | TSK-00085 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.3.2 | 1.5.9.3 | Client Review & Revisions | Final Retouched Stills Review | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.5.9.3.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.4 | 1.5.9 | Final Packaging | Final Retouched Stills Review | Final Packaging |  |  | 0 | 174 | 0 | 1.5.9.3.2 |  |  | 0 | 0
86 | DEL-0003 | TSK-00086 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.9.4.1 | 1.5.9.4 | Final Packaging | Final Retouched Stills Review | Final Packaging | Designer | Mid | 3 |  |  | 1.5.9.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10 | 1.5 | Retouching | Retouching |  |  |  | 16 | 150 | 9 | 1.5.9 |  |  | 195 | 3120
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.1 | 1.5.10 | Retouch | Retouching | Retouch |  |  | 0 | 150 | 4 | 1.5.10 |  |  | 0 | 0
102 | DEL-0003 | TSK-00102 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.1.1 | 1.5.10.1 | Retouch | Retouching | Retouch | Retoucher | Mid | 7 |  |  | 1.5.10.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.2 | 1.5.10 | Internal Review & Critique | Retouching | Internal Review & Critique |  |  | 0 | 164 | 2 | 1.5.10.1.1 |  |  | 0 | 0
100 | DEL-0003 | TSK-00100 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.2.1 | 1.5.10.2 | Internal Review & Critique | Retouching | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.5.10.2 |  |  | 0 | 0
101 | DEL-0003 | TSK-00101 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.2.2 | 1.5.10.2 | Internal Review & Critique | Retouching | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.5.10.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.3 | 1.5.10 | Client Review & Revisions | Retouching | Client Review & Revisions |  |  | 0 | 166 | 3 | 1.5.10.2.2 |  |  | 0 | 0
97 | DEL-0003 | TSK-00097 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.3.1 | 1.5.10.3 | Client Review & Revisions | Retouching | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.10.3 |  |  | 0 | 0
98 | DEL-0003 | TSK-00098 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.3.2 | 1.5.10.3 | Client Review & Revisions | Retouching | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.5.10.3.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.4 | 1.5.10 | Final Packaging | Retouching | Final Packaging |  |  | 0 | 174 | 0 | 1.5.10.3.2 |  |  | 0 | 0
99 | DEL-0003 | TSK-00099 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.10.4.1 | 1.5.10.4 | Final Packaging | Retouching | Final Packaging | Designer | Mid | 3 |  |  | 1.5.10.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.11 | 1.5 | Sound Mix | Sound Mix |  |  |  | 13 | 154 | 3 | 1.5.10 |  |  | 195 | 2535
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.11.1 | 1.5.11 | Client Review & Revisions | Sound Mix | Client Review & Revisions |  |  | 0 | 154 | 3 | 1.5.11 |  |  | 0 | 0
107 | DEL-0003 | TSK-00107 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.11.1.1 | 1.5.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.5.11.1 |  |  | 0 | 0
110 | DEL-0003 | TSK-00110 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.11.1.2 | 1.5.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Creative Director | Lead/Director | 3 |  |  | 1.5.11.1.1 |  |  | 0 | 0
109 | DEL-0003 | TSK-00109 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.11.1.3 | 1.5.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Designer | Mid | 3 |  |  | 1.5.11.1.2 |  |  | 0 | 0
108 | DEL-0003 | TSK-00108 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.11.1.4 | 1.5.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Producer | Mid | 3 |  |  | 1.5.11.1.3 |  |  | 0 | 0
112 | DEL-0003 | TSK-00112 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.11.1.5 | 1.5.11.1 | Client Review & Revisions | Sound Mix | Client Review & Revisions | Sound Designer | Mid | 3 |  |  | 1.5.11.1.4 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.12 | 1.5 | Sound Sourcing | Sound Sourcing |  |  |  | 4 | 154 | 3 | 1.5.11 |  |  | 195 | 780
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.12.1 | 1.5.12 | Music Search & License | Sound Sourcing | Music Search & License |  |  | 0 | 154 | 3 | 1.5.12 |  |  | 0 | 0
113 | DEL-0003 | TSK-00113 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.12.1.1 | 1.5.12.1 | Music Search & License | Sound Sourcing | Music Search & License | Producer | Mid | 1 |  |  | 1.5.12.1 |  |  | 0 | 0
114 | DEL-0003 | TSK-00114 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.12.1.2 | 1.5.12.1 | Music Search & License | Sound Sourcing | Music Search & License | Sound Designer | Mid | 3 |  |  | 1.5.12.1.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.13 | 1.5 | Final File Delivery | Final File Delivery |  |  |  | 10 | 157 | 3 | 1.5.12 |  |  | 195 | 1950
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.13.1 | 1.5.13 | QA (Tech & Content) | Final File Delivery | QA (Tech & Content) |  |  | 0 | 157 | 3 | 1.5.13 |  |  | 0 | 0
83 | DEL-0003 | TSK-00083 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.13.1.1 | 1.5.13.1 | QA (Tech & Content) | Final File Delivery | QA (Tech & Content) | QA Specialist | Mid | 4 |  |  | 1.5.13.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.13.2 | 1.5.13 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload |  |  | 0 | 174 | 0 | 1.5.13.1.1 |  |  | 0 | 0
80 | DEL-0003 | TSK-00080 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.13.2.1 | 1.5.13.2 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload | Media Manager / DIT | Mid | 2 |  |  | 1.5.13.2 |  |  | 0 | 0
81 | DEL-0003 | TSK-00081 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.13.2.2 | 1.5.13.2 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload | Producer | Mid | 2 |  |  | 1.5.13.2.1 |  |  | 0 | 0
82 | DEL-0003 | TSK-00082 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.13.2.3 | 1.5.13.2 | Final Checklist & Upload | Final File Delivery | Final Checklist & Upload | Project Manager | Mid | 2 |  |  | 1.5.13.2.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14 | 1.5 | True-ups (for vendor costs) | True-ups (for vendor costs) |  |  |  | 15 | 160 | 9 | 1.5.13 |  |  | 195 | 2925
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.1 | 1.5.14 | Change Orders & Tracking | True-ups (for vendor costs) | Change Orders & Tracking |  |  | 0 | 160 | 4 | 1.5.14 |  |  | 0 | 0
116 | DEL-0003 | TSK-00116 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.1.1 | 1.5.14.1 | Change Orders & Tracking | True-ups (for vendor costs) | Change Orders & Tracking | Project Manager | Mid | 1 |  |  | 1.5.14.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.2 | 1.5.14 | Internal Review & Critique | True-ups (for vendor costs) | Internal Review & Critique |  |  | 0 | 164 | 2 | 1.5.14.1.1 |  |  | 0 | 0
120 | DEL-0003 | TSK-00120 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.2.1 | 1.5.14.2 | Internal Review & Critique | True-ups (for vendor costs) | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.5.14.2 |  |  | 0 | 0
121 | DEL-0003 | TSK-00121 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.2.2 | 1.5.14.2 | Internal Review & Critique | True-ups (for vendor costs) | Internal Review & Critique | Producer | Mid | 2 |  |  | 1.5.14.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.3 | 1.5.14 | Client Review & Revisions | True-ups (for vendor costs) | Client Review & Revisions |  |  | 0 | 166 | 3 | 1.5.14.2.2 |  |  | 0 | 0
117 | DEL-0003 | TSK-00117 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.3.1 | 1.5.14.3 | Client Review & Revisions | True-ups (for vendor costs) | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.14.3 |  |  | 0 | 0
118 | DEL-0003 | TSK-00118 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.3.2 | 1.5.14.3 | Client Review & Revisions | True-ups (for vendor costs) | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.5.14.3.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.4 | 1.5.14 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation |  |  | 0 | 174 | 0 | 1.5.14.3.2 |  |  | 0 | 0
122 | DEL-0003 | TSK-00122 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.4.1 | 1.5.14.4 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation | Account Manager | Mid | 2 |  |  | 1.5.14.4 |  |  | 0 | 0
119 | DEL-0003 | TSK-00119 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.4.2 | 1.5.14.4 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation | Designer | Mid | 3 |  |  | 1.5.14.4.1 |  |  | 0 | 0
123 | DEL-0003 | TSK-00123 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.14.4.3 | 1.5.14.4 | Invoice Reconciliation | True-ups (for vendor costs) | Invoice Reconciliation | Producer | Mid | 2 |  |  | 1.5.14.4.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.15 | 1.5 | Cutdowns | Cutdowns |  |  |  | 17 | 164 | 5 | 1.5.14 |  |  | 195 | 3315
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.15.1 | 1.5.15 | Internal Review & Critique | Cutdowns | Internal Review & Critique |  |  | 0 | 164 | 2 | 1.5.15 |  |  | 0 | 0
71 | DEL-0003 | TSK-00071 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.15.1.1 | 1.5.15.1 | Internal Review & Critique | Cutdowns | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.5.15.1 |  |  | 0 | 0
72 | DEL-0003 | TSK-00072 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.15.1.2 | 1.5.15.1 | Internal Review & Critique | Cutdowns | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.5.15.1.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.15.2 | 1.5.15 | Client Review & Revisions | Cutdowns | Client Review & Revisions |  |  | 0 | 166 | 3 | 1.5.15.1.2 |  |  | 0 | 0
67 | DEL-0003 | TSK-00067 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.15.2.1 | 1.5.15.2 | Client Review & Revisions | Cutdowns | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.5.15.2 |  |  | 0 | 0
68 | DEL-0003 | TSK-00068 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.15.2.2 | 1.5.15.2 | Client Review & Revisions | Cutdowns | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.5.15.2.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.15.3 | 1.5.15 | Cutdowns (2-3) | Cutdowns | Cutdowns (2-3) |  |  | 0 | 174 | 0 | 1.5.15.2.2 |  |  | 0 | 0
70 | DEL-0003 | TSK-00070 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.15.3.1 | 1.5.15.3 | Cutdowns (2-3) | Cutdowns | Cutdowns (2-3) | Designer | Mid | 3 |  |  | 1.5.15.3 |  |  | 0 | 0
69 | DEL-0003 | TSK-00069 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.15.3.2 | 1.5.15.3 | Cutdowns (2-3) | Cutdowns | Cutdowns (2-3) | Editor | Mid | 8 |  |  | 1.5.15.3.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.16 | 1.5 | Client Review | Client Review |  |  |  | 6 | 166 | 3 | 1.5.15 |  |  | 195 | 1170
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.16.1 | 1.5.16 | Client Review Coordination | Client Review | Client Review Coordination |  |  | 0 | 166 | 3 | 1.5.16 |  |  | 0 | 0
50 | DEL-0003 | TSK-00050 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.16.1.1 | 1.5.16.1 | Client Review Coordination | Client Review | Client Review Coordination | Account Manager | Mid | 2 |  |  | 1.5.16.1 |  |  | 0 | 0
51 | DEL-0003 | TSK-00051 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.16.1.2 | 1.5.16.1 | Client Review Coordination | Client Review | Client Review Coordination | Producer | Mid | 2 |  |  | 1.5.16.1.1 |  |  | 0 | 0
52 | DEL-0003 | TSK-00052 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.16.1.3 | 1.5.16.1 | Client Review Coordination | Client Review | Client Review Coordination | Project Manager | Mid | 2 |  |  | 1.5.16.1.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.17 | 1.5 | Review & Sign-Off | Review & Sign-Off |  |  |  | 5 | 166 | 5 | 1.5.16 |  |  | 195 | 975
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.17.1 | 1.5.17 | Client Review Coordination | Review & Sign-Off | Client Review Coordination |  |  | 0 | 166 | 3 | 1.5.17 |  |  | 0 | 0
103 | DEL-0003 | TSK-00103 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.17.1.1 | 1.5.17.1 | Client Review Coordination | Review & Sign-Off | Client Review Coordination | Account Manager | Mid | 2 |  |  | 1.5.17.1 |  |  | 0 | 0
104 | DEL-0003 | TSK-00104 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.17.1.2 | 1.5.17.1 | Client Review Coordination | Review & Sign-Off | Client Review Coordination | Producer | Mid | 2 |  |  | 1.5.17.1.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.17.2 | 1.5.17 | Notes Triage | Review & Sign-Off | Notes Triage |  |  | 0 | 172 | 2 | 1.5.17.1.2 |  |  | 0 | 0
105 | DEL-0003 | TSK-00105 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.17.2.1 | 1.5.17.2 | Notes Triage | Review & Sign-Off | Notes Triage | Project Manager | Mid | 1 |  |  | 1.5.17.2 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.18 | 1.5 | Asset Library | Asset Library |  |  |  | 3 | 169 | 3 | 1.5.17 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.18.1 | 1.5.18 | Post Support | Asset Library | Post Support |  |  | 0 | 169 | 3 | 1.5.18 |  |  | 0 | 0
48 | DEL-0003 | TSK-00048 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.18.1.1 | 1.5.18.1 | Post Support | Asset Library | Post Support | Editor | Mid | 3 |  |  | 1.5.18.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.19 | 1.5 | Capture Library | Capture Library |  |  |  | 3 | 169 | 3 | 1.5.18 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.19.1 | 1.5.19 | Post Support | Capture Library | Post Support |  |  | 0 | 169 | 3 | 1.5.19 |  |  | 0 | 0
49 | DEL-0003 | TSK-00049 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.19.1.1 | 1.5.19.1 | Post Support | Capture Library | Post Support | Editor | Mid | 3 |  |  | 1.5.19.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.20 | 1.5 | Selects Deck | Selects Deck |  |  |  | 3 | 169 | 3 | 1.5.19 |  |  | 195 | 585
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.20.1 | 1.5.20 | Post Support | Selects Deck | Post Support |  |  | 0 | 169 | 3 | 1.5.20 |  |  | 0 | 0
106 | DEL-0003 | TSK-00106 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.20.1.1 | 1.5.20.1 | Post Support | Selects Deck | Post Support | Editor | Mid | 3 |  |  | 1.5.20.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.21 | 1.5 | Delivery | Delivery |  |  |  | 8 | 174 | 0 | 1.5.20 |  |  | 195 | 1560
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.21.1 | 1.5.21 | Post Support | Delivery | Post Support |  |  | 0 | 174 | 0 | 1.5.21 |  |  | 0 | 0
73 | DEL-0003 | TSK-00073 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.21.1.1 | 1.5.21.1 | Post Support | Delivery | Post Support | Editor | Mid | 8 |  |  | 1.5.21.1 |  |  | 0 | 0
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.22 | 1.5 | Stills/Footage Selection | Stills/Footage Selection |  |  |  | 8 | 174 | 0 | 1.5.21 |  |  | 195 | 1560
| DEL-0003 |  | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.22.1 | 1.5.22 | Post Support | Stills/Footage Selection | Post Support |  |  | 0 | 174 | 0 | 1.5.22 |  |  | 0 | 0
115 | DEL-0003 | TSK-00115 | Content | Post-Production | Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.22.1.1 | 1.5.22.1 | Post Support | Stills/Footage Selection | Post Support | Editor | Mid | 8 |  |  | 1.5.22.1 |  |  | 0 | 0