## Scenario A
Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Deliverable | Component | Task | Service_Department | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes | Rate_USD | Price_USD
Workbook Test | 1 |  | Workbook Test |  | Project |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0
Workbook Test | 1.1 | 1 | Brand Identity Development | Brand Identity Development | [5 empty] | 255 | 0 | 1 |  |  | Core/T2_MediumVolume | 195 | 49725
Workbook Test | 1.1.1 | 1.1 | Graphic & Copy Messaging Cornerstones | Brand Identity Development | Graphic & Copy Messaging Cornerstones |  |  |  |  | 24 | 0 | 1 | 1.1 |  |  | 195 | 4680
Workbook Test | 1.1.1.1 | 1.1.1 | Messaging Cornerstones Draft | Brand Identity Development | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft |  | Designer | Mid | 24 | 0 | 1 | 1.1.1 |  |  | 195 | 4680
Workbook Test | 1.1.2 | 1.1 | Graphic Mock-Ups | Brand Identity Development | Graphic Mock-Ups |  |  |  |  | 22 | 0 | 1 | 1.1.1 |  |  | 195 | 4290
Workbook Test | 1.1.2.1 | 1.1.2 | Mockup Scenarios (3-4) | Brand Identity Development | Graphic Mock-Ups | Mockup Scenarios (3-4) |  | Designer | Mid | 22 | 0 | 1 | 1.1.2 |  |  | 195 | 4290
Workbook Test | 1.1.3 | 1.1 | Iconography | Brand Identity Development | Iconography |  |  |  |  | 30 | 0 | 1 | 1.1.2 |  |  | 195 | 5850
Workbook Test | 1.1.3.1 | 1.1.3 | Export & Spec | Brand Identity Development | Iconography | Export & Spec |  | Designer | Mid | 30 | 0 | 1 | 1.1.3 |  |  | 195 | 5850
Workbook Test | 1.1.4 | 1.1 | Logo | Brand Identity Development | Logo |  |  |  |  | 41 | 0 | 1 | 1.1.3 |  |  | 195 | 7995
Workbook Test | 1.1.4.1 | 1.1.4 | Logo Exploration (6-8 dirs) | Brand Identity Development | Logo | Logo Exploration (6-8 dirs) |  | Designer | Mid | 41 | 0 | 1 | 1.1.4 |  |  | 195 | 7995
Workbook Test | 1.1.5 | 1.1 | Overarching Moodboard | Brand Identity Development | Overarching Moodboard |  |  |  |  | 24 | 0 | 1 | 1.1.4 |  |  | 195 | 4680
Workbook Test | 1.1.5.1 | 1.1.5 | Curate Moodboard | Brand Identity Development | Overarching Moodboard | Curate Moodboard |  | Designer | Mid | 24 | 0 | 1 | 1.1.5 |  |  | 195 | 4680
Workbook Test | 1.1.6 | 1.1 | Tagline Copy Bank | Brand Identity Development | Tagline Copy Bank |  |  |  |  | 18 | 0 | 1 | 1.1.5 |  |  | 195 | 3510
Workbook Test | 1.1.6.1 | 1.1.6 | Shortlist & Rationale | Brand Identity Development | Tagline Copy Bank | Shortlist & Rationale |  | Designer | Mid | 18 | 0 | 1 | 1.1.6 |  |  | 195 | 3510
Workbook Test | 1.1.7 | 1.1 | Textures/Patterns/Materials | Brand Identity Development | Textures/Patterns/Materials |  |  |  |  | 28 | 0 | 1 | 1.1.6 |  |  | 195 | 5460
Workbook Test | 1.1.7.1 | 1.1.7 | Build Repeating Tiles | Brand Identity Development | Textures/Patterns/Materials | Build Repeating Tiles |  | Designer | Mid | 28 | 0 | 1 | 1.1.7 |  |  | 195 | 5460
Workbook Test | 1.1.8 | 1.1 | Typography | Brand Identity Development | Typography |  |  |  |  | 37 | 0 | 1 | 1.1.7 |  |  | 195 | 7215
Workbook Test | 1.1.8.1 | 1.1.8 | Final Packaging | Brand Identity Development | Typography | Final Packaging |  | Designer | Mid | 37 | 0 | 1 | 1.1.8 |  |  | 195 | 7215
Workbook Test | 1.1.9 | 1.1 | Visual Elements/Comps | Brand Identity Development | Visual Elements/Comps |  |  |  |  | 31 | 0 | 1 | 1.1.8 |  |  | 195 | 6045
Workbook Test | 1.1.9.1 | 1.1.9 | Compositions (2-3) | Brand Identity Development | Visual Elements/Comps | Compositions (2-3) |  | Designer | Mid | 31 | 0 | 1 | 1.1.9 |  |  | 195 | 6045

## Scenario B
Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Deliverable | Component | Task | Service_Department | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes | Rate_USD | Price_USD
Workbook Test | 1 |  | Workbook Test |  | Project |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0
Workbook Test | 1.1 | 1 | Brand Identity Development | Brand Identity Development | [5 empty] | 391 | 0 | 1 |  |  | Advanced/T1_LargeVolume | 195 | 76245
Workbook Test | 1.1.1 | 1.1 | Graphic & Copy Messaging Cornerstones | Brand Identity Development | Graphic & Copy Messaging Cornerstones |  |  |  |  | 37 | 0 | 1 | 1.1 |  |  | 195 | 7215
Workbook Test | 1.1.1.1 | 1.1.1 | Messaging Cornerstones Draft | Brand Identity Development | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft |  | Designer | Mid | 37 | 0 | 1 | 1.1.1 |  |  | 195 | 7215
Workbook Test | 1.1.2 | 1.1 | Graphic Mock-Ups | Brand Identity Development | Graphic Mock-Ups |  |  |  |  | 34 | 0 | 1 | 1.1.1 |  |  | 195 | 6630
Workbook Test | 1.1.2.1 | 1.1.2 | Mockup Scenarios (3-4) | Brand Identity Development | Graphic Mock-Ups | Mockup Scenarios (3-4) |  | Designer | Mid | 34 | 0 | 1 | 1.1.2 |  |  | 195 | 6630
Workbook Test | 1.1.3 | 1.1 | Iconography | Brand Identity Development | Iconography |  |  |  |  | 46 | 0 | 1 | 1.1.2 |  |  | 195 | 8970
Workbook Test | 1.1.3.1 | 1.1.3 | Export & Spec | Brand Identity Development | Iconography | Export & Spec |  | Designer | Mid | 46 | 0 | 1 | 1.1.3 |  |  | 195 | 8970
Workbook Test | 1.1.4 | 1.1 | Logo | Brand Identity Development | Logo |  |  |  |  | 62 | 0 | 1 | 1.1.3 |  |  | 195 | 12090
Workbook Test | 1.1.4.1 | 1.1.4 | Logo Exploration (6-8 dirs) | Brand Identity Development | Logo | Logo Exploration (6-8 dirs) |  | Designer | Mid | 62 | 0 | 1 | 1.1.4 |  |  | 195 | 12090
Workbook Test | 1.1.5 | 1.1 | Overarching Moodboard | Brand Identity Development | Overarching Moodboard |  |  |  |  | 37 | 0 | 1 | 1.1.4 |  |  | 195 | 7215
Workbook Test | 1.1.5.1 | 1.1.5 | Curate Moodboard | Brand Identity Development | Overarching Moodboard | Curate Moodboard |  | Designer | Mid | 37 | 0 | 1 | 1.1.5 |  |  | 195 | 7215
Workbook Test | 1.1.6 | 1.1 | Tagline Copy Bank | Brand Identity Development | Tagline Copy Bank |  |  |  |  | 27 | 0 | 1 | 1.1.5 |  |  | 195 | 5265
Workbook Test | 1.1.6.1 | 1.1.6 | Shortlist & Rationale | Brand Identity Development | Tagline Copy Bank | Shortlist & Rationale |  | Designer | Mid | 27 | 0 | 1 | 1.1.6 |  |  | 195 | 5265
Workbook Test | 1.1.7 | 1.1 | Textures/Patterns/Materials | Brand Identity Development | Textures/Patterns/Materials |  |  |  |  | 43 | 0 | 1 | 1.1.6 |  |  | 195 | 8385
Workbook Test | 1.1.7.1 | 1.1.7 | Build Repeating Tiles | Brand Identity Development | Textures/Patterns/Materials | Build Repeating Tiles |  | Designer | Mid | 43 | 0 | 1 | 1.1.7 |  |  | 195 | 8385
Workbook Test | 1.1.8 | 1.1 | Typography | Brand Identity Development | Typography |  |  |  |  | 57 | 0 | 1 | 1.1.7 |  |  | 195 | 11115
Workbook Test | 1.1.8.1 | 1.1.8 | Final Packaging | Brand Identity Development | Typography | Final Packaging |  | Designer | Mid | 57 | 0 | 1 | 1.1.8 |  |  | 195 | 11115
Workbook Test | 1.1.9 | 1.1 | Visual Elements/Comps | Brand Identity Development | Visual Elements/Comps |  |  |  |  | 48 | 0 | 1 | 1.1.8 |  |  | 195 | 9360
Workbook Test | 1.1.9.1 | 1.1.9 | Compositions (2-3) | Brand Identity Development | Visual Elements/Comps | Compositions (2-3) |  | Designer | Mid | 48 | 0 | 1 | 1.1.9 |  |  | 195 | 9360