## Sheet1
Row_ID | Deliverable_Code | Task_Code | Service_Department | Deliverable | Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes | Rate_USD | Price_USD
[5 empty] | Casa-Dragones-Digital-MKT-RFP | 1 |  | Project Summary |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0
|  |  | Content |  | Casa-Dragones-Digital-MKT-RFP | 1.1 | 1 | Content |  |  |  |  | 0 | 0 |  |  |  | Content Department | 0 | 0
| DEL-0001 |  | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1 | 1.1 | Content Plan |  |  |  |  | 80 | 0 | 17 |  |  | Advanced/T2_MediumVolume | 185 | 14800
| DEL-0001 |  | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1 | 1.1.1 | Content Pillars | Content Pillars |  |  |  | 25 | 0 | 10 | 1.1.1 |  |  | 185 | 4625
| DEL-0001 |  | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.1 | 1.1.1.1 | Examples per Pillar | Content Pillars | Examples per Pillar |  |  | 0 | 0 | 5 | 1.1.1.1 |  |  | 0 | 0
4 | DEL-0001 | TSK-00004 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.1.1 | 1.1.1.1.1 | Examples per Pillar | Content Pillars | Examples per Pillar | Copywriter | Mid | 5 |  |  | 1.1.1.1.1 |  |  | 185 | 925
9 | DEL-0001 | TSK-00009 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.1.2 | 1.1.1.1.1 | Examples per Pillar | Content Pillars | Examples per Pillar | Creative Director | Lead/Director | 2 |  |  | 1.1.1.1.1.1 |  |  | 185 | 370
5 | DEL-0001 | TSK-00005 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.1.3 | 1.1.1.1.1 | Examples per Pillar | Content Pillars | Examples per Pillar | Designer | Mid | 7 |  |  | 1.1.1.1.1.2 |  |  | 185 | 1295
10 | DEL-0001 | TSK-00010 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.1.4 | 1.1.1.1.1 | Examples per Pillar | Content Pillars | Examples per Pillar | Strategist | Mid | 4 |  |  | 1.1.1.1.1.3 |  |  | 185 | 740
| DEL-0001 |  | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.2 | 1.1.1.1 | Internal Review & Critique | Content Pillars | Internal Review & Critique |  |  | 0 | 11 | 2 | 1.1.1.1.1.4 |  |  | 0 | 0
7 | DEL-0001 | TSK-00007 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.2.1 | 1.1.1.1.2 | Internal Review & Critique | Content Pillars | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.1.1.2 |  |  | 185 | 185
8 | DEL-0001 | TSK-00008 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.2.2 | 1.1.1.1.2 | Internal Review & Critique | Content Pillars | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.1.1.1.2.1 |  |  | 185 | 185
| DEL-0001 |  | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.3 | 1.1.1.1 | Client Review & Revisions | Content Pillars | Client Review & Revisions |  |  | 0 | 13 | 3 | 1.1.1.1.2.2 |  |  | 0 | 0
1 | DEL-0001 | TSK-00001 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.3.1 | 1.1.1.1.3 | Client Review & Revisions | Content Pillars | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.1.1.3 |  |  | 185 | 370
2 | DEL-0001 | TSK-00002 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.3.2 | 1.1.1.1.3 | Client Review & Revisions | Content Pillars | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.1.1.1.3.1 |  |  | 185 | 185
3 | DEL-0001 | TSK-00003 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.1.3.3 | 1.1.1.1.3 | Client Review & Revisions | Content Pillars | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.1.1.1.3.2 |  |  | 185 | 370
| DEL-0001 |  | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2 | 1.1.1 | Organic Social Plan | Organic Social Plan |  |  |  | 22 | 5 | 12 | 1.1.1.1 |  |  | 185 | 4070
| DEL-0001 |  | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.1 | 1.1.1.2 | Channel Roles & Cadence | Organic Social Plan | Channel Roles & Cadence |  |  | 0 | 5 | 6 | 1.1.1.2 |  |  | 0 | 0
11 | DEL-0001 | TSK-00011 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.1.1 | 1.1.1.2.1 | Channel Roles & Cadence | Organic Social Plan | Channel Roles & Cadence | Strategist | Mid | 7 |  |  | 1.1.1.2.1 |  |  | 185 | 1295
| DEL-0001 |  | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.2 | 1.1.1.2 | Internal Review & Critique | Organic Social Plan | Internal Review & Critique |  |  | 0 | 11 | 2 | 1.1.1.2.1.1 |  |  | 0 | 0
18 | DEL-0001 | TSK-00018 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.2.1 | 1.1.1.2.2 | Internal Review & Critique | Organic Social Plan | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.1.2.2 |  |  | 185 | 185
19 | DEL-0001 | TSK-00019 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.2.2 | 1.1.1.2.2 | Internal Review & Critique | Organic Social Plan | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.1.1.2.2.1 |  |  | 185 | 185
| DEL-0001 |  | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.3 | 1.1.1.2 | Client Review & Revisions | Organic Social Plan | Client Review & Revisions |  |  | 0 | 13 | 3 | 1.1.1.2.2.2 |  |  | 0 | 0
12 | DEL-0001 | TSK-00012 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.3.1 | 1.1.1.2.3 | Client Review & Revisions | Organic Social Plan | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.1.2.3 |  |  | 185 | 370
13 | DEL-0001 | TSK-00013 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.3.2 | 1.1.1.2.3 | Client Review & Revisions | Organic Social Plan | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.1.1.2.3.1 |  |  | 185 | 185
14 | DEL-0001 | TSK-00014 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.3.3 | 1.1.1.2.3 | Client Review & Revisions | Organic Social Plan | Client Review & Revisions | Producer | Mid | 2 |  |  | 1.1.1.2.3.2 |  |  | 185 | 370
| DEL-0001 |  | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.4 | 1.1.1.2 | Example Content Map | Organic Social Plan | Example Content Map |  |  | 0 | 16 | 1 | 1.1.1.2.3.3 |  |  | 0 | 0
15 | DEL-0001 | TSK-00015 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.4.1 | 1.1.1.2.4 | Example Content Map | Organic Social Plan | Example Content Map | Copywriter | Mid | 2 |  |  | 1.1.1.2.4 |  |  | 185 | 370
16 | DEL-0001 | TSK-00016 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.2.4.2 | 1.1.1.2.4 | Example Content Map | Organic Social Plan | Example Content Map | Designer | Mid | 6 |  |  | 1.1.1.2.4.1 |  |  | 185 | 1110
| DEL-0001 |  | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3 | 1.1.1 | Platform Content & Cadence Strategy | Platform Content & Cadence Strategy |  |  |  | 19 | 5 | 11 | 1.1.1.2 |  |  | 185 | 3515
| DEL-0001 |  | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.1 | 1.1.1.3 | Cadence Matrix | Platform Content & Cadence Strategy | Cadence Matrix |  |  | 0 | 5 | 6 | 1.1.1.3 |  |  | 0 | 0
30 | DEL-0001 | TSK-00030 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.1.1 | 1.1.1.3.1 | Cadence Matrix | Platform Content & Cadence Strategy | Cadence Matrix | Designer | Mid | 7 |  |  | 1.1.1.3.1 |  |  | 185 | 1295
27 | DEL-0001 | TSK-00027 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.1.2 | 1.1.1.3.1 | Cadence Matrix | Platform Content & Cadence Strategy | Cadence Matrix | Strategist | Mid | 7 |  |  | 1.1.1.3.1.1 |  |  | 185 | 1295
| DEL-0001 |  | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.2 | 1.1.1.3 | Internal Review & Critique | Platform Content & Cadence Strategy | Internal Review & Critique |  |  | 0 | 11 | 2 | 1.1.1.3.1.2 |  |  | 0 | 0
31 | DEL-0001 | TSK-00031 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.2.1 | 1.1.1.3.2 | Internal Review & Critique | Platform Content & Cadence Strategy | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.1.3.2 |  |  | 185 | 185
32 | DEL-0001 | TSK-00032 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.2.2 | 1.1.1.3.2 | Internal Review & Critique | Platform Content & Cadence Strategy | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.1.1.3.2.1 |  |  | 185 | 185
| DEL-0001 |  | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.3 | 1.1.1.3 | Client Review & Revisions | Platform Content & Cadence Strategy | Client Review & Revisions |  |  | 0 | 13 | 3 | 1.1.1.3.2.2 |  |  | 0 | 0
28 | DEL-0001 | TSK-00028 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.3.1 | 1.1.1.3.3 | Client Review & Revisions | Platform Content & Cadence Strategy | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.1.3.3 |  |  | 185 | 370
29 | DEL-0001 | TSK-00029 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.3.3.2 | 1.1.1.3.3 | Client Review & Revisions | Platform Content & Cadence Strategy | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.1.1.3.3.1 |  |  | 185 | 185
| DEL-0001 |  | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4 | 1.1.1 | Planning Recommendations | Planning Recommendations |  |  |  | 14 | 11 | 6 | 1.1.1.3 |  |  | 185 | 2590
| DEL-0001 |  | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4.1 | 1.1.1.4 | Internal Review & Critique | Planning Recommendations | Internal Review & Critique |  |  | 0 | 11 | 2 | 1.1.1.4 |  |  | 0 | 0
23 | DEL-0001 | TSK-00023 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4.1.1 | 1.1.1.4.1 | Internal Review & Critique | Planning Recommendations | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.1.4.1 |  |  | 185 | 185
24 | DEL-0001 | TSK-00024 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4.1.2 | 1.1.1.4.1 | Internal Review & Critique | Planning Recommendations | Internal Review & Critique | Producer | Mid | 1 |  |  | 1.1.1.4.1.1 |  |  | 185 | 185
| DEL-0001 |  | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4.2 | 1.1.1.4 | Client Review & Revisions | Planning Recommendations | Client Review & Revisions |  |  | 0 | 13 | 3 | 1.1.1.4.1.2 |  |  | 0 | 0
20 | DEL-0001 | TSK-00020 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4.2.1 | 1.1.1.4.2 | Client Review & Revisions | Planning Recommendations | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.1.4.2 |  |  | 185 | 370
21 | DEL-0001 | TSK-00021 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4.2.2 | 1.1.1.4.2 | Client Review & Revisions | Planning Recommendations | Client Review & Revisions | Producer | Mid | 1 |  |  | 1.1.1.4.2.1 |  |  | 185 | 185
| DEL-0001 |  | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4.3 | 1.1.1.4 | Final Packaging | Planning Recommendations | Final Packaging |  |  | 0 | 16 | 1 | 1.1.1.4.2.2 |  |  | 0 | 0
22 | DEL-0001 | TSK-00022 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4.3.1 | 1.1.1.4.3 | Final Packaging | Planning Recommendations | Final Packaging | Designer | Mid | 3 |  |  | 1.1.1.4.3 |  |  | 185 | 555
26 | DEL-0001 | TSK-00026 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4.3.2 | 1.1.1.4.3 | Final Packaging | Planning Recommendations | Final Packaging | Project Manager | Mid | 2 |  |  | 1.1.1.4.3.1 |  |  | 185 | 370
25 | DEL-0001 | TSK-00025 | Content | Content Plan | Casa-Dragones-Digital-MKT-RFP | 1.1.1.4.3.3 | 1.1.1.4.3 | Final Packaging | Planning Recommendations | Final Packaging | Strategist | Mid | 4 |  |  | 1.1.1.4.3.2 |  |  | 185 | 740