## Sheet1
Row_ID | Deliverable_Code | Task_Code | Service_Department | Deliverable | Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes | Rate_USD | Price_USD
[5 empty] | Proposal 2025-09-24 | 1 |  | Proposal 2025-09-24 | Project |  |  |  | 0 | 0 |  |  |  |  | 0 | 0
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1 | 1 | Brand Identity Development |  |  |  |  | 300 | 0 | 15 |  |  | Advanced/T2_MediumVolume | 185 | 55500
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.1 | 1.1 | Color Palette | Color Palette |  |  |  | 18 | 0 | 3 | 1.1 |  |  | 185 | 3330
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.1.1 | 1.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions |  |  | 0 | 0 | 3 | 1.1.1 |  |  | 0 | 0
475 | DEL-0008 | TSK-00466 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.1.1.1 | 1.1.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Account Manager | Mid | 1 |  |  | 1.1.1.1 |  |  | 185 | 185
480 | DEL-0008 | TSK-00471 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.1.1.2 | 1.1.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Art Director | Lead/Director | 2 |  |  | 1.1.1.1.1 |  |  | 185 | 370
476 | DEL-0008 | TSK-00467 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.1.1.3 | 1.1.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Creative Director | Lead/Director | 4 |  |  | 1.1.1.1.2 |  |  | 185 | 740
478 | DEL-0008 | TSK-00469 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.1.1.4 | 1.1.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Designer | Mid | 7 |  |  | 1.1.1.1.3 |  |  | 185 | 1295
477 | DEL-0008 | TSK-00468 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.1.1.5 | 1.1.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.1.1.4 |  |  | 185 | 185
474 | DEL-0008 | TSK-00465 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.1.1.6 | 1.1.1.1 | Client Review & Revisions | Color Palette | Client Review & Revisions | QA Specialist | Mid | 3 |  |  | 1.1.1.1.5 |  |  | 185 | 555
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.2 | 1.1 | Graphic Mock-Ups | Graphic Mock-Ups |  |  |  | 30 | 3 | 9 | 1.1.1 |  |  | 185 | 5550
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.2.1 | 1.1.2 | Compositing/Retouch | Graphic Mock-Ups | Compositing/Retouch |  |  | 0 | 3 | 4 | 1.1.2 |  |  | 0 | 0
496 | DEL-0008 | TSK-00487 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.2.1.1 | 1.1.2.1 | Compositing/Retouch | Graphic Mock-Ups | Compositing/Retouch | Retoucher | Mid | 5 |  |  | 1.1.2.1 |  |  | 185 | 925
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.2.2 | 1.1.2 | Internal Review & Critique | Graphic Mock-Ups | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.2.1.1 |  |  | 0 | 0
498 | DEL-0008 | TSK-00489 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.2.2.1 | 1.1.2.2 | Internal Review & Critique | Graphic Mock-Ups | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.2.2 |  |  | 185 | 185
499 | DEL-0008 | TSK-00490 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.2.2.2 | 1.1.2.2 | Internal Review & Critique | Graphic Mock-Ups | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.2.2.1 |  |  | 185 | 185
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.2.3 | 1.1.2 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.2.2.2 |  |  | 0 | 0
493 | DEL-0008 | TSK-00484 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.2.3.1 | 1.1.2.3 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.2.3 |  |  | 185 | 370
494 | DEL-0008 | TSK-00485 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.2.3.2 | 1.1.2.3 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.2.3.1 |  |  | 185 | 185
495 | DEL-0008 | TSK-00486 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.2.3.3 | 1.1.2.3 | Client Review & Revisions | Graphic Mock-Ups | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.2.3.2 |  |  | 185 | 185
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.2.4 | 1.1.2 | Mockup Scenarios (3-4) | Graphic Mock-Ups | Mockup Scenarios (3-4) |  |  | 0 | 15 | 0 | 1.1.2.3.3 |  |  | 0 | 0
500 | DEL-0008 | TSK-00491 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.2.4.1 | 1.1.2.4 | Mockup Scenarios (3-4) | Graphic Mock-Ups | Mockup Scenarios (3-4) | Art Director | Lead/Director | 3 |  |  | 1.1.2.4 |  |  | 185 | 555
497 | DEL-0008 | TSK-00488 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.2.4.2 | 1.1.2.4 | Mockup Scenarios (3-4) | Graphic Mock-Ups | Mockup Scenarios (3-4) | Designer | Mid | 16 |  |  | 1.1.2.4.1 |  |  | 185 | 2960
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.3 | 1.1 | Logo | Logo |  |  |  | 43 | 7 | 8 | 1.1.2 |  |  | 185 | 7955
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.3.1 | 1.1.3 | Quality Check (Specs/Accessibility) | Logo | Quality Check (Specs/Accessibility) |  |  | 0 | 7 | 3 | 1.1.3 |  |  | 0 | 0
520 | DEL-0008 | TSK-00511 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.3.1.1 | 1.1.3.1 | Quality Check (Specs/Accessibility) | Logo | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.1.3.1 |  |  | 185 | 555
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.3.2 | 1.1.3 | Internal Review & Critique | Logo | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.3.1.1 |  |  | 0 | 0
515 | DEL-0008 | TSK-00506 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.3.2.1 | 1.1.3.2 | Internal Review & Critique | Logo | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.3.2 |  |  | 185 | 185
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.3.3 | 1.1.3 | Client Review & Revisions | Logo | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.3.2.1 |  |  | 0 | 0
511 | DEL-0008 | TSK-00502 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.3.3.1 | 1.1.3.3 | Client Review & Revisions | Logo | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.3.3 |  |  | 185 | 370
512 | DEL-0008 | TSK-00503 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.3.3.2 | 1.1.3.3 | Client Review & Revisions | Logo | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.3.3.1 |  |  | 185 | 185
513 | DEL-0008 | TSK-00504 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.3.3.3 | 1.1.3.3 | Client Review & Revisions | Logo | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.3.3.2 |  |  | 185 | 185
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.3.4 | 1.1.3 | Logo Exploration (6-8 dirs) | Logo | Logo Exploration (6-8 dirs) |  |  | 0 | 15 | 0 | 1.1.3.3.3 |  |  | 0 | 0
517 | DEL-0008 | TSK-00508 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.3.4.1 | 1.1.3.4 | Logo Exploration (6-8 dirs) | Logo | Logo Exploration (6-8 dirs) | Art Director | Lead/Director | 3 |  |  | 1.1.3.4 |  |  | 185 | 555
514 | DEL-0008 | TSK-00505 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.3.4.2 | 1.1.3.4 | Logo Exploration (6-8 dirs) | Logo | Logo Exploration (6-8 dirs) | Designer | Mid | 32 |  |  | 1.1.3.4.1 |  |  | 185 | 5920
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.4 | 1.1 | Typography | Typography |  |  |  | 40 | 7 | 8 | 1.1.3 |  |  | 185 | 7400
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.4.1 | 1.1.4 | Quality Check (Specs/Accessibility) | Typography | Quality Check (Specs/Accessibility) |  |  | 0 | 7 | 3 | 1.1.4 |  |  | 0 | 0
556 | DEL-0008 | TSK-00547 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.4.1.1 | 1.1.4.1 | Quality Check (Specs/Accessibility) | Typography | Quality Check (Specs/Accessibility) | QA Specialist | Mid | 3 |  |  | 1.1.4.1 |  |  | 185 | 555
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.4.2 | 1.1.4 | Internal Review & Critique | Typography | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.4.1.1 |  |  | 0 | 0
554 | DEL-0008 | TSK-00545 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.4.2.1 | 1.1.4.2 | Internal Review & Critique | Typography | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.4.2 |  |  | 185 | 185
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.4.3 | 1.1.4 | Client Review & Revisions | Typography | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.4.2.1 |  |  | 0 | 0
549 | DEL-0008 | TSK-00540 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.4.3.1 | 1.1.4.3 | Client Review & Revisions | Typography | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.4.3 |  |  | 185 | 370
550 | DEL-0008 | TSK-00541 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.4.3.2 | 1.1.4.3 | Client Review & Revisions | Typography | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.4.3.1 |  |  | 185 | 185
551 | DEL-0008 | TSK-00542 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.4.3.3 | 1.1.4.3 | Client Review & Revisions | Typography | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.4.3.2 |  |  | 185 | 185
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.4.4 | 1.1.4 | Final Packaging | Typography | Final Packaging |  |  | 0 | 15 | 0 | 1.1.4.3.3 |  |  | 0 | 0
552 | DEL-0008 | TSK-00543 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.4.4.1 | 1.1.4.4 | Final Packaging | Typography | Final Packaging | Designer | Mid | 32 |  |  | 1.1.4.4 |  |  | 185 | 5920
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.5 | 1.1 | Graphic & Copy Messaging Cornerstones | Graphic & Copy Messaging Cornerstones |  |  |  | 28 | 10 | 5 | 1.1.4 |  |  | 185 | 5180
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.5.1 | 1.1.5 | Internal Review & Critique | Graphic & Copy Messaging Cornerstones | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.5 |  |  | 0 | 0
489 | DEL-0008 | TSK-00480 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.5.1.1 | 1.1.5.1 | Internal Review & Critique | Graphic & Copy Messaging Cornerstones | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.5.1 |  |  | 185 | 185
490 | DEL-0008 | TSK-00481 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.5.1.2 | 1.1.5.1 | Internal Review & Critique | Graphic & Copy Messaging Cornerstones | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.5.1.1 |  |  | 185 | 185
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.5.2 | 1.1.5 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.5.1.2 |  |  | 0 | 0
483 | DEL-0008 | TSK-00474 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.5.2.1 | 1.1.5.2 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.5.2 |  |  | 185 | 370
484 | DEL-0008 | TSK-00475 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.5.2.2 | 1.1.5.2 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.1.5.2.1 |  |  | 185 | 185
485 | DEL-0008 | TSK-00476 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.5.2.3 | 1.1.5.2 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.5.2.2 |  |  | 185 | 185
486 | DEL-0008 | TSK-00477 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.5.2.4 | 1.1.5.2 | Client Review & Revisions | Graphic & Copy Messaging Cornerstones | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.5.2.3 |  |  | 185 | 185
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.5.3 | 1.1.5 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft |  |  | 0 | 15 | 0 | 1.1.5.2.4 |  |  | 0 | 0
491 | DEL-0008 | TSK-00482 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.5.3.1 | 1.1.5.3 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft | Copywriter | Mid | 2 |  |  | 1.1.5.3 |  |  | 185 | 370
492 | DEL-0008 | TSK-00483 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.5.3.2 | 1.1.5.3 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft | Creative Director | Lead/Director | 3 |  |  | 1.1.5.3.1 |  |  | 185 | 555
487 | DEL-0008 | TSK-00478 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.5.3.3 | 1.1.5.3 | Messaging Cornerstones Draft | Graphic & Copy Messaging Cornerstones | Messaging Cornerstones Draft | Designer | Mid | 16 |  |  | 1.1.5.3.2 |  |  | 185 | 2960
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.6 | 1.1 | Iconography | Iconography |  |  |  | 31 | 10 | 5 | 1.1.5 |  |  | 185 | 5735
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.6.1 | 1.1.6 | Internal Review & Critique | Iconography | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.6 |  |  | 0 | 0
509 | DEL-0008 | TSK-00500 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.6.1.1 | 1.1.6.1 | Internal Review & Critique | Iconography | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.6.1 |  |  | 185 | 185
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.6.2 | 1.1.6 | Client Review & Revisions | Iconography | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.6.1.1 |  |  | 0 | 0
502 | DEL-0008 | TSK-00493 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.6.2.1 | 1.1.6.2 | Client Review & Revisions | Iconography | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.6.2 |  |  | 185 | 370
503 | DEL-0008 | TSK-00494 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.6.2.2 | 1.1.6.2 | Client Review & Revisions | Iconography | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.6.2.1 |  |  | 185 | 185
504 | DEL-0008 | TSK-00495 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.6.2.3 | 1.1.6.2 | Client Review & Revisions | Iconography | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.6.2.2 |  |  | 185 | 185
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.6.3 | 1.1.6 | Export & Spec | Iconography | Export & Spec |  |  | 0 | 15 | 0 | 1.1.6.2.3 |  |  | 0 | 0
505 | DEL-0008 | TSK-00496 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.6.3.1 | 1.1.6.3 | Export & Spec | Iconography | Export & Spec | Designer | Mid | 24 |  |  | 1.1.6.3 |  |  | 185 | 4440
508 | DEL-0008 | TSK-00499 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.6.3.2 | 1.1.6.3 | Export & Spec | Iconography | Export & Spec | Illustrator | Mid | 2 |  |  | 1.1.6.3.1 |  |  | 185 | 370
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.7 | 1.1 | Overarching Moodboard | Overarching Moodboard |  |  |  | 27 | 10 | 5 | 1.1.6 |  |  | 185 | 4995
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.7.1 | 1.1.7 | Internal Review & Critique | Overarching Moodboard | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.7 |  |  | 0 | 0
528 | DEL-0008 | TSK-00519 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.7.1.1 | 1.1.7.1 | Internal Review & Critique | Overarching Moodboard | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.7.1 |  |  | 185 | 185
529 | DEL-0008 | TSK-00520 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.7.1.2 | 1.1.7.1 | Internal Review & Critique | Overarching Moodboard | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.7.1.1 |  |  | 185 | 185
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.7.2 | 1.1.7 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.7.1.2 |  |  | 0 | 0
522 | DEL-0008 | TSK-00513 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.7.2.1 | 1.1.7.2 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.7.2 |  |  | 185 | 370
523 | DEL-0008 | TSK-00514 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.7.2.2 | 1.1.7.2 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.7.2.1 |  |  | 185 | 185
524 | DEL-0008 | TSK-00515 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.7.2.3 | 1.1.7.2 | Client Review & Revisions | Overarching Moodboard | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.7.2.2 |  |  | 185 | 185
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.7.3 | 1.1.7 | Curate Moodboard | Overarching Moodboard | Curate Moodboard |  |  | 0 | 15 | 0 | 1.1.7.2.3 |  |  | 0 | 0
526 | DEL-0008 | TSK-00517 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.7.3.1 | 1.1.7.3 | Curate Moodboard | Overarching Moodboard | Curate Moodboard | Art Director | Lead/Director | 3 |  |  | 1.1.7.3 |  |  | 185 | 555
530 | DEL-0008 | TSK-00521 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.7.3.2 | 1.1.7.3 | Curate Moodboard | Overarching Moodboard | Curate Moodboard | Copywriter | Mid | 2 |  |  | 1.1.7.3.1 |  |  | 185 | 370
525 | DEL-0008 | TSK-00516 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.7.3.3 | 1.1.7.3 | Curate Moodboard | Overarching Moodboard | Curate Moodboard | Designer | Mid | 16 |  |  | 1.1.7.3.2 |  |  | 185 | 2960
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.8 | 1.1 | Tagline Copy Bank | Tagline Copy Bank |  |  |  | 22 | 10 | 5 | 1.1.7 |  |  | 185 | 4070
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.8.1 | 1.1.8 | Internal Review & Critique | Tagline Copy Bank | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.8 |  |  | 0 | 0
536 | DEL-0008 | TSK-00527 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.8.1.1 | 1.1.8.1 | Internal Review & Critique | Tagline Copy Bank | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.8.1 |  |  | 185 | 185
537 | DEL-0008 | TSK-00528 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.8.1.2 | 1.1.8.1 | Internal Review & Critique | Tagline Copy Bank | Internal Review & Critique | Creative Director | Lead/Director | 1 |  |  | 1.1.8.1.1 |  |  | 185 | 185
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.8.2 | 1.1.8 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.8.1.2 |  |  | 0 | 0
531 | DEL-0008 | TSK-00522 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.8.2.1 | 1.1.8.2 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.8.2 |  |  | 185 | 370
532 | DEL-0008 | TSK-00523 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.8.2.2 | 1.1.8.2 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Copywriter | Mid | 1 |  |  | 1.1.8.2.1 |  |  | 185 | 185
533 | DEL-0008 | TSK-00524 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.8.2.3 | 1.1.8.2 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.8.2.2 |  |  | 185 | 185
534 | DEL-0008 | TSK-00525 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.8.2.4 | 1.1.8.2 | Client Review & Revisions | Tagline Copy Bank | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.8.2.3 |  |  | 185 | 185
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.8.3 | 1.1.8 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale |  |  | 0 | 15 | 0 | 1.1.8.2.4 |  |  | 0 | 0
538 | DEL-0008 | TSK-00529 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.8.3.1 | 1.1.8.3 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale | Copywriter | Mid | 4 |  |  | 1.1.8.3 |  |  | 185 | 740
539 | DEL-0008 | TSK-00530 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.8.3.2 | 1.1.8.3 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale | Creative Director | Lead/Director | 3 |  |  | 1.1.8.3.1 |  |  | 185 | 555
535 | DEL-0008 | TSK-00526 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.8.3.3 | 1.1.8.3 | Shortlist & Rationale | Tagline Copy Bank | Shortlist & Rationale | Designer | Mid | 8 |  |  | 1.1.8.3.2 |  |  | 185 | 1480
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.9 | 1.1 | Textures/Patterns/Materials | Textures/Patterns/Materials |  |  |  | 29 | 10 | 5 | 1.1.8 |  |  | 185 | 5365
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.9.1 | 1.1.9 | Internal Review & Critique | Textures/Patterns/Materials | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.9 |  |  | 0 | 0
546 | DEL-0008 | TSK-00537 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.9.1.1 | 1.1.9.1 | Internal Review & Critique | Textures/Patterns/Materials | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.9.1 |  |  | 185 | 185
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.9.2 | 1.1.9 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.9.1.1 |  |  | 0 | 0
542 | DEL-0008 | TSK-00533 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.9.2.1 | 1.1.9.2 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.9.2 |  |  | 185 | 370
543 | DEL-0008 | TSK-00534 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.9.2.2 | 1.1.9.2 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.9.2.1 |  |  | 185 | 185
544 | DEL-0008 | TSK-00535 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.9.2.3 | 1.1.9.2 | Client Review & Revisions | Textures/Patterns/Materials | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.9.2.2 |  |  | 185 | 185
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.9.3 | 1.1.9 | Build Repeating Tiles | Textures/Patterns/Materials | Build Repeating Tiles |  |  | 0 | 15 | 0 | 1.1.9.2.3 |  |  | 0 | 0
541 | DEL-0008 | TSK-00532 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.9.3.1 | 1.1.9.3 | Build Repeating Tiles | Textures/Patterns/Materials | Build Repeating Tiles | Designer | Mid | 24 |  |  | 1.1.9.3 |  |  | 185 | 4440
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.10 | 1.1 | Visual Elements/Comps | Visual Elements/Comps |  |  |  | 32 | 10 | 5 | 1.1.9 |  |  | 185 | 5920
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.10.1 | 1.1.10 | Internal Review & Critique | Visual Elements/Comps | Internal Review & Critique |  |  | 0 | 10 | 2 | 1.1.10 |  |  | 0 | 0
566 | DEL-0008 | TSK-00557 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.10.1.1 | 1.1.10.1 | Internal Review & Critique | Visual Elements/Comps | Internal Review & Critique | Art Director | Lead/Director | 1 |  |  | 1.1.10.1 |  |  | 185 | 185
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.10.2 | 1.1.10 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions |  |  | 0 | 12 | 3 | 1.1.10.1.1 |  |  | 0 | 0
559 | DEL-0008 | TSK-00550 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.10.2.1 | 1.1.10.2 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions | Account Manager | Mid | 2 |  |  | 1.1.10.2 |  |  | 185 | 370
560 | DEL-0008 | TSK-00551 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.10.2.2 | 1.1.10.2 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions | Creative Director | Lead/Director | 1 |  |  | 1.1.10.2.1 |  |  | 185 | 185
561 | DEL-0008 | TSK-00552 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.10.2.3 | 1.1.10.2 | Client Review & Revisions | Visual Elements/Comps | Client Review & Revisions | Project Manager | Mid | 1 |  |  | 1.1.10.2.2 |  |  | 185 | 185
| DEL-0008 |  | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.10.3 | 1.1.10 | Compositions (2-3) | Visual Elements/Comps | Compositions (2-3) |  |  | 0 | 15 | 0 | 1.1.10.2.3 |  |  | 0 | 0
562 | DEL-0008 | TSK-00553 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.10.3.1 | 1.1.10.3 | Compositions (2-3) | Visual Elements/Comps | Compositions (2-3) | Art Director | Lead/Director | 3 |  |  | 1.1.10.3 |  |  | 185 | 555
563 | DEL-0008 | TSK-00554 | Creative | Brand Identity Development | Proposal 2025-09-24 | 1.1.10.3.2 | 1.1.10.3 | Compositions (2-3) | Visual Elements/Comps | Compositions (2-3) | Designer | Mid | 24 |  |  | 1.1.10.3.1 |  |  | 185 | 4440