## Sheet1
Row_ID | Deliverable_Code | Task_Code | Service_Department | Deliverable | Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes | Rate_USD | Price_USD
[5 empty] | Casa-Dragones-Digital-MKT-RFP | 1 |  | Casa-Dragones-Digital-MKT-RFP | Project |  |  |  | 0 | 0 |  |  |  |  | 0 | 0
|  |  | Other |  | Casa-Dragones-Digital-MKT-RFP | 1.1 | 1 | Other |  |  |  |  | 0 | 0 |  |  |  | Other Department | 0 | 0
| DEL-0036 |  |  | Creative Strategy / Campaign Plan Deck | Casa-Dragones-Digital-MKT-RFP | 1.1.1 | 1.1 | Creative Strategy / Campaign Plan Deck |  |  |  |  | 582 | 0 | 28 |  |  | / | 195 | 113490
| DEL-0029 |  |  | Paid Media Planning | Casa-Dragones-Digital-MKT-RFP | 1.1.2 | 1.1 | Paid Media Planning |  |  |  |  | 82 | 28 | 33 | 1.1.1 |  | / | 195 | 15990
| DEL-0024 |  |  | Reporting | Casa-Dragones-Digital-MKT-RFP | 1.1.3 | 1.1 | Reporting |  |  |  |  | 128 | 61 | 7 | 1.1.2 |  | / | 195 | 24960