## Scenario A
Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Deliverable | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes
Vascano Tequila - RFP Creative Services 2022 (8) | 1 |  | Vascano Tequila - RFP Creative Services 2022 (8) |  | Project |  |  |  |  | 0
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1 | 1 | Development | Development | Deliverable |  |  |  | 227 | 0 | 22 |  |  | Core/T2_MediumVolume
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1 | 1.1 | research | Development | Task | research | Business Analyst | Mid | 35 | 0 | 3 | 1.1
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2 | 1.1 | design_prod | Development | Task | design_prod | UI Designer | Mid | 7 | 3 | 7 | 1.1.1
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3 | 1.1 | qa | Development | Task | qa | QA Engineer | Mid | 43 | 10 | 2 | 1.1.2
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4 | 1.1 | development | Development | Task | development | Frontend Engineer | Mid | 142 | 12 | 10 | 1.1.3
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2 | 1 | Post-Production | Post-Production | Deliverable |  |  |  | 188 | 22 | 41 | 1.1 |  | Core/T2_MediumVolume
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1 | 1.2 | research | Post-Production | Task | research | Producer | Mid | 1 | 22 | 3 | 1.2
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2 | 1.2 | prepro_docs | Post-Production | Task | prepro_docs | Copywriter | Mid | 1 | 25 | 4 | 1.2.1
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3 | 1.2 | edit | Post-Production | Task | edit | Editor | Mid | 51 | 29 | 5 | 1.2.2
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4 | 1.2 | motion | Post-Production | Task | motion | Editor | Mid | 17 | 34 | 7 | 1.2.3
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5 | 1.2 | color | Post-Production | Task | color | Colorist | Mid | 23 | 41 | 2 | 1.2.4
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6 | 1.2 | retouch | Post-Production | Task | retouch | Retoucher | Mid | 8 | 43 | 3 | 1.2.5
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7 | 1.2 | sound | Post-Production | Task | sound | Sound Designer | Mid | 14 | 46 | 2 | 1.2.6
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8 | 1.2 | qa | Post-Production | Task | qa | QA Specialist | Mid | 3 | 48 | 2 | 1.2.7
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9 | 1.2 | analytics_tagging | Post-Production | Task | analytics_tagging | Project Manager | Mid | 1 | 50 | 3 | 1.2.8
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10 | 1.2 | internal_review | Post-Production | Task | internal_review | Producer | Mid | 7 | 53 | 2 | 1.2.9
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.11 | 1.2 | client_review | Post-Production | Task | client_review | Account Manager | Mid | 19 | 55 | 3 | 1.2.10
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.12 | 1.2 | library | Post-Production | Task | library | Editor | Mid | 5 | 58 | 3 | 1.2.11
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.13 | 1.2 | notes_triage | Post-Production | Task | notes_triage | Project Manager | Mid | 1 | 61 | 2 | 1.2.12
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.14 | 1.2 | general | Post-Production | Task | general | Editor | Mid | 37 | 63 | 0 | 1.2.13
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3 | 1 | Pre-Production | Pre-Production | Deliverable |  |  |  | 396 | 63 | 57 | 1.2 |  | Core/T2_MediumVolume
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1 | 1.3 | brief | Pre-Production | Task | brief | Art Director | Lead/Director | 2 | 63 | 2 | 1.3
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2 | 1.3 | deck_build | Pre-Production | Task | deck_build | Strategist | Mid | 20 | 65 | 5 | 1.3.1
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3 | 1.3 | design_prod | Pre-Production | Task | design_prod | Media Manager / DIT | Mid | 3 | 70 | 7 | 1.3.2
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4 | 1.3 | prepro_docs | Pre-Production | Task | prepro_docs | Producer | Mid | 130 | 77 | 4 | 1.3.3
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5 | 1.3 | prepro_coord | Pre-Production | Task | prepro_coord | Producer | Mid | 63 | 81 | 7 | 1.3.4
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.6 | 1.3 | edit | Pre-Production | Task | edit | Editor | Mid | 10 | 88 | 5 | 1.3.5
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.7 | 1.3 | qa | Pre-Production | Task | qa | QA Specialist | Mid | 3 | 93 | 2 | 1.3.6
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8 | 1.3 | development | Pre-Production | Task | development | Designer | Mid | 12 | 95 | 10 | 1.3.7
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.9 | 1.3 | analytics_tagging | Pre-Production | Task | analytics_tagging | Producer | Mid | 2 | 105 | 3 | 1.3.8
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.10 | 1.3 | community_mgmt | Pre-Production | Task | community_mgmt | Designer | Mid | 9 | 108 | 5 | 1.3.9
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.11 | 1.3 | internal_review | Pre-Production | Task | internal_review | Producer | Mid | 18 | 113 | 2 | 1.3.10
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.12 | 1.3 | client_review | Pre-Production | Task | client_review | Account Manager | Mid | 35 | 115 | 3 | 1.3.11
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.13 | 1.3 | status_meeting | Pre-Production | Task | status_meeting | Creative Director | Lead/Director | 2 | 118 | 2 | 1.3.12
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.14 | 1.3 | general | Pre-Production | Task | general | Designer | Mid | 77 | 120 | 0 | 1.3.13
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15 | 1.3 | style_guide | Pre-Production | Task | style_guide | Designer | Mid | 10 | 120 | 0 | 1.3.14
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4 | 1 | Brand Identity Development | Brand Identity Development | Deliverable |  |  |  | 255 | 120 | 12 | 1.3 |  | Core/T2_MediumVolume
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1 | 1.4 | color | Brand Identity Development | Task | color | Designer | Mid | 15 | 120 | 2 | 1.4
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2 | 1.4 | retouch | Brand Identity Development | Task | retouch | Retoucher | Mid | 4 | 122 | 3 | 1.4.1
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3 | 1.4 | qa | Brand Identity Development | Task | qa | QA Specialist | Mid | 5 | 125 | 2 | 1.4.2
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4 | 1.4 | internal_review | Brand Identity Development | Task | internal_review | Art Director | Lead/Director | 12 | 127 | 2 | 1.4.3
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5 | 1.4 | client_review | Brand Identity Development | Task | client_review | Account Manager | Mid | 32 | 129 | 3 | 1.4.4
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6 | 1.4 | brand_identity | Brand Identity Development | Task | brand_identity | Designer | Mid | 187 | 132 | 0 | 1.4.5
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5 | 1 | Brand Style & Usage Guidelines | Brand Style & Usage Guidelines | Deliverable |  |  |  | 250 | 132 | 9 | 1.4 |  | Core/T2_MediumVolume
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.1 | 1.5 | color | Brand Style & Usage Guidelines | Task | color | Designer | Mid | 13 | 132 | 2 | 1.5
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2 | 1.5 | qa | Brand Style & Usage Guidelines | Task | qa | QA Specialist | Mid | 5 | 134 | 2 | 1.5.1
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3 | 1.5 | internal_review | Brand Style & Usage Guidelines | Task | internal_review | Art Director | Lead/Director | 12 | 136 | 2 | 1.5.2
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4 | 1.5 | client_review | Brand Style & Usage Guidelines | Task | client_review | Account Manager | Mid | 31 | 138 | 3 | 1.5.3
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5 | 1.5 | brand_identity | Brand Style & Usage Guidelines | Task | brand_identity | Designer | Mid | 55 | 141 | 0 | 1.5.4
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6 | 1.5 | style_guide | Brand Style & Usage Guidelines | Task | style_guide | Designer | Mid | 119 | 141 | 0 | 1.5.5
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7 | 1.5 | treatment | Brand Style & Usage Guidelines | Task | treatment | Creative Director | Lead/Director | 15 | 141 | 0 | 1.5.6

## Scenario B
Project_Name | WBS_ID | Parent_WBS_ID | Task_Name | Deliverable | Component | Task | Role | Seniority | Planned_Hours | Start_Offset_Days | Duration_Days | Dependencies | Assignee_External_ID | Notes
Vascano Tequila - RFP Creative Services 2022 (8) | 1 |  | Vascano Tequila - RFP Creative Services 2022 (8) |  | Project |  |  |  |  | 0
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1 | 1 | Development | Development | Deliverable |  |  |  | 348 | 0 | 28 |  |  | Advanced/T1_LargeVolume
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.1 | 1.1 | research | Development | Task | research | Business Analyst | Mid | 55 | 0 | 4 | 1.1
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.2 | 1.1 | design_prod | Development | Task | design_prod | UI Designer | Mid | 10 | 4 | 9 | 1.1.1
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.3 | 1.1 | qa | Development | Task | qa | QA Engineer | Mid | 66 | 13 | 3 | 1.1.2
Vascano Tequila - RFP Creative Services 2022 (8) | 1.1.4 | 1.1 | development | Development | Task | development | Frontend Engineer | Mid | 217 | 16 | 12 | 1.1.3
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2 | 1 | Post-Production | Post-Production | Deliverable |  |  |  | 288 | 28 | 51 | 1.1 |  | Advanced/T1_LargeVolume
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.1 | 1.2 | research | Post-Production | Task | research | Producer | Mid | 1 | 28 | 4 | 1.2
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.2 | 1.2 | prepro_docs | Post-Production | Task | prepro_docs | Copywriter | Mid | 2 | 32 | 5 | 1.2.1
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.3 | 1.2 | edit | Post-Production | Task | edit | Editor | Mid | 78 | 37 | 6 | 1.2.2
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.4 | 1.2 | motion | Post-Production | Task | motion | Editor | Mid | 26 | 43 | 9 | 1.2.3
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.5 | 1.2 | color | Post-Production | Task | color | Colorist | Mid | 35 | 52 | 3 | 1.2.4
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.6 | 1.2 | retouch | Post-Production | Task | retouch | Retoucher | Mid | 13 | 55 | 4 | 1.2.5
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.7 | 1.2 | sound | Post-Production | Task | sound | Sound Designer | Mid | 21 | 59 | 3 | 1.2.6
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.8 | 1.2 | qa | Post-Production | Task | qa | QA Specialist | Mid | 4 | 62 | 3 | 1.2.7
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.9 | 1.2 | analytics_tagging | Post-Production | Task | analytics_tagging | Project Manager | Mid | 1 | 65 | 4 | 1.2.8
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.10 | 1.2 | internal_review | Post-Production | Task | internal_review | Producer | Mid | 12 | 69 | 2 | 1.2.9
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.11 | 1.2 | client_review | Post-Production | Task | client_review | Account Manager | Mid | 29 | 71 | 3 | 1.2.10
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.12 | 1.2 | library | Post-Production | Task | library | Editor | Mid | 8 | 74 | 3 | 1.2.11
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.13 | 1.2 | notes_triage | Post-Production | Task | notes_triage | Project Manager | Mid | 1 | 77 | 2 | 1.2.12
Vascano Tequila - RFP Creative Services 2022 (8) | 1.2.14 | 1.2 | general | Post-Production | Task | general | Editor | Mid | 57 | 79 | 0 | 1.2.13
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3 | 1 | Pre-Production | Pre-Production | Deliverable |  |  |  | 606 | 79 | 69 | 1.2 |  | Advanced/T1_LargeVolume
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.1 | 1.3 | brief | Pre-Production | Task | brief | Art Director | Lead/Director | 4 | 79 | 3 | 1.3
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.2 | 1.3 | deck_build | Pre-Production | Task | deck_build | Strategist | Mid | 31 | 82 | 6 | 1.3.1
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.3 | 1.3 | design_prod | Pre-Production | Task | design_prod | Media Manager / DIT | Mid | 4 | 88 | 9 | 1.3.2
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.4 | 1.3 | prepro_docs | Pre-Production | Task | prepro_docs | Producer | Mid | 199 | 97 | 5 | 1.3.3
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.5 | 1.3 | prepro_coord | Pre-Production | Task | prepro_coord | Producer | Mid | 96 | 102 | 8 | 1.3.4
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.6 | 1.3 | edit | Pre-Production | Task | edit | Editor | Mid | 16 | 110 | 6 | 1.3.5
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.7 | 1.3 | qa | Pre-Production | Task | qa | QA Specialist | Mid | 4 | 116 | 3 | 1.3.6
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.8 | 1.3 | development | Pre-Production | Task | development | Designer | Mid | 18 | 119 | 12 | 1.3.7
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.9 | 1.3 | analytics_tagging | Pre-Production | Task | analytics_tagging | Producer | Mid | 3 | 131 | 4 | 1.3.8
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.10 | 1.3 | community_mgmt | Pre-Production | Task | community_mgmt | Designer | Mid | 14 | 135 | 6 | 1.3.9
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.11 | 1.3 | internal_review | Pre-Production | Task | internal_review | Producer | Mid | 27 | 141 | 2 | 1.3.10
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.12 | 1.3 | client_review | Pre-Production | Task | client_review | Account Manager | Mid | 53 | 143 | 3 | 1.3.11
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.13 | 1.3 | status_meeting | Pre-Production | Task | status_meeting | Creative Director | Lead/Director | 4 | 146 | 2 | 1.3.12
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.14 | 1.3 | general | Pre-Production | Task | general | Designer | Mid | 118 | 148 | 0 | 1.3.13
Vascano Tequila - RFP Creative Services 2022 (8) | 1.3.15 | 1.3 | style_guide | Pre-Production | Task | style_guide | Designer | Mid | 15 | 148 | 0 | 1.3.14
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4 | 1 | Brand Identity Development | Brand Identity Development | Deliverable |  |  |  | 391 | 148 | 15 | 1.3 |  | Advanced/T1_LargeVolume
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.1 | 1.4 | color | Brand Identity Development | Task | color | Designer | Mid | 23 | 148 | 3 | 1.4
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.2 | 1.4 | retouch | Brand Identity Development | Task | retouch | Retoucher | Mid | 7 | 151 | 4 | 1.4.1
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.3 | 1.4 | qa | Brand Identity Development | Task | qa | QA Specialist | Mid | 8 | 155 | 3 | 1.4.2
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.4 | 1.4 | internal_review | Brand Identity Development | Task | internal_review | Art Director | Lead/Director | 18 | 158 | 2 | 1.4.3
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.5 | 1.4 | client_review | Brand Identity Development | Task | client_review | Account Manager | Mid | 49 | 160 | 3 | 1.4.4
Vascano Tequila - RFP Creative Services 2022 (8) | 1.4.6 | 1.4 | brand_identity | Brand Identity Development | Task | brand_identity | Designer | Mid | 286 | 163 | 0 | 1.4.5
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5 | 1 | Brand Style & Usage Guidelines | Brand Style & Usage Guidelines | Deliverable |  |  |  | 382 | 163 | 11 | 1.4 |  | Advanced/T1_LargeVolume
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.1 | 1.5 | color | Brand Style & Usage Guidelines | Task | color | Designer | Mid | 20 | 163 | 3 | 1.5
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.2 | 1.5 | qa | Brand Style & Usage Guidelines | Task | qa | QA Specialist | Mid | 8 | 166 | 3 | 1.5.1
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.3 | 1.5 | internal_review | Brand Style & Usage Guidelines | Task | internal_review | Art Director | Lead/Director | 18 | 169 | 2 | 1.5.2
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.4 | 1.5 | client_review | Brand Style & Usage Guidelines | Task | client_review | Account Manager | Mid | 48 | 171 | 3 | 1.5.3
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.5 | 1.5 | brand_identity | Brand Style & Usage Guidelines | Task | brand_identity | Designer | Mid | 83 | 174 | 0 | 1.5.4
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.6 | 1.5 | style_guide | Brand Style & Usage Guidelines | Task | style_guide | Designer | Mid | 182 | 174 | 0 | 1.5.5
Vascano Tequila - RFP Creative Services 2022 (8) | 1.5.7 | 1.5 | treatment | Brand Style & Usage Guidelines | Task | treatment | Creative Director | Lead/Director | 23 | 174 | 0 | 1.5.6